BELIZE

Mesoamerica Health 2015

# (BL-G1001)

# Procurement Plan

### General Information

| Country: | Belize |
| --- | --- |
| Beneficiary: | Government of Belize |
| Executing Agency: | Ministry of Health (MOH) |
| Project name: | Mesoamerica Health 2015 |
| Project number: | BL-G1001 |
| Brief description of the project’s objectives and components: | The general objective of the program, which will consist of three consecutive operations, is to contribute to the reduction of maternal, infant and child mortality in the poorest districts of the country through interventions that strengthen primary health care services within the framework of the MH2015 Initiative. The specific objective is to improve maternal and infant, child and reproductive health in terms of access, usage and quality. |
| Estimated date of project approval: | December 2011 |
| Estimated date of signature: | January 2012 |
| Estimated date of the final disbursement: | June 2013 |

| Mesoamerica Health 2015 - Belize (BL-G1001) |
| --- |
| Procurement Plan |
| January 2012 – June 2013 |
| Ref. | Description of the contract | Estimated cost (US$) | Procure-ment Method | Review (ex ante o ex post) | Source of financing and percentage | Prequali-fication (Yes/No) | Estimated Dates | Status (pending, in process, awarded, cancelled) | Comments |
|  |  |  |  |  | % IDB | % local/other |  | Publication of specific procurement notice | Completion of contract |  |  |
| Goods |
| 1 | Servers and laptops for Belize Health Information System | 30,500 | NCB | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| 2 | Basic neonatal care equipment for Regional Hospitals | 56,962 | NCB | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| 3 | Mini laparotomy surgery kits and instruments for community hospitals | 4,800 | PC | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| 4 | Modern contraceptive methods | 53,800 | NCB | ex ante | 93 | 7 | No | I Tri/2011 | II Tri/2012 | pending |  |
| 5 | Basic supplies (medical kit, educational material, backpack, boots and field clothes) for CHW | 7,500 | PC | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| 6 | Radio system (antenna and radios) | 8,800 | PC | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| Services Different from Consulting |
| 1 | Training and coordination events | 45,675 | PC | ex ante | 89 | 11 | No | I Tri/2012 | II Tri/2013 | pending | Approx. 20 events, all less than $25,000 |
| 2 | Production of educational materials for external clients and health professionals | 21,500 | PC | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending | 2 processes |
| Consulting Firms |
| 1 | Assessment and expansion of the maternal and neonatal health care collaborative quality improvement model | 28,980 | QBS | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| 2 | Application of the quality improvement model in reproductive health and child nutrition | 42,945 | QBS | ex ante | 100 | 0 | No | II Tri/2012 | III Tri/2012 | pending |  |
| 3 | Financial auditing | 15,000 | FBS/ LCS |  |  |  |  |  |  |  |  |
| Individual consultants |
| 1 | Sexual and reproductive health policy, with standards, protocols, indicators and job aide tools | 12,940 | IICC | ex ante | 100 | 0 | No | II Tri/2012 | III Tri/2012 | pending |  |
| 2 | Child nutrition policy (including supplements and micronutrients) with standards | 12,940 | IICC | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| 3 | Child health (Integrated Management of Childhood Illness) standards, indicators and job aide tools | 12,940 | IICC | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| 4 | Creation and implementation of regulatory and accreditation mechanisms within the MOH Regulatory Unit | 13,300 | IICC | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| 5 | Revision of Service Level Agreements (SLA), addition of key performance indicators, and elaboration of an operations manual based on international best practice | 11,920 | IICC | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| 6 | Development of options for new payment schemes to replace existing supply-based financing | 11,920 | IICC | ex ante | 100 | 0 | No | III Tri/2012 | IV Tri/2012 | pending |  |
| 7 | Diagnosis of the Belize Health Information System (BHIS) in terms of design and user functionality | 9,920 | IICC | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| 8 | Design of report formats for interface with BHIS transactional database | 5,000 | NICQ | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| 9 | External facilitator for baby-friendly hospital accreditation | 12,940 | IICC | ex ante | 100 | 0 | No | II Tri/2012 | III Tri/2012 | pending |  |
| 10 | Assessment of the Community Health Worker (CHW) program | 12,940 | IICC | ex ante | 100 | 0 | No | I Tri/2012 | II Tri/2012 | pending |  |
| 11 | Quality Improvement Manager | 60,383 | NICQ | ex ante | 100 | 0 | No | I Tri/2012 | III Tri/2013 | pending |  |

Due to the need to establish a baseline for the facility-level indicators through a survey conducted by an independent consulting firm hired with MH2015 resources separate from the project funds, as determined by the MH2015 Initiative, in Belize

Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through Specialized Agencies; PA: Procurement Agents; IA: Inspection Agents; PLFI: Procurement in Loans to Financial Intermediaries; BOO/BOT/BOOT: Build, Own, Operate/Build, Operate, Transfer/Build, Own, Operate, Transfer; PBP: Performance-Based Procurement; PLGB: Procurement under Loans Guaranteed by the Bank; PCP: Community participation procurement. Consulting Firms: QCBS: Quality- and Cost-Based Selection QBS: Quality-Based Selection FBS: Selection under a Fixed Budget; LCS: Least-Cost Selection; CQS: Selection based on the Consultants’ Qualifications; SSS: Single-Source Selection. Individual Consultants: NICQ: National Individual Consultant selection based on Qualifications; IICC: International Individual Consultant selection based on Qualifications