## Sheet1
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Chile |  |  |  |  | Executing agency: Inter-American Development Bank |  |  |  |  | Public or private sector: Public sector
Project number: CH-T1139/CH-G1002 |  |  |  |  | Title of Project: Support to marine energy pilot projects in southern Chile
Period covered by the plan: July 2013 - July 2016
Threshold for ex post review of procurements: |  |  |  | Goods and services (in US$):____________ |  |  |  | Consulting services(in US$):440,000
Item No. | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (ex-ante or ex-post) (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other %
1 |  | Component 1: Knowledge development
|  | Cash Transfer Tidal Pilot | 1800000 | N/A | N/A | 100 |  |  | Ex ante | A cash transfer will be provided to private sector companies. This is not an acquisition.
|  | Cash Transfer Wave Pilot | 600000 | N/A | N/A | 100 |  |  | Ex ante | A cash transfer will be provided to private sector companies. This is not an acquisition.
Component 2: Knowledge development
2 |  | Consulting firm
|  | Technical evaluation of proposals received | 40000 | SSS | Ex-ante | 100 |  | 2013-09-01 | Ex ante | Wave Energy Center (WavEC) will be hired for this activity
|  | Desgin and construction supervision and commissioning | 200000 | QCBS | Ex-ante | 100 |  | 2014-07-01 | Ex ante
|  | Marine energy for comunities at Tierra del Fuego and Patagonia Austral including marein resource assessment | 50000 | SSS | Ex-ante | 100 |  |  |  | Proyect selected by the IDEAS program; a cash transfer will be realized to the selected company
|  | Development of ESMS and other oversight of pilot projects | 80000 | SSS | Ex-ante | 100 |  | 2014-07-01 |  | A very limited number of firms exist with experience in this sector and in Chile
|  | Evaluation of Infrastructure and Services for the Development of Marine Energy in Chile | 70000 | QCBS | Ex-ante | 100 |  | 2015-01-01
Individual consultant
|  | Knowledge database and info portal | 40000 | IICQ | Ex-ante | 100 |  | 2015-01-01
3 |  | Non consulting services
|  | Purchase of internet domain for knowledge database and info portal | 10000 | PC | Ex-ante | 100 |  | 2015-01-01
4 |  | Others
|  | Project Management | 20000 | N/A | N/A | 100 |  |  |  | This is not an acquisition
|  | Miscellaneous | 25000 | N/A | N/A | 100 |  |  |  | This is not an acquisition
|  | Consultant Travel | 15000 | N/A | N/A | 100 |  |  |  | This is not an acquisition
Total |  |  | 2950000 | Prepared by: Christoph Tagwerker |  |  | Date: Janury 21st, 2014
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(3) Ex ante/ex post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex post review is the standard modality. Ex ante review can be specified for critical or complex process. N/A : Non Aplicable, related to cash transfers or other non procurement cases.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.