## Sheet1
GLOBAL SERVICES OFFSHORING PROMOTION PROGRAMME
Project Number TT-L1038
PRELIMINARY PROCUREMENT PLAN
Ref. No. 1 | Description of and category of procurement contract | Estimated cost in (US$ thousand) | Procure-ment method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequali-fication 3 (Yes/No) | Estimated Dates |  | Status 4 (pending, in process, awarded, cancelled) | Comments
[5 empty] | IDB % | Local / Other % |  | Publication of specific procurement notice | Completion of contract
Component 1 - Drainage works for the critical flood areas in POS (USD 90 M)
| COMPONENT I: Services Internationalization Hub | 10395152.648
| Consulting Services | 1938037.3832
Internationalization Training and Support
| Consultancy for coordination of support services | 205607.4766 | QCBS | Ex-Ante | 100 | 0
| Consultancy for export support advisory services | 168224.2991 | QCBS | Ex-Ante | 100 | 0
| Consultancy for investment promotion technical liaison | 168224.2991 | QCBS | Ex-Ante | 100 | 0
| Consultancy services by certification appraisers/evaluators | 200000 | QCBS | Ex-Ante | 100 | 0
Finishing Schools (short term technical training)
| Consultancy for gap analysis study | 77881.6199 | QCBS | Ex-Ante | 100 | 0
| Consultancy for coordination of finishing schools | 168224.2991 | QCBS | Ex-Ante | 100 | 0
| Consultacies for curriculum development | 151666.6667 | QCBS | Ex-Ante | 100 | 0
| Consultancy for career advising services | 151401.8692 | QCBS | Ex-Ante | 100 | 0
Collaborative Physical & Technological Infrastructure
| Consultancy for Hub building management and administration | 261682.243 | QCBS | Ex-Ante | 100 | 0
| Consulting firm for technological needs for build-out | 46728.972 | QCBS | Ex-Ante | 100 | 0
| Consulting firm for design of nursery & lactation space | 23364.486 | QCBS | Ex-Ante | 100 | 0
| Engineering and architectural services | 101246.1059 | QCBS | Ex-Ante | 100 | 0
| Building security contract | 213785.0467 | QCBS | Ex-Ante | 100 | 0
| Non Consulting Services | 2282037.3832
Internationalization Training and Support
| Trainers and workshop facilitators | 84112.1495 | NCB | Ex-Ante | 100 | 0
| Flights and accomodation for international facilitators | 125000 | Shopping | Ex-Ante | 100 | 0
| Advertising | 14953.271 | Shopping | Ex-Ante | 100 | 0
| Flights and accomodation for certification providers | 53000 | Shopping | Ex-Ante | 100 | 0
Finishing Schools (short term technical training)
| Instructors | 1400000 | ICB | Ex-Ante | 100 | 0
| Flights and accomodation for overseas instructors | 276000 | Shopping | Ex-Ante | 100 | 0
| Advertising | 17445.4829 | NCB | Ex-Ante | 100 | 0
Collaborative Physical & Technological Infrastructure
| Utilities, insurance, and maintenance | 311526.4798 | ICB | Ex-Ante | 100 | 0
| Goods | 6175077.8816
Internationalization Training and Support
| Rental of technical equipment | 15576.324 | Shopping | Ex-Ante | 100 | 0
| Training materials | 18691.5888 | Shopping | Ex-Ante | 100 | 0
Finishing Schools (short term technical training)
| Training materials | 34890.9657 | Shopping | Ex-Ante | 100 | 0
Collaborative Physical & Technological Infrastructure
| Hub building lease (first 3 years) | 1345794.3925 |  | Ex-Ante | 100 | 0
| Hub building purchase (option following Year 3) | 3327102.8037 |  | Ex-Ante | 100 | 0
| Initial build-out labor and materials | 498442.3676 | ICB | Ex-Ante | 100 | 0
| Technology, equipment, and furnishings | 934579.4393 | ICB | Ex-Ante | 100 | 0
| COMPONENT II: Sector Promotion & Branding | 5160877.2586
| Consulting Services | 1320903.4268
Sector Data Collection & Analysis
| Consulting firm for design of sector data initiative and agency capacity-building | 62305.296 | QCBS | Ex-Ante | 100 | 0
| Consultancies for data collection services | 60000 | QCBS | Ex-Ante | 100 | 0
| Consultancy for system administration and analysis | 280373.8318 | QCBS | Ex-Ante | 100 | 0
| Consultancy for administrative assistant | 112149.5327 | QCBS | Ex-Ante | 100 | 0
Sector Branding Campaign
| Consulting firm for market research, branding campaign design, and advertising | 623052.9595 | QCBS | Ex-Ante | 100 | 0
| Consulting firm for advertising | 116822.4299 | QCBS | Ex-Ante | 100 | 0
Diaspora Engagement for Internationalization
| Consultancy for diaspora market research | 66199.3769 | QCBS | Ex-Ante | 100
| Non Consulting Services | 3377357.0093
Sector Data Collection & Analysis
| Transportation and expenses | 74766.3551 | Shopping | Ex-Ante | 100 | 0
Sector Branding Campaign
| Facilitators for stakeholder consultation events | 155763.2399 | NCB | Ex-Ante | 100 | 0
| Travel expenses for international facilitators | 9600 | Shopping | Ex-Ante | 100 | 0
| Brand dissemination events | 303738.3178 | ICB | Ex-Ante | 100 | 0
Global Services Promotion Forums
| Global services promotion forums | 778816.1994 | ICB | Ex-Ante | 100 | 0
| Travel expenses to attend forums abroad | 54517.134 | Shopping | Ex-Ante | 100 | 0
Diaspora Engagement for Internationalization
| Capacity building of investment officer for diaspora outreach | 46728.972 | Shopping | Ex-Ante | 100 | 0
| Mentor travel expenses | 1096728.972 | Shopping | Ex-Ante | 100 | 0
| Networking events. Missions, fairs, symposiums, workshops, etc. | 350467.2897 | ICB | Ex-Ante | 100 | 0
| Annual diaspora award ceremony events | 506230.5296 | ICB | Ex-Ante | 100 | 0
| Goods | 462616.8224
Sector Data Collection & Analysis
| Equipment and software | 18691.5888 | Shopping | Ex-Ante | 100 | 0
Diaspora Engagement for Internationalization
| Materials development for mentor outreach | 54517.134 | NCB | Ex-Ante | 100 | 0
| Printing and advertising expenses | 389408.0997 | Shopping | Ex-Ante | 100 | 0
| COMPONENT III: Capacity Building to Update Policy and Regulatory Framework | 1076581.9315
| Consulting Services | 576012.4611
Regulatory analysis and strategy
| Consultants to identify regulatory gaps | 249221.1838 | QCBS | Ex-Ante | 100 | 0
| Consulting firm to develop strategic policy framework for the ICT sector | 101246.1059 | QCBS | Ex-Ante | 100 | 0
Analysis of policy and agency roles to support growth
| Consultancy for best practices study | 23364.486 | QCBS | Ex-Ante | 100 | 0
Capacity-building programs for agencies
| Consultancies for design of capacity building programs | 186915.8879 | QCBS | Ex-Ante | 100 | 0
| Consultancy for revision of agency manuals | 15264.7975 | QCBS | Ex-Ante | 100 | 0
| Non Consulting Services | 490351.4019
Regulatory analysis and strategy
| Travel expenses | 41400 | Shopping | Ex-Ante | 100 | 0
Technical exchanges
| Facilitators | 124610.5919 | NCB | Ex-Ante | 100 | 0
| Logistics (equipment and materials) | 9345.7944 | Shopping | Ex-Ante | 100 | 0
| Travel expenses | 275000 | Shopping | Ex-Ante | 100 | 0
Analysis of policy and agency roles to support growth
| Roundtable facilitators | 17133.9564 | Shopping | Ex-Ante | 100 | 0
| Travel expenses | 10400 | Shopping | Ex-Ante | 100 | 0
Capacity-building programs for agencies
| Workshop facilitators | 12461.0592 | Shopping | Ex-Ante | 100 | 0
| Goods | 10218.0685
Capacity-building programs for agencies
| Program materials | 6230.5296 | Shopping | Ex-Ante | 100 | 0
| Equipment rental | 3987.5389 | Shopping | Ex-Ante | 100 | 0
| Monitoring and Evaluation | 409657.3209
| Consulting Services | 409657.3209
| Annual audits | 194704.0498 | QCBS | Ex-Ante | 100 | 0
PROGRAM MONITORING
| Consultancy for design of feedback and questionnaires for firms, students, and agencies participating | 28037.3832 | QCBS | Ex-Ante | 100 | 0
| Consultancy for administration and analysis of program evaluation system | 31152.648 | QCBS | Ex-Ante | 100 | 0
| Contingency for immediate ammendments to programs | 97352.0249 | QCBS | Ex-Ante | 100 | 0
FINAL EVALUATION
| Study of human capital impact (student placement) | 19470.405 | QCBS | Ex-Ante | 100 | 0
| Study of branding and promotion campaign impact (brand awareness) | 19470.405 | QCBS | Ex-Ante | 100 | 0
| Study of policy improvements | 19470.405 | QCBS | Ex-Ante | 100 | 0
| Program Administration | 957730.8411
| Consulting Services | 957730.8411
| Consultancy for project management | 205607.4766 | QCBS | Ex-Ante | 100 | 0
| Consultancy for project assistant | 112149.5327 | QCBS | Ex-Ante | 100 | 0
| Consultancy for procurement specialist | 168224.2991 | QCBS | Ex-Ante | 100 | 0
| Consultancy for financial specialist | 186915.8879 | QCBS | Ex-Ante | 100 | 0
| Administrative expenses | 112149.5327 | QCBS | Ex-Ante | 100 | 0
| Administrative contingency | 172684.1121 | QCBS | Ex-Ante | 100 | 0
TOTAL |  | 18000000
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.