## Sheet1
Loan 2890/OC-TT - Multiphase Wastewater Infrastructure Rehabilitation Program Phase I
PROCUREMENT PLAN
FROM JANUARY 2014 to JUNE 2015
Ref. No. 1 | Reference to SEPA code | Comp. No. | Description of and Component of procurement contract | Indicative cost (USD) | Procurement Selection method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequalification 3 (YES/NO) | Estimated Dates |  | Actual dates |  | Status 4 (pending; in process; awarded; cancelled) | Comments
[7 empty] | IDB % | Local/Other % |  | Publication of specific procurement notice | Completion of Contract | Publication of specific procurement notice | Completion of Contract
1 |  |  | GOODS
|  | 2.3 | Equipment for sewer maintenance | 200000 | ICB | Ex-ante | 100 | 0 | No | 2014-10-23 | 2015-08-26 |  |  | Pending
|  | 2.3 | Equipment for water quality monitoring | 250000 | ICB | Ex-ante | 100 | 0 | No | 2014-08-05 | 2014-10-31 |  |  | Pending
2 |  |  | WORKS
|  | 2.1 | Construction of Bridge and Access Road to the New San Fernando Wastewater Treatment Plant | 2492056.07 | NCB | Ex-ante | 100 | 0 | No | 2013-10-03 | 2014-06-09 |  |  | In process
|  | 2.1 | Construction of Malabar and San Fernando WWTPs, Collection System and Sewer Service Connections
|  |  | Construction (and Operation) of San Fernando WWTP & Collection System | 129387443.93 | ICB | Ex-ante | 100 | 0 | Yes | 2014-05-22 | 2018-05-17 |  |  | In process
|  |  | Construction (and Operation) of Malabar WWTP & Collection System | 79,062,500 | ICB | Ex-ante | 100 | 0 | Yes | 2014-05-22 | 2017-11-28 |  |  | In process
3 |  |  | NON CONSULTING SERVICES
|  | 2.3 | Environmental Education Campaign | 50000 |  |  | 100 | 0 | No | 2014-02-04 | 2017-07-31 |  |  | Pending
4 |  |  | CONSULTING SERVICES
Works Supervision
|  | 1.2 | Supervision of construction of San Fernando WWTP and Collection System | 3000000 | QCBS | Ex-ante | 100 | 0 | Yes | 2014-02-13 | 2018-04-18 |  |  | In process
|  | 1.2 | Supervision of construction of Malabar WWTP and Collection System | 2445000 | QCBS | Ex-ante | 100 | 0 | Yes | 2014-02-13 | 2018-04-18 |  |  | In process
Institutional Strengthening of WASA
|  | 2.3 | Training for water quality monitoring | 50000 | QCBS | Ex-ante | 100 | 0 | Yes | 2014-08-05 | 2014-11-24 |  |  | In process
|  | 2.3 | Training activities in O&M and BO Contract Management | 100000 | QCBS | Ex-ante | 100 | 0 | Yes | 2016-10-18 | 2017-09-13 |  |  | In process
|  | 2.3 | Corporate Governance Individual Consultant | 100000 | QCII | Ex-ante | 100 | 0 | No | 2013-08-02 | 2015-08-06 |  |  | In Process
|  | 2.3 | Corporate Governance Consulting Firm | 820000 | QCBS | Ex-ante | 100 | 0 | Yes | 2014-04-14 | 2016-04-14 |  |  | In process
|  | 2.3 | Customer database & billing engine and software integration (purchase and instalaltion) | 2600000 | ICB | Ex-ante | 100 | 0 | Yes | 2014-06-13 | 2016-06-11
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Codes from SEPA