## Procurement Plan
BH-L1035 Performance Monitoring and Public Financial Management Reform
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: | 2014-10-22 | 2019-12-31
2. Procurement Plan Details
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Individual consultants | 1830200 | 1830200
Goods | 16825100 | 16825100
Consulting firms | 11933700 | 11933700
Contingencies | 1300000 | 1300000
Total | 31889000 | 31889000
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
1. Planning and Performance Monitoring | 3160000 | 3160000
2. National Statistic | 3000000 | 3000000
3. Public Expenditure | 18160000 | 18160000
4. National Public Procurement | 6000000 | 6000000
5. Project Administration | 1380000 | 1380000
6. Contingencies | 1300000 | 1300000
Total | 33000000 | 33000000

## Detailed PP
BH-L 1035 Performance Monitoring and Public Financial Management Reform (US$) (BH-L1035)
Procurement plan 2014-2019
Dates
N. | Procurement Name/Activity | Lote/Process number | Review Method | IDB amount | Total Amount | Componente | Executing agency | Procurement Method | Publication of specific procurement notice | Completion of contract | Associated component | Description
INDIVIDUAL CONSULTANTS
1 | Preparation of a Statistics Act draft | N/A | Exante | 85800 | 85800 | 1, 2 y 3 | MOF | NICQ | 2015 | 2015 | 1 | Preparation of a Statistics Act draft, which will guide the modernization of the NSS; Lawyer in Statistics legislation
2 | Development of a National Strategy for Statistical Development (NSDS) | N/A | Exante | 114400 | 114400 |  | MOF | IICQ | 2016 | 2016 | 2 | Development and implementation of a National Strategy for Statistical Development (NSDS) including all stakeholders within the NSS;
3 | Elaboration of legal regulations, standard bidding documents and manuals. | N/A | Exante | 250000 | 250000 |  | MOF | NICQ | 2016 | 2016 | 4 | National lawyer able to elaborate regulations and documents based on the new business model, and on the new Financial Act
4 | Mid-term Monitoring report | N/A | Exante | 30000 | 30000 |  | MOF | NICQ | 2017 | 2017 | 5 | Mid -term Monitoring report
5 | Final Monitoring report | N/A | Exante | 30000 | 30000 |  | MOF | NICQ | 2019 | 2019 | 5 | Final Monitoring report
6 | Prepare mid-term evaluation of the project | N/A | Exante | 60000 | 60000 |  | MOF | NICQ | 2017 | 2017 | 5 | Mid term - evaluation of the project
7 | Prepare the final evaluation of the project | N/A | Exante | 60000 | 60000 |  | MOF | IICQ | 2019 | 2019 | 5 | Final evaluation of the project
8 | TOR preparation | N/A | Exante | 144000 | 144000 |  | MOF | NICQ | 2015 | 2015 | 5 | Preparation of all Terms of reference for the project
9 | Fiscal and procurement peripatetic external firm | N/A | Exante | 1056000 | 1056000 |  | MOF | IICQ | 2015 | 2019 | 5 | Management of the program
|  |  |  | 1830200 | 1830200
GOODS
1 | New IT System for government policies performance monitoring (off the shelf) | N/A | Exante | 700000 | 700000 | 1 | MOF | ICB | 2016 | 2016 | 1 | This is an ICT system for monitoring government priority projects and programs across government, with physical and financial targets, among other data, including the corresponding hardware infrastructure.
2 | IT infrastructure for implementation of the Performance system | N/A | Exante | 15000 | 15000 |  | MOF | NCB | 2016 | 2016 | 1 | IT infrastructure for implementation of the Performance system
3 | Laptops for the implementation of the Performance system | N/A | Exante | 30000 | 30000 |  | MOF | PC | 2016 | 2016 | 1 | IT infrastructure for implementation of the Performance system
4 | Desktops for the implementation of the Performance system | N/A | Exante | 20000 | 20000 |  | MOF | PC | 2016 | 2016 | 1 | Desktops for the implementation of the Performance system in the Prime Minister Office
5 | Specific equipment for training room | N/A | Exante | 0 | 0 |  | MOF | ICB | 2017 | 2017 | 1 | Equipment for the training room that will be support the implementation of the Performance system in the Prime Minister Office
6 | New IT statistic System and WEB site | N/A | Exante | 1900100 | 1900100 | 1 | MOF | ICB | 2017 | 2017 | 2 | Development and implementation of an information system, automating the entire processes of generating and disseminating information.
7 | IT infrastructure to implement the IT statistic system | N/A | Exante | 0 | 0 | 1 | MOF | NCB | 2017 | 2017 | 2 | Wiring and other goods related to the implementation of the statistics systems
8 | Desktops | N/A | Exante | 0 | 0 | 1 | MOF | PC | 2017 | 2017 | 2 | Desktop for the use of the new statistics organization
9 | New IFMIS system including configuration and customization | N/A | Exante | 8000000 | 8000000 |  | MOF | ICB | 2016 | 2019 | 3 | The acquisition and implementation of an off-the-shelf highly customizable IFMIS including full standard functionality, in addition to the modules for budget formulation and payroll/HR.
10 | IT Data Center Infrastructure for the IFMIS | N/A | Exante | 1000000 | 1000000 |  | MOF | ICB | 2016 | 2019 | 3 | Solution for the implementation of the new IFMIS
11 | IT Telecomm center | N/A | Exante | 500000 | 500000 |  | MOF | ICB | 2017 | 2017 | 3 | Goods to equip the help desk for the implementation of the new IFMIS
12 | Strengthen disaster recovery capability for the Mof | N/A | Exante | 1000000 | 1000000 |  | MOF | ICB | 2017 | 2017 | 3 | Servers to provide back up to the system
13 | Desktops | N/A | Exante | 360000 | 360000 |  | MOF | ICB | 2017 | 2017 | 3 | Desktops to use in the new office for the IFMS implementation
14 | Facilities and equipment for the new procurement business model | N/A | Exante | 500000 | 500000 |  | MOF | ICB | 2018 | 2018 | 4 | Printers, scanners and other equipment for the new procurmeent unit
15 | New e-procurement system | N/A | Exante | 1800000 | 1800000 |  | MOF | ICB | 2017 | 2019 | 4 | New e-procurement system
16 | IT Infrastructure | N/A | Exante | 1000000 | 1000000 |  | MOF | ICB | 2018 | 2019 | 4 | IT infrastructure for the new e-procurement system such us wires
|  |  |  | 16825100 | 16825100
CONSULTING FIRMS
1 | The development of the new management model for monitoring the implementation of priority projects and programs. | N/A | Exante | 111000 | 111000 | 1 | MOF | QCBS | 2015 | 2015 | 1 | Consultoria para la construccion conseptual del CIS, modelo de negocio, sostebilidad y de operación de los CIS 1 y 2. Asi como la caracterizacion de los tramites y servcios a prestar
2 | Design and implement an intensive training program to strengthen capacity of central team in charge of running the management model. | N/A | Exante | 1435000 | 1435000 |  | MOF | QCBS | 2017 | 2017 | 1 | The establishment of an intensive training program to strengthen capacity of central team in charge of running the management model.
3 | Design and implementation of new business processes of the Department of statistics | N/A | Exante | 517700 | 517700 |  | MOF | QCBS | 2016 | 2016 | 2 | Design and implementation of new business processes including: the new organizational structure of the Department of Statistic (DoS), staffing, IT, work flow and administrative procedures; and implementation of an institutional training program for both the DoS and the NSS
4 | Design and Implementation of an institutional training program for both the DoS and the NSS | N/A | Exante | 0 | 0 |  | MOF | CQS | 2016 | 2016 | 2 | This consultancy will help to design and Implementation of an institutional training program for both the DoS and the NSS
5 | Preparation a needs assessment for financial management and the strategic plan | N/A | Exante | 1000000 | 1000000 |  | MOF | QCBS | 2015 | 2015 | 3 | Preparation of a comprehensive needs assessment, including medium-term framework, budget formulation, budget execution, cash and debt management, accounting, internal control, external audit, reporting and ICT, as well as a detailed proposal and implementation plan for the strengthening of the current business model;
6 | The implementation of the recommendations to be proposed by the needs assessment for financial management and the strategic plan. | N/A | Exante | 4000000 | 4000000 |  | MOF | QCBS | 2016 | 2019 | 3 | The implementation of the recommendations to be proposed by the needs assessment, manage the full lifespan of the project, and create change management plan.
7 | Functional and technical specification of a new Integrated Financing Management Information System (IFMIS) including integration requirements to current systems and security access controls definis for RFP | N/A | Exante | 300000 | 300000 |  | MOF | QCBS | 2016 | 2019 | 3 | Functional and technical specification (including review and recommendations of changes needed to MoF Data Center regarding sustainability and capacity) of a new Integrated Financing Management Information System (IFMIS) including integration requirements to current systems and security access controls definis for RFP
8 | Support to the implementation of the upgrade of the current Masterpiece system to current version, new Charter of Accounts, etc. | N/A | Exante | 2000000 | 2000000 |  | MOF | QCBS | 2017 | 2019 | 3 | This consultancy upgrade of the current Masterpiece system to current version, implement new Charter of Accounts, and address key functionality and reporting gaps, aiming to sustain it for 5 years.
9 | Review of the current situation and the preparation of a proposal for a procurement business model, including an action plan for its implementation | N/A | Exante | 300000 | 300000 |  | MOF | QCBS | 2015 | 2015 | 4 | This consultancy will review of the current situation and prepare a proposal for a procurement business model, including an action plan for its implementation,
10 | Preparation of the functional and technical specification of an e-procurement system and project oversight and quality assurance of the implementation | N/A | Exante | 500000 | 500000 |  | MOF | QCBS | 2015 | 2015 | 4 | Preparation of the functional and technical specification of an e-procurement system and project oversight and quality assurance of the implementation
11 | Elaborate and implement a change management strategy based on the new procurement system | N/A | Exante | 250000 | 250000 |  | MOF | QCBS | 2016 | 2016 | 4 | This will support the implementation of the new business model, including the establishment of a new Public Procurement Unit, the new procedures, the instruments according to the new Financial Act.
12 | Elaborate and implement a training strategy for the implementation of the new procurement system | N/A | Exante | 250000 | 250000 |  | MOF | QCBS | 2016 | 2016 | 4 | This will support the implementation of the new business model, including the establishment of a new Public Procurement Unit, the new procedures, the instruments according to the new Financial Act.
13 | Development a career path startegy and curricula for public procurement officials, including a permanent training program. | N/A | Exante | 250000 | 250000 |  | MOF | QCBS | 2016 | 2016 | 4 | Development and implementation of a career path for public procurement officials, including a permanent training program
14 | Provide the training based on the career path strategy | N/A | Exante | 900000 | 900000 |  | MOF | QCBS | 2016 | 2016 | 4 | Development and implementation of a career path for public procurement officials, including a permanent training program
15 | Auditing | N/A | Exante | 120000 | 120000 |  | MOF | CQS | 2019 | 2019 | 5 | Final audit of the program
|  |  |  | 11933700 | 11933700
WORKS
|  |  |  | 0 | 0
|  |  |  | 0 | 0
| Contingencies |  |  | 1300000
33

## Detailed Budget
Performance Monitoring and Public Financial Management Reform (US$) (BH-L1035) | [19 empty] | 33000000
Component I. Planning and Performance Monitoring | [19 empty] | 3160000
Products | Consultancy |  |  |  | Systems |  | Equipment |  |  |  | Training |  |  |  | Infrastructure |  |  |  | Sub-Total | Total Product
| Description | Duration days | Honorary | total | Description | Total | Description | Quant | Unit Cost | Total | Description | Participants | Unit Cost | Total | Description | Sq. Ft | Unit Cost | total
1) The development and implementation of new procedures (management model) for monitoring the implementation of priority projects and programs. | International performance management expert (inc. 2 trips) | 30 | 3700 | 111000 | [5 empty] | 0 | Monitoring of priorities and performance improvement | 30 | 300 | 9000 |  |  |  | 0 | 120000 | 120000 | 3160000
2) The implementation of an ICT system for monitoring government priority projects and programs across government, with physical and financial targets, among other data, including the corresponding hardware infrastructure. |  |  |  | 0 | New IT System for the management of the government policies (off the self) | 700000 | Servers | 3 | 5000 | 15000 |  |  |  | 0 |  | 0 | 0 | 0 | 715000 | 1605000
|  |  |  | 0 | Maintenance | 840000 | Laptops | 20 | 1500 | 30000 |  |  |  | 0 |  |  |  | 0 | 870000
|  |  |  | 0 |  |  | Tablets | 20 | 1000 | 20000 |  |  |  | 0 |  |  |  | 0 | 20000
3) The establishment of an intensive training program to strengthen capacity of central team in charge of running the management model. | Local public policy and/or management consultants (sector analysts) | 4224 | 340 | 1435000 | [14 empty] | 1435000 | 1435000
Component II. National Statistics | [19 empty] | 3000000
Products | Consultancy |  |  |  | Systems |  | Equipment |  |  |  | Training |  |  |  | Infrastructure |  |  |  | Sub-Total | Total Product | 3000000
| Description | Duration days | Honorary | total | Description | Total | Description | Quant | Unit Cost | Total | Description | Participants | Unit Cost | Total | Description | Sq. Ft | Unit Cost | total
1)Preparation of a Statistics Act draft, which will guide the modernization of the NSS; | Lawyer in Statistics legislation | 66 | 1300 | 85800 | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | 85800 | 85800
2) Development and implementation of a National Strategy for Statistical Development (NSDS) including all stakeholders within the NSS; | Expert in Statistic Strategy | 88 | 1300 | 114400 | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | 114400 | 114400
3) Development and implementation of new business processes including: the new organizational structure of the Department of Statistic (DoS), staffing, IT, work flow and administrative procedures; | Expert in Business Processes | 396 | 1300 | 517700 | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | 517700 | 517700
4) Implementation of an institutional training program for both the DoS and the NSS |  |  |  | 0 | [6 empty] | In Statistical concepts | 280 | 1000 | 280000 |  |  |  |  | 280000 | 280000
5) Development and implementation of an information system, automating the entire processes of generating and disseminating information. | Expert in communications | 78 | 1300 | 102000 | New IT statistic System and WEB site | 1900100 | [7 empty] | 0 |  |  |  | 0 | 2002100 | 2002100
[10 empty] | 0 | [8 empty] | 0
Component III. Public Expenditure | [19 empty] | 18160000
Products | Consultancy |  |  |  | Systems |  | Equipment |  |  |  | Training |  |  |  | Infrastructure |  |  |  | Sub-Total | Total Product
| Description | Duration days | Honorary | total | Description | Total | Description | Quant | Unit Cost | Total | Description | Participants | Unit Cost | Total | Description | Sq. Ft | Unit Cost | total |  |  | 18160000
1) Preparation of a comprehensive needs assessment, including medium-term framework, budget formulation, budget execution, cash and debt management, accounting, internal control, external audit, reporting and ICT, as well as a detailed proposal and implementation plan for the strengthening of the current business model; | Consulting Firm | 1 | 1000000 | 1000000 | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | 1000000 | 1000000
2) The implementation of the recommendations to be proposed by the needs assessment, manage the full lifespan of the project, and create change management plan. | Consulting Firm for 4 years implementation of procedures and system | 1 | 4000000 | 4000000 | [14 empty] | 4000000 | 4000000
3) Functional and technical specification (including review and recommendations of changes needed to MoF Data Center regarding sustainability and capacity) of a new Integrated Financing Management Information System (IFMIS) including integration requirements to current systems and security access controls definis for RFP | Consulting Firm | 1 | 300000 | 300000 | [14 empty] | 300000 | 300000
4) The acquisition and implementation of an off-the-shelf highly customizable IFMIS including full standard functionality, in addition to the modules for budget formulation and payroll/HR, |  | 0 |  | 0 | New IFMIS system including configuration and customization) | 8000000 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 8000000 | 10860000
|  |  |  | 0 |  | 0 | IT Data Center Infrastructure | 1 | 1000000 | 1000000 |  |  |  | 0 |  |  |  | 0 | 1000000
|  |  |  | 0 |  | 0 | IT Telecomm | 1 | 500000 | 500000 |  |  |  | 0 |  |  |  | 0 | 500000
|  |  |  | 0 |  | 0 | Strengthen disaster recovery capability for the Mof | 1 | 1000000 | 1000000 |  |  |  | 0 |  |  |  | 0 | 1000000
|  |  |  | 0 |  | 0 | Desktops | 300 | 1200 | 360000 |  |  |  | 0 |  |  |  | 0 | 360000
5) The upgrade of the current Masterpiece system to current version, implement new Charter of Accounts, and address key functionality and reporting gaps, aiming to sustain it for 5 years. | Consulting firm and Infor vendor | 1 | 2000000 | 2000000 | [14 empty] | 2000000 | 2000000
Products | Consultancy |  |  |  | Systems |  | Equipment |  |  |  | Training |  |  |  | Infrastructure |  |  |  | Sub-Total | Total Product
| Description | Duration days | Honorary | total | Description | Total | Description | Quant | Unit Cost | Total | Description | Participants | Unit Cost | Total | Description | Sq. Ft | Unit Cost | total
Component IV. National Public Procurement | [19 empty] | 6000000
1) Review of the current situation and the preparation of a proposal for a procurement business model, including an action plan for its implementation | Consultancy firm | 1 | 300000 | 300000 | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | 300000 | 300000 | 6000000
2) Implementation of the new business model, including the establishment of a new Public Procurement Unit, the new procedures, the instruments according to the new Financial Act (regulations, standard bidding documents, manuals, training and change management plan), and the management of physical and technological infrastructure. | Consultancies pending international firm | 3 | 250000 | 750000 |  |  | Facilities and equipment | 25 | 20000 | 500000 |  |  |  | 0 |  |  |  |  | 1250000 | 1250000
3) Preparation of the functional and technical specification of an e-procurement system and project oversight and quality assurance of the implementation | Consultancy ¦Firm | 1 | 500000 | 500000 | [14 empty] | 500000 | 500000
4) Implementation of the e-procurement system, including e-tender functionality |  | 0 | 0 | 0 | new e-procurement system | 1800000 | IT Infrastructure | 1 | 1000000 | 1000000 |  |  |  | 0 |  |  |  | 0 | 2800000 | 2800000
5) Development and implementation of a career path for public procurement officials, including a permanent training program | Consultancy ¦Firm | 1 | 250000 | 250000 | [5 empty] | 0 | FirmTraining for procurement professionals | 1 | 900000 | 900000 |  |  |  | 0 | 1150000 | 1150000
Project Management | [19 empty] | 2680000
Project Coordinating Unit | TOR preparation | 88 | 1600 | 144000 | [5 empty] | 0 |  |  |  | 0 |  |  |  |  | 144000 | 144000 | 1200000
| Fiscal and procurement peripatetic external consultant | 660 | 1600 | 1056000 | [5 empty] | 0 |  |  |  | 0 |  |  |  |  | 1056000 | 1056000
Monitoring | monitoring Consultancy | 1 | 60000 | 60000 | [5 empty] | 0 |  |  |  | 0 |  |  |  |  | 60000 | 60000
Evaluation | Evaluation Consultancy | 1 | 120000 | 120000 | [5 empty] | 0 |  |  |  | 0 |  |  |  |  | 120000 | 120000
Auditing | Auditing/ local firm (as per Mario suggestion) and general auditor is eligible | 1 | 120000 | 120000 | [5 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | 0
Contingency | contingency | 1 | 1300000 | 1300000 | [5 empty] | 0 |  |  |  | 0 |  |  |  |  | 1300000 | 1300000
Common Unit Resources | Cost
Local Consultancy | 800
International Consultancy (including $500 perdiem and flight) | 1600 |  |  | 1296800
Desktops | 1200
Laptops | 2000
Sq. Ft Remodel | 100
Training / person | 300
Note on D5: Mariano Lafuente: Consultant fees of recommended consultant are US$ 3,000 per day. Estimate includes 30 days of work (2 trips of 10 days each and 10 days working remotely)
Note on E5: Peter: 3 experts, 3 months + overhead
Note on E6: Peter: 3 experts, 3 months + overhead
Note on P6: Familia Cracel: Cables, false floor, etc.
Note on E7: Peter: 3 experts, 3 months + overhead
Note on G7: Mariano Lafuente: 25% of total cost per year. Maintenance for years 2, 3, 4 and 5 (devt in year 1)
Note on I7: Mariano Lafuente: For performance teams in Finance and in line ministries with priority projects
Note on E8: Peter: 3 experts, 3 months + overhead
Note on C9: Mariano Lafuente: 4 consultants, full time, for 4 years (264 days a year each)
Note on D9: Mariano Lafuente: US$ 90,000 per year each consultant
Note on E9: Peter: 3 experts, 3 months + overhead
Note on C13: Familia Cracel: 3 months * 22 working days
Note on C15: Familia Cracel: 3 experts 6 months, processes, human resources, organizational structure
Note on D22: Peter: 10 experts, 3 months, + overhead
Note on D23: Peter: 4 years, 4 experts, + overhead
Note on D24: Peter: 3 experts, 3 months + overhead
Note on I26: Peter: Platforms are already in place, adding blade servers and racks and related software licensing
Note on I27: Familia Cracel: Mof and Line Ministries
Note on D30: Peter: 3 version upgrade new CoA business requirement IT changes to close functional gaps
Note on C34: Familia Cracel: 3 months * 22 working days
Note on N38: Peter: 150 SU, 2 persons, us$3,000
Note on C41: Familia Cracel: 5 years * 132 days year

## Budget POD
Table 3. Project Total Budget (in US$)
Categories* | BID | Local | Total | %
1. Direct Costs | 30320000 | 0 | 30320000 | 91.8788 |  |  |  |  | 0
1.1 Planning and Performance Monitoring | 3160000 | 0 | 3160000 | 9.5758
1.2 National Statistic | 3000000 | 0 | 3000000 | 9.0909
1.3 Public Expenditure | 18160000 | 0 | 18160000 | 55.0303
1.4 National Public Procurement | 6000000 | 0 | 6000000 | 18.1818
2. Project Administration | 1380000 | 0 | 1380000 | 4.1818
2.1 Project management | 1200000 | 0 | 1200000 | 3.6364
2.2 Monitoring and Evaluation | 180000 | 0 | 180000 | 0.54545
2.3 Audit | 0 | 0 | 0 | 0
3. Contingency | 1300000 | 0 | 1300000 | 3.9394
Total | 33000000 | 0 | 33000000 | 100
% | 100 | 0 | 100
* The financing costs will be paid by the borrower outside of the Program.
Table 4. Disbursement timetable (US$ millions)
| Source | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total | %
| BID | 4621000 | 8420300 | 8385300 | 5944200 | 5629200 | 33000000 | 100
| Local | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 4621000 | 8420300 | 8385300 | 5944200 | 5629200 | 33000000 | 100
| % | 14.003 | 25.5161 | 25.41 | 18.0127 | 17.0582 | 100

## PEP
Budget / Product / Year
Project Total | 33000000 | 14.003 | 4621000 | 25.5161 | 8420300 | 25.41 | 8385300 | 18.0127 | 5944200 | 17.0582 | 5629200
Component I. Planning and Performance Monitoring | Total Product | % | year 1 | % | year 2 | % | year 3 | % | year 4 | % | year 5
| 3160000 |  | 120000 |  | 1605000 |  | 1435000 |  | 0 |  | 0
1) The development and implementation of new procedures (management model) for monitoring the implementation of priority projects and programs. | 120000 | 100 | 120000 |  | 0 |  | 0 |  | 0 |  | 0
2) The implementation of an ICT system for monitoring government priority projects and programs across government, with physical and financial targets, among other data, including the corresponding hardware infrastructure. | 1605000 | 0 | 0 | 100 | 1605000 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
|  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
3) The establishment of an intensive training program to strengthen capacity of central team in charge of running the management model. | 1435000 | 0 | 0 | 0 | 0 | 100 | 1435000 |  | 0 |  | 0
Component II. National Statistic | Total Product | % | year 1 | % | year 2 | % | year 3 | % | year 4 | % | year 5
| 3000000 | 2.86 | 85800 | 30.4033 | 912100 | 66.7367 | 2002100 | 0 | 0 | 0 | 0
1)Preparation of a Statistics Act draft, which will guide the modernization of the NSS; | 85800 | 100 | 85800 |  | 0 |  | 0 |  | 0 |  | 0
2) Development and implementation of a National Strategy for Statistical Development (NSDS) including all stakeholders within the NSS; | 114400 | 0 | 0 | 100 | 114400 |  | 0 |  | 0 |  | 0
3) Development and implementation of new business processes including: the new organizational structure of the Department of Statistic (DoS), staffing, IT, work flow and administrative procedures; and implementation of an institutional training program for both the DoS and the NSS | 517700 |  | 0 | 100 | 517700 |  | 0 |  | 0 |  | 0
4) Implementation of an institutional training program for both the DoS and the NSS | 280000 |  | 0 | 100 | 280000 |  | 0 |  | 0 |  | 0
5) Development and implementation of an information system, automating the entire processes of generating and disseminating information. | 2002100 |  | 0 | 0 | 0 | 100 | 2002100 |  | 0 |  | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
Component III. Public Expenditure | Total Product | % | year 1 | % | year 2 | % | year 3 | % | year 4 | % | year 5
| 18160000 | 16.5198 | 3000000 | 19.1189 | 3472000 | 17.467 | 3172000 | 23.4471 | 4258000 | 23.4471 | 4258000
1) Preparation of a comprehensive needs assessment, including medium-term framework, budget formulation, budget execution, cash and debt management, accounting, internal control, external audit, reporting and ICT, as well as a detailed proposal and implementation plan for the strengthening of the current business model; | 1000000 | 100 | 1000000 |  | 0 |  | 0 |  | 0 |  | 0
2) The implementation of the recommendations to be proposed by the needs assessment, manage the full lifespan of the project, and create change management plan. | 4000000 | 0 | 0 | 25 | 1000000 | 25 | 1000000 | 25 | 1000000 | 25 | 1000000
3) Functional and technical specification (including review and recommendations of changes needed to MoF Data Center regarding sustainability and capacity) of a new Integrated Financing Management Information System (IFMIS) including integration requirements to current systems and security access controls definis for RFP | 300000 |  | 0 | 100 | 300000 |  | 0 |  | 0 |  | 0
4) The acquisition and implementation of an off-the-shelf highly customizable IFMIS including full standard functionality, in addition to the modules for budget formulation and payroll/HR, | 10860000 |  | 0 | 20 | 2172000 | 20 | 2172000 | 30 | 3258000 | 30 | 3258000
|  | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | 0
5) The upgrade of the current Masterpiece system to current version, implement new Charter of Accounts, and address key functionality and reporting gaps, aiming to sustain it for 5 years. | 2000000 | 100 | 2000000 | 0 | 0 |  | 0 |  | 0 |  | 0
Component IV. National Public Procurement | Total Product | % | year 1 | % | year 2 | % | year 3 | % | year 4 | % | year 5
| 6000000 | 13.3333 | 800000 | 32.6667 | 1960000 | 20.25 | 1215000 | 20.25 | 1215000 | 13.5 | 810000
1) Review of the current situation and the preparation of a proposal for a procurement business model, including an action plan for its implementation | 300000 | 100 | 300000 |  | 0 |  | 0 |  | 0 |  | 0
2) Implementation of the new business model, including the establishment of a new Public Procurement Unit, the new procedures, the instruments according to the new Financial Act (regulations, standard bidding documents, manuals, training and change management plan), and the management of physical and technological infrastructure. | 1250000 | 0 | 0 | 20 | 250000 | 30 | 375000 | 30 | 375000 | 20 | 250000
3) Preparation of the functional and technical specification of an e-procurement system and project oversight and quality assurance of the implementation | 500000 | 100 | 500000 |  | 0 |  | 0 |  | 0 |  | 0
4) Implementation of the e-procurement system, including e-tender functionality | 2800000 |  | 0 | 20 | 560000 | 30 | 840000 | 30 | 840000 | 20 | 560000
5) Development and implementation of a career path for public procurement officials, including a permanent training program | 1150000 |  | 0 | 100 | 1150000 |  | 0 |  | 0 |  | 0
Project Management | Total Product | % | year 1 | % | year 2 | % | year 3 | % | year 4 | % | year 5
| 1380000 | 25.7391 | 355200 | 15.3043 | 211200 | 21.8261 | 301200 | 15.3043 | 211200 | 21.8261 | 301200
TOR | 144000 | 100 | 144000 |  | 0 |  | 0 |  | 0 |  | 0
Project Coordinator | 1056000 | 20 | 211200 | 20 | 211200 | 20 | 211200 | 20 | 211200 | 20 | 211200
Monitoring | 60000 |  | 0 |  | 0 | 50 | 30000 |  | 0 | 50 | 30000
Evaluation | 120000 |  | 0 |  | 0 | 50 | 60000 |  | 0 | 50 | 60000
Auditing | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 0
Contingency | 1300000 | 20 | 260000 | 20 | 260000 | 20 | 260000 | 20 | 260000 | 20 | 260000