## Sheet1
Period comprised in this Procurement Plan: From: February 2014 until December 2018
Ref. No. 1 | Reference to SEPA code | Comp. No. | Description of and Component of procurement contract | Indicative cost (USD 000) | Procurement Selection method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequalification 3 (YES/NO) | Estimated Dates |  |  | Actual dates | Status 4 (pending; in process; awarded; cancelled) | Comments
[7 empty] | IDB % | Local/Other % |  | Publication of specific procurement notice | Signing of contract | Completion of Contract | Signing of contract
1 |  |  | GOODS
|  | 1 | Human Resources Management (HRM)
|  | 1.1.1 | Implementation of HCMES
|  | 1.1.1.2 | Software Implentation by Vendor | 4115632 | ICB | Ex-Ante for HCMES and Ex-Post for Payroll | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | Implementation of HCMES/Payroll Training (Education Services) - Train the Trainer Training for Payroll To train Project Management Office (PMO) team in use of software
|  | 1.1.1.3 | Hardware | 1999760 | ICB | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2015-12-01 | TBD |  | Hardware procured for use in the HCMES
|  | 1.1.1.4 | PC's for HR Admins in SCS, SHRM (US $900 ea) PC's for Kiosks in MDA's (US $900 ea) | 135000 | Shopping | Ex-Ante | 100 | 0 | N | 2015-04-01 | 2015-07-01 | 2015-09-01 | TBD
|  | 1.1.1.7 | Firewall Set-up and Maintenance | 9200 | Shopping | Ex-Post | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | Expansion of Network at FSL
|  | 1.1.1.7 | Expansion of Network at FSL | 2400 | Shopping | Ex-Post | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | Expansion of Network at FSL
|  | 1.1.1.7 | BVPN- Business Virtual Private Network (secondary link) | 340 | Shopping | Ex-Post | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | Expansion of Network at FSL
|  | 1.1.1.7 | Metro connection at Datacentre (J$110,000/month ie increase of J$22,000/month)) | 7920 | Shopping | Ex-Post | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | Expansion of Network at FSL
|  | 1.1.1.7 | Internet to data centre (J$175,000/month i.e. Increase J$44,000/month) | 15840 | QCBS | Ex-post | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | Expansion of Network at FSL
|  | 1.2.1 | Strengthening the Capacity of Strategic Human Resource Management Division (SHRMD)
|  | 1.2.1.1 | Workshop on international experiences on workforce planning delivered | 50000 | QCBS | Ex-Ante | 100 | 0 | N | 2015-11-01 | 2016-02-01 | 2016-08-01 | TBD |  | International flight ticket for individual international consultants and/or government officials from other Commonwealth countries
|  | 2 | Information & Communication Technologies Management (ICTM)
|  | 2.1 | Institutional strengthening of the new ICT governance framework
|  | 2.1.1.3 | IT equipment | 52000 | Shopping | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-03-01 | 2015-05-01 | TBD |  | e-Government framework & strategy
|  | 2.1.1.5 | Workshops | 10000 | Shopping | Ex-Post | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2015-12-01 | TBD |  | e-Government framework & strategy
|  | 2.1.2.2 | Workshop - Key instruments and policies to support new e-government framework | 10000 | Shopping | Ex-Post | 100 | 0 | N | 2016-04-01 | 2016-07-01 | 2016-09-01 | TBD |  | e-Government framework & strategy
|  | 2.2 | Streamling the process of the GEI
|  | 2.2.2.1 | Study tour | 50000 | shopping | Ex-Ante | 100 | 0 | N | 2015-08-01 | 2015-11-01 | 2015-01-01 | TBD |  | GEI process automation completed and online applications system in operation
|  | 2.3 | Establishment of a one-stop-shop for business registration
|  | 2.3.1.2 | ICT vendor (2 servers, server software, backup and recovery power systems) | 75000 | Shopping | Ex-Ante | 100 | 0 | N | 2015-04-01 | 2015-07-01 | 2015-09-01 | TBD |  | Online business registration system
|  | 2.3.2.1 | IT equipment (23 computers and signing pads) | 23000 | Shopping | EX-Post | 100 | 0 | N | 2015-04-01 | 2015-07-01 | 2015-12-01 | TBD |  | Business registration kiosks in operation
|  | 2.4 | Introduction of Shared Corporate Services
|  | 2.4.1.1 | Study tour to observe successful implementation of HR SCS by other Governments | 25000 | Shopping | Ex-Ante | 100 | 0 | N | 2014-08-01 | 2014-10-01 | 2014-12-01 | TBD |  | Travel and per diem
|  | 2.4.4.2 | PC, printers, UPS, Servers for case management software | 204900 | ICB | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-03-01 | 2015-05-01 | TBD |  | ICT infrastructure to operate HRSSC
|  | 2.4.4.1 | Network & Telephony - infrastructural work to include network connectivity, cabling and the procurement of a PBX system (telephones) to be used across the GOJ sector | 336594 | ICB | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-03-01 | 2015-05-01 | TBD |  | ICT infrastructure to operate HRSSC
|  | 2.4.4.3 | ICT infrastructure to operate HRSSC | 166116 | ICB | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-03-01 | 2015-05-01 | TBD |  | Case Management software (and implementation)
|  | 2.4.3.2 | HRSSC Workstations | 132730 | Shopping | Ex-Ante | 100 | 0 | N | 2015-04-01 | 2015-06-01 | 2015-09-01 | TBD |  | Agent and Manager Workstations
|  | 3 | Control Systems and Accountability
|  | 3.1 | Strengthening the AGD's capacity for Performance Audit and Information Technology Audit
|  | 3.1.1.2 | Printing of training materials | 15000 | Shopping | Ex-post | 100 | 0 | N | 2014-07-01 | 2014-07-01 | 2014-12-01 | TBD |  | Auditors trained in-country (Financial Statements)
|  | 3.1.1.3 | Projectors and LED Smart Screen Televisions | 17500 | Shopping | Ex-Ante | 100 | 0 | N | 2014-04-01 | 2014-07-01 | 2014-09-01 | TBD |  | IT equipment for FS
|  | 3.1.4 | Study tour | 96000 | Shopping | Ex-Ante | 100 | 0 | N | 2015-08-01 | 2015-10-01 | 2015-12-01 | TBD |  | Auditors trained overseas
|  | 3.1.6.2 | Licenses for interrogation software | 7200 | Shopping | Ex-Post | 100 | 0 | N | 2014-09-01 | 2014-10-01 | 2014-11-01 | TBD |  | Licenses
|  | 3.2 | Strengthening the Internal Audit System capacity
|  | 3.2.2.1 | IT Equipment - Laptops | 172000 | ICB | Ex-Ante | 100 | 0 | N | 2014-06-01 | 2014-07-01 | 2014-08-01 | TBD |  | Laptops procured for the AGD and MoF
|  | 3.2.2.2 | Server | 100000 | Shopping | Ex-Ante | 100 | 0 | N | 2014-07-01 | 2014-08-01 | 2014-10-01 | TBD |  | Software functioning at 19 IAUs and in addition, the Jamaica Customs Agency and IAD at MoF (approx. 200 licenses)
|  | 3.2.2.3 | International consultancy (firm) - Includes software purchase (licensenses), installation, configuration and training. | 375000 | ICB | Ex-Ante | 100 | 0 | N | 2014-07-01 | 2014-08-01 | 2014-11-01 | TBD |  | Software functioning at 19 IAUs and in addition, the Jamaica Customs Agency and IAD at MoF (approx. 200 licenses)
|  | 3.2.2.4 | IT support/maintenance for additional yrs for 240 licences | 230400 | ICB | Ex-Ante | 100 | 0 | N | 2016-04-01 | 2016-05-01 | 2017-04-01 | TBD |  | Software functioning at 19 IAUs and in addition, the Jamaica Customs Agency and IAD at MoF (approx. 200 licenses)
|  | 3.3 | Procurement process efficiency improved
|  | 3.3.2.5 | Procurement employees trained under new curricula (MIND) | 50000 | NCB | Ex-Ante | 100 | 0 | N | 2014-11-01 | 2014-12-01 | 2017-06-01 | TBD |  | Training facility rental
|  | 3.3.5.1 | IT Equipment | 800000 | ICB | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-03-01 | 2015-09-01 | TBD |  | e-tendering software functioning at MoF
|  | 3.3.5.2 | e-tendering software functioning at MoF | 1310000 | ICB | Ex-Ante | 100 | 0 | N | 2015-12-01 | 2016-01-01 | 2017-06-01 | TBD |  | IT support and Training material (reproduction)
|  | 3.3.5.5 | Training logistics rental | 50000 | Shopping | Ex-Ante | 100 | 0 | N | 2015-11-01 | 2015-12-01 | 2017-06-01 | TBD
|  | 3.4 | Enhancing Parliament´s oversight role
|  | 3.4.2 | IT equipment, suscription to journals, data base, office supplies | 60000 | Shopping | Ex-Ante | 100 | 0 | N | 2015-06-01 | 2015-08-01 | 2015-09-01 | TBD
|  | 3.4.3.2 | Logistics, rental facility, materials, meals, and transportation, among others | 20000 | Shopping | Ex-Post | 100 | 0 | N | 2015-06-01 | 2015-08-01 | 2015-12-01 | TBD |  | PAC and PAAC members
CONSULTING SERVICES
2 |  | 1 | Human Resources Management (HRM)
|  | 1.1 | Implementation of HCMES
|  | 1.1.1 | Procurement for Enterprise HCMES/Payroll Software Hardware | 11497603 | ICB | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | Direct Contracting provided by vendor awarded the contract for implementation of HCMES/payrolll Hardware acquisition & Implementation (HA) Storage (SAN Disk space) (28TB initial) Hardware for Secondary Location (no HA) Hosting Fees (Secondary System Hosted at Digicel) Purchasing of SAN for secondary site SAN Software & Maintenance - Secondary site
|  | 1.1.1 | Application Solutions Expert (assuming being paid by salary and not hourly) | 70000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | PMO Team
|  | 1.1.1 | 1 Technical Application Experts (Developers) (US$50,000/yr) | 150000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | PMO Team
|  | 1.1.1 | 1 Technical Application Experts (Developers) (US$50,000/yr) | 150000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | PMO Team
|  | 1.1.1 | Senior DBA (US$50,000/yr) | 150000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | PMO Team
|  | 1.1.1 | Senior QA ( Technical Tester) (US $40,000) | 120000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | PMO Team
|  | 1.1.1 | Customer Service Rep. (US $ 15,000) | 45000 | QCNI/QCII | Ex-Post | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | PMO Team
|  | 1.1.1 | Programme Director/Programme Executive | 225000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | PMO Team
|  | 1.1.1 | Project Manager | 180000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2014-06-01 | 2014-09-01 | 2017-12-01 | TBD |  | Project Manager
|  | 1.1.1 | Senior Business Analysts | 120000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2014-06-01 | 2014-09-01 | 2017-12-01 | TBD |  | 1 Senior Business Analysts
|  | 1.1.1 | 1 Business Analyst | 75000 | QCNI | Ex-Ante | 100 | 0 | N | 2014-07-01 | 2014-09-01 | 2017-12-01 | TBD |  | Business Analyst
|  | 1.1.1 | 1 Business Analyst | 75000 | QCNI | Ex-Ante | 100 | 0 | N | 2014-07-01 | 2014-09-01 | 2017-12-01 | TBD |  | Business Analyst
|  | 1.1.1 | Senior Quality Assurance Officers | 120000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | 1 Senior Quality Assurance Officers
|  | 1.1.1 | Quality Assurance Officer | 75000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | 1 Quality Assurance Officers
|  | 1.1.1 | Administrative Assistant | 45000 | QCNI/QCII | Ex-Post | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | 1 Administrative Assistant
|  | 1.1.1 | Technical Writer (HR Software Manual) | 5000 | QCNI/QCII | Ex-Post | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2017-12-01 | TBD |  | 1 Technical Writer (HR Software Manual)
|  | 1.1.2 | International Consultancy (Firm) | 300000 | QCBS | Ex-Ante | 100 | 0 | N | 2014-07-01 | 2014-10-01 | 2015-12-01 | TBD |  | International Consultancy (Firm)
|  | 1.2 | Strengthening the Capacity of Strategic Human Resource Management Division (SHRMD)
|  | 1.2.2 | SHRMD officials trained in HRM policy formulation and oversight for implementation | 100000 | QCBS | Ex-Ante | 100 | 0 | N | 2014-07-01 | 2014-09-01 | 2016-06-01 | TBD |  | International Consultancy (Individual)
|  | 1.2.3 | HRM Units in MDAs trained to carry out key HRM functions following central policies | 500000 | QCBS | Ex-Ante | 100 | 0 | N | 2014-07-01 | 2014-09-02 | 2016-06-01 | TBD |  | International Consultancy (Firm)
|  | 1.2.5 | SHRMD trained on techniques for monitoring overall and institutional-level HRM performance | 50000 | QCBS | Ex-Ante | 100 | 0 | N | 2014-07-01 | 2014-09-03 | 2016-06-01 | TBD |  | International Consultancy (Individual)
|  | 2 | Information & Communication Technologies Management (ICTM)
|  | 2.1 | Institutional strengthening of the new ICT governance framework
|  | 2.1.1.1 | International Consultancy (Individual) (includes travel and per diem) | 124000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-04-01 | 2015-07-01 | 2015-12-01 | TBD |  | e-Government strategy
|  | 2.1.1.2 | International Consultancy (organisational structure development of CIO's Office within MSTEM) | 60000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2014-06-01 | 2015-09-01 | 2015-12-01 | TBD |  | e-Government strategy
|  | 2.1.1.4 | Trained support staff (individual consultancy) | 150000 | QCNI | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2015-12-01 | TBD |  | e-Government strategy
|  | 2.1.2.1 | International consultancy, technical advice | 305000 | QCBS | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2015-10-01 | TBD |  | e-Government strategy
|  | 2.1.3.1 | International consultancy, technical advice | 639000 | QCBS | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2018-10-01 | TBD |  | e-Government strategy
|  | 2.1.3 | e-Gov Jamaica training programs | 250000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2018-10-01 | TBD |  | e-Government strategy
|  | 2.2 | Streamling the process of the GEI
|  | 2.2.2.1 | Consulting firm and training for use of new system | 410000 | QCBS | Ex-Ante | 100 | 0 | N | 2014-07-01 | 2014-10-01 | 2015-12-01 | TBD |  | GEI process automation completed and online applications system in operation Individual consultant employed to train employees on new system
|  | 2.2.1 | Individual Constultant - GEI business process reengineering roadmap | 40000 | QCNI/QCII | Ex-Post | 100 | 0 | N | 2014-07-01 | 2014-09-01 | 2014-11-01 | TBD |  | GEI consultants
|  | 2.3 | Establishment of a one-shop for business registration
|  | 2.3.1.1 | Project Manager | 40000 | QCNI/QCII | Ex-Post | 100 | 0 | N | 2014-06-01 | 2014-09-01 | 2015-12-01 | TBD |  | Online business registration
|  | 2.3.1.2 | Application Development consulting | 113000 | QCBS | Ex-Ante | 100 | 0 | N | 2015-04-01 | 2015-07-01 | 2015-09-01 | TBD |  | Online business registration
|  | 2.3.3.1 | Individual Consultant - Business registration seminars and workshops | 10000 | QCNI/QCII | Ex-Post | 100 | 0 | N | 2015-07-01 | 2015-09-01 | 2015-12-01 | TBD
|  | 2.3.3.2 | Individual Consultant - Communications campaign | 39000 | QCNI/QCII | Ex-Post | 100 | 0 | N | 2015-12-01 | 2015-02-01 | 2015-07-01 | TBD
|  | 2.4 | Introduction of Shared Corporate Services
|  | 2.4.2.1 | Consultant Transformation Director (Advisor/Coach/Mentor) | 242250 | QCBS | Ex-Ante | 100 | 0 | N | 2015-02-01 | 2015-04-01 | 2016-12-01 | TBD |  | Design of Operating Model for HRSSC
|  | 2.4.2 | Process BA x 1 (Shared Service), Consulting | 168000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2016-09-01 | TBD |  | Process BA x 1 (Shared Service), Consulting
|  | 2.4.2 | Process BA x 1(Shared Service), Consulting | 168000 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2016-09-01 | TBD |  | Process BA x 1 (Shared Service), Consulting
|  | 2.4.2 | HRSSC Agent Training | 48000 | QCNI/QCII | Ex-Post | 100 | 0 | N | 2015-01-01 | 2015-04-01 | 2015-08-01 | TBD |  | HRSSC Agent Training
|  | 2.4.2 | Design of technical specification for HRSSC facility | 108410 | QCNI/QCII | Ex-Ante | 100 | 0 | N | 2015-04-01 | 2015-07-01 | 2015-12-01 | TBD |  | Techincal specification, design, refurbishing of HRSSC facility
|  | 2.4.6 | A study to prepare the framework for implementing shared legal services | 60000 | QCII | Ex-Ante | 100 | 0 | N | 2016-01-01 | 2016-04-01 | 2016-07-01 | TBD |  | Framework for implementing shared legal services completed - Individual International Consultant
|  | 3 | Control Systems and Accountability
|  | 3.1 | Strengthening the AGD's capacity for Performance Audit and Information Technology Audit
|  | 3.1.1.1 | Auditors trained in-country (Financial Statements) | 160000 | Direct Contracting | Ex-Ante | 100 | 0 | N | 2014-04-01 | 2014-06-01 | 2014-12-01 | TBD |  | International consultancy (firm)
|  | 3.1.2.1 | Auditors trained in country (ITA) and ITA Manual drafted and disseminated | 200000 | Direct Contracting | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-03-01 | 2015-09-01 | TBD |  | International consultancy (firm)
|  | 3.1.4.3 | Licenses for interrogation software | 32000 | Shopping | Ex-Ante | 100 | 0 | N | 2014-09-01 | 2014-10-01 | 2014-11-01 | TBD
|  | 3.1.5 | ITA Manual drafted and disseminated | 61000 | QCII | Ex-Ante | 100 | 0 | N | 2015-07-01 | 2015-09-01 | 2016-03-01 | TBD
|  | 3.2 | Strengthening the Internal Audit System capacity
|  | 3.2.1 | Professional Development Framework | 105000 | QCII | Ex-Ante | 100 | 0 | N | 2016-06-01 | 2016-08-01 | 2017-01-01 | TBD |  | International consultancy (individual) (includes travel and per diem)
|  | 3.2.3 | Individual Consultant - Internal Audit Manual | 17400 | QCNI | Ex-Post | 100 | 0 | N | 2015-07-01 | 2015-09-01 | 2015-12-01 | TBD |  | National consultancy (individual)
|  | 3.2.4 | IA employees trained on PA and Payroll Audit | 152400 | QCII | Ex-Ante | 100 | 0 | N | 2017-04-01 | 2017-06-01 | 2017-12-01 | TBD |  | International consultancy (individual)
|  | 3.3 | Procurement process efficiency improved
|  | 3.3.3.1 | National consultancy (firm) for designing and implementing the sensitization and awareness campaign | 80000 | QCBS | Ex-Ante | 100 | 0 | N | 2014-12-01 | 2015-02-01 | 2017-01-01 | TBD |  | Sensitization and awareness products
|  | 3.3.4.1 | Procurement employees certified | 650000 | QCBS | Ex-Ante | 100 | 0 | N | 2014-06-01 | 2014-08-01 | 2016-06-01 | TBD |  | National consultancy (firm) Senior Procurement Employees Certified
|  | 3.3.1.1 | Redrafting of Procurement Manual | 30000 | QCII | Ex-Ante | 100 | 0 | N | 2014-08-01 | 2014-10-01 | 2015-03-01 | TBD |  | Local consultancy (individual)
|  | 3.3.1.2 | Redrafting of bidding documents | 50000 | QCII | Ex-Ante | 100 | 0 | N | 2015-02-01 | 2015-04-01 | 2015-10-01 | TBD |  | International consultancy (individual)
|  | 3.3.2.1 | Procurement employees trained under new curricula | 320000 | ICB | Ex-Ante | 100 | 0 | N | 2014-06-01 | 2014-09-01 | 2015-03-01 | TBD |  | National consultancy (individual) for preparing curricula and training material for 8-module training program preparing curricula and training material for trainers Training material (reproduction) Training material (production of tutorial DVD)
|  | 3.3.2.6 | Senior Procurement Practiotioners and Lawyers trained | 80000 | Direct Contracting | Ex-Ante | 100 | 0 | N | 2014-04-01 | 2014-05-01 | 2014-07-01 | 2014-05-08 | Awarded | Procurement Law and Practice Programme
|  | 3.4 | Enhancing Parliament´s oversight role
|  | 3.4.1 | Comprehensive assessment of the operation of the Parliament’s committees and design of a Management Accountability Framework (MAF) for the Parliament | 150000 | QCII | Ex-Ante | 100 | 0 | N | 2014-06-01 | 2014-08-01 | 2014-10-01 | TBD
|  | 3.4.2.1 | Budget Office to support both PAC and PAAC oversight role and reportingand functioning | 90000 | QCBS | Ex-Ante | 100 | 0 | N | 2014-10-01 | 2014-12-01 | 2015-05-01 | TBD
|  | 3.4.2.2 | Technical Office and research facility to support both PAC and PAAC oversight role and reporting and functioning | 378000 | QCBS | Ex-Ante | 100 | 0 | N | 2015-08-01 | 2015-11-01 | At the end of Program Execution 2018 | TBD
|  | 3.4.3.1 | Individual Consultancy (four experts; one per year) | 60000 | QCNI | Ex-Ante | 100 | 0 | N | 2015-06-01 | 2015-08-01 | 2015-12-01 | TBD |  | PAC and PAAC members trained
|  | 4 | Administrative
|  | 4.1 | Program Manager | 172990.3 | QCNI | Ex-Ante | 100 | 0 | N | 2014-07-01 | 2014-08-01 | 2017-03-01 | TBD
|  | 4.2 | Procurement Officer | 96979.95 | QCNI | Ex-Ante | 100 | 0 | N | 2014-07-01 | 2014-08-01 | 2017-03-01 | TBD
|  | 4.3 | External Auditor | 108000 | QCBS | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-03-01 | 2018-07-01 | TBD
|  | 4.2 | Evaluation | 216000 | QCNI | Ex-Ante | 100 | 0 | N | 2015-01-01 | 2015-03-01 | 2018-07-01 | TBD
|  | 5 | Contingency | 1762965
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Codes from SEPA