## Table of Contents
STRENGTHENED INFORMATION MANAGEMENT AT THE REGISTRAR GENERAL’S DEPARTMENT (SIMRG) - LO 3022/OC-TT
ANNUAL OPERATING PLAN 2015
TABLE OF CONTENTS
SECTION 1 | Project Overview
SECTION 2 | Implementation Plan
SECTION 3 | Procurement Plan
SECTION 4 | Consolidated Financial Plan
SECTION 5 | Detailed Financial Plan
SECTION 6 | Overall Financial Plan

## Project Overview
PROJECT OVERVIEW
Programme/project name | Strengthened Information Management at the Registrar General’s Department
Programme/project number | Loan Contract Lo 3022/OC-TT
Programme/project components | Component 1. Institutional Capacity Strengthening of the RGD.
Component 2. Support to Strengthen Identification of Parcels and Persons in Property Registration.
Project Administration.
Issues/constraints identified | Provide a summary of issues/constraints identified.
1 HR Services and, to a lesser extent, IT Services, Accounting Services and Legal Services are being provided by the Ministry of Legal Affairs staff. The priority to provide these services may not be as high as MLA duties and, therefore, this may lead to significant delays in the project.
2 The approval process in the Ministry of Legal Affairs may be very lengthy and, at times, be subject to significant delays owing to other priorities by the Approving Authority holder. This may lead to may lead to significant delays in the project.
3 Lack of information on past financial data termed as 'confidential' posed a threat to realistic projection and scheduling of activities to determine the path and feasibility of the project.
4
Strategies for addressing issues/constraints identified | Provide strategies for addressing issues/constraints identified.
1 Build and strengthen formal and informal relationships and seek to leverage these relationships to get things done at faster pace. Conduct a stakeholder's meeting and invite all concerned to seek 'buy in' for the project.
2 Utilise relationships built in strategy 1 and leverage required service.
3 Information on past financial data is required to prepare the Annual Operation Plan. A strategy to resolve is to seek to develop reports that would provide the information required on a monthly basis.
4
Risks with categorisation (High, medium, low) N.B. These risks should reflect those in the Risk matrix developed at the beginning of the project. | Provide a summary of opportunities and threats associated with the implementation of the programme/project.
1 A threat to the project is the delays that may occur due to high reliance on public servants for some services.
2 Risk is medium - Constant monitoring and building strong relationships shall lower risk.
3 Inaccurate information on past financial data may create uncertainty up to 20% in projecting to end of project in 2019. Risk is medium and information by monthly reports shall lower risks.
4
Risk response for high level risks | Provide mitigation measures to deal with the risks identified.
1 Create relationships within the public service employees to assist with getting the work completed.
2 Rely on the Registrar General and Permanent Secretary to assist in approvals or to remove bottlenecks where PIU members have to influence.
3 Reports that would provide financial data on a monthly basis to be implemented.
4

## Implementation Plan
SECTION 2
IMPLEMENTATION PLAN
No. of component | COMPONENT | SUB-COMPONENT | OUTPUT / PROJECT | DELIVERABLE | MILESTONE ACTIVITY1 | IDB COST (USD 000) |  |  | COUNTERPART COSTS (USD 000) |  |  | ESTIMATED START DATE | ESTIMATED END DATE | ESTIMATED START DATE | ESTIMATED END DATE | RESPONSIBILITY (PERSON/AGENCY)
[7 empty] | ACTUAL | VARIANCE | INDICATIVE | ACTUAL | VARIANCE
INDICATIVE
1 | Component 1 | [9 empty] | 0
|  | Sub-C1 | Output 1 | Deliverable 1 | [6 empty] | 0
1 | Institutional capacity strengthening of the RGD | Hire competent staff to execute scanning and digitization of land records | Staff in place, systematic scanning and digitization of records on-going - 2 supervisors, 30 data entry, 15 data control, 12 scanning clerks, 3 binders, 1 records manager, 2 records assistants, 10 vault attendants , IT technicians, drivers | Staff hired for 55 months - Commencement of land records being scanned, digitized and stored on server in accessible format | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 4519.0832 |  |  | 0 | 0 | 0 | 2015-06-30 | 2015-07-29 | 2015-04-01 | 2015-04-30 | RG/MLA & PM/PIU
[5 empty] | 2 - Advertising and interviewing | [6 empty] | 2015-07-30 | 2015-08-29 | 2015-05-01 | 2015-05-31
[5 empty] | 3 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-08-30 | 2015-09-28 | 2015-06-01 | 2015-06-30
[5 empty] | 4 - Executed contracts | [6 empty] | 2015-09-29 | 2015-10-13 | 2015-07-01 | 2015-07-15
2 | Institutional capacity strengthening of the RGD | Hire IT Specialist (local) | IT Specialist hired | IT Specialist delivering on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 1152 | [5 empty] | 2015-01-26 | 2015-01-31
[5 empty] | 2 - Advertising, shortlisting and interviewing | [6 empty] | 2015-02-01 | 2015-03-06
[5 empty] | 3 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-03-09 | 2015-03-13
[5 empty] | 4 - Executed contracts | [6 empty] | 2015-03-30 | 2015-03-31
3 | Institutional capacity strengthening of the RGD | Purchase scanners and digitizers | Equipment in place to perform the scanning and digitization of the land records. | Digitization of records in progress | 1 - IDB 'No Objection' to ITB including specifications, advertisement, evaluation panel and criteria | 180 |  |  |  |  | 0 | 2015-04-15 | 2015-05-01 | 2015-01-15 | 2015-01-31 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-05-30 | 2015-06-29 | 2015-03-01 | 2015-03-31
[5 empty] | 3 - Executed contracts | [6 empty] | 2015-06-30 | 2015-07-14 | 2015-04-01 | 2015-04-15
[5 empty] | 4 - Delivery of equipment | [6 empty] | 2015-07-29 | 2015-11-29 | 2015-04-30 | 2015-08-31
4 | Institutional capacity strengthening of the RGD | Purchase computers | Equipment in place to perform the scanning and digitization of the land records. | Digitization of records in progress | 1 - IDB 'No Objection' to ITB including specifications, advertisement, evaluation panel and criteria | 59 |  |  |  |  | 0 | 2015-06-13 | 2015-06-29 | 2015-03-15 | 2015-03-31 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-06-30 | 2015-07-14 | 2015-04-01 | 2015-04-15
[5 empty] | 3 - Executed invoice order | [6 empty] | 2015-07-15 | 2015-07-29 | 2015-04-16 | 2015-04-30
[5 empty] | 4 - Delivery of equipment | [6 empty] | 2015-07-30 | 2015-08-28 | 2015-05-01 | 2015-05-30
6 | Institutional capacity strengthening of the RGD | Study Tour to "best practice" national property registries | Best practice study on national property registries | Select a team to visit various land registries | 1 - IDB 'No Objection' | 105 | [5 empty] | 2015-04-01 | 2015-05-01 | 2015-03-01 | 2015-03-31 | RG/MLA & PM/PIU
7 | Institutional capacity strengthening of the RGD | Hire PIU Staff - Project Manager (PM) | Hired staff | Staff delivering on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 250 | [5 empty] | 2015-05-30 | 2015-06-29 | 2015-03-01 | 2015-03-31 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-05-30 | 2015-06-29 | 2015-03-01 | 2015-03-31
[5 empty] | 3 - Executed contracts | [6 empty] | 2015-06-30 | 2015-07-29 | 2015-04-01 | 2015-04-30
8 | Institutional capacity strengthening of the RGD | Hire PIU Staff - Public Relations Officer (PRO) | Hired staff | Staff delivering on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 180.625 | [5 empty] | 2015-05-30 | 2015-06-29 | 2015-03-01 | 2015-03-31 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-07-30 | 2015-08-29 | 2015-05-01 | 2015-05-31
[5 empty] | 3 - Executed contracts | [6 empty] | 2015-08-30 | 2015-09-28 | 2015-06-01 | 2015-06-30
9 | Institutional capacity strengthening of the RGD | Hire PIU Staff - Procurement Assistant (PA) | Hired staff | Staff delivering on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 127 | [5 empty] | 2015-11-30 | 2015-12-29 | 2015-09-01 | 2015-09-30 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2016-01-30 | 2016-02-13 | 2015-11-01 | 2015-11-15
[5 empty] | 3 - Executed contracts | [6 empty] | 2016-02-14 | 2016-02-28 | 2015-11-16 | 2015-11-30
10 | Institutional capacity strengthening of the RGD | Hire PIU Staff - Administrative Support Officer (ASO) | Hired staff | Staff delivering on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 299 | [5 empty] | 2015-05-17 | 2015-05-21 | 2015-02-16 | 2015-02-20 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-06-14 | 2015-06-18 | 2015-03-16 | 2015-03-20
[5 empty] | 3 - Executed contracts | [6 empty] | 2015-06-21 | 2015-06-29 | 2015-03-23 | 2015-03-31
11 | Institutional capacity strengthening of the RGD | Hire PIU Staff - Monitoring and Evaluation Officer (MEO) | Hired staff | Staff delivering on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 110.63 | [5 empty] | 2015-05-17 | 2015-05-21 | 2015-02-16 | 2015-02-20 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-06-14 | 2015-06-18 | 2015-03-16 | 2015-03-20
[5 empty] | 3 - Executed contracts | [6 empty] | 2015-06-21 | 2015-06-29 | 2015-03-23 | 2015-03-31
12 | Institutional capacity strengthening of the RGD | Hire PIU Staff - One Project Officer - Financial Assistant | Hired staff | Staff delivering on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 127 | [5 empty] | 2015-11-30 | 2015-12-29 | 2015-09-01 | 2015-09-30 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2016-01-30 | 2016-02-13 | 2015-11-01 | 2015-11-15
[5 empty] | 3 - Executed contracts | [6 empty] | 2016-02-14 | 2016-02-28 | 2015-11-16 | 2015-11-30
13 | Institutional capacity strengthening of the RGD | Hire PIU Staff - Project Officer | Hired staff | Staff delivering on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 149.5 | [5 empty] | 2015-11-30 | 2015-12-29 | 2015-09-01 | 2015-09-30 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2016-01-30 | 2016-02-13 | 2015-11-01 | 2015-11-15
[5 empty] | 3 - Executed contracts | [6 empty] | 2016-02-14 | 2016-02-28 | 2015-11-16 | 2015-11-30
14 | Institutional capacity strengthening of the RGD | Maintenance of Purchase vehicle for transport for PIU | Vehicles working without breakdown. | Maintenance carried out | Vehicle maintenance by dealerships | 26.409 | [5 empty] | 2015-04-02 | 2016-03-30 | 2015-01-02 | 2015-12-31 | RG/MLA & PM/PIU
15 | Institutional capacity strengthening of the RGD | Hire Business Analyst | Business Analyst hired | Business Analyst delivering on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 180 | [5 empty] | 2015-11-30 | 2015-12-14 | 2015-09-01 | 2015-09-15 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2016-02-13 | 2016-02-28 | 2015-11-15 | 2015-11-30
[5 empty] | 3 - Executed contracts | [6 empty] | 2016-02-29 | 2016-03-14 | 2015-12-01 | 2015-12-15
16 | Institutional capacity strengthening of the RGD | Hire firm to conduct process mapping and change management | Firm hired to conduct process mapping and change management | Firm delivering on project | 1 - IDB 'No Objection' to ITB including TOR, advertisement, evaluation panel and criteria | 500 | [5 empty] | 2015-11-30 | 2015-12-14 | 2015-09-01 | 2015-09-15 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2016-02-13 | 2016-02-28 | 2015-11-15 | 2015-11-30
[5 empty] | 3 - Executed contract | [6 empty] | 2016-02-29 | 2016-03-14 | 2015-12-01 | 2015-12-15
17 | Institutional capacity strengthening of the RGD | Hire firm to redesign workspace of RGD Vault and Work Space | Firm hired to redesign workspace of RGD Vault and Work Space | Firm delivering on project | 1 - IDB 'No Objection' to ITB including TOR, advertisement, evaluation panel and criteria | 500 | [5 empty] | 2015-10-29 | 2015-11-07 | 2015-06-01 | 2015-06-10 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-11-17 | 2015-11-27 | 2015-06-20 | 2015-06-30
[5 empty] | 3 - Executed contract | [6 empty] | 2015-11-28 | 2015-12-28 | 2015-07-01 | 2015-07-31
18 | Institutional capacity strengthening of the RGD | Hire firm to implement design (construction) of RGD Vault and Work Space | Firm hired to implement design (construction) of RGD Vault and Work Space | Firm delivering on project | 1 - IDB 'No Objection' to ITB including TOR, advertisement, evaluation panel and criteria | 1000 | [5 empty] | 2016-01-09 | 2016-02-18 | 2015-08-12 | 2015-09-21 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2016-03-30 | 2016-04-28 | 2015-11-01 | 2015-11-30
[5 empty] | 3 - Executed contract | [6 empty] | 2016-05-13 | 2016-05-29 | 2015-12-15 | 2015-12-31
2 | Component 2 |  | Output 2
1 | Component 2: Support to individuals to satisfy evidentiary requirements to link their names to their PINs | Establishment of Investigation Unit (IU) - Chief Investigator | Hired staff | Staff delivering on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 195.2 | [5 empty] | 2015-06-30 | 2015-07-29 | 2015-04-01 | 2015-04-30 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-09-13 | 2015-09-28 | 2015-06-15 | 2015-06-30
[5 empty] | 3 - Executed contracts | [6 empty] | 2015-10-13 | 2015-10-29 | 2015-07-15 | 2015-07-31
2 | Component 2: Support to individuals to satisfy evidentiary requirements to link their names to their PINs | Establishment of Investigation Unit (IU) - 8 Investigators | Hired staff | Staff delivering on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 699.15 | [5 empty] | 2015-06-30 | 2015-07-29 | 2015-04-01 | 2015-04-30 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-09-13 | 2015-09-28 | 2015-06-15 | 2015-06-30
[5 empty] | 3 - Executed contracts | [6 empty] | 2015-10-13 | 2015-10-29 | 2015-07-15 | 2015-07-31
3 | Component 2: Support to individuals to satisfy evidentiary requirements to link their names to their PINs | Establishment of Investigation Unit (IU) - 2 Clerical Officers | Hired staff | Staff delivering on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 145.92 | [5 empty] | 2015-06-30 | 2015-07-29 | 2015-04-01 | 2015-04-30 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-09-13 | 2015-09-28 | 2015-06-15 | 2015-06-30
[5 empty] | 3 - Executed contracts | [6 empty] | 2015-10-13 | 2015-10-29 | 2015-07-15 | 2015-07-31
4 | Component 2: Support to individuals to satisfy evidentiary requirements to link their names to their PINs | Purchase for IU staff (and PIU) - Office Furniture | Purchase of resources for IU staff and PIU | Resources being used on project | 1 - IDB 'No Objection' to TOR, List of Bidders, evaluation panel and criteria | 100 | [5 empty] | 2015-06-30 | 2015-07-14 | 2015-04-01 | 2015-04-15 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-08-18 | 2015-08-29 | 2015-05-20 | 2015-05-31
[5 empty] | 3 - Executed contracts | [6 empty] | 2015-08-30 | 2015-09-13 | 2015-06-01 | 2015-06-15
5 | Component 2: Support to individuals to satisfy evidentiary requirements to link their names to their PINs | Maintenance of Purchase vehicle for transport for PIU | Vehicles working without breakdown. | Maintenance carried out | Using Dealership arrangements | 19.738 | [5 empty] | 2015-04-01 | 2016-03-30 | 2015-01-01 | 2015-12-31 | RG/MLA & PM/PIU
6 | Component 2: Support to individuals to satisfy evidentiary requirements to link their names to their PINs | Purchase for IU staff (and PIU) - Telecommunications | Purchase of resources for IU staff and PIU | Resources being used on project | 1 - IDB 'No Objection' to TOR, List of bidders, evaluation panel and criteria | 100 | [5 empty] | 2015-06-30 | 2015-07-14 | 2015-04-01 | 2015-04-15 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-09-14 | 2015-09-28 | 2015-06-16 | 2015-06-30
[5 empty] | 3 - Executed contracts | [6 empty] | 2015-09-29 | 2015-10-03 | 2015-07-01 | 2015-07-05
7 | Component 2: Support to individuals to satisfy evidentiary requirements to link their names to their PINs | Purchase for IU staff (and PIU) - Office maintenance and utilities | Purchase of resources for IU staff and PIU | Resources being used on project | 1 - IDB 'No Objection' to TOR, advertisement, evaluation panel and criteria | 200 | [5 empty] | 2015-09-29 | 2015-10-13 | 2015-07-01 | 2015-07-15 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-11-29 | 2015-11-29 | 2015-08-31 | 2015-08-31
[5 empty] | 3 - Executed contracts | [6 empty] | 2015-11-30 | 2015-12-04 | 2015-09-01 | 2015-09-05
8 | Component 2: Support to individuals to satisfy evidentiary requirements to link their names to their PINs | Purchase for IU staff (and PIU) - Office rental | Purchase of resources for IU staff and PIU | Resources being used on project | 1 - Executed contracts | 1164.5952 | [5 empty] | 2015-05-02 | 2015-05-16 | 2015-02-01 | 2015-02-15 | RG/MLA & PM/PIU
9 | Component 2: Support to individuals to satisfy evidentiary requirements to link their names to their PINs | Purchase for IU staff (and PIU) - Office supplies | Purchase of resources for IU staff and PIU | Resources being used on project | 1 - IDB 'No Objection' to signed evaluation report | 100 | [5 empty] | 2015-04-01 | 2016-03-11 | 2015-01-01 | 2015-12-12 | RG/MLA & PM/PIU
2 - Invite vendors to quote
3 - Executed contracts
4 - Delivery of office supplies
10 | Component 2: Support to individuals to satisfy evidentiary requirements to link their names to their PINs | Hire consultant for Birth Name Registration Communications Campaign | Consultant hired for Birth Name Registration Communications Campaign | Birth Name Registration Communications Campaign conducted | 1 - IDB 'No Objection' to TOR, list of bidders, evaluation panel and criteria | 50 | [5 empty] | 2015-06-30 | 2015-07-29 | 2015-04-01 | 2015-04-30 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-08-30 | 2015-09-12 | 2015-06-01 | 2015-06-14
[5 empty] | 3 - Executed contract | [6 empty] | 2015-09-13 | 2015-09-28 | 2015-06-15 | 2015-06-30
11 | Component 2: Support to individuals to satisfy evidentiary requirements to link their names to their PINs | Hire consultant for study on best method to identify all property registrants and provide recommendations for strengthening the existing parcel identification numbering protocol | Consultant hired for study on best method to identify all property registrants and for study to provide recommendations for strengthening the existing parcel identification numbering protocol | Best method to identify all property registrants identified | 1 - IDB 'No Objection' to TOR, list of bidders, evaluation panel and criteria | 85 | [5 empty] | 2015-09-28 | 2015-10-27 | 2015-04-01 | 2015-04-30 | RG/MLA & PM/PIU
[5 empty] | 2 - IDB 'No Objection' to signed evaluation report with evaluation score sheets | [6 empty] | 2015-11-28 | 2015-12-11 | 2015-06-01 | 2015-06-14
[5 empty] | 3 - Executed contract | [6 empty] | 2015-12-12 | 2015-12-27 | 2015-06-15 | 2015-06-30
12 | Component 2: Audit | External audit | Auditor General of Government |  |  | 0 | [5 empty] | 2015-07-30 | 2016-03-30 | 2015-05-01 | 2015-12-31
11324.8504
[7 empty] | 0 | 0 | 0 | 0 | 0
Karen Bridgewater
Registrar General and Interim Project Manager
Authorized Signature(s) | [5 empty] | Name(s) and Title(s)
Formulas:
ESTIMATED START DATE = [ESTIMATED START DATE]+90
ESTIMATED START DATE = [ESTIMATED START DATE]+90+60
ESTIMATED END DATE = [ESTIMATED END DATE]+90
Note on J6: IADB: Total cost of component should equal the sum of the costs of all outputs/projects in that component
Note on J7: IADB: Total cost of Output / Project 1 (sum of all milestone activities)
Note on J62: IADB: Total cost of Output / Project 2

## Procurement Plan
SECTION 3
PROCUREMENT PLAN
WORKS
No | Description of and Component of procurement contract | Lots Quantity: | Indicative cost (USD 000) | Procurement Method | Review Method (Select one of the options): | IDB Funding 100% | Prequalification (Yes/No) | Estimated Dates |  | Status (pending; in process; awarded; cancelled) | Comments
[8 empty] | Publication of specific procurement notice | Completion of Contract
Component 1
GOODS
No | Description of and Component of procurement contract | Lots Quantity: | Indicative cost (USD 000) | Procurement Method | Review Method (Select one of the options): | IDB Funding % | Prequalification (Yes/No) | Estimated Dates |  | Status (pending; in process; awarded; cancelled) | Comments
[8 empty] | Publication of specific procurement notice | Completion of Contract
Component 1
1 | Computers (with 2 monitors) for restoration and digitization of document pages | 4 | 59 | Shopping | Ex-Post | 100 | No | 2015-06-13 | 2015-07-29 | In process
2 | Scanners | 8 | 180 | Shopping | Ex-Ante | 100 | No | 2015-04-15 | 2015-07-14 | In process
3 | Study Tour to "best practice" national property registries Study Tour 1 Vancouver, Canada (April 2015) Logistics and Accommodation - $ 458,388.00 TTD ( $71,400 USD) Study Tour 2 New South Wales, Australia (May 2015) Logistics and Accommodation - $ 692,076.00 TTD ($107,800 USD) | 2 | 178 | Shopping | Ex-Ante | 100 | No | 2015-04-01 | 2015-05-31 | In process
Component 2
1 | Office furniture | 1 | 100 | Shopping | Ex-Ante | 100 | No | 2015-06-30 | 2015-09-13 | In process
2 | Vehicles - Maintenance | 2 | 19.738 |  | Ex-Post | 100 | No | 2015-04-01 | 2015-12-31 | In process | Dealership
3 | Telecommunications | N/A | 100 | Shopping | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-03 | In process
4 | Office maintenance and utilities | N/A | 200 | Shopping | Ex-Ante | 100 | No | 2015-09-29 | 2015-12-31 | In process
5 | Office rental | N/A | 1164.5952 | Shopping | Ex-Ante | 100 | No | 2015-05-02 | 2015-12-31 | In process
6 | Office supplies | N/A | 100 | Shopping | Ex-Ante | 100 | No | 2015-04-02 | 2015-12-31 | In process
Project Administration
1 | Vehicles - maintenance | 1 | 26.409 |  | Ex-Post | 100 |  | 2015-04-01 | 2015-12-31 | In process | Dealership
CONSULTING FIRMS
No | Description of and Component of procurement contract | Lots Quantity: | Indicative cost (USD 000) | Procurement Method | Review Method (Select one of the options): | IDB Funding % | Prequalification (Yes/No) | Estimated Dates |  | Status (pending; in process; awarded; cancelled) | Comments
[8 empty] | Publication of specific procurement notice | Completion of Contract
Component 1
1 | Design and implementation of re-engineered, streamlined business processes, including automation of registration procedures. |  | 500 | Quality and Cost Based Selection | Ex-Ante | 100 | Yes | 2015-11-30 | 2015-12-28 | In process
2 | Re-design workspace -vault |  | 500 | Quality and Cost Based Selection | Ex-Ante | 100 | No | 2015-12-31 | 2015-12-28 | In process
Component 2
1 | Birth Name Registration Communications Campaign |  | 50 | Quality and Cost Based Selection | Ex-Ante | 100 | No | 2015-06-01 | 2015-09-28 | In process
INDIVIDUAL CONSULTANTS
No | Description of and Component of procurement contract | Lots Quantity: | Indicative cost (USD 000) | Procurement Method | Review Method (Select one of the options): | IDB Funding % | Prequalification (Yes/No) | Estimated Dates |  | Status (pending; in process; awarded; cancelled) | Comments
[8 empty] | Publication of specific procurement notice | Completion of Contract
Component 1
1 | Supervisor |  | 177.606 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-13 | In process
2 | Data entry control clerks |  | 1615.86 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-13 | In process
3 | Data entry clerks |  | 948.498 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-13 | In process
4 | Scanning clerks |  | 549.186 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-13 | In process
5 | Binder |  | 179.4 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-13 | In process
6 | Records Manager |  | 95.68 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-13 | In process
7 | Records Assistant |  | 130.0052 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-13 | In process
8 | Vault Attendant |  | 464.048 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-13 | In process
9 | IT Specialist |  | 143.52 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-01-26 | 2015-03-31 | In process
10 | IT Technicians |  | 215.28 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-13 | In process
11 | Business Analyst |  | 180 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-11-30 | 2016-02-28 | In process
Component 2
1 | Chief Investigator |  | 195.2 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-29 | In process
2 | Investigator |  | 699.15 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-29 | In process
3 | Clerical Officer |  | 145.92 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-06-30 | 2015-10-29 | In process
4 | Study to provide recommendations for strengthening the existing parcel identification numbering protocol |  | 50 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-09-28 | 2015-12-27 | In process
5 | External Audit |  | 12.5 | Auditor General | Ex-Ante | 100 | No | 2015-07-30 | 2015-12-05 | In process
Project Administration, Monitoring and Evaluation
1 | Project Manager |  | 250 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-05-30 | 2015-07-29 | In process
2 | Project Officer |  | 149.5 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-11-30 | 2016-02-28 | In process
3 | Procurement Assistant |  | 127 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-11-30 | 2016-02-28 | In process
4 | Financial Assistant |  | 127 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-11-30 | 2016-02-28 | In process
5 | PRO |  | 180.625 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-05-30 | 2015-09-28 | In process
6 | Administrative Support Officers |  | 299 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-05-17 | 2015-06-29 | In process
7 | Monitoring and Evaluation Officer |  | 110.63 | Comparison of Qualifications - National Individual Consultant | Ex-Ante | 100 | No | 2015-05-17 | 2015-06-29 | In process
Total

## Consolidated Financial Plan
SECTION 4 CONSOLIDATED FINANCIAL PLAN
Programme Components (1) | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | PROJECT TOTAL
| Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000) |  |  |  | Source of Funding (USD 000)
| IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total
Project Administration |  |  |  | (as per approved amount)
1.1 Condition Prior | 0 | 0 | 0 | 0 | 8304.3 | 0 | 0 | 8304.3 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 8304.3 | 0 | 0 | 8304.3
1.2 PIU Operation | 0 | 0 |  | 0 | 305479.56 | 0 |  | 305479.56 | 155700 |  |  | 155700 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 461179.56 | 0 | 0 | 461179.56
Subtotal | 0 | 0 | 0 | 0 | 313783.86 | 0 | 0 | 313783.86 | 155700 | 0 | 0 | 155700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469483.86 | 0 | 0 | 469483.86
Component 1 : Institutional capacity strengthening of the RGD |  |  |  | (as per approved amount)
2.1 Restoration & Digitization |  |  |  | 0 | 0 |  |  | 0 | 378300 | 0 |  | 378300 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 378300 | 0 | 0 | 378300
2.2 IT System Upgrade |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
2.3 Business Process Mapping and Change Management |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
2.4 Redesign of RGD vault and work scope |  |  |  | 0 | 0 |  |  | 0 | 500000 |  |  | 500000 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 500000 | 0 |  | 500000
2.5Study Tour to "best pratice" national porperty registries |  |  |  |  | 0 |  |  | 0 | 105000 |  |  | 105000 | [16 empty] | 105000 |  |  | 105000
Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 983300 | 0 | 0 | 983300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 983300 | 0 | 0 | 983300
Component 2 : Support to individual to satisfy evidentary requirement to link their names to their PINS |  |  |  | (as per approved amount)
3.1 Establishment of Investigation Unit |  |  |  | 0 | 55616.94 |  |  | 55616.94 | 618593 | 0 | 0 | 618593 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 674209.94 | 0 |  | 674209.94
3.2 Support to Stregthen Idenification |  |  |  | 0 | 0 |  |  | 0 | 48000 |  |  | 48000 | 0 |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 48000 | 0 |  | 48000
Subtotal | 0 | 0 | 0 | 0 | 55616.94 | 0 | 0 | 55616.94 | 666593 | 0 | 0 | 666593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 722209.94 | 0 | 0 | 722209.94
Component 3 |  |  |  | (as per approved amount)
3.1 Auditing |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0
3.2 Monitoring anf Evaluation Activities |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0
Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Component 4 |  |  |  | (as per approved amount)
4.1 Contingenices |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 369400.8 | 0 | 0 | 369400.8 | 1805593 | 0 | 0 | 1805593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2174993.8 | 0 | 0 | 2174993.8
0

## Detailed Financial Plan
DETAILED FINANCIAL PLAN: IDB RESOURCES1
|  |  | 2014 | [38 empty] | 2015
| Programme Components (1) | Total cost (as per Implementation plan)'000 | JANUARY |  |  | FEBRUARY |  |  | MARCH |  |  | APRIL |  |  | MAY |  |  | JUNE |  |  | JULY |  |  | AUGUST |  |  | SEPTEMBER |  |  | OCTOBER |  |  | NOVEMBER |  |  | DECEMBER |  |  | TOTAL for the period | TOTAL for the period | TOTAL for the period | JANUARY |  |  | FEBRUARY |  |  | MARCH |  |  | APRIL |  |  | MAY |  |  | JUNE |  |  | JULY |  |  | AUGUST |  |  | SEPTEMBER |  |  | OCTOBER |  |  | NOVEMBER |  |  | DECEMBER |  |  | TOTAL for the period | TOTAL for the period | TOTAL for the period
|  |  | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance | Indicative | Actual | Variance
Project Adminstration
1.1 | Condition Prior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2192.09 | -2192.09 | 0 | 1952.3 | -1952.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4159.91 | -4159.91 | 0 | 0 | 0 | 0 | 8304.3 | -8304.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Hire PIU Staff | [27 empty] | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | [36 empty] | 0 |  | 0
| Advertisement | [32 empty] | 2566.28 | -2566.28 |  |  | 0 |  | 2566.28
1.1.1.1 | Project Manager (PM) | [25 empty] | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
1.1.1.2 | Procurement Specialist (PS) | [25 empty] | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
1.1.1.3 | Financial Specialist (FS) | [25 empty] | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
1.1.2 | Conduct staff orientation for PS and FS | [27 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
1.1.3 | Conduct staff orientation for PM | [27 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
1.1.4 | Set up Bank Account | [27 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
1.1.5 | Authorize Signatories | [27 empty] | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
1.1.6 | Allocation of first year resources | [27 empty] | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
1.1.7 | Installation of Financial Management system | [20 empty] | 2192.09 | -2192.09 |  | 1952.3 | -1952.3 |  |  | 0 |  |  |  |  | 1593.63 | -1593.63 |  |  |  | 0 | 5738.02 | -5738.02 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
1.1.8 | Obtain legal opinion | [27 empty] | 0 | [9 empty] | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
1.2 | PEU Operation | 1245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2379.55 | -2379.55 | 0 | 7886.66 | -7886.66 | 0 | 7921.82 | -7921.82 | 0 | 15982.23 | -15982.23 | 0 | 8002.14 | -8002.14 | 0 | 233988.51 | -233988.51 | 0 | 8013.96 | -8013.96 | 0 | 12495.12 | -12495.12 | 0 | 8809.57 | -8809.57 | 0 | 305479.56 | -305479.56 | 7975 | 0 | 7975 | 7975 | 0 | 7975 | 7975 | 0 | 7975 | 7975 | 0 | 7975 | 7975 | 0 | 7975 | 12975 | 0 | 12975 | 12975 | 0 | 12975 | 17975 | 0 | 17975 | 17975 | 0 | 17975 | 17975 | 0 | 17975 | 17975 | 0 | 17975 | 17975 | 0 | 17975 | 155700 | 0 | 155700
1.2.1 | Execute and Monitor Project work | 1245 | [29 empty] | 0 | [5 empty] | 0 |  |  | 0 | 7975 |  | 7975 | 7975 |  | 7975 | 7975 |  | 7975 | 7975 |  | 7975 | 7975 |  | 7975 | 12975 |  | 12975 | 12975 |  | 12975 | 17975 |  | 17975 | 17975 |  | 17975 | 17975 |  | 17975 | 17975 |  | 17975 | 17975 |  | 17975 | 155700 |  | 155700
1.2.1.1 | Computers | [25 empty] | 0 | 57953.31 | -57953.31 |  |  | 0 | [5 empty] | 0 | 0 | 57953.31 | -57953.31 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
1.2.1.2 | Office Equipment-Photocopiers | [25 empty] | 0 | 19362.03 | -19362.03 |  |  | 0 | [5 empty] | 0 | 0 | 19362.03 | -19362.03 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
1.2.1.3 | Office Furniture | [27 empty] | 0 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
1.2.1.4 | Vehicles | [25 empty] | 0 | 131320.9 | -131320.9 |  |  | 0 | [5 empty] | 0 | 0 | 131320.9 | -131320.9 |  |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
1.2.1.9 | Office supplies | [25 empty] | 0 | 10696.25 | -10696.25 |  |  | 0 |  | 4483.81 | -4483.81 |  |  | 0 | 0 | 15180.06 | -15180.06 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
1.2.1.10 | Project Officer | 150 | [26 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
| Project Officer-Financial Assistant | 127 | [26 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
1.2.1.11 | Procurement Assistant | 127 | [26 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 0 | 0 |  | 0
1.2.1.12 | Administrative Support Officer (2) | 299 | [26 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 5000 |  | 5000 | 5000 |  | 5000 | 5000 |  | 5000 | 5000 |  | 5000 | 5000 |  | 5000 | 5000 |  | 5000 | 5000 |  | 5000 | 35000 |  | 35000
1.2.1.13 | Contract Execution - PM | 250 | [25 empty] | 6650.24 | -6650.24 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 6650.24 | -6650.24 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 5000 |  | 5000 | 5000 |  | 5000 | 5000 |  | 5000 | 5000 |  | 5000 | 5000 |  | 5000 | 25000 |  | 25000
1.2.1.14 | Contract Execution - PS | [11 empty] | 1117.44 | -1117.44 | 0 | 4330.01 | -4330.01 | 0 | 4349.18 | -4349.18 |  | 8774.56 | -8774.56 |  | 4393.33 | -4393.33 |  | 4395.33 | -4395.33 |  | 4399.82 | -4399.82 |  | 4398.37 | -4398.37 |  | 4393.4 | -4393.4 | 0 | 40551.44 | -40551.44 | 4375 |  | 4375 | 4375 |  | 4375 | 4375 |  | 4375 | 4375 |  | 4375 | 4375 |  | 4375 | 4375 |  | 4375 | 4375 |  | 4375 | 4375 |  | 4375 | 4375 |  | 4375 | 4375 |  | 4375 | 4375 |  | 4375 | 4375 |  | 4375 | 52500 |  | 52500
1.2.1.15 | Contract Execution - FS | [11 empty] | 1262.11 | -1262.11 | 0 | 3556.65 | -3556.65 | 0 | 3572.64 | -3572.64 |  | 7207.67 | -7207.67 |  | 3608.81 | -3608.81 |  | 3610.45 | -3610.45 |  | 3614.14 | -3614.14 |  | 3612.94 | -3612.94 |  | 4416.17 | -4416.17 | 0 | 34461.58 | -34461.58 | 3600 |  | 3600 | 3600 |  | 3600 | 3600 |  | 3600 | 3600 |  | 3600 | 3600 |  | 3600 | 3600 |  | 3600 | 3600 |  | 3600 | 3600 |  | 3600 | 3600 |  | 3600 | 3600 |  | 3600 | 3600 |  | 3600 | 3600 |  | 3600 | 43200 |  | 43200
| Hire Public Relations Officer | 181 | [36 empty] | 0 |  | 0 |  |  | - |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 3125 |  | 3125 | 3125 |  | 3125 | 3125 |  | 3125 | 3125 |  | 3125 | 12500 |  | 12500
| Hire Monitoring and Evaluation Officer | 111 | [36 empty] | 0 |  | 0 |  |  | - |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1850 |  | 1850 | 1850 |  | 1850 | 1850 |  | 1850 | 1850 |  | 1850 | 1850 |  | 1850 | 1850 |  | 1850 | 1850 |  | 1850 | 12950 |  | 12950
| Project Adminstration Subtotal | 1245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2379.55 | -2379.55 | 0 | 7886.66 | -7886.66 | 0 | 7921.82 | -7921.82 | 0 | 18174.32 | -18174.32 | 0 | 9954.44 | -9954.44 | 0 | 233988.51 | -233988.51 | 0 | 8013.96 | -8013.96 | 0 | 16655.03 | -16655.03 | 0 | 8809.57 | -8809.57 | 0 | 313783.86 | -313783.86 | 7975 | 0 | 7975 | 7975 | 0 | 7975 | 7975 | 0 | 7975 | 7975 | 0 | 7975 | 7975 | 0 | 7975 | 12975 | 0 | 12975 | 12975 | 0 | 12975 | 17975 | 0 | 17975 | 17975 | 0 | 17975 | 17975 | 0 | 17975 | 17975 | 0 | 17975 | 17975 | 0 | 17975 | 155700 | 0 | 155700
Component 1: Institutional capacity strengthen of RGD
2.1 | Restoration & Digitization | 5910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 2400 | 0 | 0 | 0 | 24900 | 0 | 24900 | 58650 | 0 | 58650 | 2400 | 0 | 2400 | 62900 | 0 | 62900 | 135150 | 0 | 135150 | 91900 | 0 | 91900 | 378300 |  | 378300
2.1.1 | Hire the 2 supervisors (9500), 15 data entry (10500), 30 data control (21000), 10 scanning clerks (5000), 2 binders (1200), records manager (1600), 2 records assistant (1100) and 10 vault attendants (7000), 2 IT technicians (3600). Ie 60,500 per month | 4519 | [35 empty] | 0 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2400 |  | 2400 |  |  | 0 | 2400 |  | 2400 | 2400 |  | 2400 | 2400 |  | 2400 | 62900 |  | 62900 | 62900 |  | 62900 | 62900 |  | 62900 | 198300 |  | 198300
| Supervisor | [36 empty] | 0 | [21 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 9500 |  | 9500 | 9500 |  | 9500 | 9500 |  | 9500 | 28500 |  | 28500
| Data Entry | [36 empty] | 0 | [21 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 10500 |  | 10500 | 10500 |  | 10500 | 10500 |  | 10500 | 31500 |  | 31500
| Data Control | [36 empty] | 0 | [21 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 21000 |  | 21000 | 21000 |  | 21000 | 21000 |  | 21000 | 63000 |  | 63000
| Scanning Clerks | [36 empty] | 0 | [21 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 5000 |  | 5000 | 5000 |  | 5000 | 5000 |  | 5000 | 15000 |  | 15000
| Binder | [36 empty] | 0 | [21 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1200 |  | 1200 | 1200 |  | 1200 | 1200 |  | 1200 | 3600 |  | 3600
| Record Manager | [36 empty] | 0 | [21 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1600 |  | 1600 | 1600 |  | 1600 | 1600 |  | 1600 | 4800 |  | 4800
| Record Assistant | [36 empty] | 0 | [21 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1100 |  | 1100 | 1100 |  | 1100 | 1100 |  | 1100 | 3300 |  | 3300
| Vault Attendants | [36 empty] | 0 | [21 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 7000 |  | 7000 | 7000 |  | 7000 | 7000 |  | 7000 | 21000 |  | 21000
| IT Specialist | 1152 | [29 empty] | 0 | [6 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2400 |  | 2400 | 2400 |  | 2400 | 2400 |  | 2400 | 2400 |  | 2400 | 2400 |  | 2400 | 2400 |  | 2400 | 2400 |  | 2400 | 2400 |  | 2400 | 2400 |  | 2400 | 21600 |  | 21600
| IT Technicians | [36 empty] | 0 | [21 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3600 |  | 3600 | 3600 |  | 3600 | 3600 |  | 3600 | 10800 |  | 10800
2.1.1.1 | Develop TORs for Supervisor, Data Entry, Data Control and Scanning Clerks, Records and Vault Attendant | [37 empty] | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.1.2 | Prepare Advert | [37 empty] | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.1.3 | Obtain IDB 'No Objection' | [37 empty] | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.1.4 | Advertise in local newspapers | [37 empty] | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.1.5 | Receive applications | [37 empty] | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.1.6 | Short list applicants | [37 empty] | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.1.7 | Interview | [37 empty] | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.1.8 | Offers to preferred applicants | [37 empty] | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.2 | Conduct training of restoration and archival team | [37 empty] | 0 |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.3 | Purchase of scanners and digitizers | 180 | [36 empty] | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 22500 |  | 22500 | 56250 |  | 56250 |  |  | 0 |  |  | 0 | 72250 |  | 72250 | 29000 |  | 29000 | 180000 |  | 180000
| Purchase of computers | 59 | [36 empty] | 0 |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  | 0 | [5 empty] | 0 |  |  | 30000 |  | 30000 |  |  | 0 | [9 empty] | 29000 |  | 29000 | 59000 |  | 59000
2.1.3.1 | Prepare Specifications | [37 empty] | 0 |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.3.2 | Prepare ITB & List of Bidders, Eval Criteria & Eval Panel | [37 empty] | 0 |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.3.3 | Obtain 'No Objection' from IDB | [37 empty] | 0 |  | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.3.4 | Invite bidders | [37 empty] | 0 |  | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.3.5 | Close invitation and open bids | [37 empty] | 0 |  | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.3.6 | Evaluate proposals and prepare recommendation | [37 empty] | 0 |  | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.3.7 | Obtain 'No Objection' from IDB | [37 empty] | 0 |  | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.3.8 | Award of contract | [37 empty] | 0 |  | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.1.3.9 | Deliver of equipment and customize | [37 empty] | 0 |  | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 29000 |  | 29000 | 29000 |  | 29000
2.1.4 | Data entry and digitization | [37 empty] | 0 |  | 0 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.3 | Business Process Mapping and Change Management | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.1 | Hire Business Analyst | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [12 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
2.3.1.1 | Prepare Technical TOR/Scope | [37 empty] | 0 |  | 0 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.3.1.2 | Prepare ITB & List of Bidders, Eval Criteria & Eval Panel | [37 empty] | 0 |  | 0 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.3.1.3 | Obtain 'No Objection' from IDB | [37 empty] | 0 |  | 0 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.3.1.4 | Invite bidders | [37 empty] | 0 |  | 0 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.3.1.5 | Close invitation and open bids | [37 empty] | 0 |  | 0 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.3.1.6 | Evaluate proposals and prepare recommendation | [37 empty] | 0 |  | 0 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.3.1.7 | Obtain 'No Objection' from IDB | [37 empty] | 0 |  | 0 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.3.1.8 | Award of contract | [37 empty] | 0 |  | 0 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.3.2 | Execute - Supervise Business Process Mapping and Change Management | [37 empty] | 0 |  | 0 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.4 | Redesign of RGD Vault and Work Space | 1026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 500000 | 500000 |  | 500000
| Hire firm to conduct process mapping and change management | 500
2.4.1 | Hire firm to redesign workspace of RGD Vault and work space | 500 | [36 empty] | 0 |  | 0 | [15 empty] | 0 |  | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 500000 |  | 500000 | 500000 |  | 500000
2.4.1.1 | Prepare Technical TOR/Scope | [37 empty] | 0 |  | 0 | [17 empty] | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.4.1.2 | Prepare ITB and List of Bidders, Eval Criteria and Eval Panel | [37 empty] | 0 |  | 0 | [17 empty] | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.4.1.3 | Obtain 'No Objection' from IDB | [37 empty] | 0 |  | 0 | [17 empty] | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.4.1.4 | Invite bidders | [37 empty] | 0 |  | 0 | [17 empty] | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.4.1.5 | Close invitation and open bids | [37 empty] | 0 |  | 0 | [17 empty] | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.4.1.6 | Evaluate proposals and prepare recommendation | [37 empty] | 0 |  | 0 | [17 empty] | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.4.1.7 | Obtain 'No Objection' from IDB | [37 empty] | 0 |  | 0 | [17 empty] | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.4.1.8 | Award of contract | [37 empty] | 0 |  | 0 | [17 empty] | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0
| Maintenance of Vehilces purchsed for IU (and PIU) | 26 | [36 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
2.5 | Study Tour to "best pratice" national porperty registries | 105 | [36 empty] | 0 |  | 0 | [12 empty] | 20000 |  | 20000 | [6 empty] | 20000 |  | 20000 | 20000 |  | 20000 | 15000 |  | 15000 | 15000 |  | 15000 | 15000 |  | 15000 | 105000 |  | 105000
| Subtotal | 1131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 20000 | 0 | 20000 | 15000 | 0 | 15000 | 15000 | 0 | 15000 | 515000 | 0 | 515000 | 983300 | 0 | 983300
Component 2 Support to individuals to satisfy evidiary requirements to link their names to their PINs
3.1 | Establishment of Investigation Unit (IU) | 2866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.35 | -320.35 | 0 | 171.04 | -171.04 | 0 | 132.98 | -132.98 | 0 | 0 | 0 | 0 | 27690.28 | -27690.28 | 0 | 27302.29 | -27302.29 | 0 | 55616.94 | -55616.94 | 20655 | 0 | 20655 | 23155 | 0 | 23155 | 23155 | 0 | 23155 | 23155 | 0 | 23155 | 44041 | 0 | 44041 | 44041 | 0 | 44041 | 46641 | 0 | 46641 | 46641 | 0 | 46641 | 58141 | 0 | 58141 | 154656 | 0 | 154656 | 64656 | 0 | 64656 | 69656 | 0 | 69656 | 618593 |  | 618593
3.1.1 | Hire IU staff | [37 empty] | 0 | 0 | 0 | 20655 |  | 20655 | 20655 |  | 20655 | 20655 |  | 20655 | 20655 |  | 20655 | 20655 |  | 20655 | 20655 |  | 20655 | 23255 |  | 23255 | 23255 |  | 23255 | 23255 |  | 23255 | 39770 |  | 39770 | 39770 |  | 39770 | 39770 |  | 39770 | 313005 |  | 313005
3.1.1.1 | Chief Investigator (2795) | 195 | [36 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3250 |  | 3250 | 3250 |  | 3250 | 3250 |  | 3250 | 9750 |  | 9750
3.1.1.2 | Investigator (2173 x 5) | 699 | [36 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 10865 |  | 10865 | 10865 |  | 10865 | 10865 |  | 10865 | 32595 |  | 32595
3.1.1.3 | Clerical Officer (1200 x 2) | 146 | [36 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2400 |  | 2400 | 2400 |  | 2400 | 2400 |  | 2400 | 7200 |  | 7200
3.1.1.4 | Driver ( x 3) | 100 | [36 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2600 |  | 2600 | 2600 |  | 2600 | 2600 |  | 2600 | 2600 |  | 2600 | 2600 |  | 2600 | 2600 |  | 2600 | 15600 |  | 15600
3.1.1.5 | Birth Name Registration Supervisors (740 x 1) | 0 | [31 empty] | 2827.99 | -2827.99 |  | 1412.16 | -1412.16 | 0 | 4240.15 | -4240.15 | 1480 |  | 1480 | 1480 |  | 1480 | 1480 |  | 740 | 1480 |  | 1480 | 1480 |  | 1480 | 1480 |  | 1480 | 1480 |  | 1480 | 1480 |  | 1480 | 1480 |  | 1480 | 1480 |  | 1480 | 1480 |  | 1480 | 1480 |  | 1480 | 17760 |  | 17760
3.1.1.6 | Birth Name Registration Assistant Supervisors (590 x 2) | 0 | [31 empty] | 1178.52 | -1178.52 |  | 3996.72 | -3996.72 | 0 | 5175.24 | -5175.24 | 2300 |  | 2300 | 2300 |  | 2300 | 2300 |  | 2300 | 2300 |  | 2300 | 2300 |  | 2300 | 2300 |  | 2300 | 2300 |  | 2300 | 2300 |  | 2300 | 2300 |  | 2300 | 2300 |  | 2300 | 2300 |  | 2300 | 2300 |  | 2300 | 27600 |  | 27600
3.1.1.7 | Birth Name Registration Clerk (500 x 20) | 0 | [31 empty] | 23536.66 | -23536.66 |  | 21769.48 | -21769.48 | 0 | 45306.14 | -45306.14 | 16875 |  | 16875 | 16875 |  | 16875 | 16875 |  | 16875 | 16875 |  | 16875 | 16875 |  | 16875 | 16875 |  | 16875 | 16875 |  | 16875 | 16875 |  | 16875 | 16875 |  | 16875 | 16875 |  | 16875 | 16875 |  | 16875 | 16875 |  | 16875 | 202500 |  | 202500
3.1.1.8 | Operation of IU Staff | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.2 | Hire IU study consultant | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.2.1 | Prepare Technical TOR/Scope | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.2.2 | Prepare ITB & List of Bidders, Eval Criteria & Eval Panel | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.2.3 | Obtain 'No Objection' from IDB | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.2.4 | Invite bidders | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.2.5 | Close invitation and open bids | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.2.6 | Evaluate proposals and prepare recommendation | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.2.7 | Obtain 'No Objection' from IDB | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.2.8 | Award of contract | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.3 | Operation of IU | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.4 | Sourcing of office space | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.5 | Purchase of office equipment | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
| Purchase of office furniture | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 10000 |  | 10000 | 90000 |  | 90000 |  |  | 0 |  |  | 0 | 100000 |  | 100000
| Purchase for IU staff (and PIU) | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
| Purchase of vehicles | [37 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
| Purchase for IU staff (and PIU) - Telecommunications | 100 | [19 empty] | 320.35 | -320.35 |  | 171.04 | -171.04 |  | 132.98 | -132.98 |  |  |  | 0 | 147.11 | -147.11 |  | 123.93 | -123.93 | 0 | 895.41 | -895.41 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1500 |  | 1500 | 1500 |  | 1500 | 1500 |  | 1500 | 1500 |  | 1500 | 6000 |  | 6000
| Maintenance of Vehilces purchsed for IU (and PIU) | 20 | [36 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
| Purchase for IU staff (and PIU) - Office Maintenance and utilities | 200 | [36 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 5000 |  | 5000 | 5000 |  | 5000
| Purchase for IU staff (and PIU) - Office rental | 1165 | [36 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 20886 |  | 20886 | 20886 |  | 20886 | 20886 |  | 20886 | 20886 |  | 20886 | 20886 |  | 20886 | 20886 |  | 20886 | 20886 |  | 20886 | 20886 |  | 20886 | 167088 |  | 167088
| Purchase for IU staff (and PIU) - Office supplies | 100 | [36 empty] | 0 | 0 | 0 |  |  | 0 | 2500 |  | 2500 | 2500 |  | 2500 | 2500 |  | 2500 | 2500 |  | 2500 | 2500 |  | 2500 | 2500 |  | 2500 | 2500 |  | 2500 | 2500 |  | 2500 | 2500 |  | 2500 | 2500 |  | 2500 | 2500 |  | 2500 | 27500 |  | 27500
| Hire consultant for birth Birth Name Registration Communications Campaign | 50
| Hire consultant for study to providerecommendations for strengthening the existing parcel identification numbering protocol | 85 | [36 empty] | 0 |  | 0 | [36 empty] | 0 |  | 0
3.2 | Study on property registration identification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [24 empty] | 12000 | 0 | 12000 | 12000 | 0 | 12000 | 12000 | 0 | 12000 | 12000 | 0 | 12000 | 48000 |  | 48000
3.2.1 | Hire individual consultant for study | [37 empty] | 0 |  | 0 | [21 empty] | 0 |  | 0 | 12000 |  | 12000 | 12000 |  | 12000 | 12000 |  | 12000 | 12000 |  | 12000 | 48000 |  | 48000
3.2.1.1 | Prepare Technical TOR/Scope | [37 empty] | 0 |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.2.1.2 | Prepare ITB & List of Bidders, Eval Criteria & Eval Panel | [37 empty] | 0 |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.2.1.3 | Obtain 'No Objection' from IDB | [37 empty] | 0 |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.2.1.4 | Invite bidders | [37 empty] | 0 |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.2.1.5 | Close invitation and open bids | [37 empty] | 0 |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.2.1.6 | Evaluate proposals and prepare recommendation | [37 empty] | 0 |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.2.1.7 | Obtain 'No Objection' from IDB | [37 empty] | 0 |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.2.1.8 | Award of contract | [37 empty] | 0 |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 0
3.2.2 | Conduct study | [37 empty] | 0 |  | 0 | [23 empty] | 0 | 12000 |  | 12000 | 12000 |  | 12000 | 12000 |  | 12000 | 12000 |  | 12000 | 48000 |  | 48000
| Hire consultant for study on best method to identify all property registrants | [37 empty] | 0 |  | 0 | [36 empty] | 0 |  | 0
| Subtotal | 2866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.35 | -320.35 | 0 | 171.04 | -171.04 | 0 | 132.98 | -132.98 | 0 | 0 | 0 | 0 | 27690.28 | -27690.28 | 0 | 27302.29 | -27302.29 | 0 | 55616.94 | -55616.94 | 20655 | 0 | 20655 | 23155 | 0 | 23155 | 23155 | 0 | 23155 | 23155 | 0 | 23155 | 44041 | 0 | 44041 | 44041 | 0 | 44041 | 46641 | 0 | 46641 | 46641 | 0 | 46641 | 70141 | 0 | 70141 | 166656 | 0 | 166656 | 76656 | 0 | 76656 | 81656 | 0 | 81656 | 666593 | 0 | 666593
Component 3
| 3.1 Auditing | [37 empty] | 0 |  | 0 | [12 empty] | 0 | [20 empty] | 0 |  | 0 | 0 |  | 0
| 3.2 Monitoring and evaluation | [37 empty] | 0 |  | 0 | [36 empty] | 0 |  | 0
| Hire Consultant to prepare Mid Term and Final Evaluation | [37 empty] | 0 |  | 0 | [36 empty] | 0 |  | 0
| Subtotal | 0 | [36 empty] | 0 | 0 | 0
Component 4
| Contingency | [37 empty] | 0 |  | 0 | [5 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | 0 |  | 0 | 0 |  | 0
[39 empty] | 0 |  | 0 | [36 empty] | 0 |  | 0
[39 empty] | 0 |  | 0 | [36 empty] | 0 |  | 0
| Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 5242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2379.55 | -2379.55 | 0 | 7886.66 | -7886.66 | 0 | 7921.82 | -7921.82 | 0 | 18494.67 | -18494.67 | 0 | 10125.48 | -10125.48 | 0 | 234121.49 | -234121.49 | 0 | 8013.96 | -8013.96 | 0 | 44345.31 | -44345.31 | 0 | 36111.86 | -36111.86 | 0 | 369400.8 | -369400.8 | 28630 | 0 | 28630 | 31130 | 0 | 31130 | 31130 | 0 | 31130 | 31130 | 0 | 31130 | 72016 | 0 | 72016 | 57016 | 0 | 57016 | 59616 | 0 | 59616 | 84616 | 0 | 84616 | 108116 | 0 | 108116 | 199631 | 0 | 199631 | 109631 | 0 | 109631 | 614631 | 0 | 614631 | 1805593 | 0 | 1805593
| Cumulative total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2379.55 | -2379.55 | 0 | 10266.21 | -10266.21 | 0 | 18188.03 | -18188.03 | 0 | 36682.7 | -36682.7 | 0 | 46808.18 | -46808.18 | 0 | 280929.67 | -280929.67 | 0 | 288943.63 | -288943.63 | 0 | 333288.94 | -333288.94 | 0 | 369400.8 | -369400.8 | 0 | 369400.8 | -369400.8 | 28630 | 369400.8 | -340770.8 | 59760 | 369400.8 | -309640.8 | 90890 | 369400.8 | -278510.8 | 122020 | 369400.8 | -247380.8 | 194036 | 369400.8 | -175364.8 | 251052 | 369400.8 | -118348.8 | 310668 | 369400.8 | -58732.8 | 395284 | 369400.8 | 25883.2 | 503400 | 369400.8 | 133999.2 | 703031 | 369400.8 | 333630.2 | 812662 | 369400.8 | 443261.2 | 1427293 | 369400.8 | 1057892.2 | 1805593 | 0 | 1805593
0
0
Note on C9: IADB: Total cost of Project 1 (sum of all milestone activities)
IADB: Total cost of Project 1 (sum of all milestone activities)