## Project Structure
TRADE SECTOR SUPPORT PROGRAM (BH-L1016)
Agency | Sub-Agency (If applies) | Agency's Initials
Bahamas Customs Department | n/a | BCD PEU
COMPONENTS? (YES / NO) | Component's Name (list by number or letter)
YES | Component 1: Strengthening of Customs Management
Component 2: Modernizing Customs Operations
Component 3: Enhancement of the International Trade Institutional Platform
Component 4: Administrative Costs
Component 5: Contingency

## Procurement Plan
INFORMATION FOR PROCUREMENT PLAN ONGOING ONGOING AND/OR LAST PRESENTED
TRADE SECTOR REFORM PROGRAM (2756/OC-BH)
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: | 2014-07-01 | 2015-12-01
2. Procurement Plan Details
Version ( 3-2014) :18 months
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Works | 400000 | 0
Goods | USD 10,345,000.00 | 0
Non Consulting Services | 620000 | 0
Training | USD 865,000.00 | 0
Operative Costs | 0 | 0
Consulting Services (Firms + Individuals) | USD 3,135,000.00 | 0
Transfers | 160000 | 0
Community Participation | 0 | 0
Contracted | USD 975,000.00 | 0
Total | USD 16,500,000.00 | USD 16,500,000.00
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
Component 1 - Strengthening of Customs Management | 2100000 | 0
Component 2 - Modernizing Customs Operations | 11845000 | 0
Component 3 - Enhancement of the International Trade Institutional Platform | 1295000 | 0
Component 4 - Administrative Costs | 1160000 | 0
Component 5 - Contingency | 100000 | 0
| 0 | 0
Total | 16500000 | 16500000

## Detailed Procurement Plan
PROCUREMENT PLAN INFORMATION - TRADE SECTOR REFORM PROGRAM (2756/OC-BH ) July 2014 to December 2015V3
ITEM # | WORKS
| Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Amount in u$s : |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments | Ex-Post
[7 empty] | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  | Ex-Ante
1 | BCD PMU | Renovation of Training Locations | Training Sites in NP (1) ,and GB (1) | National Competitive Bidding | 2 | 1.1.2.3 | 370000 | 100 | 0 | C 1 | Ex-Ante | 2015-02-02 | 2015-04-04 | In Process | Cancelled
2 | BCD PMU | Refurbishment of Boats | Restoration of (3) Boats for Marine Unit | Shopping | 3 | 2.3.2.4 | 150000 | 100 | 0 | C 2 | Ex-Ante | 2014-11-01 | 2015-01-01 | Pending | Cancelled
Null and Void
| GOODS | [13 empty] | Planned
| Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Amount in u$s : |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments | Rejection of all Bids
[7 empty] | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  | Re-Tendering
3 | BCD PMU | IT Software | HR Training Management Software | International Competitive Bidding | 1 | 1.1.2.2 | 370000 | 100 | 0 | C 1 | Ex-Ante | 2015-04-01 | 2015-08-01
4 | BCD PMU | IT equipment for training | Printers, projectors, and Other. | Shopping | 2 | 1.1.2.4 | 50000 | 100 | 0 | C 1 | Ex-Post | 2014-09-01 | 2014-11-01 | In Process | Direct Contracting
5 | BCD PMU | Equipment for Family Island Training Sites | (4) Family Island Customs Sites | Shopping | 4 | 1.1.2.3 | 100000 | 100 | 0 | C 1 | Ex-Post | 2014-09-01 | 2015-02-01 | Pending | Cancelled
6 | BCD PMU | PMU Equipment | Computer, Software, and Other. | Shopping | 1 | 4.1.1.4 | 5215 | 100 | 0 | C 1 | Ex-Post | 2015-01-01 | 2015-03-01 |  | Direct Contracting
7 | BCD PMU | IT Platform | Customs Automated Management System (CAS2) | International Competitive Bidding | 1 | 2.2.1.3 | 6090000 | 100 | 0 | C 2 | Ex-Ante | 2015-01-01 | 2015-07-01
8 | BCD PMU | IT Platform | Cargo & Passenger risk management platform (equipment, software, and training) | International Competitive Bidding | 1 | 2.3.1.1 | 1200000 | 100 | 0 | C 2 | Ex-Ante | 2015-01-01 | 2015-07-01
9 | BCD PMU | IT Platform | Implement IT Platforms for Trade related Agencies outside of Customs to move into a paperless operation (Min. Finance - PM Office - Statistics - Agriculture & Fisheries)-ESW | International Competitive Bidding | 1 | 2.4.1.1 | 1000000 | 100 | 0 | C 2 | Ex-Ante | 2015-01-01 | 2015-07-01 |  | National Competitive Bidding
10 | BCD PMU | Equipment/Aids | Customs Officer's Enforcement and Border Control Equipment | Shopping | 3 | 2.3.2.2 | 724600 | 100 | 0 | C 2 | Ex-Ante | 2014-09-01 | 2016-10-01
11 | BCD PMU | Marine Equipment | Three Outboard Boats for Marine Unit and training. | Shopping | 3 | 2.3.2.4 | 600000 | 100 | 0 | C 2 | Ex-Ante | 2014-07-01 | 2014-12-01 | In Process | International Competitive Bidding
12 | BCD PMU | IT Software | Active enforcement CASE Management Software | Shopping | 2 | 2.3.2.6 | 45000 | 100 | 0 | C 2 | Ex-Post | 2015-01-01 | 2015-03-01 |  | Limited International Bidding
13 | BCD PMU / MFS | IT equipment and software | Hardware and softwared for the IPR Register | Shopping | 2 | 3.2.4.3 | 100000 | 100 | 0 | C 3 | Ex-Ante | 2015-02-01 | 2015-04-01
14 | BCD PMU / MFS | Lab Equipment | Equipment to provide inhouse metrology services in Bureau | Shopping | 1 | 3.2.2.6 | 90000 | 100 | 0 | C3 | Ex-Ante | 2015-04-01 | 2015-06-01
| NON CONSULTING SERVICES | [13 empty] | Shopping
| Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Amount in u$s : |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
[7 empty] | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Bidding Documents | Contract Signature
15 | BCD PMU | Customs Control Equipment | K9 Unit (canine), equipment and training | Shopping | 3 | 2.3.2.3 | 600000 | 100 | 0 | C 2 | Ex-Ante | 2015-03-01 | 2015-06-01
16 | BCD PMU / MFS | Capacity building activities | Study tours for Bahamas Customs Department | Shopping |  | 1.1.1.2 | 105000 | 100 | 0 | C 1 | Ex-Post | 2014-12-01 |  | Technical Study Tours
17 | BCD PMU / MFS | Capacity building activities | Study tours for Standards Bureau Staff | Shopping |  | 3.2.2.4 | 10000 | 100 | 0 | C 3 | Ex-Post | 2015-11-01 |  | Shopping for air fare to travel to regional Bureaus
18 | BCD PMU / MFS | Capacity building activities | Public awareness campaign for Bureau | Shopping |  | 3.2.2.5 | 11283 | 100 | 0 | C 3 | Ex-Post | 2014-09-01 |  | Advertisement/Marketing fees
19 | BCD PMU / MFS | Capacity building activities | Public awareness campaign/activities for Modernization Project | Shopping |  | 1.1.3.4 | 42000 | 100 | 0 | C 1 | Ex-Post | 2015-01-01 |  | Advertisement/PPR/ Marketing fees
20 | BCD PMU / MFS | Capacity building activities | General trade awareness campaign | Shopping |  | 3.1.2.1 | 65000 | 100 | 0 | C 3 | Ex-Post | 2015-06-01 |  | Advertisement/Marketing fees
21 | BCD PMU | Capacity building activities | AEO Dissemination Pogramme to private sector and other stakeholders | Shopping |  | 2.4.2.2 | 20000 | 100 | 0 | C 2 | Ex-Post | 2016-03-01 |  | Advertisement/Marketing fees
Least-Cost Selection
| CONSULTING FIRMS | [13 empty] | Quality and Cost Based Selection
| Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Amount in u$s : |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments |  | Quality Based Selection
[6 empty] | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  |  | Selection Based on the Consultants' Qualifications-NICQ
22 | BCD PMU | IT Consultancy/ Equipment | Customs Network Consultancy | Quality and Cost Based Selection | 2.2.1.2 | 845000 | 100 | 0 | C2 | Ex-Ante | 2014-06-14 | 2014-11-01 | In Process |  | Shopping
23 | BCD PMU / MFS | International Consultant | International trade Expert - Vulnerability Study | Selection Based on the Consultants' Qualifications | 3.1.2.2 | 100000 | 100 | 0 | C3 | Ex-Ante | 2014-07-14 | 2014-12-01 | In Process |  | Turnkey | Goods
24 | BCD PMU / MFS | International Consultant | Expert in trade-related legislative assessment for technical standards and Regulation | Comparison of Qualifications - International Individual Consultant | 3.1.1.1 | 60000 | 100 | 0 | C3 | Ex-Ante | 2014-06-01 | 2014-12-01 | In Process
[15 empty] | Unit Prices | Goods
| INDIVIDUAL CONSULTANTS | [13 empty] | Lump-Sum | Goods
| Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Amount in u$s : |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments | Turnkey | Works
[6 empty] | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature |  | Unit Prices | Works
25 | BCD PMU | International Consultant | Expert to design and implement AEO programmes | Comparison of Qualifications - International Individual Consultant | 2.4.2.1 | 50000 | 100 | 0 | 1 | C 2 | Ex-Ante | No | 2015-10-01
26 | BCD PMU / MFS | International Consultant | Expert in trade to develop manuals for Mode 4 and Mode 3 and provide training on the manuals | Comparison of Qualifications - International Individual Consultant | 3.1.1.3 | 40000 | 100 | 0 | 1 | C 3 | Ex-Ante | No | 2015-07-01 |  |  |  | A
27 | BCD PMU / MFS | International Consultant | Expert in assessment of legislative framework, institutional capacity for EU EPA requirements for Competition | Comparison of Qualifications - International Individual Consultant | 3.1.1.4 | 50000 | 100 | 0 | 1 | C 3 | Ex-Ante | No | 2015-07-01
28 | BCD PMU / MFS | International Consultant | Development of manuals for SPS/WTO | Comparison of Qualifications - International Individual Consultant | 3.2.1.2 | 20000 | 100 | 0 | 1 | C 3 | Ex-Ante | No | 2015-11-01
29 | BCD PMU / MFS | National Consultant | Expert in Structural Engineering /Facilities/Laboratory and Environmental Assessment | Comparison of Qualifications - International Individual Consultant | 3.2.2.1 | 40000 | 100 | 0 | 1 | C 3 | Ex-Ante | No | 2015-10-01
30 | BCD PMU / MFS | International Consultant | Standards IT Consultant to assess technology needs/solutions for Bureau | Comparison of Qualifications - International Individual Consultant | 3.3.2.2. | 30000 | 100 | 0 | 1 | C 3 | Ex-Ante | No | 2015-07-01
31 | BCD PMU / MFS | International Consultant | Senior Trade Consultant to develop Annual Training Plan in Trade Policy, EPA, WTO, IPR etc. | Comparison of Qualifications - International Individual Consultant | 3.2.2.2 | 30000 | 100 | 0 | 1 | C 3 | Ex-Ante | No | 2015-06-01
32 | BCD PMU / MFS | International Consultant | Project Manager for the IPR Register | Comparison of Qualifications - International Individual Consultant | 3.2.4.1 | 90000 | 100 | 0 | 1 | C 3 | Ex-Ante | No | 2015-08-01
33 | BCD PMU / MFS | National Consultant | Patent Examiner for IPR Register | Comparison of Qualifications - National Individual Consultant (NICQ) | 3.1.1.5 | 85000 | 100 | 0 | 1 | C3 | Ex-Ante | No | 2015-12-01
34 | BCD PMU / MFS | International Consultant | Trade Consultant Accession Support Process | Comparison of Qualifications - International Individual Consultant | 3.3.2.3 | 65000 | 100 | 0 | 1 | C 3 | Ex-Ante | No | 2016-04-01
35 | BCD PMU | National Consultant | Monitoring and Evaluation Expert | Comparison of Qualifications - National Individual Consultant | 4.1.1.3 | 175000 | 100 | 0 | 1 | C 4 | Ex-Post | Yes | 2015-02-01 |  | Lump-Sum | Consulting Firms
36 | BCD PMU | National Consultant | External Evaluators | Comparison of Qualifications - National Individual Consultant | 4.2.1.1 | 100000 | 100 | 0 | 1 | C 4 | Ex-Ante | No | 2015-08-01 |  | Lump-Sum | Consulting Firms
37 | BCD PMU / MFS | International Consultant | Consultant to undertake economic revenue analysis of WTO Offer taking into account revenue reform, VAT and trade | Comparison of Qualifications - International Individual Consultant | 3.3.2.4 | 50000 | 100 | 0 | 1 | C 3 | Ex-Ante | No | 2016-02-01
38 | BCD PMU / MFS | International Consultant | Consultant to undertake Strategy plan to implement trade and services agenda in the context of trade liberalization | Comparison of Qualifications - International Individual Consultant | 3.2.3.1 | 30000 | 100 | 0 | 1 | C 3 | Ex-Ante | No | 2015-05-01
39 | BCD PMU / MFS | International Consultant | legislative Drafting For Regulations under the Draft Animal Health and Production Bill | Comparison of Qualifications - National Individual Consultant (NICQ) | 3.4.1.1 | 50000 | 100 | 0 | 1 | C 3 | Ex-Ante | Yes | 2015-03-01 | In Process
| TRAINING | [13 empty] | Time-Based | Consulting Firms
| Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Amount in u$s : |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments |  |  | Individual Consultants
[6 empty] | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Annual Training Plan (ATP) | End of Activity |  |  |  | Individual Consultants
40 | BCD PMU / MFS | Capacity building activities | Training of staff for IP office | Shopping | 3.2.4.2 | 20000 | 100 | 0 | C 3 | Ex-Ante |  | 2015-08-01
41 | BCD PMU / MFS | Capacity building activities | Training of staff for Standards Bureau | Shopping | 3.2.2.3 | 30000 | 100 | 0 | C 3 | Ex-Ante |  | 2015-10-01
42 | BCD PMU / MFS | Capacity building activities | Plant and Animal health training | Shopping | 3.2.1.1 | 30000 | 100 | 0 | C 3 | Ex-Ante |  | 2015-09-01
43 | BCD PMU / MFS | Capacity building activities | Training on negotiation skills, statistical analysis, market | Shopping | 3.3.1.1 | 150000 | 100 | 0 | C 3 | Ex-Ante |  | 2017-01-30
44 | BCD PMU / MFS | Capacity building activities | Training for new Organizational Structure | Shopping | 1.1.2.1 | 600000 | 100 | 0 | C1 | Ex-Ante | 2015-03-01 | 2017-10-01 | Will be implemented per needs and new function-skills definitions
[15 empty] | Technical Specifications | Non-Consulting Services
[15 empty] | Request for Proposals and Terms of Reference | Consulting Firms
``
Lump-Sum
Time-Based
Single Source Selection
Comparison of Qualifications - National Individual Consultant (NICQ)
Comparison of Qualifications - International Individual Consultant
3CV