## Detailed_Proc_Plan
Project Name: |  | Support to Improve the Sustainability of the Electricity Service
Program Number: |  | SU-L1009
Executing Unit: |  | N.V. Energy Bedrijven Suriname
PROCUREMENT PLAN PERIOD: 01-Augustus-2015 to 31-July-2016
WORKS
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Lots Quantity: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Review Method (Select one of the options): | Bid / Contract Number | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency ####) | Comments
[11 empty] | Submission of the Finalized Bidding Document |  | Date for non- objection offered by the bank |  | Publication (advertisement) |  | Bid Opening |  | Submission of Bid Evaluation & Draft Contract |  | No Objection to the Evaluation & draft contract |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date)
[11 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1D | Control & Dispatch Center | International Competitive Bidding | - | Procurement for Smaller Works | Lump-Sum | 1220000 | 1D | Ex-Ante | SU-L1009-030 | Planned | 2015-08-24 |  | 2015-09-11 |  | 2015-09-14 |  | 2015-10-16 |  | 2015-11-09 |  | 2015-12-04 |  | 2015-12-18 |  | 2016-06-30
2A | Civil Works foundation construction for TransmisSion/ Distribution line | Shopping | - | RFQ | Lump-Sum | 200000 | 2 | Ex-Ante | SU-L1009-018 | Planned | 2015-10-29 |  | 2015-11-12 |  | 2015-11-17 |  | 2015-12-22 |  | 2016-01-05 |  | 2016-01-19 |  | 2016-01-26 |  | 2016-02-22
3 | Civil Works SS/C (Upgrade Substation) | National Competitive Bidding | - | RFQ | Lump-Sum | 550000 | 3 | Ex-Ante | SU-L1009-019 | Planned | 2015-08-29 |  | 2015-09-12 |  | 2015-09-15 |  | 2015-10-20 |  | 2015-11-03 |  | 2015-11-17 |  | 2015-11-24 |  | 2016-11-23
2A | Cable Laying Substation Paranam and Powakka | Shopping | - | RFQ | Lump Sum | 160000 | 2A | Ex-Ante | SU-L1009-048 | Planned | 2015-09-03 |  | 2015-09-17 |  | 2015-09-20 |  | 2015-10-25 |  | 2015-11-08 |  | 2015-11-22 |  | 2015-11-29 |  | 2016-02-18
2A | Civil Works SS/D (Upgrade Substation) | Shopping | - | RFQ | Lump Sum | 100000 | 2A | Ex-Ante | SU-L1009-049 | Planned | 2016-05-20 |  | 2016-06-03 |  | 2016-06-06 |  | 2016-07-11 |  | 2016-07-25 |  | 2016-08-08 |  | 2016-08-15 |  | 2017-03-15
2A | Installation of Concrete Poles for Transmissionline 6 km | Shopping | - | RFQ | Lump Sum | 100000 | 2A | Ex-Ante | SU-L1009-050 | Planned | 2015-09-03 |  | 2015-09-17 |  | 2015-09-20 |  | 2015-10-25 |  | 2015-11-08 |  | 2015-11-22 |  | 2015-11-29 |  | 2016-02-27
2A | Installation 12kV Riser Poles for Substation POW | Shopping | - | RFQ | Lump Sum | 120000 | 2A | Ex-Ante | SU-L1009-051 | Planned | 2015-08-30 |  | 2015-09-13 |  | 2015-09-20 |  | 2015-10-25 |  | 2015-11-15 |  | 2015-11-22 |  | 2015-11-29 |  | 2016-03-28
2A | Installation River Cable | Shopping | - | RFQ | Lump Sum | 200000 | 2A | Ex-Ante | SU-L1009-052 | Planned | 2015-08-30 |  | 2015-09-13 |  | 2015-09-20 |  | 2015-10-25 |  | 2015-11-15 |  | 2015-11-22 |  | 2015-11-29 |  | 2016-04-27
2A | Installation Distributionlines (30 km) | Shopping | - | RFQ | Lump Sum | 282000 | 2A | Ex-Ante | SU-L1009-053 | Planned | 2015-08-30 |  | 2015-09-13 |  | 2015-09-20 |  | 2015-10-25 |  | 2015-11-15 |  | 2015-11-22 |  | 2015-11-29 |  | 2016-04-27
GOODS
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Lots Quantity: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Bid / Contract Number | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency) | Comments
[11 empty] | Submission of the Finalized Bidding Document |  | Date for non- objection offered by the bank |  | Publication (advertisement) |  | Bid Opening |  | Submission of Bid Evaluation & Draft Contract |  | No Objection to the Evaluation |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date)
[11 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
2 | Transmission and Distribution Materials (Insulators, Clamps, Cable ladders and Accessories) | Shopping | - | Procurement for Goods | Lump-Sum | 100000 | 2 |  | SU-L1009-033 | Planned | 2015-08-17 |  | 2015-08-31 |  | 2015-09-02 |  | 2015-09-23 |  | 2015-09-30 |  | 2015-10-14 |  | 2015-10-21 |  | 2015-11-18
1C | Procurement of SCADA/EMS system | International Competitive Bidding | - | Procurement for Goods | Lump-Sum | 6175000 | 1C | Ex-Ante | SU-L1009-032 | Planned | 2015-07-20 |  | 2015-08-03 |  | 2015-08-17 |  | 2015-11-30 |  | 2016-01-11 |  | 2016-01-25 |  | 2016-02-19 |  | 2017-03-31
1B | Client machines (Computers) | Direct Contracting | - | Procurement for Goods | Unit Prices | 40000 | 1B | Ex-Ante | SU-L1009-021 | Planned | 2015-08-10 |  | 2015-08-28 |  | N/a | N/a | N/a | N/a | 2015-08-31 |  | 2015-09-21 |  | 2015-09-29 |  | 2015-11-30
2A, 2B | Revenue Electricity Meters | Limited International Bidding | - | Procurement for Goods | Unit Prices | 525000 | 2A,2B | Ex-Ante | SU-L1009-022 | Planned | 2015-08-21 |  | 2015-09-04 |  | 2015-09-06 |  | 2015-10-04 |  | 2015-10-11 |  | 2015-10-25 |  | 2015-11-01 |  | 2015-12-01
1D | Acquisition of Solar equipment for Control and Dispatch Center | International Competitive Bidding | - | RFQ | Lump-Sum | 235400 | 1D | Ex-Ante | SU-L1009-055 | Planned | 2015-09-14 |  | 2015-10-02 |  | 2015-10-05 |  | 2015-11-06 |  | 2015-11-30 |  | 2015-12-25 |  | 2016-01-08 |  | 2016-07-21
2B | Design & Turnkey Delivery of 500kW Solar Power Plant | International Competitive Bidding | - | Procurement for Goods | Lump-Sum | 2500000 | 2B | Ex-Ante | SU-L1009-040 | Planned | 2015-07-26 | 2015-08-03 | 2015-08-09 |  | 2015-08-16 |  | 2015-09-27 |  | 2015-10-18 |  | 2015-10-25 |  | 2015-11-01 |  | 2016-05-31
NON CONSULTING SERVICES
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Lots Quantity: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Bid / Contract Number | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency ####) | Comments
[11 empty] | Submission of the Finalized Bidding Document |  | Estimated date for non- objection offered by the bank |  | Publication (advertisement) |  | Bid Opening |  | Submission of Bid Evaluation & Draft Contract |  | No Objection to the Evaluation |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date)
[11 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
2,3 | Transportation Services for Transformers (Lot 1, 002,AMPS) | Shopping | - | RFQ | Lump Sum | 50000 | 2,3 | Ex-Post | SU-L1009-027 | Planned | 2015-08-21 |  | 2015-08-28 |  | 2015-08-31 |  | 2015-09-04 |  | 2015-09-07 |  | 2015-09-14 |  | 2015-09-17 |  | 2015-09-22
CONSULTING FIRMS
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Process Number: | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Bid / Contract Number | Dates (If it does not apply, use N/A) | [21 empty] | Short List Members | Technical Score Assigned | Evaluated Price Proposal (Currency ####) | Combined Score | Comments
[10 empty] | Expression of Interest Notice |  | Submission of RFP and Short List |  | No Objection to RFP and Short List |  | RFP Submission |  | Bid Opening |  | Submission of Technical Evaluation |  | No Objection to the Technical Evaluation |  | Final Evaluation and Negotiation |  | No Objection to the Contract |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date)
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1B | GIS Application Integration | Selection Based on the Consultants' Qualifications (CQS) | - | Lump Sum | 140000 | 1B | Ex-Ante | Planned | SU-L1009-026 | N/a | N/a | N/a | N/a | N/a | N/a | 2015-10-05 |  | 2015-10-26 |  | 2015-11-09 |  | 2015-11-30 |  | 2015-12-07 |  | 2015-12-21 |  | 2015-12-28 |  | 2015-12-05
1B | On Site Esri Consulting Services | Single Source Selection | - | Lump Sum | 70950 | 1B | Ex-Ante | Planned | SU-L1009-009 | N/a | N/a | N/a | N/a | N/a | N/a | N/a | N/a | N/a | N/a | N/a | N/a | N/a | N/a | N/a | N/a | 2015-09-24 |  | 2015-10-01 |  | 2017-03-31 |  |  | n/a
2 | Impact Evaluation Baseline Survey | Least Cost Selection | - | Lump Sum | 218707.5 | 2 | Ex-Ante | In Process | SU-L1009-007 | N/a | N/a | 2015-05-22 | 2015-06-22 | 2015-06-05 | 2015-07-10 | 2015-06-12 | 2015-07-15 | 2015-08-17 |  | 2015-08-20 |  | 2015-09-03 |  | 2015-09-06 |  | 2015-09-13 |  | 2015-09-16 |  | 2016-01-31
2 | Survey for impact evaluation_Postevaluation | Single Source Selection | - | Lump Sum | 218707.5 | 2 | Ex-Ante | Planned | SU-L1009-034 |  | - |  | - |  | - |  | - |  | - |  | - |  | - |  | -
1B | Data conversion of existing data to GIS format | Least Cost Selection | - | Lump Sum | 280000 | 1B | Ex-Ante | Planned | SU-L1009-023 | 2015-10-05 |  | 2015-11-09 |  | 2015-11-16 |  | 2016-01-18 |  | 2016-01-18 |  | 2016-02-01 |  | 2016-02-08 |  | 2016-02-22 |  | 2016-03-01 |  | 2016-03-08 |  | 2017-03-08
1B | Data collection of electrical assets | QCBS | - | Lump Sum | 1600000 | 1B | Ex-Ante | Planned | SU-L1009-024 | 2015-10-05 |  | 2015-11-09 |  | 2015-11-16 |  | 2016-01-18 |  | 2016-01-18 |  | 2016-02-01 |  | 2016-02-08 |  | 2016-02-22 |  | 2016-03-01 |  | 2016-03-08 |  | 2018-03-08
INDIVIDUAL CONSULTANTS
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount, in u$s : | Estimated Number of Consultants: | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Bid / Contract Number | Dates (If it does not apply, use N/A) | [5 empty] | Consultant's Name | Period |  | Title | Comments
[10 empty] | No Objection to the TORs |  | Hiring Deadline |  | End of Activity |  |  | From | Until
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real
TRAINING
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Process Number: | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Bid / Contract Number | Dates (If it does not apply, use N/A) | [5 empty] | Detail | Amount (Currency ###) | Comments
[10 empty] | Annual Training Plan (ATP) |  | No Objection to the ATP |  | End of Activity
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real
1A | ERP: Solution Evaluation & Due Diligence(Site Visits) for EBS staff | N/a | - | N/a | 25000 | 1A | Ex-Ante | Planned | SU-L1009-041 | n/a |  | 2016-01-15 |  | 2016-02-14
1C | SCADA: Solution Evaluation & Due Diligence(Site Visits) for EBS staff | N/a | - | N/a | 25000 | 1C | Ex-Ante | Planned | SU-L1009-043 | n/a |  | 2015-12-15 |  | 2016-01-14
1B | Software extension & technical workshop training | Shopping | - | N/a | 30000 | 1B | Ex-Ante | Planned | SU-L1009-020 | n/a |  | 2015-12-15 |  | 2016-01-14
2,3 | FAT Description SU-L-1009 Switchgear 33kV/12kV OSP and POW, OSC, OSD | N/a | - | N/a | 34800 | 2,3 | Ex-Ante | Planned | SU-L1009-001 | n/a | n/a | n/a | n/a | 2015-07-21 | 2015-07-27 |  |  | ABB
2B | FAT Description SU-L-1009 Solar Power Plant | N/a | - | N/a | 18000 | 2B | Ex-Ante | Planned | SU-L1009-040 | n/a | n/a | n/a | n/a | 2016-01-15
Formulas:
Estimated = [Estimated]-14
Estimated = [Estimated]+365
Real = [Real]+21
Real = [Estimated]-7
End of Contract (Final date) = [Estimated]+365
Note on L9: Quincy Fernandes: Must be submission of the finalized doc to the bank. See instructions
Note on N9: Quincy Fernandes: Estimated date for non-objection offered by the Bank
Note on V9: Quincy Fernandes: Estimated date of non-objection provided by the Bank to the evaluation report
Note on N23: Quincy Fernandes: Estimated date for non-objection offered by the Bank