## Sheet1
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Guyana |  |  |  |  | Executing agency: CCB/CCB |  |  |  |  | Public or private sector: (indicate which applies)
Project number: GY-T1119 |  |  |  |  | Title of Project: Execution of a Crime Victimization Survey
Period covered by the plan: December 2015-December 2019
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$):____________ |  |  |  | Consulting services(in US$):_150,000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other % |  |  |  | Direct Contracting
1 |  | Components 1 and 2 | [8 empty] | International Competitive Bidding
|  | Consulting services | [8 empty] | Individual Consultant
|  | Survey Design and Training | 50000 | IICQ/CQS | ex-post | 100 |  | Jan. 2016 | yes |  | National System
2 |  | Data collection | 60000 | IICQ/CQS | ex-post | 100 |  | 2016-03-01 | yes | This consultancy will be executed by the same firm to be hired under Component 1. The designed TORs include both survey design and data collection | Ex Ante
|  | Sub-total | 110000
3 |  | Component 3 | [8 empty] | Ex Post
Individual consultants
|  | Data analysis and production of report | 40000 | IICQ | ex-post | 100 |  | 2015-06-16 | yes |  | National System
Total |  |  | 150000 | Prepared by:Diether Beuermann |  |  | Date: November 23, 2015
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.