## Procurement Plan
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Regional |  |  |  |  | Executing agency: Inter-American Development Bank |  |  |  |  | Public or private sector: Public
Project number: RG-T2675; RG-T2702 |  |  |  |  | Title of Project: Knowledge and Innovation: Disaster and Climate-Resilient Coastal Zone Management
Period covered by the plan: 24 months (October 2015 - October 2017)
Threshold for ex-post review of procurements: |  |  |  | Non consulting services (in US$): 0 |  |  |  | Consulting services(in US$): 675,000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other % |  |  |  | Direct Contracting
Consulting Services
|  | Component 1 | [8 empty] | International Competitive Bidding
|  | Tourism Surveys - Survey Specialist | 25000 | SSS | Ex-Ante | 100% | 0% | TBD
|  | Tourism Surveys - Natural Resource Economist | 15000 | SSS | Ex-Ante | 100% | 0% | TBD
|  | Preparation of Technical Note and Working Paper - Technical Report to Inform Technical Note and Working Paper and printing of said Working Paper | 74000 | IICQ | Ex-Ante | 100% | 0% | 2016-06-01 |  |  | National Competitive Bidding
|  | Preparation of Technical Note and Working Paper - Working Paper External Peer Reviewers | 6000 | SSS | Ex-Ante | 100% | 0% | 2017-03-01 |  | Two peer reviewers contracted for 5 days each
|  | Organization of a High-level Flagship Event and Production and Translation of Multimedia Materials | 179000 | QCBS | Ex-Ante | 100% | 0% | TBD
|  | Support for Regional Workshop and Policy Dialogue - 25 country participants' travel and per diem | 70000 | LCS | Ex-Ante | 100% | 0% | 2016-09-01 |  |  | Selection Based on the Consultants' Qualifications
|  | Organization of a High-Level Flagship Event and Production of Multimedia Materials- Staff travel and per diem | 6000 | LCS | Ex-Ante | 100% | 0% | TBD
|  | Organization of a High-Level Flagship Event and Production of Multimedia Materials- Panelists' travel, per diem and honorarium | 15000 | LCS | Ex-Ante | 100% | 0% | TBD
Component 2
|  | Development of an Index and Incentive Mechanism for Disaster and Climate-Resilient ICZM | 157000 | SSS | Ex-Ante | 100% | 0% | 2016-09-30
Project Administration
|  | Defined Term Contractual (DTC) 18 months | 108000 | IICQ | Ex-Ante | 100% | 0% | 2016-06-01
|  | IDB Staff Travel to Conferences - travel, per diem and registration fees | 20000 | LCS | Ex-Ante | 100% | 0% | TBD
Total |  |  | 675000 | Prepared by: Kelsey Schueler, INE/RND |  |  | Date: 6/3/2016
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection under a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical "or "complex "that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.