## CONSOLIDATED FINANCIAL PLAN (hidden)
CONSOLIDATED FINANCIAL PLAN - Component 1A- ERP Implementation
| Name of Executing Agency: | N.V.EBS
| Loan Contract number: | 3403/OC-SUL1039
| Date: | December 2015
| Category of Investment (1) | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | PROJECT TOTAL
|  | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total | IDB | Counterpart | Other | Total
#REF!
| #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! | 0 |  | #REF!
| #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! | 0 |  | #REF!
| #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! | 0 |  | #REF!
| #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! | 0 |  | #REF!
| #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! | 0 |  | #REF!
| #REF! | #REF! |  |  | #REF! | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 0 |  | #REF!
| #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! | 0 |  | #REF!
0
0
| Consulting Services | [11 empty] | 0
| #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! | 0 |  | #REF!
| #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! | 0 |  | #REF!
[6 empty] | #REF! | [6 empty] | 0
0
| Non- Consulting Services | [11 empty] | 0
| #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! | 0 |  | #REF!
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | 0
| Training |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | 0
| IT Skills Training ( New Skills Required to support new applications) | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF!
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | 0
| Total | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0 | #REF! | #REF! | 0 | 0 | #REF!
(1) The structure of the categories of investment should be consistent with the project categories entered in the WLMS.

## POA (hidden)
Annual Operating Plan - Component 1A- ERP Implementation
Name of Executing Agency: | N.V.EBS
Loan Contract number: | 3403/OC-SUL1039
Date: | DECEMBER 2015
Components | Outputs | Outcomes |  | Activities | Responsible | [20 empty] | Risks | Progress in implementing (%)
[6 empty] | Q1 2016 |  | Q2 2016 |  | Q3 2016 |  | Q4 2016 |  | Q1 2017 |  | Q2 2017 |  | Q3 2017 |  | Q4 2017 |  | Q1 2018 |  | TOTAL
|  |  | WBS Code |  |  | BID | CPL | BID | CPL | BID | CPL | BID | CPL | BID | CPL | BID | CPL | BID | CPL | BID | CPL | BID | CPL | BID | CPL
COMPONENT 1A | ERP Solution Implemented & In Use According to Organisational Change Management Plan | ERP MODULES IMPLEMENTED | 1 | Implementation Services | [19 empty] | 0
|  |  | 1.1 | Contract Execution | [19 empty] | 0
|  |  | 1.2 | Project Initiation | [19 empty] | 0
|  |  | 1.2.1 | Prepare Project Infrastructure | [5 empty] | 200000 | [13 empty] | 200000
|  |  | 1.2.2 | Project Kickoff Meeting | [5 empty] | 50000 | [13 empty] | 50000
|  |  | 1.3 | CIS Implementation | [5 empty] | 250714.29 |  | 1230714.2857 |  | 980714.2857 |  | 1280714.2857 |  | 1160714.2857 |  | 980714.2857 |  | 980714.2857 |  | 6865000.0043
|  |  | 1.4 | FIS Implementation | [19 empty] | 0
|  |  | 1.5 | WMS Implementation | [19 empty] | 0
|  | SERVER HARDWARE PROCURRED & INSTALLED | 2 | Hardware Acquisition | [7 empty] | #REF! | [5 empty] | #REF! | [5 empty] | #REF!
|  |  | 2.1 | Procure Hardware | [19 empty] | 0
|  |  | 2.1.1 | Request for No Objection | [19 empty] | 0
|  |  | 2.1.1.1 | Develop Technical Specification | [19 empty] | 0
|  |  | 2.1.1.2 | Complete Justification for No Objection for Direct Contracting | [19 empty] | 0
|  |  | 2.1.1.3 | Submit for Internal Review & Approval | [19 empty] | 0
|  |  | 2.1.1.4 | Submit Informal Request for No Objection to the IDB | [19 empty] | 0
|  |  | 2.1.1.5 | IDB Reviews Request for No Objection | [19 empty] | 0
|  |  | 2.1.1.6 | IDB Grants No Obejection to Direct Contracting | [19 empty] | 0
|  |  | 2.1.1.7 | Request Quotation from Vendor | [19 empty] | 0
|  |  | 2.1.1.8 | Receive Request for Quotation from Vendor | [19 empty] | 0
|  |  | 2.1.1.9 | Internal Review & Approval of Quotation | [19 empty] | 0
|  |  | 2.1.2 | Contract Preparation | [19 empty] | 0
|  |  | 2.1.2.1 | Prepare Draft Contract | [19 empty] | 0
|  |  | 2.1.2.2 | Internal Review & Approval of Contract | [19 empty] | 0
|  |  | 2.1.2.3 | Submit Request for Contract to the IDB | [19 empty] | 0
|  |  | 2.1.2.4 | IDB Reviews Contract Request for No Objection | [19 empty] | 0
|  |  | 2.1.2.5 | IDB Grants Request for No Objection to Contract | [19 empty] | 0
|  |  | 2.1.3 | Contract Execution | [19 empty] | 0
|  |  | 2.1.3.1 | Signing by EBS | [19 empty] | 0
|  |  | 2.1.3.2 | Signing by Vendor | [19 empty] | 0
|  |  | 2.2 | Order Hardware | [19 empty] | 0
|  |  | 2.3 | Process Order | [5 empty] | 260000 | [13 empty] | 260000
|  |  | 2.4 | Server Hardware Received by EBS | [19 empty] | 0
|  |  | 2.5 | Configure hardware | [19 empty] | 0
|  |  | 2.5.1 | Set Up & Install Hardware in EBS Server Room | [19 empty] | 0
|  |  | 2.5.2 | Configure Hardware | [19 empty] | 0
|  |  | 2.5.3 | Test installed system | [19 empty] | 0
|  |  | 2.5.4 | Hardware Acquired, Installed & Configured | [19 empty] | 0
|  | Server Software Installed | 3 | Server Software Acquisition | [5 empty] | #REF! |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF!
|  | DB Tools in Use | 4 | Database Management Tools | [5 empty] | #REF! |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF!
|  | Client Machines Installed | 5 | Client Machines | [5 empty] | #REF! |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF!
|  | Network Infrastructrure for Rural Districts & Nickerie Upgraded | 6 | Infrastructure Upgrade | [7 empty] | 100000 | [5 empty] | #REF! | [5 empty] | #REF!
|  |  | 6.1 | Development of Terms of Reference | [19 empty] | 0
|  |  | 6.2 | Internal Review & Approval of TOR | [19 empty] | 0
|  |  | 6.3 | IDB Review & Approval of TOR | [19 empty] | 0
|  |  | 6.4 | Bid Process | [19 empty] | 0
|  |  | 6.5 | Evaluation of TOR Responses | [19 empty] | 0
|  |  | 6.6 | Internal Review & Approval of TOR Evaluation | [19 empty] | 0
|  |  | 6.7 | IDB Approval of Evaluation | [19 empty] | 0
|  |  | 6.8 | Contract Award | [19 empty] | 0
|  |  | 6.9 | Execuction of Infrastructure Upgrade | [19 empty] | 0
|  | Change Program Implemented | 7 | Change Management Services | [7 empty] | #REF! |  | #REF! |  |  |  | #REF! |  | #REF! |  |  |  | #REF!
|  |  | 7.1 | Development of Terms of Reference | [19 empty] | 0
|  |  | 7.2 | Internal Review & Approval of TOR | [19 empty] | 0
|  |  | 7.3 | IDB Review & Approval of TOR | [19 empty] | 0
|  |  | 7.4 | Bid Process | [19 empty] | 0
|  |  | 7.5 | Evaluation of TOR Responses | [19 empty] | 0
|  |  | 7.6 | Internal Review & Approval of TOR Evaluation | [19 empty] | 0
|  |  | 7.7 | IDB Approval of Evaluation | [19 empty] | 0
|  |  | 7.8 | Contract Award | [19 empty] | 0
|  |  | 7.9 | Execuction of Change Mangement Services | [5 empty] | #REF! |  | #REF! |  | 105000 |  | 105000 |  | 105000 |  | 105000 |  | 105000 |  | #REF!
|  | Monitoring of Qulaity Completed | 8 | Quality Assurance Services |  |  |  | 0 |  |  |  | #REF! |  | #REF! |  |  |  | #REF! |  | #REF! |  |  |  | #REF!
|  |  | 8.1 | Development of Terms of Reference | [19 empty] | 0
|  |  | 8.2 | Internal Review & Approval of TOR | [19 empty] | 0
|  |  | 8.3 | IDB Review & Approval of TOR | [19 empty] | 0
|  |  | 8.4 | Bid Process | [19 empty] | 0
|  |  | 8.5 | Evaluation of TOR Responses | [19 empty] | 0
|  |  | 8.6 | Internal Review & Approval of TOR Evaluation | [19 empty] | 0
|  |  | 8.7 | IDB Approval of Evaluation | [19 empty] | 0
|  |  | 8.8 | Contract Award | [19 empty] | 0
|  |  | 8.9 | Execution of Quality Assurance Services | [5 empty] | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  |  | 9 | Miscellaneous Procurement | [5 empty] | #REF! |  | #REF! |  | #REF! |  | #REF! | [7 empty] | #REF!
|  | New Skills Acquired | 10 | Training | [5 empty] | #REF! | [13 empty] | #REF!
|  |  | 10 | [20 empty] | 0
Grand Total | [5 empty] | 0 | 0 | 0 | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | #REF! | 0 | 0 | 0
Components | Outputs | Outcomes |  | Activities | Responsible | [14 empty] | Risks | Progress in implementing (%)
[6 empty] | Q1 2016 |  | Q2 2016 |  | Q3 2016 |  | Q4 2016 |  | 2017 |  | 2018 |  | TOTAL
|  |  | WBS Code |  |  | BID | CPL | BID | CPL | BID | CPL | BID | CPL | BID | CPL | BID | CPL | BID | CPL
COMPONENT 1B | THE DESIGN OF THE SYSTEM | OMS & DMS SYSTEM DESIGN | 1 | Design of the OMS/DMS System | [13 empty] | 0 | 0
|  |  | 1.1 | Selection of Consultant | [13 empty] | 0 | 0
|  |  | 1.1.1 | Development of TOR | [13 empty] | 0 | 0
|  |  | 1.1.2 | Internal Review & Approval of TOR | [13 empty] | 0 | 0
|  |  | 1.1.3 | IDB Review & Approval of TOR | [13 empty] | 0 | 0
|  |  | 1.1.4 | Bid Process | [13 empty] | 0 | 0
|  |  | 1.1.5 | Evaluation of TOR Responses | [13 empty] | 0 | 0
|  |  | 1.1.6 | Internal Review & Approval of TOR Evaluation | [13 empty] | 0 | 0
|  |  | 1.1.7 | IDB Approval of Evaluation | [13 empty] | 0 | 0
|  |  | 1.1.8 | Contract Award |  |  |  | 0 | [9 empty] | 0 | 0
|  |  | 1.2 | System Design | [13 empty] | 0 | 0
| OMS AND DMS SYSTEM IMPLEMENTED | RFP COMPLETED AND APPROVED | 2 | Bidding Document Preparation | [13 empty] | 0 | 0
|  |  | 2.1 | Preparation of Technical Specification | [13 empty] | 0 | 0
|  |  | 2.1.1 | Development of Business Process Requirements | [13 empty] | 0 | 0
|  |  | 2.1.2 | Technology Definition | [13 empty] | 0 | 0
|  |  | 2.1.3 | Development of Interface Requirements | [13 empty] | 0 | 0
|  |  | 2.1.4 | Internal Review & Approval of Technical Specifications | [13 empty] | 0 | 0
|  |  | 2.1.5 | IDB Review & Approval of Technical Specifications | [13 empty] | 0 | 0
|  |  | 2.2 | Preparation of IDB Procurement Documents | [13 empty] | 0 | 0
|  |  | 2.2.1 | Preparation of Standard Bidding Document for Goods | [13 empty] | 0 | 0
|  |  | 2.2.2 | Preparation & Approval of Specific Procurement Notice (SPN) | [13 empty] | 0 | 0
|  |  | 2.2.3 | Internal Review & Approval of Bidding Document for Goods | [13 empty] | 0 | 0
|  |  | 2.2.4 | IDB Review & Approval of Bidding Document & SPN | [13 empty] | 0 | 0
|  |  | 2.3 | Preparation of Evaluation Tool | [13 empty] | 0 | 0
|  |  | 2.3.1 | Development of Tool | [13 empty] | 0 | 0
|  |  | 2.3.2 | Testing of Tool | [13 empty] | 0 | 0
|  |  | 2.3.3 | Internal Review & Approval of Evaluation Tool | [13 empty] | 0 | 0
|  |  | 2.3.4 | IDB Review of Evaluation Tool | [13 empty] | 0 | 0
|  | BID RESPONSES RECEIVED | 3 | Bidding Process | [13 empty] | 0 | 0
|  |  | 3.1 | Submission of Bids to Market | [13 empty] | 0 | 0
|  |  | 3.2 | Pre-bid Conference & Site Visits | [13 empty] | 0 | 0
|  |  | 3.3 | Clarification of Vendor Questions | [13 empty] | 0 | 0
|  |  | 3.4 | Bid Closing | [13 empty] | 0 | 0
|  |  | 3.5 | Opening of Submitted Bids | [13 empty] | 0 | 0
|  | VENDOR SELECTED | 4 | Review of Proposals | [13 empty] | 0 | 0
|  |  | 4.1 | Preliminary Review | [13 empty] | 0 | 0
|  |  | 4.2 | Technical Review | [13 empty] | 0 | 0
|  |  | 4.3 | Cost Review | [13 empty] | 0 | 0
|  |  | 4.4 | Vendor Demonstrations | [13 empty] | 0 | 0
|  |  | 4.5 | Preparation of Evaluation Report | [13 empty] | 0 | 0
|  |  | 4.6 | Internal Review & Approval of Evaluation Report | [13 empty] | 0 | 0
|  |  | 4.7 | IDB Review & Approval of Evaluation Report | [13 empty] | 0 | 0
|  | CONTRACT EXECUTED | 5 | Award of Contract | [13 empty] | 0 | 0
|  |  | 5.1 | Development of Statement of Work | [13 empty] | 0 | 0
|  |  | 5.2 | Contract Negotiation | [13 empty] | 0 | 0
|  |  | 5.3 | Internal Review & Approval of Contract | [13 empty] | 0 | 0
|  |  | 5.4 | IDB Review & Approval of Contract | [13 empty] | 0 | 0
|  |  | 6 | Hardware Acquisition | [13 empty] | 0 | 0
|  |  | 6.1 | Procure Hardware | [13 empty] | 0 | 0
|  |  | 6.1.1 | Request for No Objection | [13 empty] | 0 | 0
|  |  | 6.1.1.1 | Develop Technical Specification | [13 empty] | 0 | 0
|  |  | 6.1.1.2 | Complete Justification for No Objection for Direct Contracting | [13 empty] | 0 | 0
|  |  | 6.1.1.3 | Submit for Internal Review & Approval | [13 empty] | 0 | 0
|  |  | 6.1.1.4 | Submit Request for No Objection to the IDB | [13 empty] | 0 | 0
|  |  | 6.1.1.5 | IDB Reviews Request for No Objection | [13 empty] | 0 | 0
|  |  | 6.1.1.6 | IDB Grants No Obejection to Direct Contracting | [13 empty] | 0 | 0
|  |  | 6.1.1.7 | Request Quotation from Vendor | [13 empty] | 0 | 0
|  |  | 6.1.1.8 | Receive Request for Quotation from Vendor | [13 empty] | 0 | 0
|  |  | 6.1.1.9 | Internal Review & Approval of Quotation | [13 empty] | 0 | 0
|  |  | 6.1.2 | Contract Preparation | [13 empty] | 0 | 0
|  |  | 6.1.2.1 | Prepare Draft Contract | [13 empty] | 0 | 0
|  |  | 6.1.2.2 | Internal Review & Approval of Contract | [13 empty] | 0 | 0
|  |  | 6.1.2.3 | Submit Request for Contract to the IDB | [13 empty] | 0 | 0
|  |  | 6.1.2.4 | IDB Reviews Contract Request for No Objection | [13 empty] | 0 | 0
|  |  | 6.1.2.5 | IDB Grants Request for No Objection to Contract | [13 empty] | 0 | 0
|  |  | 6.1.3 | Contract Execution | [13 empty] | 0 | 0
|  |  | 6.1.3.1 | Signing by EBS | [13 empty] | 0 | 0
|  |  | 6.1.3.2 | Signing by Vendor | [13 empty] | 0 | 0
|  |  | 6.2 | Order Hardware | [13 empty] | 0 | 0
|  |  | 6.3 | Process Order | [13 empty] | 0 | 0
|  |  | 6.4 | Server Hardware Received by EBS |  |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0 | 0
|  |  | 6.5 | Configure Hardware | [13 empty] | 0 | 0
|  |  | 6.5.1 | Set Up & Install Hardware in EBS Server Room | [13 empty] | 0 | 0
|  |  | 6.5.2 | Configure Hardware | [13 empty] | 0 | 0
|  |  | 6.5.3 | Test installed system | [13 empty] | 0 | 0
|  |  | 6.5.4 | Hardware Acquired, Installed & Configured | [13 empty] | 0 | 0
|  | OMS IMPLEMENTED | 7 | Implementation of OMS | [9 empty] | 0 |  | 0 |  | 0 | 0
|  |  | 8 | OMS Application Implemented | [13 empty] | 0 | 0
|  | DMS IMPLEMENTED | 9 | Implementation of DMS | [13 empty] | 0 | 0
|  |  | 10 | DMS Application Implemented | [13 empty] | 0 | 0
|  | Project Close Out | 11 | Project Close Out | [13 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
Grand Total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Procurement Plan (hidden)
INFORMATION FOR PROCUREMENT PLAN INITIAL UPLOAD ONGOING AND/OR LAST PRESENTED
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: | Q1 2016 | Q4 2017
2. Procurement Plan Details
Version ( 1-2015) :
Component 1A- ERP Implementation
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Works |  | 0
Goods | 7653000 | 7653000
Non Consulting Services | 100000 | 100000
Training | 20000 | 20000
Operative Costs |  | 0
Consulting Services (Firms + Individuals) | 990000 | 990000
Transfers |  | 0
Community Participation |  | 0
Unassigned |  | 0
Total | 8763000 | 8763000
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
Component 1A | 8763000
Total | 8763000 | 8763000

## Detailed Procurement Plan2 (hidden)
Project Name: |  | Support to Improve the Sustainability of the Electricity Service
Program Number: |  | SU-L1039
Executing Unit: |  | N.V. Energy Bedrijven Suriname
Component Information |  | Component 1A- ERP Implementation Program
PROCUREMENT PLAN PERIOD: Q1 2016 THROUGH Q4 2017
WORKS
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Lots Quantity: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Review Method (Select one of the options): | Bid / Contract Number | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency ####) | Comments
[11 empty] | Submission of the Finalized Bidding Document |  | Date for non- objection offered by the bank |  | Publication (advertisement) |  | Bid Opening |  | Submission of Bid Evaluation & Draft Contract |  | No Objection to the Evaluation & draft contract |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date)
[11 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
GOODS
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Lots Quantity: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Bid / Contract Number | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency) | Comments
[11 empty] | Submission of the Finalized Bidding Document |  | Date for non- objection offered by the bank |  | Publication (advertisement) |  | Bid Opening |  | Submission of Bid Evaluation & Draft Contract |  | No Objection to the Evaluation |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date)
[11 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1A | Procurement of ERP Software & Implementation Services , Associated Expenses & Maintenance ( 2yrs) | International Competitive Bidding | 1 | Procurement Of Goods | Lump sum | 7115000 | 1A | Ex-Ante | SU-L1039-001 (1) | Planned | 2015-10-29 | 2015-10-30 | 2015-11-12 |  | 2015-11-22 |  | 2016-02-14 |  | 2016-06-19 |  | 2016-07-03 |  | 2016-07-13 |  | 2018-07-31
1A | Procurement of Server Hardware | Direct Contracting | 1 | Request for Quotation | Lump sum | 260000 | 1A | Ex-Ante | SU-L1039-002 | Planned | #REF! |  | #REF! |  | N/A |  | N/A |  | #REF! |  | N/A |  | #REF! |  | #REF!
1A | Procurement of Server Software ( Backup Tools) | Shopping | 1 | Request for Quotation | Lump sum | 90000 | 1A | Ex-Ante | SU-L1039-003 | Planned | 2016-04-29 |  | 2016-05-20 |  | 2016-05-30 |  | 2016-06-17 |  | 2016-07-01 |  | 2016-07-22 |  | 2016-07-29 |  | 2016-09-12
1A | Procurement of Database management Tools | Shopping | 1 | Request for Quotation | Lump sum | 60000 | 1A | Ex-Ante | SU-L1039-004 | Planned | 2016-05-06 |  | 2016-05-27 |  | 2016-06-06 |  | 2016-06-24 |  | 2016-07-15 |  | 2016-08-05 |  | 2016-08-19 |  | 2016-09-19
1A | Procurement of Client Machines (Desktop) | Direct Contracting | 1 | Request for Quotation | Lump sum | 12000 | 1A | Ex-Ante | SU-L1039-005 | Planned | 2016-05-02 |  | 2016-05-20 |  | N/A |  | N/A |  | 2016-05-02 |  |  |  | 2016-06-03 |  | 2016-09-02
1A | Procurement of Miscellaneous Good (Office supplies, PC's, travel, facilities, etc) | Shopping | TBD | Request for Quotation | Unit Price | 16000 | 1A | Ex-Ante | SU-L1039-006 | Planned
1A | Procurement of Tools Required to Support the implementation of Change Management Process | National Competitive Bidding | TDB | Procurement Of Goods | Lump sum | 100000 | 1A | Ex-Ante | SU-L1039-007 | Planned
NON CONSULTING SERVICES
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Lots Quantity: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Bid / Contract Number | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency ####) | Comments
[11 empty] | Submission of the Finalized Bidding Document |  | Estimated date for non- objection offered by the bank |  | Publication (advertisement) |  | Bid Opening |  | Submission of Bid Evaluation & Draft Contract |  | No Objection to the Evaluation |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date)
[11 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1A | Procurement of Goods & Services to faciliate Network Upgrades ( Communication) | Shopping | 1 | Request for Quotation | Lump Sum | 100000 | 1A | Ex-Ante | SU-L1039-008 | Planned | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | 2016-12-31
CONSULTING FIRMS
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Process Number: | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Bid / Contract Number | Dates (If it does not apply, use N/A) | [21 empty] | Short List Members | Technical Score Assigned | Evaluated Price Proposal (Currency ####) | Combined Score | Comments
[10 empty] | Expression of Interest Notice |  | Submission of RFP and Short List |  | No Objection to RFP and Short List |  | RFP Submission |  | Bid Opening |  | Submission of Technical Evaluation |  | No Objection to the Technical Evaluation |  | Final Evaluation and Negotiation |  | No Objection to the Contract |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date)
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1A | Procurement of Change Management Services | Quality & Cost Based Selection (QCBS) | - | Lump Sum | 600000 | 1A | Ex-Ante | Planned | SU-L1039-009 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | 2016-05-20 |  | 2016-06-03 |  | #REF! |  | #REF! | [6 empty] | 2016-05-20
1A | Procurement of Quality Assurance Services | Quality & Cost Based Selection (QCBS) | - | Lump Sum | 390000 | 1A | Ex-Ante | Planned | SU-L1039-010 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | 2016-05-06 |  | 2016-05-20 |  | #REF! |  | #REF!
INDIVIDUAL CONSULTANTS
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount, in u$s : | Estimated Number of Consultants: | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Bid / Contract Number | Dates (If it does not apply, use N/A) | [5 empty] | Consultant's Name | Period |  | Title | Comments
[10 empty] | No Objection to the TORs |  | Hiring Deadline |  | End of Activity |  |  | From | Until
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real
TRAINING
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Process Number: | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Bid / Contract Number | Dates (If it does not apply, use N/A) | [5 empty] | Detail | Amount (Currency ###) | Comments
[10 empty] | Annual Training Plan (ATP) |  | No Objection to the ATP |  | End of Activity
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real
1A | IT Skills Training ( New Skills Required to support new applications) | Shopping | - | Unit Price | 20000 |  | Ex-Ante |  | SU-L1039-011 | N/A |  | N/A |  | N/A
Formulas:
Estimated = [Estimated]+14
Note on L9: Quincy Fernandes: Must be submission of the finalized doc to the bank. See instructions
Note on N9: Quincy Fernandes: Estimated date for non-objection offered by the Bank
Note on V9: Quincy Fernandes: Estimated date of non-objection provided by the Bank to the evaluation report
Note on N17: Quincy Fernandes: Estimated date for non-objection offered by the Bank
Note on D24: Coleen Palmer Wright: This will be determined on a needs basis during project execution
Note on D25: Coleen Palmer Wright: This will be determined based on the Change Program which is developed.

## Detailed Procurment Plan
Project Name: | Support for the Implementation of EBS Investment Plan
Program Number: | SU-L1039
Executing Unit: | N.V. Energy Bedrijven Suriname
PROCUREMENT PLAN PERIOD: 01 July 2016 - 31 Dec 2018
Dates (If it does not apply, use N/A)
WORKS | [10 empty] | Submission of the Finalized Bidding Document to the Bank |  | Date for non- objection offered by the bank |  | Publication (advertisement) |  | Bid Opening |  | Submission of Bid Evaluation & Draft Contract |  | No Objection to the Evaluation & draft contract |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date) |  | Bidder | Proposal Price (Currency ) | Comments
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Lots Quantity: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Review Method (Select one of the options): | Bid / Contract Number | Process Status (Select one of the options): | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
2A | Civil Upgrade Substation Building Jacobusrust (J) | National Competitive Bidding | - | Procurement for Smaller Works | Lump-Sum | 500000 | 2A | Ex-Ante | SU-L1039-059 | Planned | 2016-08-11 |  | 2016-08-25 |  | 2016-09-01 |  | 2016-10-13 |  | 2016-11-03 |  | 2016-11-17 |  | 2016-12-01 |  | 2018-12-31
2A | Cable Laying and Install Cable & Cable Accessories SS/J | Shopping | - | Request for Quotation | Lump-Sum | 253400 | 2A | Ex-Ante | SU-L1039-060 | Planned | 2016-08-11 |  | 2016-08-25 |  | 2016-09-01 |  | 2016-09-29 |  | 2016-10-20 |  | 2016-11-03 |  | 2016-11-17 |  | 2017-05-16 |  |  |  | Shopping based on simple works regularly carried out by small group of local contractors
2B | Civil Upgrade Substation Building F | National Competitive Bidding | - | Procurement for Smaller Works | Lump Sum | 980000 | 2B | Ex-Ante | SU-L1039-061 | Planned | 2017-02-10 |  | 2017-02-24 |  | 2017-03-03 |  | 2017-04-14 |  | 2017-05-05 |  | 2017-05-19 |  | 2017-06-02 |  | 2018-06-02
2B | Cable Laying SS/F | Shopping | - | Request for Quotation | Lump Sum | 100000 | 2B | Ex-Ante | SU-L1039-062 | Planned | 2017-01-20 |  | 2017-02-03 |  | 2017-02-10 |  | 2017-03-10 |  | 2017-03-31 |  | 2017-04-14 |  | 2017-04-28 |  | 2018-06-11
2C | New Substation Building Boma | National Competitive Bidding | - | Procurement for Smaller Works | Lump Sum | 980000 | 2C | Ex-Ante | SU-L1039-063 | Planned | 2017-06-05 |  | 2017-06-19 |  | 2017-06-26 |  | 2017-08-07 |  | 2017-08-28 |  | 2017-09-11 |  | 2017-09-25 |  | 2019-06-20 |  |  |  | Shopping based on simple works regularly carried out by local contractors
2C | Land Clearing & Route Survey Substation Boma | Shopping | 2 | Request for Quotation | Lump Sum | 234400 | 2C | Ex-Ante | SU-L1039-064 | Planned | 2016-07-30 |  | 2016-08-13 |  | 2016-08-20 |  | 2016-09-17 |  | 2016-10-08 |  | 2016-10-22 |  | 2016-11-05 |  | 2016-12-03
2C | 12 kV Cable Laying OS/Boma & OS/E | Shopping | - | Request for Quotation | Lump Sum | 53750 | 2C | Ex-Ante | SU-L1039-065 | Planned | 2016-12-16 |  | 2016-12-30 |  | 2017-01-06 |  | 2017-02-03 |  | 2017-02-24 |  | 2017-03-10 |  | 2017-03-24 |  | 2018-05-15
2C | Civil Upgrade Substation E | National Competitive Bidding | - | Procurement for Smaller Works | Lump Sum | 620300 | 2C | Ex-Ante | SU-L1039-066 | Planned | 2016-11-08 |  | 2016-11-22 |  | 2016-11-29 |  | 2017-01-10 |  | 2017-01-31 |  | 2017-02-14 |  | 2017-02-28 |  | 2018-09-11
2C | Install transmission Cable SS/HL - SS/Boma- SS/E | International Competitive Bidding (ICB) | - | Procurement for Works | Lump Sum | 3887500 | 2C | Ex-Ante | SU-L1039-067 | Planned | 2016-09-21 |  | 2016-10-05 |  | 2016-10-12 |  | 2016-12-07 |  | 2017-01-04 |  | 2017-01-18 |  | 2017-02-01 |  | 2017-03-28
2C | Cable Laying Riser poles OS Boma | Shopping | - | Request for Quotation | Lump Sum | 25000 | 2C | Ex-Ante | SU-L1039-068 | Planned | 2017-04-03 |  | 2017-04-17 |  | 2017-04-24 |  | 2017-05-22 |  | 2017-06-12 |  | 2017-06-26 |  | 2017-07-10 |  | 2017-09-09
Dates (If it does not apply, use N/A)
GOODS | [10 empty] | Submission of the Finalized Bidding Document to the Bank |  | Date for non- objection offered by the bank |  | Publication (advertisement) |  | Bid Opening |  | Submission of Bid Evaluation & Draft Contract |  | No Objection to the Evaluation |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date) |  | Bidder | Proposal Price (Currency) | Comments
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Lots Quantity: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Bid / Contract Number | Process Status (Select one of the options): | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1A | Procurement of ERP Software & Implementation Services , Associated Expenses & Maintenance | International Competitive Bidding | 1 | Procurement Of Goods | Lump sum | 7715000 | 1A | Ex-Ante | SU-L1039-001 (1) | In process | 2015-10-29 | 2015-10-29 | 2015-11-12 | 2015-12-18 | 2015-11-22 | 2015-12-29 | 2016-02-14 | 2016-03-18 | 2016-06-19 |  | 2016-07-03 |  | 2016-07-29 |  | 2018-07-31
1A | Procurement of Server Hardware | Direct Contracting | 1 | Request for Quotation | Lump sum | 300000 | 1A | Ex-Ante | SU-L1039-002 | Planned | 2016-08-28 |  | 2016-09-11 |  | N/A |  | N/A |  | 2016-10-02 |  | 2016-10-16 |  | 2016-10-19 |  | 2017-01-17 |  |  |  | Standardisation of EBS IT Infrastructure. As advised by DELL, SIOC is the only authorised dealer in Suriname
1A | Procurement of Server Software ( Backup Tools) | National Competitive Bidding | 1 | Procurement Of Goods | Lump sum | 90000 | 1A | Ex-Ante | SU-L1039-003 | Planned | 2016-08-12 |  | 2016-08-26 |  | 2016-08-28 |  | 2016-09-18 |  | 2016-10-02 |  | 2016-10-16 |  | 2016-10-23 |  | 2016-12-22
1A | Procurement of Database management Tools | National Competitive Bidding | 1 | Procurement Of Goods | Lump sum | 60000 | 1A | Ex-Ante | SU-L1039-004 | Planned | 2016-08-19 |  | 2016-09-02 |  | 2016-09-04 |  | 2016-09-25 |  | 2016-10-09 |  | 2016-10-23 |  | 2016-10-30 |  | 2016-12-29
1A | Procurement of Client Machines (Desktop) | Direct Contracting | 1 | Request for Quotation | Lump sum | 12000 | 1A | Ex-Ante | SU-L1039-005 | Planned | 2016-08-04 |  | 2016-08-18 |  | N/A |  | N/A |  | 2016-08-18 |  | 2016-09-01 |  | 2016-09-04 |  | 2016-12-03 |  |  |  | Standardisation of EBS IT Infrastructure. As advised by DELL, SIOC is the only authorised dealer in Suriname
1A | Procurement of Miscellaneous Good (Office supplies, PC's, travel, facilities, etc) | Shopping | TBD | Request for Quotation | Unit Price | 16000 | 1A | Ex-Ante | SU-L1039-006 | Planned | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  |  |  | Neccesity Clear, but details to be determied throughout project execution
1A | Procurement of Tools Required to Support the implementation of Change Management Process | National Competitive Bidding | TDB | Procurement Of Goods | Lump sum | 100000 | 1A | Ex-Ante | SU-L1039-007 | Planned | 2016-09-05 |  | 2016-09-19 |  | 2016-09-26 |  | 2016-10-24 |  | 2016-11-14 |  | 2016-11-25 |  | 2016-12-05 |  | 2018-03-30
1B | Purchase of OMS/DMS and related services | International Competitive Bidding | 1 | Procurement of Goods | Lump Sum | 1000000 | 1B | Ex-Ante | SU-L1039-012 | Planned | 2017-03-01 |  | 2017-03-15 |  | 2017-03-18 |  | 2017-06-22 |  | 2017-08-31 |  | 2017-09-21 |  | 2017-10-18 |  | 2018-10-18
1B | Purchase of hardware for OMS/DMS | International Competitive Bidding | 1 | Procurement of Goods | Limp Sum | 273000 | 1B | Ex-Ante | SU-L1039-013 | Planned | 2017-05-08 |  | 2017-05-22 |  | 2017-05-25 |  | 2017-06-15 |  | 2017-07-06 |  | 2017-07-20 |  | 2017-07-23 |  | 2017-10-21
1D | Procurement of Energy Management Services | National Competitive Bidding | 1 | Procurement of Goods | Lump Sum | 200000 | 1D | Ex-Ante | SU-L1039-020 | Planned | 2016-09-23 |  | 2016-10-07 |  | 2016-10-10 |  | 2016-11-07 |  | 2016-11-28 |  | 2016-12-19 |  | 2016-12-26 |  | 2018-12-26
1D | Procurement for the LED Project | International Competitive Bidding | - | Procurment of Goods | Lump Sum | 888000 | 1D | Ex-Ante | SU-L1039-019 | Planned | 2016-08-31 |  | 2016-09-14 |  | 2016-09-17 |  | 2016-10-29 |  | 2016-11-19 |  | 2016-12-03 |  | 2016-12-10 |  | 2017-03-10
2A - 2B - 2C | Switchgear, SCADA, Protection Panels, Cap. Bank & Ext. Diff relays. | Limited International Bidding | 1 | Procurement for Goods | Lump-Sum | 3840000 | 2A - 2B - 2C | Ex-Ante | SU-L1039-069 | Planned | 2016-08-26 |  | 2016-09-09 |  | 2016-09-16 |  | 2016-11-11 |  | 2016-12-02 |  | 2016-12-16 |  | 2016-12-30 |  | 2018-05-08 |  |  |  | LIB: Due to compatibility with existing equipment from specific suppliers
2A - 2B - 2C | Electrical Materials (Aux. trafo, Sec. Mat., Sub. Grounding, DC Chargers, LV panel, Cable Ladders & Acc., 33 kV Lighting Arres. & Omicron tester) | International Competitive Bidding | 8 | Procurement for Goods | Lump-Sum | 1478000 | 2A - 2B - 2C | Ex-Ante | SU-L1039-070 | Planned | 2016-08-26 |  | 2016-09-09 |  | 2016-09-16 |  | 2016-11-11 |  | 2016-12-02 |  | 2016-12-16 |  | 2016-12-30 |  | 2018-05-08
2A - 2C | Cable & Cable Accessories | International Competitive Bidding | 1 | Procurement for Goods | Lump-Sum | 1255000 | 2A - 2C | Ex-Ante | SU-L1039-071 | Planned | 2016-08-26 |  | 2016-09-09 |  | 2016-09-16 |  | 2016-11-11 |  | 2016-12-02 |  | 2016-12-16 |  | 2016-12-30 |  | 2018-05-08
2C | Riserpoles OS Boma(EL) | Shopping | 1 | Request for Quotation | Lump-Sum | 10750 | 2C | Ex-Ante | SU-L1039-072 | Planned | 2016-08-26 |  | 2016-09-09 |  | 2016-09-16 |  | 2016-10-14 |  | 2016-11-04 |  | 2016-11-18 |  | 2016-12-02 |  | 2018-04-10
1A | Procurement of Network Switches and Services (for the ERP connection of all EBS location to the Head Office) | Shopping | - | Request for Quotation | Lump Sum | 100000 | 1A | Ex-Ante | SU-L1039-008 | Planned | 2016-08-15 |  | 2016-08-29 |  | 2016-09-05 |  | 2016-10-03 |  | 2016-10-24 |  | 2016-11-07 |  | 2016-11-21 |  | 2016-12-19 |  |  |  | This cost represents the acquisition of several common items and related services which can be procured locally
Dates (If it does not apply, use N/A)
NON CONSULTING SERVICES | [10 empty] | Submission of the Finalized Bidding Document to the Bank |  | Date for non- objection offered by the bank |  | Publication (advertisement) |  | Bid Opening |  | Submission of Bid Evaluation & Draft Contract |  | No Objection to the Evaluation & draft contract |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date) |  | Bidder | Proposal Price (Currency ) | Comments
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Lots Quantity: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Review Method (Select one of the options): | Bid / Contract Number | Process Status (Select one of the options): | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
2A | Transportation & Insurance of electrical equipment for SS/J | Shopping | - | Request for Quotation | Lump Sum | 75000 | 2A | Ex-Ante | SU-L1039-073 | Planned | 2017-09-30 |  | 2017-10-14 |  | 2017-10-21 |  | 2017-11-11 |  | 2017-11-25 |  | 2017-12-09 |  | 2017-12-16 |  | 2017-12-23
2B | Soil Investigation SS / F | Shopping | - | Request for Quotation | Lump Sum | 3000 | 2B | Ex-Ante | SU-L1039-075 | Planned | 2016-10-10 |  | 2016-10-24 |  | 2016-10-27 |  | 2016-11-24 |  | 2016-12-08 |  | 2016-12-22 |  | 2016-12-29 |  | 2017-01-29
2C | Soil Investigation Substation Boma | Shopping | - | Request for Quotation | Lump Sum | 1950 | 2C | Ex-Ante | SU-L1039-076 | Planned | 2016-10-10 |  | 2016-10-24 |  | 2016-10-27 |  | 2016-11-24 |  | 2016-12-08 |  | 2016-12-22 |  | 2016-12-29 |  | 2017-01-29
1D | Procurement for the Renewable Energy & Energy Efficiency Fair, Seminar and Workshop | National Competivie Bidding | - | Procurement of Non-Consulting Services | Lump Sum | 175000 | 1D | Ex-Ante | SU-L1039-021 | Planned | 2016-10-11 |  | 2016-10-25 |  | 2016-10-28 |  | 2016-12-09 |  | 2016-12-23 |  | 2017-01-06 |  | 2017-01-13 |  | 2017-02-13
Dates (If it does not apply, use N/A)
CONSULTING FIRMS | [9 empty] | Expression of Interest Notice |  | Submission of RFP and Short List |  | No Objection to RFP and Short List |  | RFP Submission |  | Bid Opening |  | Submission of Technical Evaluation |  | No Objection to the Technical Evaluation |  | Final Evaluation and Negotiation |  | No Objection to the Contract |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date) |  | Short List Members | Technical Score Assigned | Evaluated Price Proposal (Currency ####) | Combined Score | Comments
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Process Number: | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Bid / Contract Number | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1A | Procurement of Change Management Services | Quality & Cost Based Selection (QCBS) | - | Lump Sum | 200000 | 1A | Ex-Ante | Planned | SU-L1039-009 | 2016-07-29 |  | 2016-08-19 |  | 2016-09-02 |  | 2016-10-07 |  | 2016-10-07 |  | 2016-11-04 |  | 2016-11-18 |  | 2016-12-02 |  | 2016-12-16 |  | 2016-12-30 |  | 2018-08-22
1A | Procurement of Quality Assurance Services | Quality & Cost Based Selection (QCBS) | - | Lump Sum | 150000 | 1A | Ex-Ante | Planned | SU-L1039-010 | 2016-08-22 |  | 2016-09-12 |  | 2016-09-26 |  | 2016-10-31 |  | 2016-10-31 |  | 2016-11-28 |  | 2016-12-12 |  | 2016-12-26 |  | 2017-01-09 |  | 2017-01-23 |  | 2018-08-06
1C | Consulting Services for the Improvement of EBS procurement processes | Single Source Selection | - | Lump Sum | 122000 | 1C | Ex-Ante | In Process | SU-L1039-079 | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 2016-08-10 |  | 2016-08-17 |  | 2016-12-30 |  | SUNECON
1D | Consulting services for Education Programs | Quality & Cost Based Selection | - | Lump Sum | 700000 | 1D | Ex-Ante | Planned | SU-L1039-029 | 2016-10-11 |  | 2016-11-01 |  | 2016-11-15 |  | 2016-12-13 |  | 2016-12-13 |  | 2017-01-03 |  | 2017-01-17 |  | 2017-02-07 |  | 2017-02-21 |  | 2017-02-28 |  | 2018-02-16
1D | Consulting services for Sectorial Awareness & Outreach | Quality & Cost Based Selection | - | Lump Sum | 160000 | 1D | Ex-Ante | Planned | SU-L1039-030 | 2016-10-11 |  | 2016-11-01 |  | 2016-11-15 |  | 2016-12-13 |  | 2016-12-13 |  | 2017-01-06 |  | 2017-01-20 |  | 2017-02-10 |  | 2017-02-24 |  | 2017-03-03 |  | 2018-04-20
1C | Consulting Services for the Design & Implementation of EBS Management Development Policy | Quality Based Selection | - | Lump Sum | 180000 | 1C | Ex-Ante | Planned | SU-L1039-017 | 2016-08-08 |  | 2016-08-22 |  | 2016-09-02 |  | 2016-10-07 |  | 2016-10-07 |  | 2016-10-21 |  | 2016-11-11 |  | 2016-11-14 |  | 2016-11-28 |  | 2016-12-02 |  | 2018-12-02
1C | Consulting Services for the Implementation of the Energy Law phase 2 | Quality Based Selection | - | Lump Sum | 168000 | 1C | Ex-Ante | Planned | SU-L1039-015 | 2016-10-17 |  | 2016-10-31 |  | 2016-11-11 |  | 2016-11-14 |  | 2016-11-14 |  | 2017-01-09 |  | 2017-01-20 |  | 2017-01-23 |  | 2017-02-03 |  | 2017-02-10 |  | 2017-08-04
ADMIN | Consulting servicers for Financial auditing & monitoring | Quality & Cost Based Selection | - | Lump Sum | 82500 | ADMIN | Ex-Ante | Planned | SU-L1039-080 | 2016-09-08 |  | 2016-09-29 |  | 2016-10-13 |  | 2016-10-20 |  | 2016-11-10 |  | 2016-11-24 |  | 2016-12-08 |  | 2016-12-15 |  | 2016-12-29 |  | 2017-01-05 |  | 2021-04-30
1762500
INDIVIDUAL CONSULTANTS
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount, in u$s : | Estimated Number of Consultants: | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Bid / Contract Number | Dates (If it does not apply, use N/A) | [5 empty] | Consultant's Name | Period |  | Title | Comments | Amount (Currency ###)
[10 empty] | No Objection to the TORs |  | Hiring Deadline |  | End of Activity |  |  | From | Until
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real
1B | Design of OMS/DMS System | CQ II | - | Lump Sum | 67000 | 1B | Ex-Ante | In Process | SU-L1039-014 | 2016-06-21 | 2016-06-29 | 2016-08-31 |  | 2016-12-20
1C | Consulting Services for the Implementation of the Energy Law | CQ NI | - | Lump Sum | 110000 | 1C | Ex-Ante | In Process | SU-L1039-078 | 2016-07-01 | 2016-06-22 | 2016-07-15 |  | 2017-07-15 |  | M.Kopinsky
1C | Consulting services for the Design of Corporate Planning function within EBS | CQ NI | - | Lump Sum | 50000 | 1C | Ex-Ante | Planned | SU-L1039-016 | 2016-10-14 |  | 2016-12-30 |  | 2017-04-07
1C | Consulting Services for the Design & Implementation of the EBS Governance Risk & Compliance Framework | CQ NI | - | Lump Sum | 100000 | 1C | Ex-Ante | Planned | SU-L1039-018 | 2016-09-02 |  | 2016-11-25 |  | 2017-05-26
TRAINING
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Process Number: | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Bid / Contract Number | Dates (If it does not apply, use N/A) | [5 empty] | Detail | Amount (Currency ###) | Comments
[10 empty] | Annual Training Plan (ATP) |  | No Objection to the ATP |  | End of Activity
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real
1A | IT Skills Training ( New Skills Required to support new applications) | Shopping | - | Unit Price | 20000 | 1A | Ex-Ante | Planned | SU-L1039-011 | n/a |  | n/a |  | n/a
1C | Team Building Activities | Shopping | - | n/a | 20000 | 1C | Ex-Ante | Planned | n/a | 2016-09-30 |  | 2016-10-14 |  | 2016-10-28
ADMIN. CHECK OF AMOUNTS
| Aggregate Amount of all Categories | Estimated | Real
| Works: | 7634350 | 0
| Goods: | 17337750 | 0
| Non-Consulting Services: | 79950 | 0
| Consulting Services (Firms): | 1762500 | 0
| Consulting Services (Individuals): | 177000 | 0
| Training: | 40000 | 0
| Grand Total: | 27031550 | 0
| Aggregate Amount of all Components | Estimated | Real
1A
1B
1C
1D
2A
2B
2C
| Grand Total: | 0 | 0
Formulas:
Estimated = [Estimated]+14
Estimated = [Estimated, row above]+7
Real = [Planned]+21
Real = [Real]+14
End of Contract (Final date) = [Estimated]+600
Planned = [Real]-21
Planned = [Planned, row above]+10