## Impacts
Indicator Plan
Impacts | Indicators | Status | Unit | Baseline | Baseline Year | 2015 | 2016 | 2017 | 2018 | 2019 | End of Project

## Results
Indicator Plan
Results | Indicator | Status | Unit | Baseline | Baseline Year | 2017 | 2018 | 2019 | 2020 | 2021 | End of Project

## Products
# | Component | Product |  | Cost | Unit | Baseline | Physical Planning | [6 empty] | Financial Planning | [6 empty] | Comments
[7 empty] | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Total | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Total
| Component 1 | Product 1.1 | Removal and rehabilitation of causeways on East Grand Bahama | 2500000 |  | 0 | 1 | 5 | 6 | 0 | 1 | 1 | 14 | 125000 | 430000 | 875000 | 786500 | 141750 | 141750 | 2500000 | To include equipment purchase of 1 tide gauge, 1 streamflow adcp and traiing for MOWUD staff in GB and Nassau
|  |  | Hydrodynamic/baseline survey | 266500 | Study | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 50000 | 100000 | 100000 | 16500 | 0 | 0 | 266500
|  |  | Ecological survey and ecosystem service assessment | 70000 | Study | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 10000 | 20000 | 25000 | 15000 | 0 | 0 | 70000
|  |  | Environmental impact assessment | 100000 | Document | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 40000 | 50000 | 10000 | 0 | 0 | 0 | 100000
|  |  | Detailed designs | 50000 | Document | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 25000 | 25000 | 0 | 0 | 0 | 0 | 50000
|  |  | Improvements to marine ecology (mangrove rehabilitation) | 60000 | Rehabilitation | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 10000 | 25000 | 25000 | 0 | 0 | 60000
|  |  | Raised road | 60000 | Construction | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 20000 | 20000 | 20000 | 0 | 0 | 60000
|  |  | Causeway excavations | 1130000 | Construction | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 100000 | 450000 | 500000 | 40000 | 40000 | 1130000
|  |  | Upgraded causeway | 400000 | Construction | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 50000 | 150000 | 100000 | 50000 | 50000 | 400000
|  |  | Supervision including environmental (6%) | 99000 | Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 30000 | 30000 | 9500 | 9500 | 99000
|  |  | 15% contingency on construction | 238500 | Assesment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 60000 | 80000 | 34250 | 34250 | 238500
|  |  | Stakeholder consultations | 10000 | Meeting | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 5000 | 5000 | 0 | 0 | 0 | 10000
|  |  | Maintenance | 16000 | Report | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 8000 | 8000 | 16000
| Component 1 | Product 1.2 | Beach and dune stabilization in Junkanoo Beach | 18000000 |  | 0 | 0 | 6 | 7 | 1 | 1 | 1 | 16 | 900000 | 2794720 | 6005000 | 6014080 | 1143100 | 1143100 | 18000000
|  |  | Option development report (hydraulic modelling and hydrodynamic/baseline surveys) with 20% risk | 1000720 | Study | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 600000 | 400720 | 0 | 0 | 0 | 0 | 1000720 | To include equipment purchase of 1 tide gauge, 1 nearshore ADCP, 1 offshore ADCP, 1 unmanned surface vessel, 1 unmanned aerial vehicle, 1 RTK GNSS mapper and training for Nassau MOWUD staff
|  |  | Environmental impact assessment and cost benefit analysis | 151000 | Report | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100000 | 51000 | 0 | 0 | 0 | 0 | 151000
|  |  | Detailed designs | 400000 | Document | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 200000 | 200000 | 0 | 0 | 0 | 0 | 400000
|  |  | Breakwaters rehabilitation | 10000000 | Construction | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 970000 | 3500000 | 3500000 | 1015000 | 1015000 | 10000000
|  |  | Repaired/upgraded drainage outlet | 30000 | Construction | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000
|  |  | Repairs/upgrade sea walls | 30000 | Construction | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000
|  |  | Beach replenishment | 708000 | Deposition | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 108000 | 300000 | 300000 | 0 | 0 | 708000
|  |  | Beach control structures (groynes) | 2800000 | Construction | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 800000 | 1000000 | 1000000 | 0 | 0 | 2800000
|  |  | Supervision including environmental (6%) | 814080 | Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 300000 | 314080 | 50000 | 50000 | 814080
|  |  | 15% contingency on construction | 2035200 | Assesment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 900000 | 900000 | 67600 | 67600 | 2035200
|  |  | Stakeholder consultations | 10000 | Meeting | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 5000 | 5000 | 0 | 0 | 0 | 10000
|  |  | Maintenance | 21000 | Report | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 10500 | 10500 | 21000
| Component 1 | Product 1.3 | Coastal flood reduction infrastructure at Central Long Island | 3000000 |  | 0 | 2 | 8 | 4 | 1 | 1 | 1 | 17 | 280000 | 680000 | 950000 | 791240 | 149380 | 149380 | 3000000
|  |  | Hydrodynamic/baseline survey | 280000 | Study | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 100000 | 180000 | 0 | 0 | 0 | 0 | 280000 | To include equipment purchase of 1 nearshore ADCP, 1 offshore ADCP, 1 tide gauge. Also includes LIDAR survey.
|  |  | Surge modelling (west coast) | 280000 | Study | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 50000 | 50000 | 100000 | 80000 | 0 | 0 | 280000
|  |  | Environmental impact assessment and cost benefit analysis | 180000 | Document | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 80000 | 100000 | 0 | 0 | 0 | 0 | 180000
|  |  | Detailed designs | 100000 | Document | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 40000 | 60000 | 0 | 0 | 0 | 0 | 100000
|  |  | Improvements to marine ecology (mangrove rehabilitation) | 400000 | Rehabilitation | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 50000 | 150000 | 150000 | 25000 | 25000 | 400000
|  |  | Installation of drainage wells | 151240 | Construction | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 40000 | 60000 | 51240 | 0 | 0 | 151240
|  |  | Bypass road with land purchase | 1000000 | Construction | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 50000 | 400000 | 400000 | 75000 | 75000 | 1000000
|  |  | Revetment | 100000 | Construction | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 40000 | 60000 | 0 | 0 | 0 | 100000
|  |  | Flood Gate | 100000 | Construction | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 40000 | 60000 | 0 | 0 | 0 | 100000
|  |  | Supervision including environmental (6%) | 105074.4 | Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 40000 | 30000 | 2537 | 2537 | 105074
|  |  | 15% contingency on construction | 202686 | Assesment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 80000 | 80000 | 6343 | 6343 | 202686
|  |  | Stakeholder consultations | 20000 | Meeting | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 10000 | 10000 | 0 | 0 | 0 | 0 | 20000
|  |  | Maintenance | 81000 | Report | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 40500 | 40500 | 81000
| Component 2 | Product 2.1 | Natural infrastructure for hazard resilience in Andros | 3000000 |  | 0 | 0 | 8 | 4 | 3 | 0 | 0 | 15 | 0 | 1170000 | 1010000 | 820000 | 0 | 0 | 3000000
|  |  | Baseline studies for selection of priority sites for demonstration projects: applying socioeconomic and biophysical suitability parameters (shoreline vulnerability, coastal change assessment, ecosystem services assessment, mangrove assessment and vulnerability mapping) | 200000 | Document | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 200000 | 0 | 0 | 0 | 0 | 200000
|  |  | Stakeholder consultation and validation workshops | 10000 | Workshops | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000
|  |  | Advisor on nature-based solutions best practice | 50000 | Employee | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000
|  |  | Assessments, baseline studies and diagnostics at pilot sites to inform design and implementation of nature-based solutions (autoecology, hydrologic patterns, genetics, modification of original environment) and management plan including maintenance and monitoring plan | 700000 | Document | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 4 | 0 | 700000 | 0 | 0 | 0 | 0 | 700000
|  |  | Conservation and restoration activities in 4 pilot sites | 2000000 | Sites | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 4 | 0 | 200000 | 1000000 | 800000 | 0 | 0 | 2000000
|  |  | Communication Plan including community awareness activities and preparation of replicable guidelines to inform future rehabilitation efforts | 40000 | Plan | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 10000 | 10000 | 20000 | 0 | 0 | 40000
| Component 3 | Product 3.1 | Coastal Zone Management Governance Strengthened | 3500000 |  | 0 | 0 | 15 | 13 | 5 | 4 | 4 | 41 | 0 | 600000 | 1050000 | 725000 | 610000 | 515000 | 3500000
|  |  | Establishment of the Coastal Management Program Unit in MOWUD | 1400000 | Employee | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 200000 | 300000 | 300000 | 300000 | 300000 | 1400000
|  |  | Travel | 50000 | Trips | 0 | 0 | 0 | 2 | 3 | 2 | 3 | 10 | 0 | 0 | 10000 | 15000 | 10000 | 15000 | 50000
|  |  | Training Programs | 250000 | Trainees | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 100000 | 150000 | 0 | 0 | 250000
|  |  | Equipment and Software | 500000 | Equipment | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 14 | 0 | 200000 | 300000 | 0 | 0 | 0 | 500000
|  |  | Technical Assistance | 80000 | Contracts | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 40000 | 40000 | 0 | 0 | 80000
|  |  | Sustainable Coastal Infrastructure Action Plan | 100000 | Document | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 40000 | 60000 | 0 | 0 | 100000
|  |  | Updated Building Codes and Coastal Infrastructure Design Guidence | 100000 | Document | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 60000 | 40000 | 0 | 0 | 100000
|  |  | Shoreline Management Plans | 450000 | Plan | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 250000 | 200000 | 450000
|  |  | Sustainable Finance Strategy for Coastal Risk Management | 70000 | Document | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 70000 | 0 | 0 | 70000
|  |  | Pilot nearshore monitoring program and information management | 500000 | Document | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 200000 | 200000 | 50000 | 50000 | 0 | 500000
|  |  | Management | 5000000 | [8 empty] | 0 | [6 empty] | 0
|  |  | Audits | 200000 | [8 empty] | 0 | [6 empty] | 0
|  |  | Evaluation | 300000 | [8 empty] | 0 | [6 empty] | 0
|  |  | Supervison (PIU) | 1500000 | [15 empty] | 0
|  |  | Contingencies | 3000000 | [8 empty] | 0 | [6 empty] | 0
|  |  | Total | 35000000 |  | 0 | 3 | 42 | 34 | 10 | 7 | 7 | 103 | 1305000 | 5674720 | 9890000 | 9136820 | 2044230 | 1949230 | 30000000
***Funding source is IDB in all instances
| Spending Categories |  |  | Amount | % | Institution
| Component 1 |  |  | 23500000 | 67.14%
| Component 2 |  |  | 3000000 | 8.571%
| Component 3 |  |  | 3500000 | 10%
| Supervision |  |  | 1500000 | 4.286%
| Audits |  |  | 200000 | 0.5714%
| Evaluation |  |  | 300000 | 0.8571%
| Contingencies |  |  | 3000000 | 8.571%
| Total |  |  | 35000000 | 100%

## PPM
| Executing Agency |  | Ministry of Works and Urban Development
| Program Name and Number |  | BH-L1043
| Date Prepared |  | 2017-02-10 | [22 empty] | Période du rapport | [22 empty] | Période du rapport
Period Covered by Procurement Plan : Q3 2017 to Q4 2018
Procurement Plan | [18 empty] | REGISTRE D'EXECUTION DU PLAN DE PASSATION DES MARCHES | [23 empty] | Suivi de L'EXECUTION DU PLAN DE PASSATION DES MARCHES et de la GESTION DES CONTRATS
Number | Project Component | Product(s) from the results matrix au(x)quel(s) contribuent l'activité et la dépense associées au marché | Description | Cost (USD) | Procurement Method (1) | Clause de référence pour la justification de l'entente directe* | Type de Document à utiliser (2) | Révision (Ex-ante ou ex-post) | Source et pourcentage de financement |  | Pre-qualification | Estimated Dates |  |  |  |  | Comments | Status: pending, in progress, awarded, canceled, closed | Dates réelles (lors du reporting semestriel, expliquer en cas d'écarts substantiels avec la planification) | [7 empty] | Nom de adjudicataire | Montant du Contrat (US$000) | Numéro du Contrat (PRISM/BID) | Paiement de l'avance de démarrage (N/A pour les biens) |  |  | Garantie d'avance |  |  | Garantie de bonne exécution |  |  |  | Avenant à la Garantie de Bonne Exécution |  |  | Avenant #1 au contrat original |  |  | Avenant #N au contrat original (ajouter autant de colonnes que d'avenants) |  |  | Remise des livrables et paiements associés (rajouter autant de colonnes qu'il y a de livrables prévus dans le contrat et les avenants) | [11 empty] | Solde restant à payer à date (montant total du contrat - montant avance de démarrage - montant des paiements successifs cumulés)
[9 empty] | BID (%) | Autre (%) | Yes/No | Call for Expressions of Interest to develop the shortlist (only for Services) | Publication of the specific opinion (Goods and Works) / Invitation (Shorlist) | Finalization of tender evaluation report (full evaluation if Goods or Works; technical evaluation Of Consulting Services) | Contract Signature | Contract End |  |  | Lancement Appel à Manifestation d'intérêt pour constitution de la liste restreinte (uniquement pour les Services) | Publication d'avis spécifique (Biens et Travaux) / Invitation (Liste restreinte) | Réception des offres (la période de validité des offres commence à courir) | Date de transmission du rapport d'évaluation à la Banque (évaluation complète si Biens ou Travaux; évaluation technique si Services de Consultants) | NO de la Banque au rapport d'évaluation complète (NO à l'adjudication) ou technique (NO à l'ouverture de l'offre financière, avant adjudication) | Date de publication des résultats sur UNDB et IADB | Date de signature du contrat (doit intervenir dans le délai de validité des offres) | Date de fin du contrat |  |  |  | Montant (US$000) | % du montant | Date | Montant (US$000) | Banque/ pays | Date expiration | Montant (US$000) | % montant du contrat | Type (Banque ou assurance) | Date expiration | Montant (US$000) | Type (Bancaire ou d'assurance) | Date expiration | Date de NO de la BID | Date signature | Montant | Date de NO de la BID | Date signature | Montant | Date d'approbation par le client du livrable 1 (services et travaux) | Date du paiement correspondant au livrable 1 (services et travaux) | Montant | Date d'approbation par le client du livrable N (services et travaux) | Date du paiement correspondant au livrable N (services et travaux) | Montant | Date d'approbation par le client du dernier livrable (Services) ou Date de la réception provisoire (Travaux) ou Date de réception des Biens | Date du paiement correspondant au dernier livrable ou à la réception provisoire des travaux ou à la réception des biens | Montant | Date de la réception définitive (uniquement pour les travaux) | Date du paiement de la retenue de garantie de bonne exécution (uniquement pour les travaux) | Montant de la retenue de garantie
Related goods and services | [18 empty] | Biens et services connexes | [23 empty] | Biens et services connexes
| Component 3 | Product 3.1 | Purchase of equipment and software | 500000 | ICB | [5 empty] | Yes | 3 Q 2018 |  |  | 4 Q 2018
TOTAL |  |  |  | 500000
Works | [18 empty] | Travaux | [23 empty] | Travaux
| Component 1 | Product 1.1 | Rehabilitation and removal of causeways in East Grand Bahamas | 1650000 | Shopping | [5 empty] | Yes | 1 Q 2018 | 2017 | 2019 | 2 Q 2018 | 2019 |  | Pending
| Component 1 | Product 1.2 | Construction and rehabilitation of coastal infrastructure in Junkanoo Beach | 13568000 | ICB | [5 empty] | Yes | 3 Q 2018 | 2017 | 2020 | 4 Q 2018 | 2020 | Time needed to facilitate construction of breakwaters and groynes | Pending
| Component 1 | Product 1.3 | Construction of coastal flood reduction infraestructure in Central Long Island | 1751240 | Shopping | [5 empty] | Yes | 1 Q 2018 | 2017 | 2019 | 2 Q 2018 | 2019 | Time needed to facilitate land purchase | Pending
TOTAL |  |  |  | 16969240
Non-consulting services | [18 empty] | Services autre que consultations | [23 empty] | Services autre que consultations
TOTAL |  |  |  | 0
Consulting services (firms) | [18 empty] | Bureaux de services-conseils | [23 empty] | Bureaux de services-conseils
| Component 1 | Product 1.1 | Supervision of works in East Grand Bahamas | 99000 | Selection Based on the Consultants' Qualifications | [5 empty] | Yes | 1 Q 2018 |  | 2018 | 1 Q 2018 | 2018 | Surveys to include 1 session storm season and 1 session non-storm season creek discharge measurements | Pending
| Component 1 | Product 1.1 | Baseline and design of infrastructure in East Grand Bahamas | 486500 | Quality and Cost Based Selection | [5 empty] | No | 3 Q 2017 |  | 2019 | 1 Q 2018 | 2019 |  | Pending
| Component 1 | Product 1.2 | Baseline study and design for Junkanoo Beach | 1551720 | Quality and Cost Based Selection | [5 empty] | Yes | 2 Q 2018 | 2017 | 2018 | 3 Q 2018 | 2018 |  | Pending
| Component 1 | Product 1.2 | Supervision of coastal works in Junkanoo Beach | 814080 | Quality and Cost Based Selection | [5 empty] | Yes | 3 Q 2018 | 2017 | 2018 | 4 Q 2018 | 2018 |  | Pending
| Component 1 | Product 1.3 | Supervision of infrastructure in Long Island | 105074 | Least cost Selection | [5 empty] | Yes | 1 Q 2018 |  | 2018 | 2 Q 2018 | 2018 | Surveys to include 1 month storm season and 1 month non-storm season measurements | Pending
| Component 1 | Product 1.3 | Baseline and design of infrastructure in Long Island | 840000 | Least cost Selection | [5 empty] | Yes | 4 Q 2017 | 2017 | 2018 | 1 Q 2018 | 2018 |  | Pending
| Component 2 | Product 2.1 | Baseline studies for selection of priority sites for demonstration projects | 200000 | Quality and Cost Based Selection | [6 empty] | 1Q 2018 |  |  | 3Q 2018 |  |  | Pending
| Component 2 | Product 2.1 | Assessments, baseline studies and diagnostics at pilot sites to inform design and implementation of nature-based solutions and management plan including maintenance and monitoring plan | 700000 | Quality and Cost Based Selection | [6 empty] | 1Q 2018 |  |  | 4Q 2018 |  |  | Pending
| Component 2 | Product 2.1 | Conservation and restoration activities in 4 pilot sites | 2000000 | Single Source Selection | [5 empty] | Yes | 3Q 2018 |  | 2018 | 4Q 2018 | 2018 | Surveys to include 1 month storm season and 1 month non-storm season wave and current measurements | Pending
| Component 3 | Product 3.1 | Sustainable Coastal Infrastructure Action Plan | 100000 | Quality and Cost Based Selection | [6 empty] | 4Q 2018 | [5 empty] | Pending
| Component 3 | Product 3.1 | Shoreline Management Plans | 450000 | Quality and Cost Based Selection | [12 empty] | Pending
| Component 3 | Product 3.1 | Pilot nearshore monitoring program and information management | 500000 | Quality and Cost Based Selection | [6 empty] | 4Q 2017 |  |  | 3Q 2017 |  |  | Pending
| Component 3 | Product 3.1 | Training Programs | 250000 | Quality and Cost Based Selection | [6 empty] | 2Q 2018 |  |  | 4Q2018 |  |  | Pending
| Audits |  | Audits | 200000 | [13 empty] | Pending
| Evaluations |  | Evaluations | 300000 | [13 empty] | Pending
TOTAL |  |  |  | 8596374
11836374
Consulting services (individuals) | [18 empty] | Services de consultants individuals | [23 empty] | Services de consultants individuals
| Component 2 | Product 2.1 | Advisor on nature-based solutions best practice | 50000 | International | [6 empty] | 4Q 2017 |  |  | 1Q 2018 |  |  | Pending
| Component 2 | Product 2.1 | Communication Plan | 40000 | National | [12 empty] | Pending
| Component 3 | Product 3.1 | Establishment of the Coastal Management Program Unit in MOWUD | 1400000 | National | [6 empty] | 3Q 2017 |  |  | 4Q 2017 |  |  | Pending
| Component 3 | Product 3.1 | Updated Building Codes and Coastal Infrastructure Design Guidance | 100000 | International | [12 empty] | Pending
| Component 3 | Product 3.1 | Technical Assistance | 80000 | 3CV | [6 empty] | 1Q 2018 |  |  | 2Q 2018 |  | Approx. 3 contracts | Pending
| Component 3 | Product 3.1 | Sustainable Finance Strategy for Coastal Risk Management | 70000 | International | [12 empty] | Pending
| Supervision |  | Supervision (PIU) | 1500000 | National | [6 empty] | 3 Q 2017 |  |  | 4 Q 2017 |  | 5 Contracts | Pending
TOTAL |  |  |  | 3240000
Operational expenses | [18 empty] | Dépenses Opérationnelles | [23 empty] | Dépenses Opérationnel
| Component 1 | Product 1.1 | Stakeholder consultations | 10000 | ED (MOWUD) | [5 empty] | No
| Component 1 | Product 1.1 | Maintenance | 16000 | ED (MOWUD) | [5 empty] | No
| Component 1 | Product 1.2 | Stakeholder consultations | 10000 | ED (MOWUD) | [5 empty] | No
| Component 1 | Product 1.2 | Maintenance | 21000 | ED (MOWUD) | [5 empty] | No
| Component 1 | Product 1.3 | Stakeholder consultations | 20000 | ED (MOWUD) | [5 empty] | No
| Component 1 | Product 1.3 | Maintenance | 81000 | ED (MOWUD) | [5 empty] | No
| Component 2 | Product 2.1 | Stakeholder consultation and validation workshops | 10000 | ED (MOWUD) | [5 empty] | No
| Component 3 | Product 3.1 | Travel | 50000 | ED (MOWUD) | [5 empty] | No
TOTAL |  |  |  | 218000
Contingencies
| Contingencies |  | Contingencies | 3000000
| Component 1 | Product 1.1 | 15% contingency on construction | 238500
|  | Product 1.2 | 15% contingency on construction | 2035200
|  | Product 1.3 | 15% contingency on construction | 202686
TOTAL |  |  |  | 5476386
TOTAL |  |  |  | 35000000
Goods and Works: ICB: International Competitive Bidding; AOIR: International Restricted Call for Bids; AON: National Competitive Bidding; CP: Price Comparison; ED: Direct Agreement; FA: force account; Service Offices Tips: SFQC: Selection based on quality and cost; SFQ: Selection based on quality; SCBD: Selection within a specific budget; SMC: Low Cost Selection; QC: Selection based on the qualifications of the consultants; SED: Selection by direct agreement; Individual Consultant Services: QCNI: Selection based on the qualifications of individual national consultants; QCII: Selection Based on the Qualifications of Individual International Consultants]
Goods and Works: DSAOI-B (Standard International Bidding Documents); DAON-B (National Bidding Documents); DSAOI-T (Works); DAON-T (Works); DSAOI-PT (Small Works); DAON-PT (Small Work); DAOI-TCR (Works Design and Realization); DAON-TCR (Works Design and Realization); DAOI-ECFI (Equipment Designing Supply and Install); DAON-ECFI (Supply and Install Design Equipment); DAOI-ST (Technical Services); DAON-ST (Technical Services); DAOI-SM (Services Management); DAON-SM (Services Management); CP-BS (Simple goods); CP-BC (Complex Property); CP-TS (Simple Work); CP-TC (Complex Works); CP-STS (Single Technical Service); CP-STC (Technical Service Complex); Offices of the Services Advice: DSAO (Standard Document of invitation to tender); Individual Consultant Services: TDR / GE (Terms of Reference and Evaluation Grid)
3) Status: Pending - Process not yet started; Ongoing - Ongoing procurement process; Awarded no objection from the Bank obtained for the award of the contract; Canceled - Canceled process; Closed - Duly executed contract - last payment executed