## TCM Period 2017
|  | Operation Number: |  |  |  | BR-T1362 | [14 empty] | Inter-American Development Bank - IDB
|  | TCM Cycle: |  |  |  | TCM Period 2017
|  | Last Update: |  |  |  | 2017-08-04 12:21
Result Matrix
Outcomes
Outcome: | 1 Los resultados de la CT permiten la aprobación del programa de inversiones por parte del BID/WSA
Indicators |  |  | Flags* |  | Unit of Measure |  |  | Baseline | Baseline Year |  | Means of verification |  |  |  | 2017 | 2018 |  |  | EOP
1.1 Programa aprobado según las especificaciones de los estudios/diseños/planes financiados por la CT |  |  |  |  | Program |  |  | 0 | 2017 |  |  |  |  | P
P(a)
A
Outputs: Annual Physical and Financial Progress
1 Componente 1: Apoyo Técnico Institucional a la CORSAN | [16 empty] | Physical Progress | [6 empty] | Financial Progress
Outputs |  |  |  | Fund Indicator |  |  | Unit of Measure |  |  | Baseline |  | Baseline Year | Means of Verification |  |  |  |  | 2017 |  | 2018 |  | 2019 | EOP |  | 2017 | 2018 |  | 2019 |  | EOP |  | Theme | Flags
1.1 Civil works design completed |  |  |  | Other(INF) INF |  |  | Designs (#) |  |  | 0 |  | 2017 | Productos de consultoria y Informes de la TC |  |  |  | P |  |  | 1 |  |  | 1 | P | 6000 | 201000 |  | 23000 |  | 230000 |  | Water and Sanitation
[17 empty] | P(a) |  |  | 1 |  |  | 1 | P(a) | 6000 | 201000 |  | 23000 |  | 224000
[17 empty] | A | [6 empty] | A
1.2 Project implementation unit strenghtened |  |  |  | Other(INF) INF |  |  | PIUs (#) |  |  | 0 |  | 2017 | Productos de consultoria y Informes de la TC |  |  |  | P |  |  |  |  | 1 | 1 | P | 0 | 14000 |  | 6000 |  | 20000 |  | Water and Sanitation
[17 empty] | P(a) |  |  |  |  | 1 | 1 | P(a) | 0 | 14000 |  | 6000 |  | 20000
[17 empty] | A | [6 empty] | A
1.3 Institutional arrangements aimed at regional coordination |  |  |  | Other(INF) INF |  |  | Arrangements (#) |  |  | 0 |  | 2017 | Productos de consultoria y Informes de la TC |  |  |  | P |  |  | 1 |  |  | 1 | P | 9000 | 63000 |  | 18000 |  | 90000 |  | Water and Sanitation
[17 empty] | P(a) |  |  | 1 |  |  | 1 | P(a) | 9000 | 63000 |  | 18000 |  | 81000
[17 empty] | A | [6 empty] | A
2 Componente 2: Apoyo en la Preparación del Programa | [16 empty] | Physical Progress | [6 empty] | Financial Progress
Outputs |  |  |  | Fund Indicator |  |  | Unit of Measure |  |  | Baseline |  | Baseline Year | Means of Verification |  |  |  |  | 2017 |  | 2018 |  | 2019 | EOP |  | 2017 | 2018 |  | 2019 |  | EOP |  | Theme | Flags
2.1 Diagnostics and assessments completed |  |  |  | Other(INF) INF |  |  | Diagnostics (#) |  |  | 0 |  | 2017 | Productos de consultoria y Informes de la TC |  |  |  | P | 1 |  | 2 |  |  | 3 | P | 20000 | 45000 |  | 0 |  | 65000 |  | Water and Sanitation
[17 empty] | P(a) | 1 |  | 2 |  |  | 2 | P(a) | 20000 | 45000 |  | 0 |  | 45000
[17 empty] | A | [6 empty] | A
2.2 Environmental impact assessment completed |  |  |  | Other(INF) INF |  |  | Assessments (#) |  |  | 0 |  | 2017 | Productos de consultoria y Informes de la TC |  |  |  | P |  |  | 1 |  |  | 1 | P | 5000 | 20000 |  | 0 |  | 25000 |  | Water and Sanitation
[17 empty] | P(a) |  |  | 1 |  |  | 1 | P(a) | 5000 | 20000 |  | 0 |  | 20000
[17 empty] | A | [6 empty] | A
2.3 Monitoring and Evaluation Plan developed |  |  |  | Other(INF) INF |  |  | Plans (#) |  |  | 0 |  | 2017 | Productos de consultoria y Informes de la TC |  |  |  | P |  |  | 2 |  | 3 | 5 | P | 0 | 18000 |  | 27000 |  | 45000 |  | Water and Sanitation
[17 empty] | P(a) |  |  | 2 |  | 3 | 5 | P(a) | 0 | 18000 |  | 27000 |  | 45000
[17 empty] | A | [6 empty] | A
2.4 Feasibility study completed |  |  |  | Other(INF) INF |  |  | Studies (#) |  |  | 0 |  | 2017 | Productos de consultoria y Informes de la TC |  |  |  | P |  |  | 2 |  |  | 2 | P | 8000 | 48000 |  | 24000 |  | 80000 |  | Water and Sanitation
[17 empty] | P(a) |  |  | 2 |  |  | 2 | P(a) | 8000 | 48000 |  | 24000 |  | 72000
[17 empty] | A | [6 empty] | A
2.5 Tools for the execution of the elaborated program |  |  |  | Other(INF) |  |  | UN |  |  | 0 |  | 2017 | Productos de consultoria y Informes de la TC |  |  |  | P |  |  | 1 |  |  | 1 | P | 0 | 20000 |  | 0 |  | 20000 |  | Water and Sanitation
[17 empty] | P(a) |  |  | 1 |  |  | 1 | P(a) | 0 | 20000 |  | 0 |  | 20000
[17 empty] | A | [6 empty] | A
Other Cost
Total Cost | [24 empty] | 2017 |  | 2018 |  | 2019 |  | Total Cost
[24 empty] | P | 48000 |  | 429000 |  | 98000 |  | 575000
[24 empty] | P(a) | 48000 |  | 429000 |  | 98000 |  | 527000
A