## TCM Period 2017
|  | Operation Number: |  |  |  | BR-T1371
|  | TCM Cycle: |  |  |  | TCM Period 2017
|  | Last Update: |  |  |  | 2017-07-14 10:16
Result Matrix
Outcomes
Outcome: | 1 Relevant information, data and evidence to guide the design and implementation of the "Rural Sustentavel" Project - Phase II (PRS-II) is available
Indicators |  |  | Flags* |  | Unit of Measure |  |  | Baseline | Baseline Year |  | Means of verification |  |  |  | EOP
1.1 Reports with the relevant information and data for designed of Phase II produced |  |  |  |  | Reports (#) |  |  | 0 | 2017 |  | Report with Phase II data |  |  | P | 2
P(a)
A
1.2 Reports with baselines and Methodologies for implementing Phase II defined and developed |  |  |  |  | Reports (#) |  |  | 0 | 2017 |  | Baseline and Methodology Report |  |  | P | 2
P(a)
A
1.3 Proposal for the development and implementation of Phase II submitted. |  |  |  |  | Reports (#) |  |  | 0 | 2017 |  | Proposal Document |  |  | P | 1
P(a)
A
Outputs: Annual Physical and Financial Progress
1 Component I. Lessons learned from Phase I and prioritization of areas of intervention | [15 empty] | Physical Progress |  |  |  | Financial Progress
Outputs |  |  |  | Fund Indicator |  |  | Unit of Measure |  |  | Baseline |  | Baseline Year | Means of Verification |  |  |  | 2017 | 2018 | EOP |  | 2017 | 2018 |  | EOP |  | Theme | Flags
1.1 Environmental impact assessment completed |  |  |  | Other(LCA) Assessments of best practices and lessons learned completed |  |  | Assessments (#) |  |  | 0 |  | 2017 | Assessment on Best Practices from Phase I |  |  | P | 1 |  | 1 | P | 53000 |  |  | 53000 |  | Biodiversity and Ecosystem Conservation
[16 empty] | P(a) |  |  | 0 | P(a) |  |  |  | 0
[16 empty] | A |  |  |  | A
1.2 Diagnostics and assessments completed |  |  |  | Other(LCA) Diagnostic on prioritization of areas of intervention completed |  |  | Diagnostics (#) |  |  | 0 |  | 2017 | Report on prioritized areas of intervention |  |  | P | 1 |  | 1 | P | 89000 |  |  | 89000 |  | Agricultural Productivity and Food Security
[16 empty] | P(a) |  |  | 0 | P(a) |  |  |  | 0
[16 empty] | A |  |  |  | A
2 Component II. Financial mechanisms and capacity building for rural producers and technical assistance agents | [15 empty] | Physical Progress |  |  |  | Financial Progress
Outputs |  |  |  | Fund Indicator |  |  | Unit of Measure |  |  | Baseline |  | Baseline Year | Means of Verification |  |  |  | 2017 | 2018 | EOP |  | 2017 | 2018 |  | EOP |  | Theme | Flags
2.1 Feasibility study completed |  |  |  | Other(LCA) Analysis on the most appropriate financial mechanisms for Rural SMEs in MATOPIBA produced |  |  | Studies (#) |  |  | 0 |  | 2017 | Financial Mechanisms analysis and proposal |  |  | P | 1 |  | 1 | P | 38000 |  |  | 38000 |  | Agricultural Productivity and Food Security
[16 empty] | P(a) |  |  | 0 | P(a) |  |  |  | 0
2.2 Technical models designed |  |  |  | Other(LCA) Proposal on training methodology to better address Rural SMEs in MATOPIBA designed |  |  | Models (#) |  |  | 0 |  | 2017 | Training Methodology Proposal |  |  | P | 1 |  | 1 | P | 30000 |  |  | 30000 |  | Agricultural Productivity and Food Security
[16 empty] | P(a) |  |  | 0 | P(a) |  |  |  | 0
[16 empty] | A |  |  |  | A
3 Component III. Evaluation and Communications Strategy | [15 empty] | Physical Progress |  |  |  | Financial Progress
Outputs |  |  |  | Fund Indicator |  |  | Unit of Measure |  |  | Baseline |  | Baseline Year | Means of Verification |  |  |  | 2017 | 2018 | EOP |  | 2017 | 2018 |  | EOP |  | Theme | Flags
3.1 Methodologies designed/strengthened |  |  |  | Other(LCA) Baseline and methodology to measure success based on the ICF's Key Performance Indicators defined |  |  | Methodologies (#) |  |  | 0 |  | 2017 | Monitoring and Evaluation Methodology |  |  | P | 1 |  | 1 | P | 50000 |  |  | 50000 |  | Agricultural Productivity and Food Security
[16 empty] | P(a) |  |  | 0 | P(a) |  |  |  | 0
[16 empty] | A |  |  |  | A
3.2 Strategies designed |  |  |  | Other(LCA) Communications strategy oriented to stakeholders designed and established |  |  | Strategies (#) |  |  | 0 |  | 2017 | Communications strategy |  |  | P |  | 1 | 1 | P |  | 31000 |  | 31000 |  | Biodiversity and Ecosystem Conservation
[16 empty] | P(a) |  |  | 0 | P(a) |  |  |  | 0
[16 empty] | A |  |  |  | A
4 Component IV. Design of Phase II project “Low-Carbon Agriculture for Avoided Deforestation” | [15 empty] | Physical Progress |  |  |  | Financial Progress
Outputs |  |  |  | Fund Indicator |  |  | Unit of Measure |  |  | Baseline |  | Baseline Year | Means of Verification |  |  |  | 2017 | 2018 | EOP |  | 2017 | 2018 |  | EOP |  | Theme | Flags
4.1 Project proposal developed |  |  |  | Other(LCA) Proposal for the design of Phase II project completed |  |  | Proposals (#) |  |  | 0 |  | 2017 | Phase II Project proposal |  |  | P |  | 1 | 1 | P |  | 49000 |  | 49000 |  | Biodiversity and Ecosystem Conservation
[16 empty] | P(a) |  |  | 0 | P(a) |  |  |  | 0
[16 empty] | A |  |  |  | A
Other Cost
Total Cost | [20 empty] | 2017 |  | 2018 |  | Total Cost
[20 empty] | P | 260000 |  | 80000 |  | 340000
P(a)
A