## Project Structure
Agency | Sub-Agency (If applies) | Agency's Initials
Ministry of Works
COMPONENTS? (YES / NO) | Component's Name (list by number or letter)
YES | Component 1 - Climate risk reduction in the tourism sector
Component 2 - Governance for disaster risk management and CC adaptation
Project Management

## Procurement Plan
INFORMATION FOR PROCUREMENT PLAN INITIAL UPLOAD ONGOING AND/OR LAST PRESENTED
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: BL-L1028 | 2017 | 2021
2. Procurement Plan Details
Version 1 - (2017) :
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Works | 7091678 | 7091678
Goods | 80000 | 80000
Non Consulting Services | 275698 | 275698
Training |  | 0
Operating Costs (Travel & Per diem) |  | 0
Consulting Services (Firms + Individuals) | 2552624 | 2552624
0
Total | 10000000 | 10000000
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
Component 1 - Climate risk reduction in the tourism sector | 8539461 | 8539461
Component 2 - Governance for disaster risk management and CC adaptation | 618241 | 618241
Project Management | 627298 | 627298
Evaluations | 115000 | 115000
Audits | 100000 | 100000
Total | 10000000 | 10000000

## Detailed Procurement Plan
PROCUREMENT PLAN INITIAL LOAD INFORMATION (ONGOING AND/OR LAST PRESENTED)
WORKS | [13 empty] | National System
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Ex-Post
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  | Ex-Ante
Ministry of Works | Protective Works Package 1 (Belize) |  | International Competitive Bidding | 1 | W1 | 3478348 | 100% | 0% | Component 1 - Climate risk reduction in the tourism sector | Ex-Ante | 2017-11-29 | 2018-08-02 | N/A | Cancelled
| Protective Works Package 2 (Belize) |  | International Competitive Bidding | 1 | W2 | 2739330 | 100% | 0% | Component 1 - Climate risk reduction in the tourism sector | Ex-Ante | 2019-11-01 | 2020-09-10 | N/A | Contract Concluded
| Protective Works Package 3 (Caye Caulker y Goff's Caye) |  | National Competitive Bidding | 1 | W3 | 874000 | 100% | 0% | Component 1 - Climate risk reduction in the tourism sector | Ex-Ante | 2020-06-02 | 2021-11-01 | N/A | Contract in Execution
| Sub-total |  |  |  |  | 7091678 | [7 empty] | Null and Void
Ongoing
GOODS | [13 empty] | Planned
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Rejection of all Bids
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  | Re-Tendering
| Vehicle |  | Price Comparison/Shopping |  | G2 | 40000 | 100% | 0% | Project Management | Ex-Post | 2018-07-27 | 2018-10-05 | N/A
| Furniture |  | Price Comparison/Shopping |  | G3 | 40000 |  | 0% | Project Management | Ex-Post | 2018-02-01 | 2018-10-05 | N/A
| Sub-total |  |  |  |  | 80000 | [7 empty] | Direct Contracting
National System
NON CONSULTING SERVICES | [13 empty] | Limited Competitive Bidding
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Prequalification
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Bidding Documents | Contract Signature |  | Two-envelope International Competitive Bidding
| Operating Expenses |  | Price Comparison/Shopping | 3 | NC1 | 75698 | 100% | 0% | Project Management |  | 2018-10-15 | 2018-11-05 | N/A | International Competitive Bidding by Lots
| Environmental measures |  | Price Comparison/Shopping | 3 | NC2 | 200000 | 100% | 0% | Component 1 - Climate risk reduction in the tourism sector |  | 2019-04-28 | 2018-05-11 | N/A
| Sub-total |  |  |  |  | 275698 | [7 empty] | Quality Based Selection
Selection Based on the Consultants' Qualifications
CONSULTING FIRMS | [13 empty] | Single Source Selection
Executing Agency: |  | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method |  | National System
| Activity: |  |  |  | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  |  | Least cost Selection
| Works Supervision Package 1 |  | Quality and Cost Based Selection |  | 403109 | 100% | 0% | Component 1 - Climate risk reduction in the tourism sector | Ex-Ante | 2017-11-01 | 2018-08-25 | N/A
| Works Supervision Package 2 |  | Quality and Cost Based Selection |  | 339933 | 100% | 0% | Component 1 - Climate risk reduction in the tourism sector | Ex-Ante | 2020-01-01 | 2020-11-01 | N/A
| Works Supervision Package 3 |  | CQS |  | 87400 | 100% | 0% | Component 1 - Climate risk reduction in the tourism sector | Ex-Ante | 2020-04-30 | 2021-02-01 | N/A |  | Comparison of Qualifications - National Individual Consultant
| Coastal monitoring for Goff's Caye (erosion and coral reef) |  | Quality and Cost Based Selection |  | 303691 | 100% | 0% | Component 1 - Climate risk reduction in the tourism sector | Ex-Ante | 2020-06-01 | 2021-04-01 | N/A
| Management plans for Palapa beach (Caye Caulker) and Goff's Caye |  | CQS |  | 113650 | 100% | 0% | Component 1 - Climate risk reduction in the tourism sector | Ex-Ante | 2018-03-01 | 2018-08-01 | N/A
| Risk information system |  | Quality and Cost Based Selection |  | 478241 | 100% | 0% | Component 2 - Governance for disaster risk management and CC adaptation | Ex-Ante | 2021-02-01 | 2021-04-01 | N/A
| Audits |  | Selection Based on the Consultants' Qualifications |  | 100000 | 100% | 0 | Project Management | Ex-Ante | 2018-09-21 | 2018-11-27 | N/A
| Sub-total |  |  |  | 1826024 | [8 empty] | Turnkey | Goods
[14 empty] | Unit Prices | Goods
INDIVIDUAL CONSULTANTS | [13 empty] | Lump-Sum | Goods
Executing Agency: |  | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Turnkey | Works
| Activity: |  |  |  | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature |  | Unit Prices | Works
| Designing of building codes |  | Comparison of Qualifications - National Individual Consultant |  | 70000 | 100% | 0% |  | Component 2 - Governance for disaster risk management and CC adaptation | Ex-Ante | 2021-04-01 | 2021-07-01 | N/A
| Climate risk financing strategy for the tourism and agriculture sectors |  | Comparison of Qualifications - National Individual Consultant |  | 70000 | 100% | 0% |  | Component 2 - Governance for disaster risk management and CC adaptation | Ex-Ante | 2021-02-01 | 2021-07-01 | N/A
| Project Coordinator |  | Comparison of Qualifications - National Individual Consultant |  | 55000 | 100% | 0% |  | Project Management | Ex-Ante | 2018-03-01 | 2018-06-01 | N/A
| Project Manager |  | Comparison of Qualifications - National Individual Consultant |  | 115000 | 100% | 0% |  | Project Management | Ex-Ante | 2018-03-01 | 2018-06-01 | N/A
| Coastal engineer |  | Comparison of Qualifications - National Individual Consultant |  | 90000 | 100% | 0% |  | Project Management | Ex-Ante | 2018-03-01 | 2018-06-01 | N/A
| Procurement Specialist |  | Comparison of Qualifications - National Individual Consultant |  | 48000 | 100% | 0% |  | Project Management | Ex-Ante | 2018-03-01 | 2018-06-01 | N/A
| Financial Specialist |  | Comparison of Qualifications - National Individual Consultant |  | 43000 | 100% | 0% |  | Project Management | Ex-Ante | 2018-03-01 | 2018-06-01 | N/A
| Planning, Monitoring & Evaluation Officer |  | Comparison of Qualifications - National Individual Consultant |  | 43000 | 100% | 0% |  | Project Management | Ex-Ante | 2018-03-01 | 2018-06-01 | N/A
| Specialist in environmental and social issues |  | Comparison of Qualifications - International Individual Consultant |  | 20000 | 100% | 0% |  | Project Management | Ex-Ante | 2018-03-01 | 2018-06-01 | N/A
| Account Clerk |  | Comparison of Qualifications - National Individual Consultant |  | 28800 | 100% | 0% |  | Project Management | Ex-Ante | 2018-03-01 | 2018-06-01 | N/A
| Driver |  | Comparison of Qualifications - National Individual Consultant |  | 28800 | 100% | 0% |  | Project Management | Ex-Ante | 2018-03-01 | 2018-06-01 | N/A
| Intermediate Evaluation |  | Comparison of Qualifications - National Individual Consultant |  | 35000 | 100% | 0% |  | Project Management | Ex-Ante | 2020-08-01 | 2020-11-01 | N/A
| Final Evaluation |  | Comparison of Qualifications - National Individual Consultant |  | 30000 | 100% | 0% |  | Project Management | Ex-Ante | 2021-07-01 | 2021-11-01 | N/A
| Impact evaluation |  | Comparison of Qualifications - National Individual Consultant |  | 50000 | 100% | 0% |  | Project Management | Ex-Ante | 2021-07-01 | 2021-11-01 | N/A
| Sub-total |  |  |  | 726600 | [8 empty] | Lump-Sum | Consulting Firms
[14 empty] | Lump-Sum + Reimbursable Expenses | Consulting Firms
|  |  | TOTAL |  | 10000000 | [8 empty] | Price Comparison | Non-Consulting Services
[14 empty] | Terms of Reference | Non-Consulting Services
[14 empty] | Procurement of Non-Consulting Services | Non-Consulting Services
[14 empty] | Technical Specifications | Non-Consulting Services
[14 empty] | Request for Proposals and Terms of Reference | Consulting Firms
[14 empty] | Terms of Reference | Consulting Firms
Lump-Sum
Time-Based
Single Source Selection
Comparison of Qualifications - National Individual Consultant
Comparison of Qualifications - International Individual Consultant
3CV