## Sheet1
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Perú |  |  |  |  | Executing agency: IADB |  |  |  |  | Public or private sector: Público
Project number: PE-T1371 |  |  |  |  | Title of Project: Apoyo a la preparación y ejecución inicial del Programa Nacional de Inversiones en Agua y Saneamiento Rural
Period covered by the plan: 2016 - 2018
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$):____________ |  | 15000 |  | Consulting services(in US$):____________ | 485000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (ex-ante or ex-post) (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other %
Servicios de Consultoría
|  | Consultor - Estudio de Impacto Ambiental y Social | 20000 | IICQ | Ex-ante | 100% |  | Mayo de 2017
|  | Consultor - Propuesta de Programa de Inversión | 50000 | IICQ | Ex-ante | 100% |  | Mayo de 2017
|  | Consultorías para elaboración de expedientes técnicos | 155000 | QCBS | Ex-ante | 100% |  | Mayo de 2017
|  | Consultoría - Estudios de factibilidad realizados | 70000 | QCBS | Ex-ante | 100% |  | Mayo de 2017
|  | Consultor - Análisis SECI para el Organismo Ejecutor | 15000 | IICQ | Ex-ante | 100% |  | Mayo de 2017
|  | Consultor - Análisis financiero | 10000 | IICQ | Ex-ante | 100% |  | Mayo de 2017
|  | Consultor - Instrumentos de gestión (incluyendo Manual Operativo) | 25000 | IICQ | Ex-ante | 100% |  | Mayo de 2017
|  | Consultorías para elaboración de normas técnicas | 30000 | QCBS | Ex-ante | 100% |  | Junio de 2017
|  | Consultorías para la actualización de las guías de O&M | 70000 | QCBS | Ex-ante | 100% |  | Junio de 2017
Servicios diferentes a consultoría
|  | Talleres de socialización, eventos e imprevistos | 15000 |  | Ex-ante | 100% |  | Junio de 2017
|  | Encuestas Socioeconómicas (la unidad es encuestas) | 40000 | CP | Ex-ante | 100% |  | Mayo de 2017
Total |  |  | 500000 | Prepared by: Edgar Orellana |  |  | Date: 04/04/2017
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.