## Project Structure
Procurement Plan for May 2017 through November 2018
Agency | Sub-Agency (If applies) | Agency's Initials
Ministry of Tourism and Civil Aviation
COMPONENTS? (YES / NO) | Component's Name (list by number or letter)
YES | Component I: Enhancement of the Tourism Product
Component II: Promoting Disaster and Climate Resilient Destinations
Component III: Institutional Strengthening and Capacity Building
Management
Contingency

## Procurement Plan
INFORMATION FOR PROCUREMENT PLAN
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: | 2017-05-01 | 2018-11-01
2. Procurement Plan Details
Version 2 - 2017
3. Amounts by Investment Category entire project
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Works | 4570000 | 4570000
Goods | 57750 | 57750
Non Consulting Services | 325000 | 325000
Training | 250000 | 250000
Consulting Services (Firms + Individuals) | 4658345 | 4799220
Other | 700000 | 1059125
Unassigned/contingency | 4438905 | 4438905
Total | 15000000 | 15500000
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
Component I: Enhancement of the Tourism Product | 9592500 | 9592500
Component II: Promoting Disaster and Climate Resilient Destinations | 1575000 | 1575000
Component III: Institutional Strengthening and Capacity Building | 2100000 | 2100000
Project Execution' | 1198125 | 1698125
Contingency | 534375 | 534375
Total | 15000000 | 15500000

## Detailed Procurement Plan
STPII PROCUREMENT PLAN July 2017-December 2018
PROCUREMENT PLAN
WORKS
Executing Agency: |  | Activity: | Procurement Method (Select one of the options): | Process Number: | ESTIMATED AMOUNT |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments | ex-poste
[5 empty] | Estimated Amount in USD | Estimated Amount Counterpart in USD | Estimated Amount, IDB %: | Estimated Amount, Counterpart %: |  |  | No Objection to ToRs | Contract Signature |  | ex-ante
MTCA | 1.1.4 | Nim Li Punit - works -parking (clear, level, fill and compacting) | Shopping |  | 70000 | 0 | 100% | 0% | Component 1 | ex-ante | 2017-08-01 | 2017-10-01
MTCA | 1.2.1, 1.4.1, 1.4.3 | Corozal- Cultural Heritage Bayside Plaza streetscape (drainage, lighting, street furniture - benches, garbage bins etc.), parking signage, concession space, visitor information, restrooms, marine gateway, waterfront enhancement and shoreline stabilization measures | International Competitive Bidding |  | 1700000 | 0 | 100% | 0% | Component 1 | ex-ante | 2018-04-01 | 2018-08-01
MTCA | 1.2.2 | Toledo Welcome Plaza Works - restrooms, House of Culture building, hard & soft landscaping, drainage, lighting, street furniture - benches, garbage bins etc. | International Competitive Bidding |  | 1300000 | 0 | 100% | 0% | Component 1 | ex-ante | 2018-03-01 | 2018-06-01
MTCA | 1.3.1 and 1.3.2 and 1.5.3 | Construction of a new Mountain Pine Ridge -Information and Logistics center including a communication and emergency response post, restrooms, low key concession space, power & water supply, visitor information Center. Access trail, parking for Rio Frio Cave and visitor facilities and improvements at 2 prioritized sites in the MPR. Production and installation of signage. | International Competitive Bidding |  | 1200000 | 0 | 100% | 0% | Component 1 | ex-ante | 2018-09-01 | 2018-11-01
MTCA | 1.3.3 and 2.5.3 | Protected Areas Visitor Facilities- Caye Caulker | National Competitive Bidding |  | 300000 | 0 | 100% | 0% | Component 1 | ex-ante | 2019-04-01 | 2020-01-01
SUBTOTAL |  |  |  |  | 4570000
GOODS
Executing Agency: |  | Activity: | Procurement Method (Select one of the options): | Process Number: | Amount in US$ : |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
[5 empty] | Estimated Amount, in US$ | Estimated Amount Counterpart (US$) | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Specific Procurement notice | Contract Signature
MTCA | 4.3.3 | Furniture & equipment | Shopping (3 quotations) |  | 57750 | 0 | 100% | 0% | operations | ex-ante | 2016-04-01 |  | majority contracted
Force Account
Subtotal |  |  |  |  | 57750 | [8 empty] | Shopping
NON CONSULTING SERVICES | [13 empty] | Direct Contracting (Single Source Selection)
Executing Agency: |  | Activity: | Procurement Method (Select one of the options): | Process Number: | Amount in US$ : |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments | International Competitive Bidding
[5 empty] | Estimated Amount, in US$ | Estimated Amount Counterpart US$ | Estimated Amount, BID %: | Estimated Amount, Counterpart %: |  |  | Bidding Documents | Contract Signature |  | National Competitive Bidding
MTCA | 1.5.1 and 1.5.2 | Tourist signage Toledo and Corozal | Shopping |  | 100000 | 0 | 100% | 0% | Component 1 | ex-ante | 2018-03-01 | 2018-05-01 |  | Quality Cost Based Selection
MTCA | 1.5.4 | Tourist signage Caye Caulker | Shopping |  | 75000 | 0 | 100% | 0% | component 1 | ex-ante | 2016-10-01 | 2017-01-01 | Contracted
MTCA | 3.4 | Responsible tourism and awareness program | Shopping |  | 100000 | 0 | 100% | 0% | Component 1 | ex-ante | 2017-05-01 | 2017-07-01
MTCA | 1.3.4 | Interpretation Corozal Bay wildlife sanctuary | Shopping |  | 50000 | 0 | 100% | 0% | Component 1 | ex-ante | 2018-06-01 | 2019-03-01 |  | Selection based on Consultants Qualifications (CQS)
Subtotal |  |  |  |  | 325000
CONSULTING FIRMS
Executing Agency: |  | Activity: | Procurement Method (Select one of the options): | Amount in US$ : |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
|  |  |  | Estimated Amount, in u$s : | Estimated Amount, BID %: | Estimated Amount Counterpart | Estimated Amount, Counterpart %: |  |  | Specific Procurement notice | Contract Signature
MTCA | 1.2.2 | Toledo Welcome Plaza- technical studies including management plans and drawings | Quality Cost Based Selection (QCBS) | 117000 | 100% | 0 | 0% | Component 1 | ex-ante | 2017-03-01 | 2017-08-01
MTCA | 1.1.2 and 1.1.4 | Santa Rita and Nim Li Punit- Architectural Drawings and Bidding Docs and supervision | Direct Contracting (Single Source Selection) | 33400 | 100% | 0 | 0% | component 1 | ex-ante | 2016-09-01 | 2016-12-01 | Contracted
MTCA | 2.5.3 | Caye Caulker visitor center technical studies, architectural designs and marine management plan update | Quality Cost Based Selection (QCBS) | 55500 | 100% | 0 | 0% | Component 1 | ex-ante | 2018-03-01 | 2018-07-01 |  |  | Component 1
MTCA | 1.2.1 | Corozal Heritage Plaza technical studies including management plans, drawings and bidding documents | Selection Based on Consultants Qualifications (CQS) | 100000 | 100% | 0 | 0% | Component 1 | ex-ante | 2017-01-01 | 2017-06-01 | Contracted
MTCA | 1.1.3 | Caracol - technical studies, architectural drawings and bidding docs | Quality Cost Based Selection (QCBS) | 126000 | 100% | 0 | 0% | Component 1 | ex-ante | 2018-02-01 | 2018-07-01 |  |  | Component 2
MTCA | 1.1.5 | Toledo archaeological site- technical studies, dawings and bidding docs and construction supervision | Selection Based on Consultants Qualifications (CQS) | 28000 | 100% | 0 | 0% | Component 1 | ex-ante | 2018-11-01 | 2019-01-01 |  |  | Component 3
MTCA | 1.3.1, 1.3.5, 1.3.2 and 3.3.4 | Mountain Pine Ridge Info and logistic center and visitor sites- technical studies, drawings and bidding documents including signage, PPP plan and carrying capacity studies | Selection Based on Consultants Qualifications (CQS) | 194000 | 100% | 0 | 0% | component 1 | ex-ante | 2017-08-01 | 2017-12-01
MTCA | 1.4.3.1 | Coastal baseline studies for Toledo & Caye Caulker | Quality Cost Based Selection (QCBS) | 700000 | 100% | 0 | 0% | component 1 | ex-ante | 2017-01-01 | 2017-06-01 | contracted
MTCA | 2.1 | National Guidelines for Disaster Risk for the Tourism Sector | Selection Based on Consultants Qualifications (CQS) | 75000 | 100% | 0 | 0% | Component 2 | ex-ante | 2018-02-01 | 2018-05-01
MTCA | 2.2, 2.3, 2.4 | Toledo and Corozal Disaster Risk and Climate Resilience Plans and crisis management plans and training | Quality Cost Based Selection (QCBS) | 700000 | 100% | 0 | 0% | Component 2 | ex-ante | 2018-01-01 | 2018-06-01
MTCA | 2.5.1 | Develop environmental monitoring program | Quality Cost Based Selection (QCBS) | 200000 | 100% | 0 | 0% | component 2 | ex-ante | 2018-04-01 | 2018-08-01
MTCA | 2.5.2 | Ecosystem service valuation Toledo | Quality Cost Based Selection (QCBS) | 400000 | 100% | 0 | 0% | Component 2 | ex-ante | 2018-07-01 | 2018-11-01
MTCA | 3.1.1 | Improve national tourism statistics (domestic survey) | single source selection | 50000 | 100% | 0 | 0% | component 3 | ex-ante | 2017-06-01 | 2018-09-01
MTCA | 3.1.2 | Improve destination statistical system | Quality Cost Based Selection (QCBS) | 450000 | 100% | 0 | 0% | component 3 | ex-ante | 2018-02-01 | 2018-05-01
MTCA | 3.3.1 | Mexican Market Study | selection Based on Consultants Qualifications (CQS) | 50000 | 100% |  | 0% | component 3 | ex-ante | 2017-03-01 | 2017-08-01 | Contracted
MTCA | 3.3.2 | Product development, marketing & branding through the development of tourist corridors and trails in the emerging destinations of Corozal and Toledo | Quality Cost Based Selection (QCBS) | 200000 | 100% | 0 | 0% | Component 3 | ex-ante | 2017-04-01 | 2017-08-01 | In Negotiations
MTCA | 4.1 | Audits (annual) | Quality Cost Based Selection (QCBS) | 60000 | 100% | 0 | 0% | Auditing and evaluation | ex-ante | 2017-01-01 | 2017-05-01 | contracted
MTCA | 3.4.2. | Grant Administrator and development of matching grant manual | Direct Contracting Single Source Selection | 100000 | 100% | 0 | 0% | Component 3 | ex-ante | 2018-03-01 | 2018-06-01
Subtotal |  |  |  | 3638900
Management
INDIVIDUAL CONSULTANTS
Executing Agency: |  | Activity: | Procurement Method (Select one of the options): | Amount in USD : |  |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments
|  |  |  | Estimated Amount, in US$ : | Estimated Amount, BID %: | Estimated Amount Counterpart USD | Estimated Amount, Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature
Quality Cost Based Selection (QCBS)
MTCA | 4.1 | Finance Specialist | Comparison of Qualifications - National Individual Consultant | 135000 | 100% | 0 | 0% |  | management | ex-ante | 2016-04-01 | 2017-02-01 | contracted for 2 years | single source selection
MTCA | 4.1 | Procurement Specialist | Comparison of Qualifications - National Individual Consultant | 121800 | 100% | 0 | 0% |  | management | ex-ante | 2016-04-01 | 2016-08-01 | contracted for 1 year
MTCA | 4.1 | Climate Change Adaptation, Social and environmental management specialist | Comparison of Qualifications - National Individual Consultant | 87750 | 65% | 47250 | 35% |  | management | ex-ante | 2016-04-01 | 2016-09-01 | contracted for 2 years
MTCA | 4.1 | Physical Planner and Infrastructure Specialist | Comparison of Qualifications - National Individual Consultant | 105625 | 65% | 56875 | 35% |  | management | ex-ante | 2016-04-01 | 2016-09-01 | contracted for 2 years
MTCA | 4.1 | Monitoring and Evaluation Project Support Specialist | Comparison of Qualifications - National Individual Consultant | 68250 | 65% | 36750 | 35% |  | management | ex-ante | 2017-07-01 | 2017-04-01 | contracted for 2 years
MTCA | 3.2.1 | National Tourism Policy developed | Comparison of Qualifications - International Individual Consultant | 75460 | 100% | 0 | 0% |  | component 3 | ex-ante | 2016-06-01 | 2016-12-01 | contracted
MTCA | 3.2.2 | Development of legal frameworks (National Tourism Act) | Comparison of Qualifications - International Individual Consultant | 30000 | 100% | 0 | 0% |  | Component 3 | ex-ante | 2017-12-01 | 2018-02-01
MTCA | 4.2 | Midterm evaluation | Selection Based on Consultants Qualifications (CQS) | 100000 | 100% | 0 | 0% |  | Auditing and evaluation | ex-ante | 2018-04-01 | 2018-07-01
MTCA | 5.1 | Construction supervision of Corozal investments | Comparison of Qualifications - National Individual Consultant | 75960 | 100% | 0 | 0% |  | Component 4 | ex-ante | 2017-09-01 | 2018-01-01
MTCA | 5.2 | construction supervision of Toledo investments | Comparison of Qualifications - National Individual Consultant | 94000 | 100% | 0 | 0% |  | component 4 | ex-ante | 2017-09-01 | 2018-01-01
MTCA | 5.3 | Construction supervision of MPR/Caracol investments | Comparison of Qualifications - National Individual Consultant | 93600 | 100% | 0 | 0% |  | component 4 | ex-ante | 2017-12-01 | 2018-04-01
MTCA | 5.4 | Construction supervision of Caye Caulker investments | Comparison of Qualifications - National Individual Consultant | 32000 | 100% | 0 | 0% |  | component 4 | ex-ante | 2018-04-01 | 2018-08-01
Subtotal |  |  |  | 1019445 |  | 140875
[14 empty] | Lump-Sum + Reimbursable Expenses | Consulting Firms
TRAINING | [13 empty] | Time-Based | Consulting Firms
Executing Agency: |  | Activity: | Procurement Method (Select one of the options): | Amount in u$s : |  |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments |  |  | Individual Consultants
|  |  |  | Estimated Amount, in $US : | Estimated Amount, BID %: | Counterpart Estimated amount US$ | Estimated Amount, Counterpart %: |  |  | Annual Training Plan (ATP) | End of Activity |  |  |  | Individual Consultants
MTCA | 3.4.2 | Excursion sector training | Shopping | 200000 | 100% | 0 | 0% | component 3 | ex-ante | 4 years | 2020-02-01 |  |  | Procurement of Textbooks and Reading Materials | Goods
MTCA | 3.2.3 and 3.2. 4 | Training Support for Compliance | Selection based on Consultants Qualifications (CQS) | 50000 | 100% | 0 | 0% | Component 3 | ex-ante |  | 2018-12-01
Subtotal |  |  |  | 250000
[14 empty] | Price Comparison for Goods | Goods
OTHER | [13 empty] | Technical Specifications | Goods
|  | Activity | Procurement method | amount |  |  | Estimated Amount, Counterpart %: | Associated component | Dates |  | comments |  |  | Procurement of plant Design , Supply and Installation | Goods
|  |  |  | estimated amount US$ | Estimated Amount, BID %: | Counterpart Estimated amount US$ | [7 empty] | Procurement of IT Products and/or Services | Goods
MTCA | 3.3.3 and 3.2.3 | Support coordination to local tourism committees and promotion of PPPs |  | 100000 | 100% | 0 | 0% | Component 3 | 2017-01-01 | 2020-01-01
MTCA | 3.4.2 | Matching Grant and support to the private sector | selection criteria and evaluation | 600000 | 100% | 0 | 0 | Component 3 | 2018-11-01 | 2020-05-01
subtotal |  |  |  | 700000 | [9 empty] | Price Comparison | Non-Consulting Services
[14 empty] | Terms of Reference | Non-Consulting Services
[14 empty] | Procurement of Non-Consulting Services | Non-Consulting Services
TOTAL |  |  |  | 10561095 | [9 empty] | Technical Specifications | Non-Consulting Services
[14 empty] | Request for Proposals and Terms of Reference | Consulting Firms
[14 empty] | Terms of Reference | Consulting Firms
[14 empty] | Lump-Sum | ex-ante
[14 empty] | Time-Based | ex-poste
Single Source Selection
Comparison of Qualifications - National Individual Consultant
Comparison of Qualifications - International Individual Consultant
3CV