## Introduction
Work calendar model for the collection phase
This Excel file presents two examples of work calendars or Gantt charts for an impact evaluation survey. Both calendars have the same duration of activities but in the summarized version some activities have been combined.
The activities list brings together the essential activities in surveys of this type, and in any case, depending on the particular survey, other activities should be added or removed from the existing list.
Similarly, the times assigned to each activity should be adjusted. Special care has been taken in these models with respect to the duration and order of the activities, such that each component is in agreement with the best practices for performing these surveys. Surely for some users some of the activities might seem to be excessively long, but we recommend that you conduct a detailed analysis before making any modifications so as not to underestimate the duration of any activity, which can be especially problematic when the work calendar represents contractual commitments.
It is recommended that the work calendars be detailed, ideally containing tangible product checkpoints, for example, "Version of the questionnaire for the pilot"; "Data entry program"; "Pilot report"; etc.
Finally, evaluating the possible risks that could prevent the activities from developing as stipulated in the calendar is suggested in order to improve the estimations and/or take actions to mitigate these risks.

## Guide
Note for Adapting the Materials
The activities list in these examples is common to all impact evaluations and surveys of this type, however, the need to add new activities or eliminate existing activities if they are not relevant should be considered. Note that greater detail about the activities and the inclusion of verifiable outputs facilitates follow up and monitoring of activity implementation.
These examples are presented in Excel, but the Gantt chart can evidently be developed with other tools such as MS Project. One important aspect that should be respected, independent of the tool used, is the order of activities. In the example, these are given by formulas that take the completion date of the activity that proceeds the event being scheduled into account. For example, the questionnaire must be finalized before carrying out the training.
The duration of the activities presented is only a guide, however, these examples use the minimum amount of time reasonably needed to develop impact evaluations that use survey instruments like those included in this portal.
The total duration of surveying in the field is conditional on the total number of sampling points, the number of surveys to be performed at each sampling point, and the average estimated time to perform the surveys at each sampling point, in addition to the number of field teams deemed necessary. Keep in mind that the general recommendation suggests spending more time in the field with fewer teams than the contrary of less time and more teams. The former allows for better control of aspects of survey quality. However, keep in mind that these times should be consistent with the project's activities. Do not forget that, as the example impact evaluation Gantt chart shows, the baseline survey must be performed before the start of the project's interventions, which may make it necessary to shorten time in the field and thus increase the number of teams.
If you want to use Excel to construct your Gantt chart you can modify the examples presented, keeping in mind that you must manually modify the graphic representation of the activities calendar.

## Detailled_model
1 | MANAGEMENT, FINANCE, LOGISTICS, AND INSTITUTIONAL AGREEMENTS |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
1.01 | First meeting with the selected firm(s) | 2015-04-15 | 2015-04-15 | 1
1.02 | Signing of contracts with the data collection firm(s) | 2015-04-22 | 2015-04-22 | 1
1.03 | Presentation of the firm's central team | 2015-04-24 | 2015-04-24 | 1
1.04 | Hiring of telecommunication services | 2015-04-25 | 2015-05-24 | 30
1.05 | Hiring of computer equipment | 2015-04-25 | 2015-05-24 | 30
1.06 | Obtention/purchase of anthropometric materials | 2015-04-25 | 2015-05-24 | 30
1.07 | Obtention/purchase of hemoglobin test | 2015-04-25 | 2015-05-24 | 30
1.08 | Development of the Ethics committee presentation | 2015-04-25 | 2015-07-23 | 90
1.09 | Presentation to the ethics committee | 2015-07-24 | 2015-08-22 | 30
1.1 | Development and implementation of awareness raising plan | 2015-09-01 | 2015-10-31 | 61
1.11 | Receipt of materials by the firm (model questionnaires, programs, etc.) | 2015-04-29 | 2015-04-29 | 1
2 | DEVELOPMENT OF QUESTIONNAIRES, FIELD MANUALS |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
2.01 | First version of the questionnaire | 2015-04-30 | 2015-05-17 | 18
2.02 | Revision of the questionnaires | 2015-05-20 | 2015-05-31 | 12
2.03 | Pre-test of the questionnaires | 2015-06-01 | 2015-06-07 | 7
2.04 | Modification of the questionnaires after the pre-test (version for the pilot) | 2015-06-04 | 2015-06-12 | 9
2.05 | Preparation of the field manual | 2015-06-13 | 2015-06-28 | 16
2.06 | Modification of questionnaires, procedures, and survey materials after the pilot | 2015-07-22 | 2015-08-02 | 12
2.07 | Printing of the final questionnaires | 2015-08-03 | 2015-08-03 | 1
3 | DATA MANAGEMENT |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
3.01 | Definition of the validation rules | 2015-06-13 | 2015-06-18 | 6
3.02 | First version of the data entry program | 2015-06-13 | 2015-07-03 | 21
3.03 | Manual for the data entry operator | 2015-07-04 | 2015-07-08 | 5
3.04 | Test of the pilot program | 2015-07-12 | 2015-07-15 | 4
3.05 | Definition of the data management procedures | 2015-07-22 | 2015-07-26 | 5
3.06 | Data entry program finalization after observations of the pilot | 2015-07-22 | 2015-08-02 | 12
3.07 | Definition of the dictionary of final data sets | 2015-08-03 | 2015-09-02 | 31
3.08 | Delivery of final data sets | 2016-02-21 | 2016-02-21 | 1
4 | PILOT TEST |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
4.01 | Preparation of the pilot test | 2015-06-10 | 2015-06-14 | 5
4.02 | Recruitment of supervisors and surveyors for the pilot test | 2015-06-17 | 2015-06-28 | 12
4.03 | Training for the pilot test | 2015-07-01 | 2015-07-07 | 7
4.04 | Production of questionnaires for the pilot test | 2015-07-05 | 2015-07-06 | 2
4.05 | Pilot test in the field including data entry | 2015-07-08 | 2015-07-14 | 7
4.06 | Pilot test report | 2015-07-15 | 2015-07-19 | 5
5 | TRAINING |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
5.01 | Prepare training materials | 2015-07-15 | 2015-08-02 | 19
5.02 | Preparation of logistics for the training | 2015-07-22 | 2015-08-02 | 12
5.03 | Training of the field staff | 2015-08-05 | 2015-08-25 | 21
5.04 | Written evaluation and selection of the staff | 2015-08-27 | 2015-08-30 | 4
6 | SAMPLE |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
6.01 | Identification of the selected working areas | 2015-07-15 | 2015-07-25 | 11
6.02 | Mapping of the selected areas | 2015-07-27 | 2015-07-30 | 4
6.03 | Selected areas' households listing | 2015-09-16 | 2016-02-09 | 147
6.04 | Household selection procedure | 2015-09-16 | 2016-02-09 | 147
6.05 | Household replacement procedures | 2015-09-16 | 2016-02-13 | 151
7 | FIELDWORK AND STAFF |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
7.01 | Identification and hiring of the field workers | 2015-09-02 | 2015-09-12 | 11
7.02 | Organization of the field teams (supervisors and surveyors) | 2015-09-02 | 2015-09-12 | 11
7.03 | Organization of the field teams' transportation | 2015-09-02 | 2015-09-12 | 11
7.04 | Design of the supervision procedures | 2015-09-02 | 2015-10-02 | 31
7.05 | Survey in the field | 2015-09-16 | 2016-02-13 | 151
7.06 | Consolidation of the partial data sets | 2015-09-20 | 2016-02-14 | 148
7.07 | Data quality monitoring | 2015-09-16 | 2016-02-13 | 151
7.08 | Feedback from the field teams | 2015-09-17 | 2016-02-13 | 150

## Summarized_model
1 | MANAGEMENT, FINANCE, LOGISTICS, AND INSTITUTIONAL AGREEMENTS |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
1.01 | First meeting with the selected firm(s) | 2015-04-15 | 2015-04-15 | 1
1.02 | Signing of contracts with the data collection firm(s) | 2015-04-22 | 2015-04-22 | 1
1.03 | Hiring of services and purchase of materials | 2015-04-26 | 2015-05-25 | 30
1.04 | Development of the Ethics committee presentation | 2015-04-26 | 2015-07-24 | 90
1.05 | Presentation to the ethics committee | 2015-07-25 | 2015-08-23 | 30
1.06 | Development and implementation of awareness raising plan | 2015-09-02 | 2015-11-01 | 61
1.07 | Receipt of materials by the firm (model questionnaires, programs, etc.) | 2015-04-29 | 2015-04-29 | 1
2 | DEVELOPMENT OF QUESTIONNAIRES, FIELD MANUALS |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
2.01 | First version of the questionnaire and initial test | 2015-04-30 | 2015-06-07 | 39
2.02 | Modification of the questionnaires after the pre-test (version for the pilot) | 2015-06-04 | 2015-06-12 | 9
2.03 | Preparation of the field manual | 2015-06-13 | 2015-06-28 | 16
2.04 | Modification of questionnaires, procedures, and survey materials after the pilot | 2015-07-22 | 2015-08-02 | 12
2.05 | Printing of the final questionnaires | 2015-08-03 | 2015-08-03 | 1
3 | DATA MANAGEMENT |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
3.01 | Development of data entry program | 2015-06-13 | 2015-07-03 | 21
3.02 | Manual for the data entry operator | 2015-06-28 | 2015-07-02 | 5
3.03 | Definition of the data management procedures | 2015-07-22 | 2015-07-26 | 5
3.04 | Data entry program finalization after observations of the pilot | 2015-07-22 | 2015-08-02 | 12
3.05 | Definition of the dictionary of final data sets | 2015-08-03 | 2015-09-02 | 31
3.06 | Delivery of final data sets | 2016-02-21 | 2016-02-21 | 1
4 | PILOT TEST |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
4.01 | Preparation of the pilot test | 2015-06-10 | 2015-06-14 | 5
4.02 | Recruitment of supervisors and surveyors for the pilot test | 2015-06-17 | 2015-06-28 | 12
4.03 | Training for the pilot test | 2015-07-01 | 2015-07-07 | 7
4.04 | Production of questionnaires for the pilot test | 2015-07-05 | 2015-07-06 | 2
4.05 | Pilot test in the field including data entry | 2015-07-08 | 2015-07-14 | 7
4.06 | Pilot test report | 2015-07-15 | 2015-07-19 | 5
5 | TRAINING |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
5.01 | Prepare training materials | 2015-07-15 | 2015-08-02 | 19
5.02 | Preparation of logistics for the training | 2015-07-22 | 2015-08-02 | 12
5.03 | Training of the field staff | 2015-08-05 | 2015-08-25 | 21
5.04 | Written evaluation and selection of the staff | 2015-08-27 | 2015-08-30 | 4
6 | SAMPLE |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
6.01 | Identification and mapping of the selected working areas | 2015-07-15 | 2015-07-25 | 11
6.02 | Selected areas' households listing | 2015-09-16 | 2016-02-09 | 147
6.03 | Household selection procedure | 2015-09-16 | 2016-02-09 | 147
7 | FIELDWORK AND STAFF |  |  | Days | 2015 | [8 empty] | 2016
[5 empty] | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
[5 empty] | 15 | 6 | 3 | 1 | 5 | 2 | 7 | 4 | 2 | 6 | 3
7.01 | Identification and hiring of the field workers | 2015-09-02 | 2015-09-12 | 11
7.02 | Organization of the teams and logistical aspects | 2015-09-02 | 2015-09-12 | 11
7.03 | Design of the supervision procedures | 2015-09-02 | 2015-10-02 | 31
7.04 | Survey in the field | 2015-09-16 | 2016-02-13 | 151
7.05 | Data quality Monitoring | 2015-09-16 | 2016-02-13 | 151