## NEW CHECKLIST
Impact Evaluation Checklist from A to Z |  |  |  |  | Institution/person in charge | Completed (Yes/No) | Resources
1. Designing an Impact Evaluation
| 1.1 | Diagnostic
|  | 1.1.1 | Identify and quantify the development problem of interest
|  | 1.1.2 | Identify context factors in the problem diagnostic
|  | 1.1.3 | Describe the target population and sub-populations of interest
|  | 1.1.4 | Review the literature related to the problem and target population
|  | 1.1.5 | Review the literature for evidence based interventions (both for internal and external validity) used to address this problem
| 1.2 | Identification of a cost-effective intervention to address the problem
|  | 1.2.1 | State the purpose of the intervention and rationale within national context
|  | 1.2.2 | Identify intervention components/activities
|  | 1.2.3 | Identify intervention location(s)
|  | 1.2.4 | Conduct economic analysis (cost-benefit and/or cost-effectiveness) to determine economic viability of proposed intervention |  |  |  | Economic analysis webpape
|  | 1.2.5 | Define the intended use of results by policy and decision makers
| 1.3 | Logical Framework
|  | 1.3.1 | Define the project components to be impact-evaluated
|  | 1.3.2 | Spell out the evaluation questions and hypotheses
|  | 1.3.3 | Identify SMART primary and secondary outcome indicators (program impacts and results)
|  | 1.3.4 | Calculate summary statistics (means, prevalence, standard deviation) for primary and secondary outcome indicators
|  | 1.3.5 | Map the program's logic (through a results matrix, theoretical model, or other format)
|  | 1.3.6 | Identify data collection means (questionnaire, samples, etc.)
| 1.4 | Identify an evaluation methodology |  |  |  |  | Impact evaluation methods
|  | 1.4.1 | Define whether the evaluation will be experimental or quasi-experimental
|  | 1.4.2 | Identify the optimal unit of treatment assignment (individual, household, village, school, health clinic, firm, farm, etc.)
|  | 1.4.3 | Identify unit of analysis and of cluster (if applicable)
|  | 1.4.4 | Identify whether treatment can be blinded or double blinded
|  | 1.4.5 | Document randomization or treatment assignment procedure
|  | 1.4.6 | Document treatment and comparison groups
|  | 1.4.7 | Identify complementary evaluation strategies for the project including mixed methods, process evaluations, etc.
| 1.5 | Conduct power calculations (significance = 0.05 and power = 0.8 or 0.9) |  |  |  |  | Power calculations tool
|  | 1.5.1 | Identify minimum detectable effect size (MDE) using CBA, existing literature, simulation analysis, models, etc.
|  | 1.5.2 | Calculate intra-cluster correlation using existing data (if applicable)
|  | 1.5.3 | Calculate sample sizes (number of units and clusters) for each sub-population of interest that identify the proposed MDE
|  | 1.5.4 | Adjust (increase) sample size to account for sample attrition
| 1.6 | Sample Selection
|  | 1.6.1 | Identify sample framework including sampling universe
|  | 1.6.2 | Identify stratification criteria
|  | 1.6.3 | Determine number of stages for sample selection
|  | 1.6.4 | Determine sample weighting properties (self-weighted or with sample weighgts)
|  | 1.6.5 | Select sample
|  | 1.6.6 | Document sample selection process
| 1.7 | Identify Data Sources
|  | 1.7.1 | Existing Data
|  | 1.7.2 | Primary Data requirements
| 1.8 | Identify candidates for evaluation team |  |  |  |  | Comprehensive terms of reference
|  | 1.8.1 | Principal Investigator(s) |  |  |  | Terms of reference (Principal investigator)
|  | 1.8.2 | Field Coordinator(s)
|  | 1.8.3 | Research Assistant(s)
|  | 1.8.4 | Statistician/Sampling Expert
|  | 1.8.5 | Data Quality Assurance |  |  |  | Terms of reference (Quality Assurance)
| 1.9 | Draft an Evaluation Schedule/Timeline |  |  |  |  | Impact evaluation Gantt chart
| 1.1 | Identify Intended Audiences for impact results
|  | 1.10.1 | Dissemination and publication strategy
| 1.11 | Identify funding/economic sources for the impact evaluation
| 1.12 | Draft Evaluation Budget |  |  |  |  | Budget template
| 1.13 | Define a strategy for monitoring implementation adherence to treatment and control assignment during the evaluation period
| 1.14 | Evaluation Concept Note |  |  |  |  | Concept note template
|  | 1.13.1 | Document all previous steps (1.1-1.12)
|  | 1.13.2 | Write out analysis plan with equation(s) to be estimated
| 1.15 | Present evaluation design to relevant stakeholders
| 1.16 | Conduct a peer-review of the evaluation design and update design accordingly
| 1.17 | Submit the experiment to an IRB |  |  |  |  | Protection of human subjects webpage
| 1.18 | Register the Experiment and analysis plan |  |  |  |  | Clinicaltrials.gov | socialscienceregistry.org
| 1.19 | Draft dissemination plan for each stage of the evaluation
| 1.2 | Present Final evaluation design to relevant stakeholders
2. Implementing an Impact Evaluation
| 2.1 | Identify evaluation execution scheme (centralized with multiple service providers and consultants; decentralized with single executing agency)
| 2.2 | Hire evaluation team, including:
|  | 2.2.1 | Principal Investigator(s) |  |  |  | Terms of reference (Principal investigator)
|  | 2.2.2 | Field Coordinator(s)
|  | 2.2.3 | Research Assistant(s)
|  | 2.2.4 | Statistician/Sampling Expert
|  | 2.2.5 | Data Quality Assurance |  |  |  | Terms of reference (Quality Assurance)
| 2.3 | Ensure program operational guidelines are consistent with evaluation design (and vice-versa)
| 2.4 | Identify and contract data collection entity |  |  |  |  | Terms of reference (Data collection firm)
| 2.5 | Monitor that the program is being implemented according to the original design
| 2.6 | Supervise the program evaluation activities
| 2.7 | Collect Baseline Data (if necessary) |  |  |  |  | Data collection tools
| 2.8 | Collect Endline Data (if necssary) |  |  |  |  | Data collection tools
3. Collecting data
| 3.1 | Instrument design (questionnaire, tests, etc.) |  |  |  |  | Data collection tools
|  | 3.1.1 | Identify the topics/modules to be included
|  | 3.1.2 | Use previously tested and validated measurement instruments when possible
|  | 3.1.3 | Identify the instrument format (paper-based, CATI, CAPI, etc.)
|  | 3.1.4 | Construct the instrument |  |  |  | Data collection tools
|  | 3.1.5 | Check with the technical team and counterparts that all questions necessary to construct variables and indicators of interest are included
|  | 3.1.6 | Double check that all primary and secondary outcome measures are included
|  | 3.1.7 | Develop supervisor manual with field work protocols |  |  |  | Data collection tools
|  | 3.1.8 | Develop enumerator manual with field work protocols |  |  |  | Data collection tools
|  | 3.1.9 | Ensure consistency of unique identifiers in survey with other potential data sources to be linked later on (census, monitoring data, etc.)
|  | 3.1.10 | Pre-test the instrument
|  | 3.1.11 | Pilot the instrument
|  | 3.1.12 | FInalize survey instrument incorporating feedback from pre-test and pilot
|  | 3.1.13 | Update supervisor manual with feed back from pre-test and pilot
|  | 3.1.14 | Update surveyor manual with feedback from pre-test and pilot
|  | 3.1.15 | Develop the data-entry program |  |  |  | Data collection tools
|  | 3.1.16 | Develop secure data transmission protocol
| 3.2 | Assemble survey team
|  | 3.2.1 | Field manager
|  | 3.2.2 | Data manager
|  | 3.2.3 | Surveyors (paper-pencil and specialized measurements)
|  | 3.2.4 | Cartography specialists
|  | 3.2.5 | Transport and logistics
| 3.3 | Survey Training |  |  |  |  | Data collection training materials
|  | 3.3.1 | Prepare instrument trainning materials
|  | 3.3.2 | Train survey team
|  |  | 3.3.2.1 | Academic sessions
|  |  | 3.3.2.2 | Classroom exercises: mock interviews, vignettes, case studies
|  |  | 3.3.2.3 | Field practice
| 3.4 | Ensure Human Subject Protection standards/protocols and all IRB commitments are implemented |  |  |  |  | Protection of human subjects webpage
| 3.5 | Data-collection
|  | 3.5.1 | Develop field work plan and itinerary |  |  |  | Data collection Gantt chart
|  | 3.5.2 | Analyze security/safety requirements and risk mitigation strategies for survey teams
|  | 3.5.3 | Hire/buy necessary and supplementary services or goods for data collection process (vehicles, GPS, tablets, phones, scales, hemocue, etc.)
|  | 3.5.4 | Print survey materials (questionnaires, maps, etc.)
|  | 3.5.5 | Prepare households/individuals consent form
|  | 3.5.6 | List households/individuals in sample units
|  | 3.5.7 | Collect data
|  | 3.5.8 | Produce routine Field work reports
|  | 3.5.9 | Supervise field work
| 3.6 | Data process |  |  |  |  | Data entry programs
|  | 3.6.1 | Input data from the field
|  | 3.6.2 | Check data consistency
|  | 3.6.3 | Go back to the field to correct survey mistakes
|  | 3.6.4 | Consolidate final complete database
|  | 3.6.5 | Create variables dictionary
|  | 3.6.6 | Anonymize data for analysis |  |  |  | Anonymization of data
|  | 3.6.7 | Document data collection
|  | 3.6.8 | Develop field work diary
|  | 3.6.9 | Develop supervision reports
| 3.7 | Other data
|  | 3.7.1 | Obtain program implementation monitoring data
4. Analyzing data and Disseminating Results | [6 empty] | Analysis and dissemination webpage
| 4.1 | Dataset
|  | 4.1.1 | Construct outcome and control variables
|  | 4.1.2 | Write analysis code with clear documentation so analysis can be replicated
| 4.2 | Data analysis
|  | 4.2.1 | Program econometric analysis according to pre-established analysis plan
|  | 4.2.2 | Cluster standard errors (if applicable)
|  | 4.2.3 | Analyze treatment compliance
|  | 4.2.4 | Analyze sample attrition
|  | 4.2.5 | Check balance between control and treatment group variables (baseline)
|  | 4.2.6 | Program descriptive analysis code
|  | 4.2.7 | Program impact analysis code
|  |  | 4.2.7.1 | Calculate the intention to treat average impact estimate
|  |  | 4.2.7.2 | Calculate the treatment on the treated or local average treatment effect (if applicable)
|  |  | 4.2.7.3 | Analyze impacts by population sub-groups proposed in analysis plan
|  |  | 4.2.7.4 | Produce tables and graphs
| 4.3 | Report and publications
|  | 4.3.1 | Discuss preliminary results with key stakeholders (program managers, etc.)
|  | 4.3.2 | Write impact evaluation report |  |  |  | Impact evaluation report template
|  | 4.3.3 | Publish working paper
|  | 4.3.4 | Publish academic paper
| 4.4 | Dissemination
|  | 4.4.1 | Present final results to key stakeholders
|  | 4.4.2 | Publish non-academic outlets (policy notes, social media, etc.)
|  | 4.4.3 | Present at Conferences and seminars
|  | 4.4.4 | Publish anonymized data |  |  |  | Anonymization of data
|  | 4.4.5 | Archive final reports, data, code, questionnaires, sample frame, IRB approvals, etc.