## Stakeholders
N° | Stakeholder | Description of Stakeholder (Who exactly are they, what motivates them, what concerns them the most) | Component | Attitude towards project (+positive, -negative, Neutral) | Interest (Very High 5, High 4, Low 2, Very Low 1) | Influence (Very High 5, High 4, Moderate 3, Low 2, Very Low 1) | Objective | Measures to achieve objective
1 | IDB Team | -Ensure IDB Loan Resources are used efficiently and in accordance with Bank rules and policies. | ALL | + | 5 | 5 | Involve early in design and monitor closely. | 1) Have Regular Consultations. 2) Develop working relationship with OA.
2 | Business Associations and Chambers of Commerce (e.g. TTMA and TTCIC) | -Entities that represent Business Community. -Ensuring that the systems meets the needs of their membership and improves sector efficiency. | ALL | + | 5 | 4 | Involve early in design and monitor closely. | 1) Have Regular Consultations.
3 | Ministry of Food Production | -Key Player in Goods Declaration Process. -Interested in obtaining resources. | 1&3 | + | 4 | 2 | Keep informed. | 1) Have Regular Consultations.
4 | Ministry of National Security | -Involved in Work Permit and Maritime Modules. -Has an interest in Multimodal Module. | 1&2 | + | 4 | 4 | Involve early in design and monitor closely. | 1) Have Regular Consultations.
5 | Ministry of Planning and Sustainable Development | -Focal Point for IDB Project. -Determine quantum of funds available to Project under the Development Programme. -Interested in achievement of the Project's results. | ALL | + | 5 | 5 | Involve early in design and monitor closely. | 1) Include in all discussions with the IDB. 2) Provide regular project updates to Ministry. 3) Keep Minister of Planning informed on project performance.
6 | Ministry of Finance and Economy | -Dependent on Release of Funds. -Line Ministry for the Customs and Excise Division and Board of Inland Revenue. -Critical in Legislative Process relating to Funding, Electronic Payments and Customs Modernization. -Concerned with increased tax collection. | ALL | + | 4 | 5 | Involve early in design and monitor closely. | 1) Work with Budget Division and Treasury Solicitor Closely.
7 | Ministry of Transport | -Important Player in National Logistics Architecture. | ALL | + | 3 | 2 | Monitor. | 1) Send Regular Project Updates.
8 | ExportTT | -Player in Certificate of Origin Module and also a Training Partner. | ALL | + | 5 | 3 | Keep Informed. | 1) Send Regular Project Updates.
9 | Customs and Excise Division | - Key collaborator. - Interested in preservation of ASYCUDA system and its role/importance. - Enforcement of Customs laws. - Ensure that SEW complies with Customs laws. | ALL | + | 5 | 4 | Monitor closely and keep them in the planning process. | 1) Include in Project Steering Committee. 2) Have Regular Meetings.
10 | Port Authorities | -Instrumental in Maritime Module and Multimodal Module. -Ability to obtain real-time manifest and trade data to improve operational efficicency. | 2 | + | 4 | 4 | Monitor closely and keep them in the planning process. | 1) Include Ports in Techncial Working Groups.
11 | Front-end Users | -Important in building international inter-operabiity of System. -Concerned with legal framework for cross border exchange of trade documentation. | ALL | + | 5 | 4 | Monitor closely and keep them in the planning process.
12 | Ministry of the Attorney General | -Instrumental in Drafting of Legislation. -Critical in Preparation of Loan and Other Contracts. | ALL | + | 4 | 4 | Monitor closely and keep them in the planning process. | 1) Make available Draft Loan and Contract Documents to Solictor General's Department early. 2) Obtain Cabinet Approval early.
13 | Ministry of Legal Affairs | -Responsible for the Companies Registry. -Concerned with being able to independently control module. | 1&3 | + | 4 | 3 | Keep Informed. | 1) Keep Registrar General Updated on Project Progress.
14 | Training Partners | -Conduct Training for FE Users. -Ability to earn income from Training. | ALL | + | 5 | 2 | Keep Informed. | 1) Send Regular Project Updates.
15 | International Trading Partner | -Important in building international inter-operabiity of System. -Concerned with legal framework for cross border exchange of trade documentation. | 2 | + | 2 | 2 | Monitor. | 1) Engage on a bilateral basis and Hemispheric through Red VUCE.
16 | Existing Vendors | -Current developer of TTBizlinK Platform. -Concerned wirh protection background IPR and being able to participate in further development of System. | 1 &2 | + | 5 | 4 | Monitor closely and keep them in the planning process.
17 | Ministry of Science and Technology | -Has Responsibility for National Authentication System. -Will play a key role in National Electronic Payments Solution. | 1 | + | 2 | 2 | Keep Informed. | 1) Involve in discussions with Electronic Payments. 2) Send Regular Project updates.
18 | Trinidad and Tobago Bureau of Standards | -Key Player in Goods Clearance Process. -Interested in making sure that Bureau has necessary tools to use system. | 1 &2 | + | 5 | 4 | Monitor closely and keep them in the planning process.
19 | Ministry of Health | -Key Player in Goods Clearance Process. -Interested in making sure that staff has necessary tools to use system. | 1 &3 | + | 4 | 4 | Monitor closely and keep them in the planning process.
20 | MTIIC Staff | -Team Cohesion. -Will be concerned that increased work load do not negatively impact existing operations of SEW. | ALL | + | 5 | 4 | Monitor closely and keep them in the planning process. | 1) Conduct Team Building Sessions. 2) Recruit additional technical expertise to assist in project execution. 2) Ensure Knowledge Transfer for with recruited Consultants.
21 | Inter-Ministerial Steering Committee | -Important for Inter-Ministerial Coordination. -Concerned with timely Project Execution to reflect governmental achievement. | ALL | + | 5 | 5 | Monitor closely and keep them in the planning process. | 1) Have Semi-annual Inter-Ministerial Meetings.
22 | National Procurement Body | -Will be concerned to ensure all procurement conforms to governmental rules and regulations. | ALL | + | 3 | 5 | Keep satisfied. | 1) Obtain Technical Training on Procuurement.

## Stakeholder Matrix (hidden)
Power - Influence
Interest
0
0
6
6
5,5
4,4
TT-L1044 - Stakeholder Matrix (Power/Interest)

## Matrix
1,5,21
4,10,12,19
2,9,11,16,18,20
22
13
8
14
7
15,17
6,8
3