## PDA
INFORMATION FOR PROCUREMENT PLAN INITIAL UPLOAD ONGOING AND/OR LAST PRESENTED
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: | 2017 | 2021
2. Procurement Plan Details
Version ( 1-xxxx (Year) ) : | v1. 2017 - 2021
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Works | 15687500 | 0
Goods | 205000 | 0
Non Consulting Services | 0 | 0
Training | 45000 | 0
Operative Costs | 1550000 | 0
Consulting Services (Firms + Individuals) | 2512500 | 0
Transfers | 0 | 0
Community Participation | 0 | 0
Unassigned | 0 | 0
Total | 20000000 | 0
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
1. URBAN INTERVENTIONS | 15000000 | 0
2. RESIDENTIAL AND PRIVATE BUSINESS DEVELOPMENT | 2200000 | 0
3. INSTITUTIONAL STRENGTHENING | 1250000 | 0
PROJECT ADMINISTRATION | 1550000 | 0
Total | 20000000 | 0

## PDA DET
PROCUREMENT PLAN INITIAL LOAD INFORMATION (ONGOING AND/OR LAST PRESENTED)
WORKS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
| Construction of waterfront |  | International Competitive Bidding |  |  | 5460000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2019-12-01 | 2021-07-01
| Restoration of the Parliament building |  | International Competitive Bidding |  |  | 2850000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2017-11-01 | 2019-10-01
| Restoration of building 2 |  | International Competitive Bidding |  |  | 1187500 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2017-11-01 | 2019-10-01
| Restoration of building 3 |  | International Competitive Bidding |  |  | 1137500 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2019-09-01 | 2021-04-01
| Construction of alternative transit corridors |  | National Competitive Bidding |  |  | 1900000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2019-03-01 | 2019-08-01
| Construction of bycicle lanes |  | National Competitive Bidding |  |  | 475000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2019-06-01 | 2019-11-01
| Construction of pedestrian infrastructure |  | National Competitive Bidding |  |  | 807500 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2019-03-01 | 2019-08-01
| Construction of Housing Scheme |  | National Competitive Bidding |  |  | 935000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2018-09-01 | 2020-02-01
| Construction of Business Development Scheme |  | National Competitive Bidding |  |  | 935000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2018-09-01 | 2020-02-01
GOODS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
| Modernization of AIT systems |  | International Competitive Bidding |  |  | 200000 | 100% |  | 3. INSTITUTIONAL STRENGTHENING | Ex-Ante | 2018-01-01 | 2018-02-01
| Development of Project Management System |  | National Competitive Bidding |  |  | 5000 | 100% |  | 3. INSTITUTIONAL STRENGTHENING | Ex-Ante | 2017-04-01 | 2017-07-01
NON CONSULTING SERVICES
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Bidding Documents | Contract Signature
CONSULTING FIRMS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
| Waterfront design work |  | Quality and Cost Based Selection |  | 240000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2018-04-01 | 2018-09-01
| Waterfront construction supervision |  | Quality and Cost Based Selection |  | 300000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2019-06-01 | 2019-11-01
| Parliament rehabilitation supervision |  | Quality and Cost Based Selection |  | 150000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2017-11-01 | 2019-10-01
| Rehabilitation of building 2 supervision |  | Quality and Cost Based Selection |  | 62500 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2017-11-01 | 2019-10-01
| Design work for building 3 |  | Quality and Cost Based Selection |  | 50000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante
| Rehabilitation of building 3 supervision |  | Quality and Cost Based Selection |  | 62500 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2019-09-01 | 2021-04-01
| Alternative transit corridors construction supervision |  | Quality and Cost Based Selection |  | -100000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2019-03-01 | 2019-08-01
| Bycicle lanes construction supervision |  | Quality and Cost Based Selection |  | 25000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2019-06-01 | 2019-11-01
| Pedestrian infrastructure construction supervision |  | Quality and Cost Based Selection |  | 42500 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2019-03-01 | 2019-08-01
| PPP Model for Parking |  | Quality and Cost Based Selection |  | 150000 | 100% |  | 1. URBAN INTERVENTIONS | Ex-Ante | 2019-10-01 | 2020-03-01
| Financial Model for Pilot Housing Scheme |  | Quality and Cost Based Selection |  | 110000 | 100% |  | 2. RESIDENTIAL AND PRIVATE BUSINESS DEVELOPMENT | Ex-Ante | 2017-04-01 | 2017-10-01
| Supervision of housing construction |  | Quality and Cost Based Selection |  | 55000 | 100% |  | 2. RESIDENTIAL AND PRIVATE BUSINESS DEVELOPMENT | Ex-Ante | 2018-09-01 | 2020-02-01
| Financial Model for Pilot Business Development |  | Quality and Cost Based Selection |  | 110000 | 100% |  | 2. RESIDENTIAL AND PRIVATE BUSINESS DEVELOPMENT | Ex-Ante | 2017-04-01 | 2017-10-01
| Supervision of business development building(s) construction |  | Quality and Cost Based Selection |  | 55000 | 100% |  | 2. RESIDENTIAL AND PRIVATE BUSINESS DEVELOPMENT | Ex-Ante | 2018-09-01 | 2020-02-01
| Development of PWHS Master Plan |  | Quality and Cost Based Selection |  | 300000 | 100% |  | 3. INSTITUTIONAL STRENGTHENING | Ex-Ante | 2017-04-01 | 2017-11-01
| Development and Implementation of Tourism Plan |  | Quality and Cost Based Selection |  | 200000 | 100% |  | 3. INSTITUTIONAL STRENGTHENING | Ex-Ante | 2020-02-01 | 2021-09-01
| Development and Implementation of Communication Plan |  | Quality and Cost Based Selection |  | 500000 | 100% |  | 3. INSTITUTIONAL STRENGTHENING | Ex-Ante | 2017-04-01 | 2018-03-01
INDIVIDUAL CONSULTANTS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature
TRAINING
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Annual Training Plan (ATP) | End of Activity
| Capacity Training |  |  |  | 45000 | 100% |  |  | Ex-Ante |  | 2017-08-01
TRANSFERS
Executing Agency: | Transfer Purpose: | Additional Information: | Process Number: | Estimated Amount |  |  | Associated Component: | Estimated Number of Transfers: | Dates |  | Comments - for UCS include selection method
|  |  |  | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Contract Signature | Transfer Date