## Sheet1
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: JAMAICA |  |  |  |  | Executing agency: Ministry of Economic Growth and Job Creation |  |  |  |  | Sector: Public
Project number: JA-T1165 |  |  | Title of Project: Strengthening Jamaica's Capacity transparency requirements under the Paris Agreement
Period covered by the plan: February 2020 - December 2021
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$): N/A |  |  | Consulting services(in US$): $1,183,000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB % | Local/ other % |  |  |  | Direct Contracting
|  | Component 1 | [8 empty] | International Competitive Bidding
|  | Capacity Needs and Gaps Assessment of Institutional Enabling Environment for Transparency Related Activities | 15000 | ICQ |  | 100 |  | 2020-05-01
|  | Assessment of institutional arrangements across ministeries for transparency related activities | 55000 | ICQ |  | 100 |  | 2020-05-01 |  |  | Shopping
|  | Component 2 | [8 empty] | Least-Cost Selection
|  | Assessment of enabled technologies for the establishment of Jamaica’s domestic MRV system | 36000 | QCBS |  | 100 |  | 2020-11-01
|  | Design and implementation of national transparency process, that includes software tool to calculate estimations for the mitigation targets defined in the NDC | 325000 | QCBS |  | 100 |  | 2020-08-01
|  | Technical Expert to manage the implementation of the MRV system | 80000 | ICQ |  | 100 |  | 2020-05-01
|  | Assist in the implementation and management of the MRV system | 60000 | ICQ |  | 100 |  | 2020-05-01
|  | Climate Adaptation Mapping GIS Infrastructure | 125000 | QCBS |  | 100 |  | 2020-09-01
|  | GIS Expert for Climate Finance Mapping and Tracking | 40000 | ICQ |  | 100 |  | 2020-07-01 |  |  | Quality and Cost Based Selection
Component 3
|  | Design of Centralized Knowledge Platform for Transparency | 297000 | QCBS |  | 100 |  | 2020-12-01 |  |  | Quality Based Selection
|  | Design and delivery of national training program on IPCC GHG Software, guidelines and carbon accounting | 100000 | QCBS |  | 100 |  | 2020-12-01
|  | IT Consultant to manage the knowledge platform | 50000 | ICQ |  | 100 |  | 2021-02-01 |  |  | Selection Based on the Consultants' Qualifications
Total |  |  | 1183000 | Prepared by: Gerard Alleng |  |  | Date: November 2019
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection under a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical "or "complex "that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.