## Sheet1
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Barbados |  |  |  |  | Executing agency: IFD/FMM |  |  |  |  | Public or private sector: (indicate which applies)
Project number: BA-T1030 / BA-T1031 |  |  |  |  | Title of Project: Implementation of the Emerging & Sustainable Cities Initiative (ESCI) in the City of Bridgetown
Period covered by the plan: October 2015 - April 2016
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$):____________ |  |  |  | Consulting services(in US$):_1,200,000_
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other % |  |  |  | Direct Contracting
1 |  | Component 1 | [8 empty] | International Competitive Bidding
National Competitive Bidding
|  | Consulting services | [8 empty] | Shopping
|  | Climate change and urban development studies | 260000 | QCBS | NA | 100 | 0 | I Quarter 2014 | IV Quarter 2015 |  | Least-Cost Selection
|  | Rapid evaluation of the fiscal and financial capacity of Bridgetown | 10000 | QCBS | NA | 100 | 0 | I Quarter 2016 | III Quarter 2016 |  | Quality and Cost Based Selection
|  | Administration and analysis of a public opinion survey in the Greater Bridgetown Area | 25000 | SSS | NA | 100 | 0 | IV Quarter 2015 | I Quarter 2016
Individual consultants
|  | Support to the implementation of the ESCI methodology in Bridgetown: individual local consultant | 55000 | NICQ | NA | 100 | 0 | II Quarter 2015 | II Quarter 2016
2 |  | Component 2
National Competitive Bidding
|  | Consulting services | [8 empty] | Shopping
|  | Pre-investment studies for prioritized interventions | 472000 | QCBS | NA | 100 | 0 | II Quarter 2016 | IV Quarter 2017
|  | Administration and analysis of a travel survey for the Greater Bridgetown Area | 78000 | QCBS | NA | 100 | 0 | IV Quarter 2015 | II Quarter 2016
Ex Ante
3 |  | Component 3
National Competitive Bidding
|  | Consulting services | [8 empty] | Shopping
|  | Establishment of a monitoring system for the Greater Bridgetown Area | 100000 | QCBS | NA | 100 | 0 | IV Quarter 2015 | II Quarter 2016 |  | Ex Post
Ex Ante
4 |  | Component 4
National Competitive Bidding
|  | Non consulting services | [8 empty] | Shopping
|  | Intersectoral work for the application of the ESCI in Bridgetown | 200000 | QCBS | NA | 100 | 0 | IV Quarter 2016 | I Quarter 2017 |  | Ex Post
National System
Total |  |  | 1200000 | Prepared by: |  |  | Date: 13 October 2015
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; NICQ: National Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.