## Project Structure
Agency | Sub-Agency (If applies) | Agency's Initials
Ministry of National Security (MNS)
NOTE: 1. There may only be one Organism which coordinates the Procurement Plan information and submits it to the Bank 2. Each Sub-Organism shall upload one sheet #2 with its processes
COMPONENTS? (YES / NO) | Component's Name (list by number or letter)
YES | Social Crime and Violence Prevention in New Providence
Youth Employability and Employment Training and Strengthening of the Public Employment Services (PES)
Strengthening of the Justice Administration System
Rehabilitation and Reintegration of Offenders
NOTE: Name the components in the loan agreement; use only main components

## Procurement Plan
INFORMATION FOR PROCUREMENT PLAN INITIAL UPLOAD ONGOING AND/OR LAST PRESENTED
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: 2017
2. Procurement Plan Details
Version ( 1-2017 ) :
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Works | 4425000 | 4425000 | 4425000
Goods | 2543700 | 2543700 | 3208700
Non Consulting Services | 2587586 | 2587586 | 2562198
Training | 0 | 0
Operative Costs | 0 | 0
Consulting Services (Firms + Individuals) | 7059926 | 7059926 | #REF!
Transfers | 0 | 0
Community Participation | 0 | 0
Unassigned | 0 | 0
Total | 16616212 | 16616212
4. Methods / Levels of Performance and Process Types Deadlines | This information will be uploaded in the system during the training session.
5. Procurement Plan Details | This data depend on the investment category and is desegregated on this file's last tab

## Procurement Plan Details
WORKS
Executing Agency: | Component: | Country's political Division (Region / Department / Jurisdiction, Province) | Region | Contract Name: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency BSD) | Comments
[15 empty] | Bidding Document |  | No objection to the Documents |  | Publication |  | Opening |  | Evaluation |  | No Objection to the Evaluation |  | Contract Signing |  | End of Contract
[15 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
Component 1
2017
MNS | Component 1 |  | Caribbean | Refurbishment of Youth Centres Bain Town, Bamboo Town/Pinewood, Yellow Elder, Kemp Road, Nassau Village |  | National Competitive Bidding | 5 | 1.1 | Price Comparison for Works | Lump-Sum | 1621770 |  | Without | Planned | 2017-09-01 | N/A | 2017-09-15 | N/A | 2017-09-30 | N/A | 2017-09-16 | N/A | 2017-09-17 | N/A | 2017-09-22 | N/A | 2017-09-23 | N/A | 2018-03-01 | N/A | N/A | N/A
MNS | Component 1 |  | Caribbean | Refurbishment of Youth Centres Fox Hill and Grants Town |  | National Competitive Bidding | 2 | 1.1 | Price Comparison for Works | Lump-Sum | 653230 |  | Without | Contract in Execution | N/A | N/A | N/A | N/A | Feb-15-17 | N/A | N/A | 2016-09-20 | N/A | 2016-09-20 | N/A | 2016-09-22 | 2016-11-04 | 2016-11-04 | 2017-03-01 | N/A | (1) Warren Davis Construction; (2) Centreline Construction | (1) $328,412.50; (2) 324,817.50
MNS | Component 1 |  | Caribbean | Refurbishment of Youth Centres Centreville and Englerston |  | National Competitive Bidding | 2 | 1.1 | Price Comparison for Works | Lump-Sum | 650000 |  | Without | Planned | 2017-03-01 | N/A | 2017-03-07 | N/A | 2017-03-30 | N/A | Mar-15-17 | N/A | Mar-16-17 | N/A | 2017-03-21 | N/A | 2017-04-01 | N/A | 2017-10-01 | N/A | N/A | N/A
Component 3
2017
MNS | Component 3 |  | Caribbean | Continued Implementation of Integrated Justice System | Excavation/Cabling | National Competitive Bidding |  | 3.1.5 | Price Comparison for Works | Lump-Sum | 1500000 |  | Without | Planned | 2017-10-01 | N/A | 2017-10-07 | N/A | 2017-10-08 | N/A | Oct-30-17 | N/A | Oct-31-17 | N/A | 2017-11-01 | N/A | 2017-11-02 | N/A | 2018-05-02 | N/A | N/A | N/A
GOODS
Executing Agency: | Component (if applies) | Country's political Division (Region / Department / Jurisdiction, Province) | Region | Contract Name: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency BSD) | Comments
[15 empty] | Bidding Document |  | No objection to the Documents |  | Publication |  | Opening |  | Evaluation |  | No Objection to the Evaluation |  | Contract Signing |  | End of Contract
[15 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
Component 1
2017
MNS | Component 1 |  | Caribbean | Equipment for of Youth Centres | Laptops | National Competitive Bidding |  | 1.2.1 | Procurement of Goods | Unit Prices | 400000 |  | Without | Planned | Jan-20-17 | N/A | Feb-11-17 | N/A | N/A | N/A | Feb-3-17 | N/A | Feb-3-17 | N/A | Feb-11-17 | N/A | Feb-12-17 | N/A | Mar-12-17 | N/A | N/A | N/A
MNS | Component 1 |  | Caribbean | Furniture for Youth Centres | Furniture | Shopping |  | 1.2.3 | Procurement of Goods | Unit Prices | 50000 |  | Without | Planned | Jan-20-17 | N/A | Feb-18-17 | N/A | N/A | N/A | Feb-11-17 | N/A | Feb-11-17 | N/A | Feb-18-17 | N/A | Feb-19-17 | N/A | Mar-19-17 | N/A | N/A | N/A
MNS | Component 1 |  | Caribbean | Architectural Drafting Services | Layouts | Shopping |  | 1.2.5 | Procurement of Goods | Unit Prices | 3200 |  | Without | Contract Concluded | N/A | Sep-8-16 | N/A | N/A | N/A | N/A | N/A | Nov-21-16 | N/A | Nov-21-16 | N/A | Dec-14-16 | N/A | Dec-14-16 | N/A | Dec-31-16 | Perpetual Drafting | 3200
2018-2021
MNS | Component 1 |  | Caribbean | Marco's Law Implementation | Children Alert System (International Competitive Bidding) | National Competitive Bidding | 1 | 1.8 | Procurement of Goods | Lump-Sum | 580000 |  | Without | Planned | Jul-1-18 | N/A | Jul-7-18 | N/A | N/A | N/A | Aug-7-18 | N/A | Aug-8-18 | N/A | Aug-15-18 | N/A | Aug-16-18 | N/A | Aug-15-18 | N/A | N/A | N/A
Component 2
2017
MNS | Component 2 |  | Caribbean | Hardware for One Stop Shop |  | Shopping |  | 2.3.1 | Procurement of IT Products and/or Services | Lump-Sum | 120000 |  | Without | Planned | Jan-20-17 | N/A | Feb-11-17 | N/A | N/A | N/A | Feb-3-17 | N/A | Feb-3-17 | N/A | Feb-11-17 | N/A | Feb-12-17 | N/A | Mar-12-17 | N/A | N/A | N/A
MNS | Component 2 |  | Caribbean | Consultancy to Enhance Electronic Labour Exchange |  | Single Source Selection |  | 2.3 | Procurement of IT Products and/or Services | Lump-Sum | 60000 |  | Without | Planned | Jan-31-17 | Jan-31-17 | Feb-3-17 | Feb-2-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Feb-11-17 | N/A | Feb-10-18 | N/A | N/A | N/A
Component 3
2017
MNS | Component 3 |  | Caribbean | Enhancement of Court Reporting Unit (Equipment) |  | Shopping |  | 3.3.1 | Price Comparison for Goods | Lump-Sum | 50000 |  | Without | Planned | Mar-1-17 | N/A | Mar-14-17 | N/A | N/A | N/A | Mar-14-17 | N/A | Mar-14-17 | N/A | Mar-19-17 | N/A | Mar-20-17 | N/A | Apr-20-17 | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Enhancement of Court Reporting Unit (Furniture) |  | Shopping |  | 3.3.2 | Procurement of Goods | Lump-Sum | 150000 |  | Without | Planned | Mar-1-17 | N/A | Mar-14-17 | N/A | N/A | N/A | Mar-14-17 | N/A | Mar-14-17 | N/A | Mar-19-17 | N/A | Mar-20-17 | N/A | Apr-20-17 | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Court Reporting Unit Management Software |  | International Competitive Bidding |  | 3.3.3 | Price Comparison for Goods | Lump-Sum | 250000 |  | Without | Planned | Mar-1-17 | N/A | Mar-14-17 | N/A | N/A | N/A | Mar-14-17 | N/A | Mar-14-17 | N/A | Mar-19-17 | N/A | Mar-20-17 | N/A | Apr-20-17 | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Enhancement of Supreme Court (Equipment) |  | Shopping |  | 3.5.2 | Price Comparison for Goods | Lump-Sum | 50000 |  | Without | Planned | Mar-1-17 | N/A | Mar-14-17 | N/A | N/A | N/A | Mar-14-17 | N/A | Mar-14-17 | N/A | Mar-19-17 | N/A | Mar-20-17 | N/A | Apr-20-17 | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Enhanacement of Office of The Attorney General |  | Shopping |  | 3.7 | Price Comparison for Goods | Lump-Sum | 49000 |  | Without | Planned | Mar-1-17 | N/A | Mar-14-17 | N/A | N/A | N/A | Mar-14-17 | N/A | Mar-14-17 | N/A | Mar-19-17 | N/A | Mar-20-17 | N/A | Apr-20-17 | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Enhancement of Office of The Attorney General |  | Shopping |  | 3.7.1 | Price Comparison for Goods | Lump-Sum | 35000 |  | Without | Planned | Mar-1-17 | N/A | Mar-14-17 | N/A | N/A | N/A | Mar-14-17 | N/A | Mar-14-17 | N/A | Mar-19-17 | N/A | Mar-20-17 | N/A | Apr-20-17 | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | License to Case Law Database |  | Direct Contracting |  | 3.7.2 | Procurement of Goods | Lump-Sum | 100000 |  | Without | Planned | Mar-1-17 | N/A | Mar-7-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Mar-15-17 | N/A | N/A | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Jury Summonsing Office Enhancement |  | Shopping |  | 3.2.1 | Price Comparison for Goods | Lump-Sum | 25000 |  | Without | Planned | Mar-1-17 | N/A | Mar-14-17 | N/A | N/A | N/A | Mar-14-17 | N/A | Mar-14-17 | N/A | Mar-19-17 | N/A | Mar-20-17 | N/A | Apr-20-17 | N/A | N/A | N/A
2018-2021
MNS | Component 3 |  | Caribbean | Refurbishment of DPP's Office |  | Shopping |  | 3.4 | Price Comparison for Goods | Lump-Sum | 25000 |  | Without | Planned | Apr-1-17 | N/A | Apr-7-17 | N/A | N/A | N/A | Apr-15-17 | N/A | Apr-15-17 | N/A | Apr-20-17 | N/A | May-1-17 | N/A | Jun-1-17 | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Refurbishment of DPP's Office |  | Shopping |  | 3.4.1 | Price Comparison for Goods | Lump-Sum | 25000 |  | Without | Planned | Apr-1-17 | N/A | Apr-7-17 | N/A | N/A | N/A | Apr-15-17 | N/A | Apr-15-17 | N/A | Apr-20-17 | N/A | May-1-17 | N/A | Jun-1-17 | N/A | N/A | N/A
| Component 4 | [12 empty] | Planned
2017
MNS | Component 4 |  | Caribbean | Refurbishment of Juvenile Facilities |  | Shopping |  | 4.7 | Price Comparison for Goods | Lump-Sum | 387500 |  | Without | Planned | Feb-14-17 | N/A | Feb-28-17 | N/A | N/A | N/A | Feb-28-17 | N/A | Feb-28-17 | N/A | Mar-5-17 | N/A | Mar-6-17 | N/A | Apr-5-17 | N/A | N/A | N/A
MNS | Component 4 |  | Caribbean | Video Visititation Equipment |  | International Competitive Bidding |  | 4.1 | Price Comparison for Goods | Lump-Sum | 300000 |  | Without | Planned | N/A | N/A | N/A | Oct-28-16 | N/A | N/A | Jan-25-17 | Jan-25-17 | Jan-25-17 | Feb-11-17 | Feb-16-17 | N/A | Mar-1-17 | N/A | Mar-1-18 | N/A | N/A | N/A
MNS | Component 4 |  | Caribbean | Refurbishment of Prison Industries in Department of Corrections |  | Shopping |  | 4.4 | Price Comparison for Goods | Lump-Sum | 500000 |  | Without | Planned | Feb-14-17 | N/A | Feb-28-17 | N/A | N/A | N/A | Feb-28-17 | N/A | Feb-28-17 | N/A | Mar-5-17 | N/A | Mar-6-17 | N/A | Apr-5-17 | N/A | N/A | N/A
Lump-Sum
NON CONSULTING SERVICES
Executing Agency: | Component (if applies) | Country's political Division (Region / Department / Jurisdiction, Province) | Region | Contract Name: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [15 empty] | Bidder | Proposal Price (Currency ####) | Comments
[15 empty] | Bidding Document |  | No objection to the Documents |  | Publication |  | Opening |  | Evaluation |  | No Objection to the Evaluation |  | Contract Signing |  | End of Contract
[15 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
Component 1
2017
MNS | Component 1 |  | Caribbean | Implementation for Violence interruption Model |  | Shopping |  | 1.8 | Price Comparison | Lump-Sum | 7612 |  | Without | Contract Concluded | N/A | Sep-13-16 | N/A | Sep-13-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Sep-1-16 | N/A | Sep-1-16 | N/A | N/A
MNS | Component 1 |  | Caribbean | Supply of Sundries for Opening of Community Centres |  | Shopping |  | 1.2.8 | Price Comparison | Lump-Sum | 45317 |  | Without | Planned | N/A | N/A |  | Mar-30-17 | N/A | N/A | N/A | N/A | N/A | Mar-27-17 | N/A | Mar-30-17 | N/A | N/A | N/A | Apr-2-17
MNS | Component 1 |  | Caribbean | Supply of Sundries for Opening of Community Centres | Fox Hill | Shopping |  | 1.2.8.1 | Price Comparison | Lump-Sum | 24161 |  | Without | Contract Concluded | N/A | N/A |  | Mar-30-18 | N/A | N/A | N/A | N/A | N/A | Mar-27-18 | N/A | Mar-30-18 | N/A | N/A | N/A | Apr-2-18
MNS | Component 1 |  | Caribbean | Supply of Sundries for Opening of Community Centres | Grants Town (Quakoo Street) | Shopping |  | 1.2.8.2 | Price Comparison | Lump-Sum | 10522 |  | Without | Planned | N/A | N/A | Apr-10-17 | N/A | N/A | N/A | N/A | N/A | N/A | Apr-7-17 | N/A | Apr-10-17 | N/A | N/A | N/A | Apr-18-17
MNS | Component 1 |  | Caribbean | Supply of Sundries for Opening of Community Centres | Nassau Village/Bain Town | Shopping |  | 1.2.8.3 | Price Comparison | Lump-Sum | 20000 |  | Without | Planned | N/A | N/A | May-16-17 | N/A | N/A | N/A | N/A | N/A | May-10-17 | N/A | May-16-16 | N/A | N/A | N/A | N/A | N/A
MNS | Component 1 |  | Caribbean | Training for Violence Interruptors |  | Shopping |  | 1.5 | Price Comparison | Lump-Sum | 100000 |  | Without | Planned | Jan-23-17 | N/A | Jan-30-17 | N/A | Jan-31-17 | N/A | Jan-27-17 | N/A | Jan-27-17 | N/A | Jan-31-17 | N/A | Jan-31-17 | N/A | Feb-28-17 | N/A | N/A | N/A
2018-2021
MNS | Component 1 |  | Caribbean | Operational Capacity Training on Community Mobilization |  | International Competitive Bidding |  | 1.4.1 | Price Comparison | Lump-Sum | 32000 |  | Without | Planned | Jul-1-18 | N/A | Jul-7-18 | N/A | N/A | N/A | Jul-20-18 | N/A | Jul-21-18 | N/A | Jul-26-18 | N/A | Aug-1-18 | N/A | Aug-1-19 | N/A | N/A | N/A
MNS | Component 1 |  | Caribbean | Sexual Assault Prevention Training |  | International Competitive Bidding |  | 1.7 | Price Comparison | Lump-Sum | 94000 |  | Without | Planned | Jul-1-18 | N/A | Jul-7-18 | N/A | N/A | N/A | Jul-20-18 | N/A | Jul-21-18 | N/A | Jul-26-18 | N/A | Aug-1-18 | N/A | Aug-1-19 | N/A | N/A | N/A
MNS | Component 1 |  | Caribbean | Parenting Conflict Resolution and Mediation Training Sessions for Community Members |  | International Competitive Bidding |  | 1.4 | Price Comparison | Lump-Sum | 100000 |  | Without | Planned | Jul-1-18 | N/A | Jul-7-18 | N/A | N/A | N/A | Jul-20-18 | N/A | Jul-21-18 | N/A | Jul-26-18 | N/A | Aug-1-18 | N/A | Aug-1-19 | N/A | N/A | N/A
MNS | Component 1 |  | Caribbean | School training program: Drug abuse model and PAYA model adaptation |  | Shopping |  | 1.6 | Price Comparison | Lump-Sum | 200000 |  | Without | Planned | Jul-1-18 | N/A | Jul-7-18 | N/A | N/A | N/A | Jul-20-18 | N/A | Jul-21-18 | N/A | Jul-26-18 | N/A | Aug-1-18 | N/A | Aug-1-19 | N/A | N/A | N/A
| Component 2 |  |  |  |  | Shopping
2017
MNS | Component 2 |  | Caribbean | Soft and Technical Skills Training for Youth At-Risk (ages 15-29) in the "training for employment" in New Providence |  | Shopping |  | 2.1 | Price Comparison | Lump-Sum | 1000000 |  | Without | Planned | Oct-1-17 | N/A | Oct-7-17 | N/A | N/A | N/A | Nov-7-17 | N/A | Nov-8-17 | N/A | Nov-15-17 | N/A | Nov-20-17 | N/A | Nov-20-19 | N/A | N/A | N/A
MNS | Component 2 |  | Caribbean | Soft Skills Training for Youth At-Risk (ages 15-29) in the "training for employability" in New Providence |  | Shopping |  | 2.1 | Price Comparison | Lump-Sum | 12000 |  | Without | Contract Concluded | Oct-1-17 | N/A | Oct-7-17 | N/A | N/A | N/A | Nov-7-17 | N/A | Nov-8-17 | N/A | Nov-15-17 | N/A | Nov-20-17 | N/A | Nov-20-19 | N/A | N/A | N/A
Component 3
2017
MNS | Component 3 |  | Caribbean | Training of Stakeholders in New Integrated Justice System |  | Shopping |  | 3.1 | Price Comparison | Lump-Sum | 40000 |  | Without | Planned | Apr-30-17 | N/A | May-6-17 | N/A | N/A | N/A | May-15-17 | N/A | May-16-17 | N/A | May-30-17 | N/A | Jun-5-17 | N/A | Jun-5-18 | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Case Management Training for Judges and Prosecutors |  | Shopping |  | 3.1.2 | Price Comparison | Lump-Sum | 60000 |  | Without | Planned | Apr-30-17 | N/A | May-6-17 | N/A | N/A | N/A | May-15-17 | N/A | May-16-17 | N/A | May-30-17 | N/A | Jun-5-17 | N/A | Jun-5-18 | N/A | N/A | N/A
2018-2021
MNS | Component 3 |  | Caribbean | DPP Knowledge Exchange with UK Law Enforcement Agencies |  | Shopping |  | 3.4.2 | Price Comparison | Lump-Sum | 64000 |  | Without | Planned | Mar-30-18 | N/A | Apr-6-18 | N/A | N/A | N/A | Apr-20-18 | N/A | Apr-21-18 | N/A | Apr-26-18 | N/A | Apr-30-18 | N/A | May-1-18 | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Training of Prosecutors in DPP Office |  | Shopping |  | 3.4.4 | Price Comparison | Lump-Sum | 26586 |  | Without | Ongoing | Mar-30-18 | N/A | Apr-6-18 | N/A | N/A | N/A | Apr-20-18 | N/A | Apr-21-18 | N/A | Apr-26-18 | N/A | Apr-30-18 | N/A | May-1-18 | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Advocacy and Ethics Training for Prosecutors and, PDO |  | Shopping |  | 3.4.3 | Price Comparison | Lump-Sum | 70000 |  | Without | Planned | Mar-30-18 | N/A | Apr-6-18 | N/A | N/A | N/A | Apr-20-18 | N/A | Apr-21-18 | N/A | Apr-26-18 | N/A | Apr-30-18 | N/A | May-1-18 | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Knowledge Exchange in Trinidad and Tobago for Observation and Assessment of Family Court (Drug Rehabilitation Unit) |  | Shopping |  | 3.4.5 | Price Comparison | Lump-Sum | 12000 |  | Without | Planned | Mar-30-18 | N/A | Apr-6-18 | N/A | N/A | N/A | Apr-20-18 | N/A | Apr-21-18 | N/A | Apr-26-18 | N/A | Apr-30-18 | N/A | May-1-18 | N/A | N/A | N/A
Component 4
MNS | Component 4 |  | Caribbean | Training of DOC & DRWS staff certified in Rehabilitation Model |  | Shopping |  | 4.5 | Price Comparison | Lump-Sum | 448000 |  | Without | Planned | Oct-1-17 | N/A | Oct-7-17 | N/A | N/A | N/A | Oct-30-17 | N/A | Nov-1-17 | N/A | Nov-5-17 | N/A | Nov-10-17 | N/A | Nov-15-17 | N/A | N/A | N/A
MNS | Component 4 |  | Caribbean | Inmates Trained and Certified |  | Shopping |  | 4.3 | Price Comparison | Lump-Sum | 390000 |  | Without | Planned | Dec-1-17 | N/A | Dec-7-17 | N/A | N/A | N/A | Dec-30-17 | N/A | Jan-7-18 | N/A | Jan-15-18 | N/A | Jan-20-18 | N/A | Feb-1-18 | N/A | N/A | N/A
MNS | Component 4 |  | Caribbean | Study Tour to Panama Juvenile Rehabilitation Model Plan |  | Shopping |  | 4.1.2 | Price Comparison | Lump-Sum | 15000 |  | Without | Planned | April-1-17 | N/A | April-7-17 | N/A | N/A | N/A | Apr-15-17 | n/a | Apr-20-17 | N/A | Apr-25-17 | N/A | May-1-17 | n/a | May-15-17 | N/A | N/A | N/A
CONSULTING FIRMS
Executing Agency: | Component (if applies) | Country's political Division (Region / Department / Jurisdiction, Province) | Region | Contract Name: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [21 empty] | Short List Members | Technical Score Assigned | Evaluated Price Proposal (Currency ####) | Combined Score | Comments
[14 empty] | Expression of Interest Notice |  | RFP and Short List |  | No Objection to RFP and Short List |  | RFP Submission |  | Opening |  | Technical Evaluation |  | No Objection to the Technical Evaluation |  | Final Evaluation and Negotiation |  | No Objection to the Contract |  | Contract Signing |  | End of Contract
[14 empty] | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
2017
MNS | Component 1 |  | Caribbean | Consultancy to design and implement public campaigns for awareness, for awareness, attitude, and behavior change to prevent inter-personal violence for individuals |  | Quality and Cost Based Selection | 1.9 | Request for Proposals and Terms of Reference | Lump-Sum | 350000 |  | Without | Planned | Feb-14-17 | N/A | Feb-28-17 | N/A | Mar-5-17 | N/A | Mar-6-17 | N/A | Apr-6-17 | N/A | Apr-6-17 | N/A | Apr-9-17 | N/A | Apr-13-17 | N/A | Apr-18-17 | N/A | May-1-17 | N/A | May-1-19 | N/A | N/A | N/A | N/A | N/A | N/A
MNS | Component 1 |  | Caribbean | Training for Violence Interruptors |  | Single Source Selection | 1.5 | Terms of Reference | Lump-Sum | 100000 |  | Without | Planned | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Nov-19-16 | N/A | Dec-5-16 | N/A | Dec-6-16 | N/A | Dec-5-16 | N/A | Dec-6-16 | Feb-4-17 | N/A | N/A | N/A | N/A | N/A | N/A
MNS | Component 1 |  | Caribbean | Graphic Design Services |  | Least-Cost Selection | 1.2.7 | Terms of Reference | Lump-Sum | 1000 |  | Without | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Jan-27-17 | N/A | Jan-27-17 | N/A | Feb-2-17 | N/A | Feb-3-17 | N/A | Feb-8-17 | N/A | N/A | N/A | Mar-30-17 | N/A | N/A | N/A | N/A | N/A | N/A
2018-2021
MNS | Component 1 |  | Caribbean | Sexual Assault Prevention Training |  | Quality and Cost Based Selection | 1.7 | Request for Proposals and Terms of Reference | Lump-Sum | 30000 |  | Without | Planned | Jun-1-18 | N/A | Jul-1-18 | N/A | N/A | N/A | Aug-1-18 | N/A | Aug-2-18 | N/A | Aug-2-18 | N/A | Aug-7-18 | N/A | Aug-30-18 | N/A | Sep-5-18 | N/A | Sep-15-18 | N/A | Sep-15-19 | N/A | N/A | N/A | N/A | N/A | N/A
MNS | Component 1 |  | Caribbean | School training program: Drug abuse model and PAYA model adaptation |  | Quality and Cost Based Selection | 1.6 | Request for Proposals and Terms of Reference | Lump-Sum | 265000 |  | Without | Planned | Jun-1-18 | N/A | Jul-1-18 | N/A | N/A | N/A | Aug-1-18 | N/A | Aug-2-18 | N/A | Aug-2-18 | N/A | Aug-7-18 | N/A | Aug-30-18 | N/A | Sep-5-18 | N/A | Sep-15-18 | N/A | Sep-15-19 | N/A | N/A | N/A | N/A | N/A | N/A
Component 2
2017
MNS | Component 2 |  | Caribbean | Soft and Technical Skills Training for Youth At-Risk (ages 15-29) in the "training for employment" in New Providence |  | Quality and Cost Based Selection | 2.1 | Request for Proposals and Terms of Reference | Lump-Sum | 2500000 |  | Without | Planned | Sep-1-17 | N/A | Oct-1-17 | N/A | N/A | N/A | Oct-30-17 | N/A | Oct-31-17 | N/A | Oct-31-17 | N/A | Nov-7-17 | N/A | Nov-30-17 | N/A | Dec-5-17 | N/A | Dec-15-17 | N/A | Dec-15-19 | N/A | N/A | N/A | N/A | N/A | N/A
MNS | Component 2 |  | Caribbean | Soft Skills Training for Youth At-Risk (ages 15-29) in the "training for employability" in New Providence |  | Quality and Cost Based Selection | 2.1 | Request for Proposals and Terms of Reference | Lump-Sum | 34530 |  | Without | Planned | Sep-1-17 | N/A | Oct-1-17 | N/A | N/A | N/A | Oct-30-17 | N/A | Oct-31-17 | N/A | Oct-31-17 | N/A | Nov-7-17 | N/A | Nov-30-17 | N/A | Dec-5-17 | N/A | Dec-15-17 | N/A | Dec-15-19 | N/A | N/A | N/A | N/A | N/A | N/A
MNS | Component 2 |  | Caribbean | Soft Skills Training for Youth At-Risk (ages 15-29) in the "training for employability" in New Providence |  | Quality and Cost Based Selection | 2.1 | Terms of Reference | Lump-Sum | 12000 |  | With | Contract Concluded | Sep-25-16 | Sep-28-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Nov-25-16 | N/A | N/A | N/A | 2017-12-16 | N/A | N/A | N/A | N/A | N/A
Component 3
2018-2021
MNS | Component 3 |  | Caribbean | Update to Real Time Stenographer Software |  | CQS | 3.7.5 | Request for Proposals and Terms of Reference | Lump-Sum | 30000 |  | Without | Planned | Mar-1-17 | N/A | Apr-1-17 | N/A | N/A | N/A | Apr-30-17 | N/A | May-1-17 | N/A | May-1-17 | N/A | May-7-17 | N/A | May-30-17 | N/A | Jun-5-17 | N/A | Jun-15-17 | N/A | Jun-15-18 | N/A | N/A | N/A | N/A | N/A | N/A
Component 4
2017
MNS | Component 4 |  | Caribbean | Implementation of Rehabilitation Model Plan for Inmates |  | Quality and Cost Based Selection | 4.1 | Request for Proposals and Terms of Reference | Lump-Sum | 100000 |  | Without | Planned | Mar-1-17 | N/A | Apr-1-17 | N/A | N/A | N/A | Apr-30-17 | N/A | May-1-17 | N/A | May-1-17 | N/A | May-7-17 | N/A | May-30-17 | N/A | Jun-5-17 | N/A | Jun-15-17 | N/A | Jun-15-18 | N/A | N/A | N/A | N/A | N/A | N/A
MNS | Component 4 |  | Caribbean | Design and Implementation of Rehabilitation Model Plan for Juvenile Offenders |  | Quality and Cost Based Selection | 4.1.1 | Request for Proposals and Terms of Reference | Lump-Sum | 350000 |  | Without | Planned | Mar-1-17 | N/A | Apr-1-17 | N/A | N/A | N/A | Apr-30-17 | N/A | May-1-17 | N/A | May-1-17 | N/A | May-7-17 | N/A | May-30-17 | N/A | Jun-5-17 | N/A | Jun-15-17 | N/A | Jun-15-18 | N/A | N/A | N/A | N/A | N/A | N/A
MNS | Component 4 |  | Caribbean | Design and Implementation of Case Management Intake and Monitoring System |  | Quality and Cost Based Selection | 4.9 | Request for Proposals and Terms of Reference | Lump-Sum | 425000 |  | Without | Planned | Mar-1-17 | N/A | Apr-1-17 | N/A | N/A | N/A | Apr-30-17 | N/A | May-1-17 | N/A | May-1-17 | N/A | May-7-17 | N/A | May-30-17 | N/A | Jun-5-17 | N/A | Jun-15-17 | N/A | Jun-15-18 | N/A | N/A | N/A | N/A | N/A | N/A
INDIVIDUAL CONSULTANTS
Executing Agency: | Component (if applies) | Country's political Division (Region / Department / Jurisdiction, Province) | Region | Contract Name: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Estimated Number of Consultants: | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [5 empty] | Consultant's Name | Period |  | Title | Comments
[14 empty] | No Objection to the TORs |  | Hiring Deadline |  | End of Activity |  |  | From | Until
[14 empty] | Estimated | Real | Estimated | Real | Estimated | Real
Component 1
2017
MNS | Component 1 |  | Caribbean | Consultancy to Design and implement (one per community) needs and asset assessment |  | Comparison of Qualifications - National Individual Consultant | 1.1 | Lump-Sum | 120000 | 1 |  | Without | Contract Concluded | N/A | Jul-1-16 | N/A | N/A | Oct-21-16 | Dec-19-16 | Gabriella Fraser | Aug-22-16 | Dec-19-16
MNS | Component 1 |  | Caribbean | Quantity Surveyor |  | Comparison of Qualifications - National Individual Consultant | 1.2.6 | Lump-Sum | 48000 | 1 |  | Without | Ongoing | n/a | Jan-30-16 | N/A | N/A | 2017-12-18 | N/A | Adrian Rollins | Feb-1-17 | Jan-31-18
Component 2
2017
MNS | Component 2 |  | Caribbean | Consultancy to Support Public Employment Service Engagement to Employers |  | Selection Based on the Consultants' Qualifications | 2.3 | Terms of Reference | 60000 | 1 |  | Without | Planned | Feb-1-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MNS | Component 2 |  | Caribbean | Youth At-Risk Program Coordinator |  | Selection Based on the Consultants' Qualifications | 2.1.1 | Terms of Reference | 161250 | 1 |  | Without | Contract in Execution | N/A | Aug-17-16 | N/A | N/A | Aug-16-2021 | N/A | Chet Pratt | Sep-1-16 | Sep-1-19
MNS | Component 2 |  | Caribbean | Youth Program Skills Survey Execution |  | Selection Based on the Consultants' Qualifications | 2.2 | Terms of Reference | 43000 | 1 |  | Without | Planned | Feb-1-17 | N/A | Mar-1-17 | N/A | Mar-1-18 | N/A | N/A | N/A | N/A
MNS | Component 2 |  | Caribbean | Youth Program Clerks |  | Selection Based on the Consultants' Qualifications | 2.1.2 | Terms of Reference | 21840 | 2 |  | Without | Planned | Feb-1-17 | N/A | Mar-1-17 | N/A | Mar-1-18 | N/A | N/A | N/A | N/A
Component 3
2017
MNS | Component 3 |  | Caribbean | Current Assessment of Component Three (3) Needs |  | Single Source Selection | 3.1.4 | Terms of Reference | 13196 | 1 |  | Without | Contract Concluded | N/A | Jun-17-16 | N/A | N/A | N/A | Jun-25-16 | Linda Dobbs | Jun-20-16 | Jun-25-16
MNS | Component 3 |  | Caribbean | Monitoring, Evaluation and Knowledge Management |  | QCNI | 3.7.4 | Terms of Reference | 70000 | 1 |  | Without | Ongoing | N/A | Jan-17-17 | N/A | N/A | feb-1-17 | jan-31-18 | Kelsie Dorsett | Feb-1-17 | Jan-31-18
MNS | Component 3 |  | Caribbean | Integrated Justice System Training |  | Selection Based on the Consultants' Qualifications | 3.1 | Terms of Reference | 50000 | 1 |  | Without | Planned | Feb-15-17 | n/a | Mar-15-17 | n/a | Mar-15-18 | n/a | n/a | n/a | n/a
MNS | Component 3 |  | Caribbean | Management of Jury Summonsing System |  | QCBS | 3.1 | Terms of Reference | 250000 | 1 |  | Without | Planned | Feb-15-17 | n/a | Mar-15-17 | n/a | Mar-15-18 | n/a | n/a | n/a | n/a
MNS | Component 3 |  | Caribbean | Management of Court Reporting Unit |  | Selection Based on the Consultants' Qualifications | 3.3 | Terms of Reference | 80000 | 1 |  | Without | Planned | Jun-1-17 | n/a | Jul-1-17 | n/a | Jul-1-18 | n/a | n/a | n/a | n/a
MNS | Component 3 |  | Caribbean | Oversight Case Management Strategy Rolled Out |  | Single Source Selection | 3.1.1 | Terms of Reference | 280000 | 1 |  | Without | Planned | Jul-1-17 | n/a | Aug-1-17 | n/a | Aug-1-18 | n/a | n/a | n/a | n/a
MNS | Component 3 |  | Caribbean | Reduction of Historic Backlog |  | Selection Based on the Consultants' Qualifications | 3.5 | Terms of Reference | 95132 | 1 |  | Without | Planned | Mar-1-17 | n/a | Apr-1-17 | n/a | Apr-1-18 | n/a | n/a | n/a | n/a
MNS | Component 3 |  | Caribbean | Drug Rehabilitation Court Assessment |  | Selection Based on the Consultants' Qualifications | 3.6.1 | Terms of Reference | 100000 | 1 |  | Without | Planned | Jun-1-17 | n/a | Jul-1-17 | n/a | Jul-1-18 | n/a | n/a | n/a | n/a
MNS | Component 3 |  | Caribbean | Family Court Assessment |  | Selection Based on the Consultants' Qualifications | 3.6 | Terms of Reference | 100000 | 1 |  | Without | Planned | Jun-1-17 | n/a | Jul-1-17 | n/a | Jul-1-18 | n/a | n/a | n/a | n/a
MNS | Component 3 |  | Caribbean | Office of The Attorney General IT Assessment |  | Selection Based on the Consultants' Qualifications | 3.7.1 | Terms of Reference | 50000 | 1 |  | Without | Planned | Jun-1-17 | n/a | Jul-1-17 | n/a | Jul-1-18 | n/a | n/a | n/a | n/a
MNS | Component 3 |  | Caribbean | Communications Strategy OAG |  | Selection Based on the Consultants' Qualifications | 3.1 | Terms of Reference | 150000 | 1 |  | Without | Planned | Jun-1-17 | n/a | Jul-1-17 | N/A | Jul-1-18 | n/a | n/a | n/a | n/a
MNS | Component 3 |  | Caribbean | Component Three (3) Coordinator |  | Single Source Selection | 3.7.6 | Terms of Reference | 50000 | 1 |  | Without | Planned | Jun-1-17 | n/a | Jul-1-17 | n/a | Jul-1-18 | n/a | n/a | n/a | n/a
2018-2021
MNS | Component 3 |  | Caribbean | Training of Registrar and deputies on electronic Jury Selection System |  | Single Source Selection | 3.2 | Terms of Reference | 2500 | 1 |  | Without | Planned | Mar-1-18 | N/A | Apr-1-18 | N/A | Apr-1-19 | N/A | N/A | N/A | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Design and implementation of pilot listing system in the Supreme Court including training |  | Selection Based on the Consultants' Qualifications | 3.5.1 | Terms of Reference | 62000 | 1 |  | Without | Planned | Mar-1-18 | N/A | Apr-1-18 | N/A | Apr-1-19 | N/A | N/A | N/A | N/A | N/A | N/A
MNS | Component 3 |  | Caribbean | Training of Prosecutors in DPP Office |  | Single Source Selection | 3.4 | Terms of Reference | 7225 | 1 |  | Without | Contract Concluded | N/A | Nov-10-16 | Nov-1-16 | Nov-1-16 | Nov-20-16 | Nov-20-16 | Desiree Artesi | Nov-1-16 | Nov-20-16 | N/A | N/A
Component 4
MNS | Component 4 |  | Caribbean | Component Four (4) Coordinator |  | Selection Based on the Consultants' Qualifications | 4 | Terms of Reference | 50000 | 1 |  | Without | Planned | Feb-1-17 | N/A | Mar-31-17 | N/A | Apr-1-20 | N/A | N/A | N/A | N/A | N/A | N/A
TRAINING
Executing Agency: | Component (if applies) | Country's political Division (Region / Department / Jurisdiction, Province) | Region | Contract Name: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) | [5 empty] | Detail | Amount (Currency ###) | Comments
[14 empty] | Annual Training Plan (ATP) |  | No Objection to the ATP |  | End of Activity
[14 empty] | Estimated | Real | Estimated | Real | Estimated | Real
Lump-Sum
TRANSFERS
Executing Agency: | Component (if applies) | Country's political Division (Region / Department / Jurisdiction, Province) | Region | Transfer Purpose: | Additional Information: | Process Number: | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Estimated Number of Transfers: | Process Status (Select one of the options): | Dates (If it does not apply, use N/A) |  |  |  | Detail | Amount (Currency ###) | Comments
[12 empty] | Contract Signing / Transfer Award Agreement |  | Transfer Date
[12 empty] | Estimated | Real | Estimated | Real

## Listas_Opciones_de_Referencia (hidden)
LISTAS DE OPCIONES DE DATOS DE REFERENCIA DE CAMPOS CON VALORES PREDEFINIDOS
Versión de Normas de Adquisición (BID): | Versión de Normas de Adquisición (BM):
Enero 1995. Políticas Básicas y Procedimientos de Adquisiciones del BID (Bienes y Obras) (GP-118) | Enero 1995. Edición revisada Septiembre 1997.
Enero 2005. Políticas para la Adquisición de Bienes y Obras financiados por el Banco Interamericano de Desarrollo (GN-2349-4) | Enero 1995. Edición revisada Enero 1999.
Febrero 2006. Políticas para la Adquisición de Bienes y Obras financiados por el Banco Interamericano de Desarrollo (GN-2349-6) | Mayo 2004.
Julio 2006. Políticas para la Adquisición de Bienes y Obras financiados por el Banco Interamericano de Desarrollo (GN-2349-7) | Mayo 2004. Edición revisada Octubre 2006.
Versión de Normas de Consultoría (BID): | Versión de Normas de Consultoría (BM):
Febrero 2004. Políticas y Procedimientos para la Adquisición de Servicios de Consultoría (GN-2220-10) | Enero 1997. Edición revisada Septiembre 1997.
Enero 2005. Políticas para la Selección y Contratación de Consultores financiados por el Banco Interamericano de Desarrollo (GN-2350-4) | Enero 1997. Edición revisada Enero 1999.
Febrero 2006. Políticas para la Selección y Contratación de Consultores financiados por el Banco Interamericano de Desarrollo (GN-2350-6) | Enero 1997. Edición revisada Mayo 2002.
Julio 2006. Políticas para la Selección y Contratación de Consultores financiados por el Banco Interamericano de Desarrollo (GN-2350-7) | Mayo 2004.
Mayo 2004. Edición revisada Octubre 2006.
Categoría de Inversión :
Obras
Bienes
Servicios de no consultoría
Consultoría Firmas
Consultoría Individuos
Capacitación
Gastos Operativos
Subproyectos Comunitarios
TRANSFERENCIAS
Subproyectos
Subsidios
Cápitas
No asignados
Método de Adquisición :
Comparación de precios
Licitación Pública Nacional
Contratación Directa
Licitación Internacional Limitada
Licitación Pública Internacional
Licitación Pública Internacional con Precalificación
Licitación Pública Internacional en 2 etapas
Licitación Pública Internacional por Lotes
Según Normativa Local
Método de Selección :
3 CVs
Contratación Directa
Recontratación
Selección basada en el menor costo
Selección Basada en la Calidad
Selección Basada en la Calidad y Costo
Selección basada en las calificaciones de los consultores
Selección Basado en Presupuesto Fijo
Selección con base en una sola fuente
Documento Base :
Documento | Categoría
Adq. libros de textos y material de lectura | Bienes
Adquisición de Bienes | Bienes
Adquisición de Bienes - Sector Salud | Bienes
Adquisición de Servicios de no consultoría | Servicios de No Consultoría
Comparación de Precios para Bienes | Bienes
Comparación de Precios para Obras | Obras
Contratación de obras | Obras
Contratación de Obras Mayores - Derecho Civil | Obras
Contratación de Obras Menores | Obras
Contratación de obras y servicios basado en resultados | Obras
Doc. de precalificación para construcción de obras | Obras
Especificaciones Técnicas | Bienes
Solicitud Estándar de Propuestas | Consultoría - Firmas
Suministro e instalación de plantas y equipos | Bienes
Suministro e instalación de sist. de información | Bienes
Términos de Referencia | Consultoría - Firmas
Forma de Contrato :
Forma | Categoría
Llave en mano | Bienes
Llave en mano | Obras
Locación de Obra | Consultoría - Individuos
Locación de Obra (Suma Alzada) | Servicios de No Consultoría
Locación de Servicio (Basado en el Tiempo) | Consultoría - Individuos
Locación de Servicios | Servicios de No Consultoría
Precios Unitarios | Obras
Precios Unitarios | Bienes
Suma Alzada | Bienes
Suma alzada | Obras
Suma global | Consultoría - Firmas
Suma global | Servicios de No Consultoría
Suma global + gastos reembolsables | Consultoría - Firmas
Tiempo Trabajado | Consultoría - Firmas
Estado del Proceso :
Previsto
Proceso en curso
Relicitación
Proceso Cancelado
Declaración de Licitación Desierta
Rechazo de Ofertas
Contrato En Ejecución
Contrato Terminado