## Operation Profile_1
PMR Operational Report
Operation Number | UR-L1016 |  | Chief of Operations Validation Date
Year- PMR Cycle |  |  | Division Chief Validation Date
Last Update |  |  | Country Representative Validation Date
PMR Validation Stage |  |  | Current Validated Classification
Basic Data
Operation Profile
Operation Name | Support for Agricultural Public Management |  | Loan Number |  |  | 2182/OC-UR, 2182/OC-UR-1
|  |  | Sector/Subsector |  |  | AG - AGRICULTURE AND RURAL DEVELOPMENT
Executing Agency | MINISTERIO DE GANADERIA Y AGRICULTURA, MINISTERIO DE GANADERIA Y AGRICULTURA |  | Overall Stage |  |  | Closed
Team Leader | HINTZE, LUIS HERNANDO |  | Country |  |  | URUGUAY
Operation Type | Loan Operation |  | PMR required |  |  | YES
Lending Instrument | Investment Loan |  | Convergence related Operation(s)
Borrower | REPUBLICA ORIENTAL DE URUGUAY
Events Data |  | Objective
Supervision |  | The goal of the Program is to improve the competitiveness of the agricultural producers of Uruguay. The purpose is to achieve a more effective and efficient public administration of the agricultural sector.
Signature | 2010-02-09
Ratification
Legal effectiveness | 2010-02-09 | Environmental and Social Safeguards |  |  | Expense Categories by Loan Contract (cumulative values)
Total Eligibility |  | Impacts Category |  | B | Was/Were the objective(s) of this operation reformulated? |  |  |  | NO
Partial Eligibility | 2010-07-15 | Risk |  |  | Date of approval
First Disbursement | 2010-07-21 | Safeguard Performance Rating
Original Disbursement Expiration | 2016-07-31 | Safeguard Performance Rating - Rationale
Current Disbursement Expiration | 2016-07-31 | Financial Data
Preparation |  | Item | Total Cost and Source |  |  |  |  | Available Funds (US$)
On pipeline | 2005-06-23 |  | Original IDB | Current IDB | Local Counterpart | Co-Financing / Country | Total Original Cost | Current IDB | Disb. Amount to Date | % Disb | Undisbursed Amount
Start date | 2008-01-31
ERM
PP Approved | 2008-03-24
POD Approved | 2009-04-17
DLP Approved by OPC | 2009-04-28
Negotiation | 2009-08-05
Operation Approved | 2009-09-09
Development Effectiveness Matrix |  | Expense Categories by Loan Contract (cumulative values)
Economic Analysis
Undefined | Yes
Cost benefit analysis | No
Cost effectiveness analysis | No
General economic analysis (Economic rate of return) | No
Evaluation
Undefined | Yes
Random assignment | No
Non-experimental method | No
Ex-post cost benefit analysis | No
Ex-post cost effectiveness analysis | No
Before/after or With/without comparison | No
Please note that the Overall Stage represents the stage of the operation at the time of this report’s publication, which might not necessarily match the stage of the operation during the PMR Cycle to which the report pertains
Developed by ITE/ITO |  |  |  | - 1 - |  |  | Printed on: Nov 19, 2018 9:07:29 AM

## data_Operation Profile_1_1 (hidden)
| Disbursed | Undisbursed
SEGUIM. EVALUACION Y AUDITORIA 03000000 | 29907.14 | 0
COSTOS DIRECTOS 02000000 | 9655135.32 | 0
ADMINISTRACION DEL PROGRAMA 01000000 | 745069.66 | 0

## Impacts_2
RESULTS MATRIX
IMPACTS
Impact Nbr. 1: Mejorar la competitividad del secotr agropecuario del país, para garantizar la seguridad alimentaria y mantener y ampliar los mercados de exportación
Observation:
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
1.1 | Productividad agropecuaria incrementada |  | % aumento | 0 | 2010 | P | -1
[6 empty] | P(a) | 5
[6 empty] | A | -1
Details
Means of verification: DIEA - FAOSTAT
Observations:
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
1.2 | Volumen de exportaciones |  | % aumento | 0 | 2010 | P | -1
[6 empty] | P(a) | 10
[6 empty] | A | -1
Details
Means of verification: Banco Central
Observations:
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
1.3 | Valor de las exportaciones |  | % aumento | 0 | 2010 | P | -1
[6 empty] | P(a) | 5
[6 empty] | A | -1
Details
Means of verification: Banco Central
Observations:
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Developed by ITE/ITO |  |  |  | - 2 - | Printed on: Nov 19, 2018 9:07:29 AM

## Outcomes_3
RESULTS MATRIX
OUTCOMES
Outcome Nbr. 1: Gestión del Ministerio de Ganadería, Agricultura y Pesca (MGAP) mejorada
Observation:
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
1.1 | Tiempo de respuesta a 5 trámites prioritarios |  | días | 5 | 2010 | P | 0.001
[6 empty] | P(a) | 0
[6 empty] | A | 1.4
Details
Means of verification: registros adminiatrtivos del MSGP
Observations: Las líneas de base requieren ser calculadas para considerar todos los procesos que se estarán optimizando por intervención del Programa. Considerando que la línea de base no fue levantada en su momento, se incluirá como una actividad de la evaluación final la búsqueda de información que permita evaluar lo alcanzado respecto a este resultado.
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
1.2 | Sistema de gestión del MGAP basado en prioridades, estrategias y resultados |  | sistema | 0 | 2010 | P | 0.001
[6 empty] | P(a) | 1
[6 empty] | A | 1
Details
Means of verification: medición ad-hoc
Observations: En la línea de base el Sistema de gestión se basaba en la ejecución de actividades
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Outcome Nbr. 2: Gestión de los servicios sanitarios adecuada a estándares nacionales e internacionales, con énfasis en el área de barreras sanitarias y servicios de laboratorio
Observation:
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
2.1 | Competencia de los paraprofesionales de la Dirección General de Servicios Ganaderos (DGSG) |  | indice | 3 | 2008 | P | 4
[6 empty] | P(a) | 4
[6 empty] | A | 3
Details
Means of verification: Auditoría independiente
Observations: Metodología DVE, PVS o similar - Organización Mundial de Sanidad Animal OEI
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
2.2 | Recursos Físicos de la DGSG |  | indice | 4 | 2008 | P | 5
[6 empty] | P(a) | 5
[6 empty] | A | 4
Details
Means of verification: Auditoría independiente
Observations: Metodología DVE, PVS o similar - Organización Mundial de Sanidad Animal OEI
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
2.3 | Calidad de Laboratorios de la DGSG |  | indice | 4 | 2008 | P | 5
[6 empty] | P(a) | 5
[6 empty] | A | 3
Details
Means of verification: Auditoría independiente
Observations: Metodología DVE, PVS o similar - Organización Mundial de Sanidad Animal OEI
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
2.4 | Comunicación de la DGSG |  | indice | 4 | 2008 | P | 5
[6 empty] | P(a) | 5
[6 empty] | A | 4
Details
Means of verification: Auditoría independiente
Observations: Metodología DVE, PVS o similar - Organización Mundial de Sanidad Animal OEI
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
2.5 | Medidas sanitarias y procedimientos aplicados científicamnete en la Dirección General de Servicios Agrícolas (DGSA) |  | % | 50 | 2006 | P | 60
[6 empty] | P(a) | 60
[6 empty] | A | 60
Details
Means of verification: Auditoría independiente
Observations: Medición del Instituto Interamericano de Cooperacióna para Agricultura (IICA)
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
2.6 | Actualización de Recursos Humanos de la DGSA |  | % | 25 | 2006 | P | 50
[6 empty] | P(a) | 50
[6 empty] | A | 50
Details
Means of verification: Auditoría independiente
Observations: Medición del Instituto Interamericano de Cooperacióna para Agricultura (IICA)
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
2.7 | Difusión oportuna sobre programas sanitarios de la DGSA |  | % | 50 | 2006 | P | 60
[6 empty] | P(a) | 60
[6 empty] | A | 50
Details
Means of verification: Auditoría independiente
Observations: Medición del Instituto Interamericano de Cooperación para Agricultura (IICA)
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Indicator |  |  | Unit of Measure | Baseline | Baseline Year |  | EOP 2016
2.8 | Servicios y procesos certificados de la DGSA |  | % | 50 | 2006 | P | 75
[6 empty] | P(a) | 75
[6 empty] | A | 75
Details
Means of verification: Auditoría independiente
Observations: Medición del Instituto Interamericano de Cooperación para Agricultura (IICA)
| Pro-Gender | No | Pro-Ethnicity | No | CRF indicator
Strategic Alignment
Developed by ITE/ITO |  |  |  | - 3 - | Printed on: Nov 19, 2018 9:07:29 AM

## Outputs_4
RESULTS MATRIX
OUTPUTS PHYSICAL PROGRESS
Component Nbr.1: Fortalecimiento de la gestión institucional del MGAP
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
1.1 | Herramienta de Gestión del Plan estratégico del MGAP implementada |  |  | herramienta de gestión | P | bar: 2015; EOP 2016
P(a) | bar: 2015; EOP 2016
[5 empty] | A | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5
Details
Means of verification:
| Pro-Gender | No | CRF indicator
| Pro-Ethnicity | No | Strategic Alignment
[6 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
| Milestone |  | % de avance en la implemnetación del plan | % | P |  | 15 | 35 | 12 | 13 | 25 |  | 100
[5 empty] | P(a) |  | 15 | 15 | 15 | 30 | 25 |  | 100
[5 empty] | A | 0 | 15 | 15 | 15 | 30 | 0 | 0 | 75
|  |  | Tablero de control diseñado | tablero de control | P | EOP 2016: 0
[5 empty] | P(a) | EOP 2016: 0
[5 empty] | A | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  |  | Tablero de control implementado a nivel piloto en Dirección General de Secretaría del MGAP | tablero de control | P | EOP 2016: 0
P(a) | bar: 2013; EOP 2016
[5 empty] | A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
|  |  | Tablero de control extendido | Tablero de control | P | EOP 2016: 0
P(a) | bar: 2014 to 2015; EOP 2016
[5 empty] | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
1.2 | Plan director del sitema de información, informática y telecomunicaciones implementado |  |  | plan | P | bar: 2014; EOP 2016
P(a) | bar: 2015 to EOP 2016
[5 empty] | A | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5
Details
Means of verification:
| Pro-Gender | No | CRF indicator
| Pro-Ethnicity | No | Strategic Alignment
[6 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
| Milestone |  | % de avance en la impelmentación del plan | % | P | 2012: 40; 2013: 40; 2014: 20; EOP 2016: 100
[5 empty] | P(a) | 2012: 30; 2013: 30; 2014: 10; EOP 2016: 100
[5 empty] | A | 0 | 40 | 30 | 20 | 10 | 0 | 0 | 100
|  |  | Plan de mejora de la seguridad de la información elaborado | plan | P | EOP 2016: 0
[5 empty] | P(a) | EOP 2016: 0
[5 empty] | A | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  |  | Plan director diseñado | plan | P | EOP 2016: 0
[5 empty] | P(a) | EOP 2016: 0
[5 empty] | A | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  |  | Plan de implementación anual ejecutado | plan | P | EOP 2016: 0
[5 empty] | P(a) | 2013: 1; EOP 2016: 2
[5 empty] | A | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
1.3 | Estrategia de recursos humanos implementada |  |  | estrategia | P | bar: 2013; EOP 2016
[5 empty] | P(a) | 2014: 0.3; 2015: 0.5; EOP 2016: 1
[5 empty] | A | 0 | 0 | 0 | 0.2 | 0.3 | 0 | 0 | 0.5
Details
Means of verification:
| Pro-Gender | No | CRF indicator
| Pro-Ethnicity | No | Strategic Alignment
[6 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
| Milestone |  | % de implementación de la estrategia | % | P | 2012: 40; 2013: 60; EOP 2016: 100
[5 empty] | P(a) |  |  | 0 | 40 | 50 | 30 |  | 100
[5 empty] | A | 0 | 10 | 0 | 40 | 20 | 0 | 0 | 70
|  |  | Funcionarios capacitados en nuevas técnicas y herramientas de gestión y atención al ciudadano | personas | P | 2012: 320; 2013: 320; 2014: 960; EOP 2016: 1600
[5 empty] | P(a) |  |  | 0 | 400 | 400 | 466 |  | 1000
[5 empty] | A | 0 | 20 | 0 | 214 | 300 | 0 | 0 | 534
|  |  | Sistema de gestión humana (SGH) integrado a sistemas del MGAP | sistema | P | EOP 2016: 0
[5 empty] | P(a) | 2013: 1; 2015: 0; EOP 2016: 1
[5 empty] | A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
1.4 | Oficinas departamentales adecuadas al nuevo modelo de gestión, con ventanilla única y procesos TICs |  |  | oficinas | P | 2013: 8; 2014: 8; 2015: 3; EOP 2016: 19
[5 empty] | P(a) | 2012: 4; 2013: 5; 2015: 1; EOP 2016: 10
[5 empty] | A | 0 | 0 | 4 | 5 | 0 | 1 | 0 | 10
Details
Means of verification:
| Pro-Gender | No | CRF indicator
| Pro-Ethnicity | No | Strategic Alignment
[6 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
| Milestone |  | Funcionarios de las delegaciones sensibilizados y capacitados | personas | P | 2013: 120; 2014: 120; 2015: 60; EOP 2016: 300
[5 empty] | P(a) | 2013: 20; 2014: 25; 2015: 0; EOP 2016: 50
[5 empty] | A | 0 | 0 | 30 | 20 | 0 | 0 | 0 | 50
|  |  | Sistema de ventanilla única diseñado e implmentado a nivel piloto | sistema | P | bar: 2013; EOP 2016
[5 empty] | P(a) | 2012: 1; EOP 2016: 1.4
[5 empty] | A | 0 | 0.4 | 1 | 0 | 0 | 0 | 0 | 1.4
|  |  | Remodelación y equipamiento contratado | contrato | P | 2012: 1; 2013: 1; EOP 2016: 2
[5 empty] | P(a) | 2012: 1; 2013: 1; EOP 2016: 2.5
[5 empty] | A | 0 | 0.5 | 1 | 1 | 0 | 0 | 0 | 2.5
|  |  | Procesos mejorados en los centros de atención ministerial (CAM) | procesos | P | EOP 2016: 0
[5 empty] | P(a) | 2013: 5; 2015: 5; EOP 2016: 18
[5 empty] | A | 0 | 0 | 5 | 5 | 3 | 5 | 0 | 18
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
1.5 | Estrategia de comunicación y difusión del MGAP implementada |  |  | estrategia | P | bar: 2013; EOP 2016
P(a) | bar: 2014; EOP 2016
[5 empty] | A | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Details
Means of verification:
| Pro-Gender | No | CRF indicator
| Pro-Ethnicity | No | Strategic Alignment
[6 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
| Milestone |  | Estrategia de comunicación y difusión elaborada | estrategia | P | bar: 2012; EOP 2016
[5 empty] | P(a) | 2012: 1; EOP 2016: 1.1
[5 empty] | A | 0 | 0.1 | 1 | 0 | 0 | 0 | 0 | 1.1
|  |  | Estudio de imagen institucional elaborada | estudio | P | EOP 2016: 0
P(a) | bar: 2013; EOP 2016
[5 empty] | A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
|  |  | Nuevo portal de internet implementado | portal | P | EOP 2016: 0
P(a) | bar: 2015; EOP 2016
[5 empty] | A | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0.8
Component Nbr.2: Apoyo a la gestión técnica de los servicios de sanidad e inocuidad
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
2.1 | Plan estratégico de inocuidad de alimentos con mecanismo de seguimiento y evaluación implementado |  |  | plan | P | bar: 2011; EOP 2016
[5 empty] | P(a) | 2011: 1; 2015: 0.3; 2016: 0.05; EOP 2016: 1
[5 empty] | A | 0 | 0.3 | 0 | 0.2 | 0.2 | 0.25 | 0 | 0.95
Details
Means of verification:
| Pro-Gender | No | CRF indicator
| Pro-Ethnicity | No | Strategic Alignment
[6 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
| Milestone |  | Plan estratégico elaborado y consensuado | plan | P | EOP 2016: 0
[5 empty] | P(a) | EOP 2016: 0
[5 empty] | A | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  |  | Certificado internacional de inocuidad (evaluación) obtenido | certificado | P | EOP 2016: 0
P(a) | bar: 2015 to EOP 2016
[5 empty] | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Funcionarios del MGAP capacitados en los procesos de inocuidad | personas | P | EOP 2016: 0
[5 empty] | P(a) | 2013: 60; 2014: 30; 2015: 0; EOP 2016: 100
[5 empty] | A | 0 | 0 | 0 | 60 | 40 | 0 | 0 | 100
|  |  | Sistema de información integral diseñado a nivel conceptual | sistema | P | EOP 2016: 0
P(a) | bar: 2013; EOP 2016
[5 empty] | A | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
2.2 | Sistema de gestión de barreras sanitarias diseñado e implementado |  |  | sistema | P | bar: 2014; EOP 2016
P(a) | bar: 2015 to EOP 2016
[5 empty] | A | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7
Details
Means of verification:
| Pro-Gender | No | CRF indicator
| Pro-Ethnicity | No | Strategic Alignment
[6 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
| Milestone |  | % de avance en la implementación de la estrategia | % | P | 2012: 50; 2013: 30; 2014: 20; EOP 2016: 100
[5 empty] | P(a) |  |  | 20 | 30 | 40 | 20 |  | 100
[5 empty] | A | 0 | 10 | 20 | 30 | 20 | 20 | 0 | 100
|  |  | Sistema de gestión de barreras sanitarias diseñado | sistema | P | bar: 2011; EOP 2016
P(a) | bar: 2011; EOP 2016
[5 empty] | A | 0 | 0.2 | 1 | 0 | 0 | 0 | 0 | 1.2
|  |  | Funcionarios capacitados en gestión de barreras sanitarias | personas | P | 2012: 100; 2013: 100; EOP 2016: 200
[5 empty] | P(a) |  |  | 0 | 30 | 60 | 35 |  | 150
[5 empty] | A | 0 | 0 | 0 | 65 | 50 | 35 | 0 | 150
|  |  | Adecuación edilicia y equipamienrto de puestos de barreras sanitarias | % | P | 2012: 50; 2013: 30; 2014: 20; EOP 2016: 100
[5 empty] | P(a) |  |  | 20 | 25 | 50 | 35 |  | 125
[5 empty] | A | 0 | 0 | 0 | 25 | 65 | 35 | 0 | 125
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
2.3 | Plan director de laboratorios diseñado e implementado en su primera etapa |  |  | plan | P | bar: 2014; EOP 2016
[5 empty] | P(a) | EOP 2016: 0
[5 empty] | A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
Details
Means of verification:
| Pro-Gender | No | CRF indicator
| Pro-Ethnicity | No | Strategic Alignment
[6 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
| Milestone |  | Avance en la implementación del Plan director del sistema de laboratorios | % | P | 2012: 30; 2013: 20; 2014: 50; EOP 2016: 100
[5 empty] | P(a) | 2012: 30; 2013: 20; EOP 2016: 100
[5 empty] | A | 0 | 50 | 30 | 20 | 0 | 0 | 0 | 100
|  |  | Certificado de cumplimiento de normas de calidad - ISO 17025:2005 obtenido | certificado | P | 2012: 3; 2013: 1; 2014: 2; EOP 2016: 6
[5 empty] | P(a) | 2012: 1; 2014: 2; 2015: 2; EOP 2016: 5
[5 empty] | A | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 5
|  |  | Plan de infraestructura edilicia de laboratorios acorde con normas de bioseguridad y gestión ambiental, elaborado | plan | P | bar: 2011; EOP 2016
P(a) | bar: 2011; EOP 2016
[5 empty] | A | 0 | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5
|  |  | Funcionarios capacitados en gestión de sistemas de laboratorio | personas | P | 2012: 50; 2013: 100; 2014: 50; EOP 2016: 200
[5 empty] | P(a) |  |  | 50 | 2 | 1 | 4 |  | 17
[5 empty] | A | 0 | 10 | 0 | 2 | 1 | 15 | 0 | 28
|  |  | Laboratorios con infraestructura edilicia y equipamiento mejorados | laboratorios | P | EOP 2016: 0
[5 empty] | P(a) | 2015: 1; 2016: 1; EOP 2016: 3
[5 empty] | A | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 3
OUTPUTS FINANCIAL PROGRESS (US$)
Component Nbr.1: Fortalecimiento de la gestión institucional del MGAP | [5 empty] | 2011: Component revised cost
5755560.23
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
1.1 |  | Herramienta de Gestión del Plan estratégico del MGAP implementada |  | herramienta de gestión | P |  | 22663 | 80671 | 73801 | 833 | 199 |  | 178167
[5 empty] | P(a) | 1833 | 22663 | 31000 | 140000 | 94384 | 119636.41 |  | 329519.98
[5 empty] | A | 0 | 501 | 37902 | 17346 | 154134.57 | 0 | 0 | 209883.57
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
1.2 |  | Plan director del sitema de información, informática y telecomunicaciones implementado |  | plan | P |  | 245514 | 873936 | 799511 | 9024 | 2154 |  | 1930139
[5 empty] | P(a) | 19861 | 245514 | 350000 | 643600 | 486015 | 168485.85 | 502837.48 | 2244401.18
[5 empty] | A | 0 | 160401 | 578915 | 453835 | 397936.43 | 150476.27 | 504775.13 | 2246338.83
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
1.3 |  | Estrategia de recursos humanos implementada |  | estrategia | P |  | 15109 | 53781 | 49201 | 555 | 132 |  | 118778
[5 empty] | P(a) | 1222 | 15109 | 60000 | 74000 | 60968 | 24142.61 |  | 131793.4
[5 empty] | A | 0 | 1533 | 16058 | 41640 | 48419.79 | 8539.89 | 0 | 116190.68
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
1.4 |  | Oficinas departamentales adecuadas al nuevo modelo de gestión, con ventanilla única y procesos TICs |  | oficinas | P | 12659 | 384009 | 1366926 | 1250517 | 14114 | 3369 |  | 3031594
[5 empty] | P(a) | 31065 | 384009 | 700000 | 460000 | 467607 | 1156496.56 | 126970.62 | 3023709.41
[5 empty] | A | 12659 | 275892 | 364413 | 705627 | 326924.97 | 1211222.82 | 124846.79 | 3021585.58
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
1.5 |  | Estrategia de comunicación y difusión del MGAP implementada |  | estrategia | P |  | 12590 | 44817 | 41001 | 463 | 110 |  | 98981
[5 empty] | P(a) | 1019 | 12590 | 20000 | 46350 | 0 | 338.88 |  | 26136.26
[5 empty] | A | 0 | 1179 | 1400 | 22718 | 500.38 | 0 | 0 | 25797.38
Component Nbr.2: Apoyo a la gestión técnica de los servicios de sanidad e inocuidad | [5 empty] | 2011: Component revised cost
4170228.34
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
2.1 |  | Plan estratégico de inocuidad de alimentos con mecanismo de seguimiento y evaluación implementado |  | plan | P |  | 31358 | 86540 | 64668 | 26472 | 962 |  | 210000
[5 empty] | P(a) | 0 | 31358 | 80000 | 52866 | 84080 | 609484.69 | 22950.6 | 243911.8
[5 empty] | A | 0 | 0 | 39951 | 62590 | 118420.2 | 0 | 0 | 220961.2
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
2.2 |  | Sistema de gestión de barreras sanitarias diseñado e implementado |  | sistema | P |  | 211292 | 583113 | 435737 | 178369 | 6489 |  | 1415000
[5 empty] | P(a) | 0 | 211292 | 200000 | 977000 | 336500 | 44234.31 | 3500 | 693553.12
[5 empty] | A | 0 | 1339 | 37661 | 503332 | 134400.73 | 13320.39 | 3135 | 693188.12
Output |  |  |  | Unit of Measure |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | EOP 2016
2.3 |  | Plan director de laboratorios diseñado e implementado en su primera etapa |  | plan | P |  | 444235 | 1225979 | 916125 | 375016 | 13645 |  | 2975000
[5 empty] | P(a) | 0 | 444235 | 400000 | 1417000 | 304147 | 640802.75 | 541097.04 | 3232763.42
[5 empty] | A | 0 | 152223 | 439006 | 1153911 | 207543.91 | 738982.47 | 548667.18 | 3240333.56
Other Cost
Output
[6 empty] | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | Cost
| Administración del programa |  |  |  | P | 8619 | 224867 | 213168 | 224432 | 200355 | 2588 |  | 874029
[5 empty] | P(a) | 34590 | 224867 | 300000 | 213000 | 215470 | 140982 | 55137.71 | 843881.87
[5 empty] | A | 8619 | 131539 | 172000 | 202102 | 160499.25 | 113984.91 | 70451.52 | 859195.68
| Seguimiento, evaluación y auditoría |  |  |  | P |  | 18000 | 27000 | 14000 | 34000 | 7000 |  | 100000
[5 empty] | P(a) | 0 | 18000 | 27000 | 15000 | 20000 | 20000 | 25000 | 39430
[5 empty] | A |  | 0 | 0 | 0 | 14430 | 0 | 15477 | 29907
Total Cost
| Output |  |  |  |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | Cost
| Total Cost |  |  |  | P | 21278 | 1609637 | 4555931 | 3868993 | 839201 | 36648 |  | 10931688
[5 empty] | P(a) | 89590 | 1609637 | 2168000 | 4038816 | 2069171 | 2924604.06 | 1277493.45 | 10809100.44
[5 empty] | A | 21278 | 724607 | 1687306 | 3163101 | 1563210.23 | 2236526.75 | 1267352.62 | 10663381.6
Developed by ITE/ITO | [5 empty] | 2010: - 4 -; 2013: Printed on: Nov 19, 2018 9:07:29 AM

## Changes to the Matrix_5
CHANGES TO THE MATRIX
No information available for this section

## Finding and Recommendations_6
FINDING AND RECOMMENDATIONS
Findings and Recomendations
No information available for this section

## Evaluation Tracking_7
EVALUATION TRACKING
Evaluación intermedia
Evaluation
Evaluation Methodology as per DEM: |  | Before & After
Current Evaluation Methodology: |  | Before & After |  | Status of the evaluation:
Stage: |  | Design |  | Expected Date of Final Evaluation Report: |  | 2014-06-30
Main Topic of the Intervention: |  | AGRICULTURE AND RURAL DEVELOPMENT |  | Responsible: |  | Project Team & External
Other Topics of the Intervention: |  | AGRICULTURE AND RURAL DEVELOPMENT |  | Information on Responsible: |  | Ejecutor
Main Topic of the Evaluation: |  | AGRICULTURE AND RURAL DEVELOPMENT
Other Topics of the Evaluation: |  | AGRICULTURE AND RURAL DEVELOPMENT
Funding |  |  |  | Comments
Source of funding: |  |  |  | Date: | 2016-03-15 11:20
Amount in USD (Thousands): |  |  |  | User: | fbachino
Code:
Total amount in USD (Thousands) spent to date in data collection: |  | 14.43
Documents
Stage | Type of document | Name | Description | Creation date | Document Number | Permission | User
Concluded | Final Report | Documento final Evaluación Intermedia de la operación UR-L1016.pdf | Informe final de Evaluación Intermedia |  | 40177042 | Team Members | fbachino
Evaluación final
Evaluation
Evaluation Methodology as per DEM: |  | N/A |  | -
Current Evaluation Methodology: |  | Other |  | Status of the evaluation:
Stage: |  | Design |  | Expected Date of Final Evaluation Report: |  | 2017-10-31
Main Topic of the Intervention: |  | AGRICULTURE AND RURAL DEVELOPMENT |  | Responsible: |  | Project Team
Other Topics of the Intervention: |  | AGRICULTURE AND RURAL DEVELOPMENT |  | Information on Responsible:
Main Topic of the Evaluation: |  | AGRICULTURE AND RURAL DEVELOPMENT
Other Topics of the Evaluation: |  | AGRICULTURE AND RURAL DEVELOPMENT
Funding |  |  |  | Comments
Source of funding: |  |  |  | Date: | 2016-03-15 11:20 | -
Amount in USD (Thousands): |  |  |  | User: | fbachino
Code:
Total amount in USD (Thousands) spent to date in data collection: |  | 0
Documents
Stage | Type of document | Name | Description | Creation date | Document Number | Permission | User

## Validation Process_8
Validation Process
No information available for this section

## MI Stage I_9
MONITORING INDICATORS
Stage 1: From Approval to Eligibility
Benchmark Indicator Value
Indicator (I) | Project Indiactor Value | Satisfactory | Alert | Problem | Traffic Light
Days elapsed from approval to Legal Effectiveness | 153 | 0 <= I <= 74 days | 74 days <= I <= 100.5 days | > 100.5 days | PROBLEM
Days elapsed Legal Effectiveness to Eligibility | 156 | 0 <= I <= 133 days | 133 days <= I <= 181 days | > 181 days | ALERT
% of General conditions prior achieved | 100% | N/A | N/A | N/A | For tracking purpose only
% of Special conditions prior achieved | 0% | N/A | N/A | N/A | For tracking purpose only

## data_MI Stage I_9_1 (hidden)
| ALERT_LVL | PROBLEM_LVL | Remaining To Max | Days
URUGUAY | 74 | 26.5 | 1238.5
UR-L1016 | 0 | 0 | 0 | 153

## data_MI Stage I_9_2 (hidden)
| ALERT_LVL | PROBLEM_LVL | Remaining To Max | Days
URUGUAY | 133 | 48 | 506
UR-L1016 | 0 | 0 | 0 | 156

## data_MI Stage I_9_3 (hidden)
PROJ_IND_VAL
UR-L1016 | 100

## data_MI Stage I_9_4 (hidden)
PROJ_IND_VAL
UR-L1016

## MI Stage II_10
MONITORING INDICATORS
Stage 2: After Eligibility
Indicator (I) | Project Indicator Value | Benchmark Value |  |  |  | Traffic Light
|  | Satisfactory | Alert | Problem | Outlier
Synthetic Indicator (SI) | 3 | 2.5 <= I | 2<=I<2.5 | I<2 | N/A | SATISFACTORY
Accumulated disbursements to country's historic disbursements | 1 | 1 >= I > 0.9 | 0.9 >= I >=0.81 | 0.81> I >= 0 | N/A | SATISFACTORY
Cost Performance Index (annual - CPI(a) |  | 0.80 <= I <= 2.00 | 0.40 <= I < 0.80 | 0.00 <= I < 0.40 | >2.00
Cost Performance Index - CPI |  | 0.80 <= I <= 2.00 | 0.40 <= I < 0.80 | 0.00 <= I < 0.40 | >2.00
Schedule Performance Index - SPI |  | 0.80 <= I <= 2.00 | 0.40 <= I < 0.80 | 0.00 <= I < 0.40 | >2.00
Schedule Performance Index (annual)- SPI(a) |  | 0.80 <= I <= 2.00 | 0.40 <= I < 0.80 | 0.00 <= I < 0.40 | >2.00
Expected additional execution duration (months) |  | N/A | N/A | N/A | N/A | For tracking purpose only
% outputs achieved of the plan at operation start-up plan | 0.7% | N/A | N/A | N/A | N/A | For tracking purpose only
% outputs achieved of the re-planned end of project (EOP) | 0.71% | N/A | N/A | N/A | N/A | For tracking purpose only
Environmental and social safeguards performance rating | 0 | N/A | N/A | N/A | N/A | For tracking purpose only
PV, AC, EV, PV(a), EV(a)
CPI, Annual CPI, SPI, Annual SPI

## MI Stage III_11
MONITORING INDICATORS
Stage 3: After Operation Reaches 95% of total Disbursements
Indicator (I) | Project Indicator Value | Benchmark Value |  |  |  | Traffic Light
|  | Satisfactory | Alert | Problem | Outlier
Synthetic Indicator (SI) | 3 | 2.5 <= I | 2<=I<2.5 | I<2 | N/A | SATISFACTORY
# of months elapsed after 95% disbursements reached | 9 | I <11.35 | 11.35<=I<15.59 | I>15.59 | N/A | SATISFACTORY
Accumulated disbursements to country's historic disbursements | 1 | 1 >= I > 0.80 | 0.80 >= I >= 0.68 | 0.68 > I >= 0 | >2.00 | SATISFACTORY
Cost Performance Index (annual - CPI(a) |  | 0.80 <= I <= 2.00 | 0.40 <= I < 0.80 | 0.00 <= I < 0.40 | >2.00
Cost Performance Index - CPI |  | 0.80 <= I <= 2.00 | 0.40 <= I < 0.80 | 0.00 <= I < 0.40 | >2.00
Schedule Performance Index - SPI |  | 0.80 <= I <= 2.00 | 0.40 <= I < 0.80 | 0.00 <= I < 0.40 | >2.00
Schedule Performance Index (annual)- SPI(a) |  | 0.80 <= I <= 2.00 | 0.40 <= I < 0.80 | 0.00 <= I < 0.40 | >2.00
Expected additional execution duration (months) | % | N/A | N/A | N/A | N/A | For tracking purpose only
% outputs achieved of the plan at operation start-up plan | 0.7% | N/A | N/A | N/A | N/A | For tracking purpose only
% outputs achieved of the re-planned end of project (EOP) | 0.71 | N/A | N/A | N/A | N/A | For tracking purpose only
Environmental and social safeguards performance rating | 0 | N/A | N/A | N/A | N/A | For tracking purpose only

## data_MI Stage III_11_1 (hidden)
| PROJ_IND_VAL | Satisfactory Level | Alert Level | Problem Level
UR-L1016 | 9 | 0 | 0 | 0
URUGUAY | 0 | 11.35 | 4.24 | 18.06