## Sheet1
PROCUREMENT PLAN
Project: Strengthening the Institutional Capacity of the Financial Services Commission
Project number: JA-T1101 and Loan Contract number: Not Applicable
Period included in this Procurement Plan: From: 2017 until 2020
Ref. No. 1 | Comp. No. | Description of and Component of procurement contract | Estimated cost (USD 000) | Procurement Selection method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  | Prequalification 3 (YES/NO) | Estimated Dates |  | Actual dates |  | Status 4 (pending; in process; awarded; cancelled) | Comments
[6 empty] | IDB % | Local/Other % |  | Publication of specific procurement notice | Completion of Contract | Publication of specific procurement notice | Completion of Contract
1 | 1 | GOODS
1.2 |  | Integrated Regulatory System Software Description: A technological platform for which the technical specification developed by the Business Process Analyst Consultant (comp. no. 1.1) ,will be used to integrate the business processes of the FSC in order to improve the overall operations of the organization. | 150000 | ICB | Ex-ante | 67% | 33% | NO | 2019-01-01 |  |  |  | Pending
2 | 1 | CONSULTING SERVICES
1.1 |  | Business Process Analyst Description: The consultant will also be required to assess the business pocesses of the FSC and existing technological infrastucture and re-engineer the business processes and propose the necessary infrastructural changes to meet the business objectives of the FSC. | 50000 | QCBS | Ex-ante | 83% | 17% | NO | 2016-09-01 |  | 2017-09-01 |  | In progress
3.1 | 3 | Customer Satisfaction & Investor Education Survey Consultant Description: To design survey instrument and conduct survey to determine customer satisfaction levels and to guide the development of a proactive customer education programme. | 20000 | QCBS | Ex-ante | 67% | 33% | NO | 2018-02-01 |  |  |  | Pending
2.1 | 2 | Strengthening Capacity to Establish a Compensation Scheme Description: To conduct a situational analysis and review , update and implement exisitng proposals for the establishment of a compensation scheme to protect policy holders, investors and pensioners. | 50000 | QCBS | Ex-ante | 83% | 17% | NO | 2016-11-01 |  | 2017-09-01 |  | In progress
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education project that includes school construction might include an item labeled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Note on B10: Test: Put reference numbers under the "Ref. No." column to the left.
Note on C10: Test: Pplease add the description here and remove the separate description row below.
Note on I10: Test: "No" for each procurement you are sure will not use prequalification
Note on C11: Test: use the expression: "Consulting Services"