## TCM Period 2017
|  | Operation Number: |  |  |  | BL-T1110 | [14 empty] | Inter-American Development Bank - IDB
|  | TCM Cycle: |  |  |  | TCM Period 2017
|  | Last Update: |  |  |  | 2018-04-17 15:18
Results Matrix
Outcomes
Outcome: | 1 Improved efficiency in the business climate that meets the different needs of women owned and male owned firms
Indicators |  |  | Flags* |  | Unit of Measure |  |  | Baseline |  | Baseline Year |  | Means of verification |  |  | 2018 |  | 2019 |  | 2020 |  |  | EOP
1.1 Time taken to complete a business process (example: starting a business) |  |  |  |  | days |  |  | 43 |  | 2017 |  |  |  | P | 43 |  | 43 |  | 42
[14 empty] | P(a) | 0 |  | 0 |  | 0
A
1.2 Perception of increased efficiency in business process (gender sensitive survey design and disaggregated responses) |  |  |  |  | % |  |  | 0 |  | 2017 |  |  |  | P | 0 |  | 0 |  | 60
[14 empty] | P(a) | 0 |  | 0 |  | 0
A
Outputs: Annual Physical and Financial Progress
1 Design and Piloting of Technological Solution to Streamline Business Processes | [15 empty] | Physical Progress | [8 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2018 |  | 2019 |  |  | 2020 | EOP |  | 2018 | 2019 |  | 2020 |  | EOP |  | Theme | Fund | Flags
1.1 Diagnostics and assessments completed |  |  |  | Mapping Reports and National Competitiveness and/or Sector Specific Action Plans for improving ease of doing business indicators |  |  | Diagnostics (#) |  | 0 |  | 2017 |  | Project Monitoring Report |  |  | P |  | 1 |  | 0 |  |  | 0 | 1 | P | 15000 | 0 |  | 0 |  | 15000 |  | Institutional Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
1.2 Pilot interventions designed |  |  |  | Technological Solution/Integration Solution Designed |  |  | Pilots (#) |  | 0 |  | 2017 |  | Project Monitoring Report |  |  | P |  | 0 |  | 1 |  |  | 0 | 1 | P | 20000 | 0 |  | 0 |  | 20000 |  | Institutional Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
1.3 Pilot interventions implemented |  |  |  | Technological Solution/Integration Solution Implemented |  |  | Pilots (#) |  | 0 |  | 2017 |  | Project Monitoring Report |  |  | P |  | 0 |  | 1 |  |  | 0 | 1 | P | 0 | 90000 |  | 0 |  | 90000 |  | Institutional Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
1.4 Diagnostics and assessments completed |  |  |  | User Need Assessment Report (gender, sector, size) |  |  | Diagnostics (#) |  | 0 |  | 2017 |  | Project Monitoring Report |  |  | P |  | 1 |  | 0 |  |  | 0 | 1 | P | 10000 | 0 |  | 0 |  | 10000 |  | Institutional Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
1.5 Operational manuals developed |  |  |  | Operations Manual |  |  | Manuals (#) |  | 0 |  | 2017 |  | Project Monitoring Report |  |  | P |  | 0 |  | 1 |  |  | 0 | 1 | P | 0 | 5000 |  | 0 |  | 5000 |  | Institutional Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
1.6 Training workshops delivered |  |  |  | Training Workshop Delivered (disaggregated by Gender) |  |  | Workshops (#) |  | 0 |  | 2017 |  | Project Monitoring Report |  |  | P |  | 0 |  | 1 |  |  | 0 | 1 | P | 0 | 10000 |  | 0 |  | 10000 |  | Institutional Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
2 Legislative Review and Drafting | [15 empty] | Physical Progress | [8 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2018 |  | 2019 |  |  | 2020 | EOP |  | 2018 | 2019 |  | 2020 |  | EOP |  | Theme | Fund | Flags
2.1 Legislation developed |  |  |  | Gender Sensitized Legislative Review Report, Policy /Legislative Reform Drafted |  |  | Bills (#) |  | 0 |  | 2017 |  | Project Monitoring Report |  |  | P |  | 0 |  | 1 |  |  | 0 | 1 | P | 0 | 25000 |  | 0 |  | 25000 |  | Institutional Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
3 Communication and Knowledge Dissemination | [15 empty] | Physical Progress | [8 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2018 |  | 2019 |  |  | 2020 | EOP |  | 2018 | 2019 |  | 2020 |  | EOP |  | Theme | Fund | Flags
3.1 Policy dialogue events organized |  |  |  | Prime Minister's Business Forum |  |  | Events (#) |  | 0 |  | 2017 |  | Project Monitoring Report |  |  | P |  | 0 |  | 1 |  |  | 0 | 1 | P | 0 | 10000 |  | 0 |  | 10000 |  | Institutional Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
3.2 Awareness raising campaigns designed/implemented |  |  |  | Campaign Strategy |  |  | Campaigns (#) |  | 0 |  | 2017 |  | Project Monitoring Report |  |  | P |  | 0 |  | 1 |  |  | 0 | 1 | P | 0 | 10000 |  | 0 |  | 10000 |  | Institutional Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
3.3 Pilot interventions designed |  |  |  | Kiosk Pilot design and testing (rural areas and women) |  |  | Pilots (#) |  | 0 |  | 2017 |  | Project Monitoring Repor |  |  | P |  | 0 |  | 1 |  |  | 0 | 1 | P | 0 | 5000 |  | 0 |  | 5000 |  | Institutional Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
4 Coordination and Monitoring | [15 empty] | Physical Progress | [8 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2018 |  | 2019 |  |  | 2020 | EOP |  | 2018 | 2019 |  | 2020 |  | EOP |  | Theme | Fund | Flags
4.1 Monitoring and Evaluation Plan developed |  |  |  | Monitoring Work Plan Developed |  |  | Plans (#) |  | 0 |  | 2017 |  | Project Monitoring Repor |  |  | P |  | 1 |  | 0 |  |  | 0 | 1 | P | 5000 | 0 |  | 0 |  | 5000 |  | Social Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
4.2 Annual reports published |  |  |  | Progress reports and evaluation reports submitted by project manager |  |  | Reports (#) |  | 0 |  | 2017 |  | Project Monitoring Report |  |  | P |  | 1 |  | 1 |  |  | 1 | 3 | P | 4000 | 5000 |  | 4000 |  | 13000 |  | Institutional Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
4.3 Technical notes created |  |  |  | Leveraging Technological Innovation for Reducing the Cost of Doing Business: The Case of Belize |  |  | Notes (#) |  | 0 |  | 2017 |  | Project Monitoring Report |  |  | P |  | 0 |  | 0 |  |  | 1 | 1 | P | 0 | 0 |  | 2000 |  | 2000 |  | Institutional Development | TBD
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 | 0 | P(a) | 0 | 0 |  | 0 |  | 0
[16 empty] | A | [8 empty] | A
Other Cost
Total Cost | [25 empty] | 2018 |  | 2019 |  | 2020 |  | Total Cost
[25 empty] | P | 54000 |  | 160000 |  | 6000 |  | 220000
P(a)
A