## Project Structure
Agency | Sub-Agency (If applies) | Agency's Initials
NOTE: 1. There may only be one Organism which coordinates the Procurement Plan information and submits it to the Bank 2. Each Sub-executing Agency shall upload one sheet #2 with its activities
COMPONENTS? (YES / NO) | Component's Name (list by number or letter)
YES / NO? | Component 1
Component 2
Component 3
Component 4
Component 5
NOTE: Name the components in the loan agreement; use only main components

## Procurement Plan
INFORMATION FOR PROCUREMENT PLAN INITIAL UPLOAD ONGOING AND/OR LAST PRESENTED
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage:
2. Procurement Plan Details
Version ( 1-xxxx (Year) ) :
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Works | 0 | 0
Goods | 0 | 0
Non Consulting Services | 0 | 0
Training | 0 | 0
Operative Costs | 0 | 0
Consulting Services (Firms + Individuals) | 0 | 0
Transfers | 0 | 0
Community Participation | 0 | 0
Unassigned | 0 | 0
Total | 0 | 0
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
Component 1 - Description | 0 | 0
Component 2 - Description | 0 | 0
Component 3 - Description | 0 | 0
Component 4 - Description | 0 | 0
Component 5 - Description | 0 | 0
Component 6 - Description | 0 | 0
Total | 0 | 0

## Detailed Procurement Plan
PROCUREMENT PLAN INITIAL LOAD INFORMATION (ONGOING AND/OR LAST PRESENTED) 6/8/2017
WORKS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
GOODS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
MOF | Customize ICT system for Delivery Unit | ICB | International Competitive Bidding |  | 1.4.2 | 800000 | 100% | 0% | Component I | Ex-ante | 2018-12-21 |  | Software purchased for the Delivery Unit to facilitate their oversight of key government priority projects.
MOF | Hardware acquisition | ICB | International Competitive Bidding |  | 1.4.3 | 180000 | 100% | 0% | Component I | Ex-ante | 2018-04-28 |  | Hardware purchased for the Delivery Unit to facilitate their oversight of key government priority projects
MOF | IT System for NSS | ICB | International Competitive Bidding |  | 2.9 | 1880000 | 100% | 0% | Component II | Ex-ante | 2018-12-01
MOF | IFMIS HARDWARE | PC | Shopping |  | 3.2.3 | 3000 | 100% | 0% | Component III | Ex-ante | 2017-05-16
MOF | E-Tender system designed and developed | QCBS | Quality and Cost Based Selection |  | 4.2.1 | 1300000 | 100% | 0% | Component lV | Ex-ante | 2018-01-03 |  | E-tendering system to be reviewed with the possibility of attaching modules for Minintry of Works, Education, etc
MOF | Hardware for new system acquired | ICB | International Competitive Bidding |  | 4.2.2 | 1500000 | 100% | 0% | Component IV | Ex-ante | 2018-08-21 |  | Hardware for new E-tendering and Procurement system
MOF | Materials Management Information System Implemented | ICB | International Competitive Bidding |  | 4.4 | 845000 | 100% | 0% | Component IV | Ex-ante | 2018-01-03
MOF | Purchase of equipment and office supplies | PC | Shopping |  | 4.7.2 | 30000 | 100% | 0% | Component IV | Ex-ante | 2018-01-03 |  | Hardware and office supplies for PPU after being established
NON CONSULTING SERVICES
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Bidding Documents | Contract Signature
MOF | Change management activities for the Delivery Unit: VENUE | QCII | Comparison of Qualifications - International Individual Consultant |  | 1.1.2 | 25000 | 100% | 0% | Component I | Ex-ante | 2017-03-07 |  | Procurement for venue for seminar presented by Sir Michael Barber
MOF | Rental space for PPU | DC | Direct Contracting |  | 4.7.1 | 150000 | 100% | 0% | Component IV | Ex-ante | 2018-01-03 |  | Office space for PPU after being established
CONSULTING FIRMS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
MOF | (1)Framework for Monitoring & Evaluation for NDP (2)Website and Dashboard (3)Preliminary Workshop for high level monitor and evaluation reports | QCBS | Quality and Cost Based Selection | 1.5 | 210000 | 100% | 0% | Component I | Ex-ante | 2017-07-31 |  |  | This relates to the procurement of a FIRM to provide the consultancy under 1.5. this sub component relates to the development of the M&E framework for the NDP, development of Website and M&E Reports
MOF | Bahamas Investment Authority Re-structure | QCII | Comparison of Qualifications - International Individual Consultant | 1.6 | 150000 | 100% | 0% | Component I | Ex-ante | 2017-07-03 |  |  | This refers to the hiring of a consultant to review BIA and provide a roadmap for reform.
MOF | New organizational structure for the NSS including processes definition, workflows, procedures (Development of action plan and business model) | QCBS | Quality and Cost Based Selection | 2.5 | 175000 | 100% | 0% | Component ll | Ex-ante | 2018-04-19 |  | To identify weakness in statistics and rectify activities in government functions
MOF | Institutional training program for both the DOS and the NSS. | QCBS | Quality and Cost Based Selection | 2.6 | 345000 | 100% | 0% | Component ll | Ex-ante | 2018-08-14
MOF | Advisory Firm to review/ monitor and give guidance throughout the project | QCBS | Quality and Cost Based Selection | 3.1 | 2000000 | 100% | 0% | Component lll | Ex-ante | 2017-04-27
MOF | New Business Model & Needs Analysis | QCBS | Quality and Cost Based Selection | 3.3 | 1500000 | 100% | 0% | Component lll | Ex-ante | 2017-10-01 |  | 9 months for completing (using report from Deloitte)
MOF | Functional and technical specification of a new IFMIS prepared and off the shelf highly customizable IFMIS Implemented | QCBS | Quality and Cost Based Selection | 3.4 | 11882000 | 100% | 0% | Component lll | Ex-ante | 2018-10-01
MOF | IFMIS Training program | QCBS | Selection Based on the Consultants' Qualifications | 3.5 | 2000000 | 100% | 0% | Component lll | Ex-ante | 2018-09-01
MOF | Institutional training program for procurement unit implemented | QCBS | Quality and Cost Based Selection | 4.3 | 450000 | 100% | 0% | Component IV | Ex-ante | 2019-01-31 | 2021-12-31 | Public Procurement Unit (PPU) to be established and trained
MOF | Career path for public procurement officials, including a permanent training program | QCBS | Quality and Cost Based Selection | 4.5 | 250000 | 100% | 0% | Component IV | Ex-ante | 2018-11-08 | 2019-09-03 | Preparation & delivery of job description for PPU
INDIVIDUAL CONSULTANTS
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature
MOF | Change management activities for the Delivery Unit | QCII | Comparison of Qualifications - International Individual Consultant | 1.1.1 | 25000 | 100% | 0% | 1 | Component I | Ex-ante | 2017-03-07 |  | Sir Michael Barber has been identified as the preferred candidate and the second Ano-objection received from IDB
MOF | Delivery Unit Established | QCII | Comparison of Qualifications - International Individual Consultant | 1.2.1 | 240000 | 100% | 0% | 1 | Component I | Ex-ante | 2018-04-28 |  | This relates to the hiring of the Unit Coordinator for the Devlivery Unit. This component was delayed to allow for input form the Advisory and Training consultants on the road map as well as the assessment of the skills required for persons in this post. Proposed salary ($60,000 for 4 years)
MOF | Delivery Unit Established | QCNI | Comparison of Qualifications - National Individual Consultant | 1.2.2 | 720000 | 100% | 0% | 4 | Component I | Ex-ante | 2018-04-28 |  | This relates to the hiring of 4 staff members (sector leaders) for the Devlivery Unit. Proposed salary ($45,000 per year, for 4 persons for 4 years)
MOF | Training Program (LEAD ADVISOR) | QCII | Comparison of Qualifications - International Individual Consultant | 1.3.1 | 393000 | 100% | 0% | 1 | Component I | Ex-ante | 2017-07-31 |  | Consultants for the Advisory and Training Program - MUST START BEFORE 1.2 Proposed salary ($120,000 FOR 3 YRS) plus housing and per diem
MOF | Training Program (ADVISOR II) | QCNI | Comparison of Qualifications - National Individual Consultant | 1.3.2 | 170000 | 100% | 0% | 1 | Component I | Ex-ante | 2017-07-31 |  | Consultants for the Advisory and Training Program - MUST START BEFORE 1.2 Proposed salary (52,000 PER YR FOR 3 YEARS-plus gratuity
MOF | Training Program (ADVISOR I) | QCNI | Comparison of Qualifications - National Individual Consultant | 1.3.3 | 227000 | 100% | 0% | 1 | Component I | Ex-ante | 2018-04-28 |  | Contyratcing for this position will occur after the contreacting for the other two advisory and training position and will be dependant on need. It is anticipated to be critical when the training program begins. Proposed salary $69,000 PER YEAR FOR 3 YEARS-plus gratuity
MOF | Consulting service for ICT System Implementation (Delivery Unit) | QCNI | Comparison of Qualifications - National Individual Consultant | 1.4.1 | 20000 | 100% | 0% |  | Component I | Ex-ante | 2018-07-05 |  | Hiring of a consultant to Develop of RFP for ICT
MOF | Statistical Act redefined/Updated | QCNI | Comparison of Qualifications - National Individual Consultant | 2.1 | 40000 | 100% | 0% |  | Component II | Ex-ante | 2017-12-01 |  | Consulting for updating current Statistical Act | 207
MOF | Consultant: Assessment of National Statistical System in place | QCII | Comparison of Qualifications - International Individual Consultant | 2.2 | 50000 | 100% | 0% |  | Component II | Ex-ante | 2017-03-07
MOF | Consultant: Drafting of National Statistical Development Plan | QCII | Comparison of Qualifications - International Individual Consultant | 2.3 | 65000 | 100% | 0% |  | Component II | Ex-ante | 2017-12-01
MOF | Consultant to DOS to facilitate Implementation of NSS | QCII | Comparison of Qualifications - International Individual Consultant | 2.4 | 325000 | 100% | 0% | 1 | Component II | Ex-ante | 2018-07-31 |  | Consultant to be used as advisor for the implementation for the duration of the project.
MOF | Consultant: Functional & Technical Specification prepared | QCBS | Quality and Cost Based Selection | 2.7 | 20000 | 100% | 0% |  | Component II | Ex-ante | 2018-07-01
MOF | Multi-level awareness campaign to facilitate access to statistical information and improving | QCBS | Quality and Cost Based Selection | 2.8 | 100000 | 100% | 0% |  | Component II | Ex-ante | 2019-06-30
MOF | Establish IFMIS Unit (Sr. Consultant) | QCNI | Comparison of Qualifications - National Individual Consultant | 3.2.1 | 325000 | 100% | 0% | 1 | Component III | Ex-ante | 2017-07-01 |  | Senior Consultant (CPA Preferred) to assist with CoA and Treasury. Salary proposed ($65,000 per year for 5 years)
MOF | Establish IFMIS Unit ( 2 Jr. Consultants) | QCNI | Comparison of Qualifications - National Individual Consultant | 3.2.2 | 400000 | 100% | 0% | 2 | Component III | Ex-ante | 2017-06-01 |  | 2 Individual person assisting Budget, Public Service and payroll (Salary proposed $40,000 per year each for 5 years)
MOF | IFMIS planning workshop | DC | Direct Contracting | 3.3.1 | 50000 | 100% | 0% | 1 | Component lll | Ex-ante | 2017-07-19 |  | EOI Completed 4/27/17
MOF | Procurement Consultant | QCNI | Comparison of Qualifications - National Individual Consultant | 4.1 | 261000 | 100% | 0% | 1 | Component IV | Ex-ante | 2017-07-31 |  | Procurement Specialist at a salary of $58,000 per year for 4.5 years
MOF | Assessment of the current E-Procurement system prepared | QCII | Comparison of Qualifications - International Individual Consultant | 4.2 | 150000 | 100% | 0% | 2 | Component IV | Ex-ante | 2018-01-03 |  | 2 Consultants (Completion of existing E-Tendering system) (Implementation of new module for Min. of Works, Education, etc.)
MOF | Strategic plan, organizational manual and code of ethics for PPU developed | QCII | Comparison of Qualifications - International Individual Consultant | 4.6 | 150000 | 100% | 0% | 2 | Component IV | Ex-ante | 2018-01-13 |  | 2 Consultants (Organizational manual) (Strategic plan and guidelines for PPU)
MOF | Staffing for PPU | PC | Shopping | 4.8 | 514000 | 100% | 0% |  | Component IV | Ex-ante | 2018-01-03 |  | Establishment of staff for PPU
MOF | Awareness campaign-TV, Radio, Newspaper-delivered | NCB | National Competitive Bidding | 4.9 | 200000 | 100% | 0% |  | Component IV | Ex-ante | 2018-04-01 |  | Advertising and Promotion of New Procurement/E-tendering System
MOF | IT Consultant | QCNI | Comparison of Qualifications - National Individual Consultant | 5.1 | 100000 | 100% | 0% |  | Component V | Ex-ante | 2017-10-01
MOF | General Awareness Campaign | NCB | National Competitive Bidding | 5.2 | 100000 | 100% | 0% |  | Component V | Ex-ante | 2017-05-26 |  | General Awareness Campaign for the entire project.
TRAINING
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Annual Training Plan (ATP) | End of Activity
TRANSFERS
Executing Agency: | Transfer Purpose: | Additional Information: | Process Number: | Estimated Amount |  |  | Associated Component: | Estimated Number of Transfers: | Dates |  | Comments - for UCS include selection method
|  |  |  | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Contract Signature | Transfer Date

## Sheet1
2017 PROCUREMENT ACTIVITIES
MOF | Change management activities for the Delivery Unit | QCII | Comparison of Qualifications - International Individual Consultant | 1.1.1 | 25000 | 100% | 0% | 1 | Component I | Ex-ante | 2017-03-07
MOF | Change management activities for the Delivery Unit: VENUE | QCII | Comparison of Qualifications - International Individual Consultant | 1.1.2 | 25000 | 100% | 0% |  | Component I | Ex-ante | 2017-03-07
MOF | Training Program (LEAD ADVISOR) | QCII | Comparison of Qualifications - International Individual Consultant | 1.3.1 | 393000 | 100% | 0% | 1 | Component I | Ex-ante | 2017-07-31
MOF | Training Program (ADVISOR II) | QCNI | Comparison of Qualifications - National Individual Consultant | 1.3.2 | 170000 | 100% | 0% | 1 | Component I | Ex-ante | 2017-07-31
MOF | Consultancy framework for Monitoring & Evaluation for NDP | SSS | Single Source Selection | 1.5.1 | 40000 | 100% | 0% |  | Component I | Ex-ante | 2017-05-30
MOF | Consultancy for High Level Expert in Monitor & Evaluation Models (REPORTS) | SSS | Single Source Selection | 1.5.3 | 160000 | 100% | 0% |  | Component I | Ex-ante | 2017-10-27
MOF | Bahamas Investment Authority Re-structure | QCII | Comparison of Qualifications - International Individual Consultant | 1.6 | 150000 | 100% | 0% |  | Component I | Ex-ante | 2017-07-03
MOF | Statistical Act redefined/Updated | QCNI | Comparison of Qualifications - National Individual Consultant | 2.1 | 40000 | 100% | 0% |  | Component II | Ex-ante | 2017-12-01
MOF | Consultant: Assessment of National Statistical System in place | QCII | Comparison of Qualifications - International Individual Consultant | 2.2 | 50000 | 100% | 0% |  | Component II | Ex-ante | 2017-03-07
MOF | Consultant: Drafting of National Statistical Development Plan | QCII | Comparison of Qualifications - International Individual Consultant | 2.3 | 65000 | 100% | 0% |  | Component II | Ex-ante | 2017-12-01
MOF | Advisory Firm to review/ monitor and give guidance throughout the project | QCBS | Quality and Cost Based Selection | 3.1 | 2000000 | 100% | 0% |  | Component lll | Ex-ante | 2017-04-27
MOF | Establish IFMIS Unit (Sr. Consultant) | QCNI | Comparison of Qualifications - National Individual Consultant | 3.2.1 | 325000 | 100% | 0% | 1 | Component III | Ex-ante | 2017-07-01
MOF | Establish IFMIS Unit ( 2 Jr. Consultants) | QCNI | Comparison of Qualifications - National Individual Consultant | 3.2.2 | 400000 | 100% | 0% | 2 | Component III | Ex-ante | 2017-06-01
MOF | IFMIS HARDWARE | PC | Shopping | 3.2.3 | 3000 | 100% | 0% |  | Component III | Ex-ante | 2017-05-16
MOF | New Business Model & Needs Analysis | QCBS | Quality and Cost Based Selection | 3.3 | 1500000 | 100% | 0% |  | Component lll | Ex-ante | 2017-10-01
MOF | IFMIS planning workshop | DC | Direct Contracting | 3.3.1 | 50000 | 100% | 0% | 1 | Component lll | Ex-ante | 2017-07-19
MOF | Procurement Consultant | QCNI | Comparison of Qualifications - National Individual Consultant | 4.1 | 261000 | 100% | 0% | 1 | Component IV | Ex-ante | 2017-07-31