## TCM Period 2018
|  | Operation Number: |  | RG-T3344 | [7 empty] | Inter-American Development Bank - IDB
|  | TCM Cycle: |  | TCM Period 2018
|  | Last Update: |  | 2018-10-24 15:06
Results Matrix
Outcomes
Outcome: | 1 Prestación sostenible de los servicios de agua potable y saneamiento a través de intercambios de experiencia y conocimiento ent
re los operadores de la región LAC
Outputs: Annual Physical and Financial Progress
1 Component I: Twinnings among water and sanitation operators to foster knowledge | [8 empty] | Physical Progress | [6 empty] | Financial Progress
Outputs |  |  | Output Description |  | Unit of Measure | Baseline | Baseline Year | Means of verification |  | 2018 | 2019 |  | 2020 | 2021 | EOP |  | 2018 | 2019 |  |  | 2020 |  |  | 2021 |  |  | EOP |  |  | Theme | Fund | Flags
1.1 Twinnings organized among water operators |  |  |  |  | # of twinnings | 0 | 2018 | Report from the coordinator WOP-LAC (ALOAS) | P | 0 | 5 |  | 10 | 5 | 20 | P | 0 | 60000 |  |  | 90000 |  |  | 70800 |  |  | 220800 |  |  | Water and Sanitation | MAF
[9 empty] | P(a) | [5 empty] | 0 | P(a) | [10 empty] | 0
[9 empty] | A | [6 empty] | A
2 Component II: Promotion of good practices among operators | [8 empty] | Physical Progress | [6 empty] | Financial Progress
Outputs |  |  | Output Description |  | Unit of Measure | Baseline | Baseline Year | Means of verification |  | 2018 | 2019 |  | 2020 | 2021 | EOP |  | 2018 | 2019 |  |  | 2020 |  |  | 2021 |  |  | EOP |  |  | Theme | Fund | Flags
2.1 Workshops organized |  |  |  |  | # workshops | 0 | 2018 | surveys to the operators and report from WOP-LAC coordinator | P | 0 | 1 |  | 1 | 1 | 3 | P | 7000 | 35000 |  |  | 30000 |  |  | 10000 |  |  | 82000 |  |  | Water and Sanitation | MAF
[9 empty] | P(a) | [5 empty] | 0 | P(a) | [10 empty] | 0
[9 empty] | A | [6 empty] | A
3 Component III: promotion of the WOP-LAC initiative | [8 empty] | Physical Progress | [6 empty] | Financial Progress
Outputs |  |  | Output Description |  | Unit of Measure | Baseline | Baseline Year | Means of verification |  | 2018 | 2019 |  | 2020 | 2021 | EOP |  | 2018 | 2019 |  |  | 2020 |  |  | 2021 |  |  | EOP |  |  | Theme | Fund | Flags
3.1 Events organized |  |  |  |  | # events | 1 | 2018 | report from the coordinator of WOP-LAC | P | 1 | 1 |  | 1 | 1 | 4 | P | 2000 | 5000 |  |  | 6000 |  |  | 4200 |  |  | 17200 |  |  | Water and Sanitation | MAF
[9 empty] | P(a) | [5 empty] | 0 | P(a) | [10 empty] | 0
[9 empty] | A | [6 empty] | A
Other Cost | [16 empty] | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | Cost
[16 empty] | P | 20000 |  |  | 20000 |  |  | 20000 |  |  | 20000 |  |  | 80000
Coordination of WOP-LAC Secretariat
[16 empty] | P(a) | [12 empty] | 0
Total Cost | [16 empty] | 2018 |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | Total Cost
[16 empty] | P | 29000 |  | 120000 |  |  | 146000 |  |  | 105000 |  |  | 400000
P(a)
A