## TCM Period 2019
|  | Operation Number: |  |  |  | AR-T1223 | [13 empty] | Inter-American Development Bank - IDB
|  | TCM Cycle: |  |  |  | TCM Period 2019
|  | Last Update: |  |  |  | 2019-05-23 10:26
Results Matrix
Outcomes
Outcome: | 1 improve the competitiveness of the textile industry in Argentina and the quality of jobs through the development and upgrade of
skills in the workforce.
Indicators |  |  | Flags* |  | Unit of Measure |  |  | Baseline |  | Baseline Year |  | Means of verification |  |  | 2022 |  | EOP
1.1 Graduates in the new textile training program |  |  |  |  | Individuals |  |  | 0 |  | 2018 |  | Certificates of completition |  | P | 150 |  | 150
[14 empty] | P(a) | 150 |  | 150
[14 empty] | A |  |  | 150
1.2 Textile technical educational’s course in place in Argentina |  |  |  |  | Course |  |  | 0 |  | 2018 |  | UNSAM academic offer |  | P | 1 |  | 1
[14 empty] | P(a) | 1 |  | 1
[14 empty] | A |  |  | 1
Outputs: Annual Physical and Financial Progress
1 Development of a relevant and quality training program that contributes to closing the skills gap i | [15 empty] | Physical Progress | [6 empty] | Financial Progress
n the upper stages of the textile industry chain in the country
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2020 | 2021 |  | 2022 | EOP |  | 2020 | 2021 |  | 2022 |  | EOP |  | Theme | Fund | Flags
1.1 Diagnostics and assessments completed |  |  |  | Research on the global trends and perspectives in technology applied to textile production, with focus on the Korean case |  |  | Diagnostics (#) |  | 0 |  | 2018 |  | Consultant's report |  |  | P |  | 1 | 0 |  | 0 | 1 | P | 15000 | 0 |  | 0 |  | 15000 |  | Labor Markets | KPR
[16 empty] | P(a) |  | 1 | 0 |  | 0 | 1 | P(a) | 15000 | 0 |  | 0 |  | 15000
[16 empty] | A | [6 empty] | A
1.2 Surveys conducted |  |  |  | Survey of Argentine textiles firms in terms of unsatisfied demand for skills and main barriers to the incorporation of technology |  |  | Surveys (#) |  | 0 |  | 2018 |  | Consultant's report |  |  | P |  | 1 | 0 |  | 0 | 1 | P | 15000 | 0 |  | 0 |  | 15000 |  | Labor Markets | KPR
[16 empty] | P(a) |  | 1 | 0 |  | 0 | 1 | P(a) | 15000 | 0 |  | 0 |  | 15000
[16 empty] | A | [6 empty] | A
1.3 Agreement on the training for the trainers | [6 empty] | Agreement |  | 0 |  | 2018 |  | Agreement |  |  | P |  | 1 | 0 |  | 0 | 1 | P | 35000 | 0 |  | 0 |  | 35000 |  | Labor Markets | KPR
[16 empty] | P(a) |  | 1 | 0 |  | 0 | 1 | P(a) | 35000 | 0 |  | 0 |  | 35000
[16 empty] | A | [6 empty] | A
1.4 Training products developed |  |  |  | Development of curricula contents for the training program validated by textiles firms in Argentina |  |  | Products (#) |  | 0 |  | 2018 |  | Consultant's report |  |  | P |  | 1 | 0 |  | 0 | 1 | P | 45000 | 0 |  | 0 |  | 45000 |  | Education | KPR
[16 empty] | P(a) |  | 1 | 0 |  | 0 | 1 | P(a) | 45000 | 0 |  | 0 |  | 45000
[16 empty] | A | [6 empty] | A
1.6 Machinery for training students in place | [6 empty] | equipment |  | 0 |  | 2018 |  | Report from UNSAM |  |  | P |  | 1 | 0 |  | 0 | 1 | P | 40000 | 0 |  | 0 |  | 40000 |  | Institutional Development | KPR
[16 empty] | P(a) |  | 1 | 0 |  | 0 | 1 | P(a) | 40000 | 0 |  | 0 |  | 40000
[16 empty] | A | [6 empty] | A
1.6 Trainers trained | [6 empty] | Individuals |  | 0 |  | 2018 |  | Certificate of completion |  |  | P |  | 3 | 2 |  | 0 | 5 | P | 100000 | 70000 |  | 0 |  | 170000 |  | Labor Markets | KPR
[16 empty] | P(a) |  | 3 | 2 |  | 0 | 5 | P(a) | 100000 | 70000 |  | 0 |  | 170000
[16 empty] | A | [6 empty] | A
2 Training of students in the textile sector | [15 empty] | Physical Progress | [6 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2020 | 2021 |  | 2022 | EOP |  | 2020 | 2021 |  | 2022 |  | EOP |  | Theme | Fund | Flags
2.1 Individuals Trained |  |  |  | Students trained |  |  | Individuals (#) |  | 0 |  | 2018 |  | Certificate of completion |  |  | P |  | 30 | 60 |  | 60 | 150 | P | 55000 | 55000 |  | 60000 |  | 170000 |  | Education | KPR
[16 empty] | P(a) |  | 30 | 60 |  | 60 | 150 | P(a) | 55000 | 55000 |  | 60000 |  | 170000
[16 empty] | A | [6 empty] | A
2.2 Awareness raising campaigns designed/implemented |  |  |  | Activity for the dissemination of the training program |  |  | Campaigns (#) |  | 0 |  | 2018 |  | Event schedule |  |  | P |  | 1 | 0 |  | 1 | 2 | P | 5000 | 0 |  | 5000 |  | 10000 |  | Labor Markets | KPR
[16 empty] | P(a) |  | 1 | 0 |  | 1 | 2 | P(a) | 5000 | 0 |  | 5000 |  | 10000
[16 empty] | A | [6 empty] | A
Other Cost
Total Cost | [23 empty] | 2020 |  | 2021 |  | 2022 |  | Total Cost
[23 empty] | P | 310000 |  | 125000 |  | 65000 |  | 500000
[23 empty] | P(a) | 310000 |  | 125000 |  | 65000 |  | 500000
A