## Sheet1
Procurement Plan
Approval Number | 4676/BL-GY-2 4676/BL-GY-1
Operation Number | GY-L1066
Country | GUYANA
Coverage Plan | 19 Oct 2020 - 19 Apr 2022
Executing Agency | GUYANA POWER AND LIGHT, INC. GUYANA ENERGY AGENCY (GEA)
Goods and Services Total | $ 25,000.00
Works Total | $ 18,124,961.00
Consulting Services Total | $ 930,000.00
Version | 2020-11
Procurement Name | Procurement Type | Procurement Method | Process ID | Total Estimated Cost | % IDBCost | % Counterpart | % Cofinancier | Component | Supervision Method | Start Date | End Date | Status | Comments
Installation of Solar PV mini-grid systems in the township of Bartica including storage capacity (1 LOT) | Works | National Competive Bidding | GY-L1066-P0828 | $ 3,619,048.00 | 100.00 % | 0.00 % | 0.00 % | Component # 1 – Renewable energy solutions for the hinterland | Ex-ante | 20 Sep 2019 | 02 Nov 2020 | Expected
Installation of solar PV mini-grid systems in the township of Lethem including storage capacity (1 LOT) | Works | International Competitive Bidding | GY-L1066-P0829 | $ 2,412,698.00 | 100.00 % | 0.00 % | 0.00 % | Component # 1 – Renewable energy solutions for the hinterland | Ex-ante | 20 Sep 2019 | 02 Nov 2020 | Expected
Consultancy for the development of a Revegetation Plan for Bartica | Individual Consultants | Individual Consultant Selection (3CV) | GY-L1066-P0830 | $ 40,000.00 | 100.00 % | 0.00 % | 0.00 % | Component # 1 – Renewable energy solutions for the hinterland | Ex-ante | 02 Oct 2019 | 31 Mar 2020 | Expected
Consultancy for the Environmental Assessment for new site at Mahdia | Individual Consultants | Individual Consultant Selection (3CV) | GY-L1066-P0831 | $ 40,000.00 | 100.00 % | 0.00 % | 0.00 % | Component # 1 – Renewable energy solutions for the hinterland | Ex-ante | 20 May 2020 | 04 Jan 2021 | Expected
Contracts Administration - Advisor to the Director of Energy | Individual Consultants | Individual Consultant Selection (3CV) | GY-L1066-P0832 | $ 250,000.00 | 100.00 % | 0.00 % | 0.00 % | Component # 3 – Institutional Strengthening and Governance of the Department of Energy | Ex-ante | 24 Feb 2021 | 09 May 2021 | Expected | 24 Sep 2020 - phillip.bryan - This Consultancy will commence at an output of the Specialist Consultant and is expected to have a duration of 80 weeks.
Specialist Technical Consultant | Individual Consultants | Individual Consultant Selection (3CV) | GY-L1066-P0833 | $ 250,000.00 | 100.00 % | 0.00 % | 0.00 % | Component # 3 – Institutional Strengthening and Governance of the Department of Energy | Ex-ante | 12 Oct 2020 | 25 Jan 2021 | Expected | 24 Sep 2020 - phillip.bryan - This Consultant will be retained to access the needs of the Department of Energy, towards preparing the TORs for the advisors to the Director of Energy in the capacity of (i) Contracts Administrator, (ii) Subsurface Engineer, (iii) Oil and Gas Specialist.
Communication Specialist Firm | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | GY-L1066-P0834 | $ 100,000.00 | 100.00 % | 0.00 % | 0.00 % | Component # 3 – Institutional Strengthening and Governance of the Department of Energy | Ex-ante | 12 Oct 2020 | 22 Mar 2021 | Expected | 24 Sep 2020 - phillip.bryan - The terms of reference for this Activity is receiving the review of the Director of Energy before it is submitted to the Director of GEA, who leads the execution of this Loan Operation Component III.
Contracts Administration Software and Training | Goods | Shopping/Request for minimum 3 Quotations | GY-L1066-P0835 | $ 25,000.00 | 100.00 % | 0.00 % | 0.00 % | Component # 3 – Institutional Strengthening and Governance of the Department of Energy | Ex-ante | 20 Oct 2020 | 19 Jan 2021 | Expected
Consultancy for supporting GPL in the elaboration of ToR, draft bidding document and support in the technical review of proposals for 10MVAR Statcom at New Sophia Substation | Individual Consultants | Individual Consultant Selection (3CV) | GY-L1066-P0836 | $ 50,000.00 | 50.00 % | 50.00 % | 0.00 % | Component # 2 – Reinforcement of transmission infrastructure | Ex-ante | 12 Apr 2019 | 04 May 2020 | Expected
Reinforcements of the DBIS with the rehabilitation of 5 kilometers of associated transmission line and substations and construction of a new kilometer transmission line /5km new transmissions line to be constructed 5km of current line to be rehabi | Works | International Competitive Bidding | GY-L1066-P0837 | $ 2,550,000.00 | 100.00 % | 0.00 % | 0.00 % | Component # 2 – Reinforcement of transmission infrastructure | Ex-ante | 01 Oct 2020 | 31 May 2021 | Expected
Consultancy for Development of GPL Corporate Gender Policy as a mainstream practice in the organization | Individual Consultants | Individual Consultant Selection (3CV) | GY-L1066-P0838 | $ 50,000.00 | 100.00 % | 0.00 % | 0.00 % | Component # 2 – Reinforcement of transmission infrastructure | Ex-ante | 30 Aug 2019 | 18 Nov 2019 | Process ongoing
Installation of Solar PV mini-grid systems in the township of Mahdia including storage capacity (1 Lot) | Works | International Competitive Bidding | GY-L1066-P0839 | $ 1,568,254.00 | 100.00 % | 0.00 % | 0.00 % | Component # 1 – Renewable energy solutions for the hinterland | Ex-ante | 22 Sep 2020 | 02 Apr 2021 | Expected
Procurement and Installation of SMART meters and digitalization component as a pilot project in the consuming units | Works | National Competive Bidding | GY-L1066-P0840 | $ 140,000.00 | 100.00 % | 0.00 % | 0.00 % | Component # 1 – Renewable energy solutions for the hinterland | Ex-ante | 11 Jan 2021 | 23 Jul 2021 | Expected
Transmission design and route to accommodate the Solar Farm at Bartica, Lethem and Mahdia (3 Lots) | Works | International Competitive Bidding | GY-L1066-P0841 | $ 634,961.00 | 100.00 % | 0.00 % | 0.00 % | Component # 1 – Renewable energy solutions for the hinterland | Ex-ante | 22 Sep 2020 | 02 Apr 2021 | Expected
Gender consultancy to train and develop the market based advisory for Female trainees in building up local solutions for solar technology development | Individual Consultants | Individual Consultant Selection (3CV) | GY-L1066-P0842 | $ 150,000.00 | 100.00 % | 0.00 % | 0.00 % | Component # 1 – Renewable energy solutions for the hinterland | Ex-ante | 30 Jul 2021 | 11 Nov 2022 | Expected
Procurement and installation of reactive power compensation equipment in the New Sophia substation- Installation of 10MVAR STATCOM Unit at New Sophia | Works | International Competitive Bidding | GY-L1066-P0843 | $ 7,200,000.00 | 45.00 % | 55.00 % | 0.00 % | Component # 2 – Reinforcement of transmission infrastructure | Ex-ante | 30 Apr 2021 | 27 Oct 2021 | Expected
Consultancy for revision ad development of a technical guideline document for GPL to store, dispose and and treat unused electrical equipment | Individual Consultants | Individual Consultant Selection (3CV) | GY-L1066-P0844 | $ 50,000.00 | 100.00 % | 0.00 % | 0.00 % | Component # 2 – Reinforcement of transmission infrastructure | Ex-ante | 16 Aug 2019 | 18 Nov 2019 | Expected
Consultancy for supporting GPL in the elaboration of ToR for the bidding process and support in the technical review of proposals for L5 Transmission Line | Individual Consultants | Individual Consultant Selection (3CV) | GY-L1066-P0845 | $ 50,000.00 | 100.00 % | 0.00 % | 0.00 % | Component # 2 – Reinforcement of transmission infrastructure | Ex-ante | 12 Apr 2019 | 11 Oct 2019 | Expected