## Sheet1
Annex IV - RG-T3044
IFD/CMF
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Regional |  |  |  |  | Executing agency: IFD/CMF |  |  |  |  | Public or private sector: Public Sector
Project number: RG-T3044 |  |  |  |  | Title of Project: Strengthening the ICT border connectivity in borders in Central-America
Period covered by the plan:
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$):__160,000__________ |  |  |  | Consulting services(in US$):____________ | 540000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (ex-ante or ex-post) (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/ other %
1 |  | Component 1: Assessment of challenges
Consulting Firm
1.1 |  | Assessment of the current status and technology | 190000 | QCBS |  | 100% |  | 1Q19
Individual Consultants
1.2 |  | Technical study showing the differences betweend the current offer and demand | 40000 | IICQ |  | 100% |  | 1Q19
Non-consulting Services
1.3 |  | Mission travels (Interviews with public and private sectors, etc.) | 20000 | DC |  | 100% |  | 1Q19
2 |  | Component 2: Border broadband infrastructure protection plan.
Consulting Firm
2.1 |  | Analysis of vulnerability and threats toward broadband infrastructure | 40000 | QCBS |  | 100% |  | 2Q19
Individual Consultants
1.2 |  | Design of border broadband infrastructure protection plan | 90000 | IICQ |  | 100% |  | 1Q19
Non-consulting Services
2.5 |  | Mission travels (Interviews with public and private sectors, etc.) | 20000 | DC |  | 100% |  | 2Q19
3 |  | Component 3 : Development of the action plan
Consulting Firm
3.1 |  | Detailed action plan to improve border connectivity | 100000 | QCBS |  | 100% |  | 2Q19
Individual Consultants
3.2 |  | Analysis of the network development plan | 50000 | IICQ |  | 100% |  | 3Q19
4 |  | Component 4: Financial analysis and corresponding sensitivity analysis
Individual Consultants
1.2 |  | Associated investment and economic analysis | 30000 | IICQ |  | 100% |  | 3Q19
Non-consulting services
4.1 |  | Reports and promotion material for dissemination (at least 2 publications) | 50000 | PC |  | 100% |  | 3Q19
4.2 |  | Organization of regional workshops for knowledge sharing and dissemination (at least 2 events) | 70000 | PC |  | 100% |  | 3Q19
Total |  |  | 700000 | Prepared by: Antonio Garcia Zaballos |  |  | Date: 09/10/2018
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.