## Table of Contents
ANNUAL OPERATING PLAN
TABLE OF CONTENTS
SECTION 1 | Project Overview
SECTION 2 | Implementation Plan
SECTION 3 | Procurement Plan
SECTION 4 | Consolidated Financial Plan
SECTION 5 | Detailed Financial Plan
SECTION 6 | AOP Checklist

## Project Overview
SECTION 1
PROJECT OVERVIEW
| Programme/project name | Agricultural Competitiveness Programme (ACP)
| Programme/project number | LOAN CONTRACT No. 2444/OC-JA
| Programme/project components | Component 1: “Development of Farm-to-Market Linkages”. The objective of this component is to improve the capacity of organized small and medium sized farmers to undertake efficient and market-oriented production processes, and to foster management and organizational capacities to access national and international markets. Component 2: Food Quality and Food Safety Management Systems. The objective of this component is to establish an Agricultural Health and Food Quality Management System that will contribute to improving the competitiveness of Jamaican agriculture, as well as the health status of the human population, through the production of safe and good quality agricultural products and food for local consumption and the export market. Component 3: “Agribusiness Value Chain Development”. The objective of this component is to promote the integration of farmers and/or farmer organizations into agribusiness value chains while also contributing also to stimulate private investment in the sector.
| Issues/constraints identified | Provide a summary of Issues/Constraints identified
1. There is high competition for the limited fiscal space available to the Government annually within the current economic environment
2. Project targets will compete with stakeholder entities' operational workload for human resources and organisational focus
3. A number of working groups and committees exist at various levels outside of the project governance architecture whose activities and decision making impact project outputs under various components
4. The Project reflects a significant change effort, within an environment of wage restraint, austerity and employee apathy. Stakeholder buy-in will not be easy.
| Strategies for addressing issues/constraints identified | Provide strategies for addressing issues/constraints identified
1. Continuously review the implementation plan to make sure target expenditure is realisable ahead of budget negotiation with the MoAF
2. PIU will have to establish formal agreements with entities that clarify roles, responsibilities and commitments and tightly manage execution of those agreements
3. Through the lead entity stakeholders, sensitise identified working groups and decision making bodies to project targets and agree communicaton protocols
4. Change management will be factored into the planning of the programme, through timely and consistent communication and engagement.
| Risks with categorisation (High, medium, low) N.B. These risks should reflect those in the Risk matrix developed at the beginning of the project. | Provide a summary of opportunities and threats associated with the implementation of the Programme/project
1. Coordination among government entities may be difficult due to the large project scope (high)
2. Lack of ownerhsip may lead to implementation failure (high)
3. Resistance to change may undermine achievement of expected efficiency gains (high)
4. Limited capacity may delay implementation of technically complex reforms (high)
5. Budget estimates may be insufficient to fullfill actual costs under the project (high)
6. Limited fiscal space may affect project budget allocations (high)
7. Lack of buy-in may result in implementation and execution delays (high)
| Risk response for high level risks | Provide mitigation measures to deal with the risks identified
1. Establish the PCU, and strengthen as necessary, and form Steering Committee with entity stakeholders
2. Establish formal agreements on roles and responsibilities and agree schedules and protocols for regular communication and escalation of issues
3. Change Management expert will be hired under the Programme
4. Full-time project management and technical capacity will be assigned to the more complex activities under the project
5. Undertake constant financial review of the project to identify areas of savings and make provision of contingent counterpart funding by GOJ
6. Continuous guidance with MOFP to secure budget allocation for disbursement according to projections
7. Add human resources and make provision for training
8. Use Steering Committee and other high level decision-making bodies to reinforce importance of priotising programme activities
The Annual Operating Plan consists of
1 | Project Overview
2 | Implementation Plan
3 | Procurement Plan
4 | Consolidated Financial Plan
5 | Financial Plan
10/22/201310/22/201310/22/201310/22/201310/22/2013

## Procurement Plan April 2017
PROCUREMENT PLAN
AGRICULTURAL COMPETITIVENESS PROGRAMME
Project Number 2444/OC-JA
Period comprised in this Procurement Plan: January 2016 to March 2018
Exchange Rate | Ref. No. 1 | Description of and category of procurement contract | Actual Cost in ( US $ 000) | Estimated cost in (US$ 000) | Estimated cost in (JMD 000) | Procure-ment method 2 | Review (ex-ante or ex-post) | Source of financing and percentage |  |  | Prequali-fication 3 (Yes/No) | Estimated Dates |  |  | Status 4 (pending, in process, awarded, cancelled) | Comments
128 | [7 empty] | IDB% | GOJ |  |  | Publication of specific procurement notice | Signing of Contract | Completion of Contract
GOODS
| 2.3.2 M7.1 | GAP Soil Analysis & Inputs |  | 30 | 3840 | PC | Ex-post | 100% | 0 | 0 | No | 2017-08-01 | 2017-09-01 | 2017-09-12 | Pending | Pending the nearing of completion of infrastructure activities
| 3.2.2J1 | Purchase of SPSS Software |  | 19552 | 2502656 | SSS | Ex- post | [5 empty] | 2017-09-01 | 2017-09-02 | In Progress
|  | SUB-TOTAL - GOODS |  | 30 | 2506496
| B | WORKS
| 3.2.2(A31) | Electrical Installation (JPSCO) |  | 31 | 3968 | SSS | Ex-ante | 100% | 0 | 0 | No | 2016-09-11 | 2017-03-12 | 2017-08-12 | In Progress | PE
| 3.2.2(A32) | Water Installation |  | 1.5 | 192 | SSS | Ex-ante | 100% | 0 | 0 | No | 2016-09-11 | 2017-03-13 | 2017-08-13 | In Progress | All awaiting IDB Response
3 | 3.2.2(A33) | Cold Room Installation |  | 31 | 3968 | NCB | Ex-ante | 100% | 0 | 0 | No | 2016-09-11 | 2017-03-14 | 2017-08-14 | In progress | All awaiting IDB Response
| 3.2.2(A34) | Access Road and Courtyard |  | 132.674 | 16982.272 | NCB | Ex-ante | 100% | 0 | 0 | No | 2016-09-11 | 2017-03-15 | 2017-08-15 | InProgress | All awaiting IDB Response | 25110.272
| 3.5.2 | Establishment of New Agro Park at Hounslow (Roads, drains and irrigation networks) |  | 811.48 | 103869.44 | NCB | Ex-ante | 100% | 0 | 0 | No | 2016-04-01 | 2017-02-01 | 2017-06-02 | Inprogress | Roads and Drains is awaiting the NCC endorsement to contract. Irrigation is awaiting the IDB's no objection as the NCC inidcated we should go ahead with negotiations through SS with JDI. | W
|  | Irrigation Works |  | 509.3709 | 65708839.96
|  | Roads & Drains (6.91Km) |  | 353.1559 | 45557106.6
Road 1- 1.24 Km
Road 2- 0.78 Km
Road 3 - 0.53 Km
Road 4- 2.08 Km
Road 7- 2.08 Km
Road 10- 0.20 Km
| 2.3.2 M9 | GAP Chemical storage containers including pallets & Hand wash Stations |  | 101.5504 | 13100
| 2.3.2 M10 | GAP sanitation facilities |  | 139.53 | 18000
| 2.3.2 M1 | GAP Infrastructure works in Ebony Park/ Spring Plain - GAP Combo Structure & Courtyard - 2880Sq. Ft. |  | 286.28 | 36930.1143 | NCB | Ex-ante | 100% | 0 | 0 | No | 2016-08-30 | 2017-05-22 | 2017-08-27 | In progress | Need 50 No. 40Ft Containers
Shower - 24 Sq.Ft.
Male Rest Room - 32Sq.Ft
Female Rest Room - 32Sq.Ft
Office - 64 Sq.Ft
Lunch Area - 88 Sq.Ft
Pesticide Storage - 160 Sq.Ft
Fertitilizer - 160 Sq.Ft
Washing Area 160 Sq.Ft
Food Processing - 480 Sq.Ft
Garbage Disposal - 100 Sq.Ft
Chemical Mixing - 100 Sq.Ft
Courtyard - 1440 Sq.Ft
| 2.3.2 M2 | GAP Infrastructure works in PGR & Yallahs -- GAP Combo Structure & Courtyard - 2880Sq. Ft. |  | 201.2605 | 25962.607 | NCB | Ex-ante | 100% | 0 | 0 | No | 2016-08-30 | 2017-09-30 | 2017-10-01 | In progress | I
Shower - 24 Sq.Ft.
Male Rest Room - 32Sq.Ft
Female Rest Room - 32Sq.Ft
Office - 64 Sq.Ft
Lunch Area - 88 Sq.Ft
Pesticide Storage - 160 Sq.Ft
Fertitilizer - 160 Sq.Ft
Washing Area 160 Sq.Ft
Food Processing - 480 Sq.Ft
Garbage Disposal - 100 Sq.Ft
Chemical Mixing - 100 Sq.Ft
Courtyard - 1440 Sq.Ft
| 2.3.2 M3 | GAP Infrastructure works in New Forest/Duff House - GAP Combo Structure & Courtyard - 2880Sq. Ft. |  | 303.8816 | 39200732 | NCB | Ex-ante | 100% | 0 | 0 | No | 2016-08-30 | 2017-05-30 | 2017-08-27 | In progress
Shower - 24 Sq.Ft.
Male Rest Room - 32Sq.Ft
Female Rest Room - 32Sq.Ft
Office - 64 Sq.Ft
Lunch Area - 88 Sq.Ft
Pesticide Storage - 160 Sq.Ft
Fertitilizer - 160 Sq.Ft
Washing Area 160 Sq.Ft
Food Processing - 480 Sq.Ft
Garbage Disposal - 100 Sq.Ft
Chemical Mixing - 100 Sq.Ft
Courtyard - 1440 Sq.Ft
| 2.3.2 M3.1 | GAP Infrastructure works Mobile Toilets and Chemical Storage Boxes |  | 382.678 | 48982.784 | NCB | Ex-ante | 100% | 0 | 0 | No | 2017-07-30 | 2017-09-04 | 2017-10-30 | Pending
|  | TOTAL GAP INFRASTRUCTURE BUDGET |  |  |  | 39312607.5053 | [9 empty] | GIS Servey. Peteronia Not making any progress so Exploring Direct Contracting option to UWI. Petronia Will identify Activity for this
|  | SUB-TOTAL - WORKS |  | 3089.1872 | 150713523.5053
| C | NON CONSULTANCY SERVICES
| 2.2.1 (B) | Workshop on Pest Surveillance and to update preparedness plan (medfly) |  | 12 | 1536 | PC | Ex- ante | 100% | 0 | 0 | No | 2016-05-01 | 2017-06-10 | 2017-07-13 | Pending |  | N
| 2.2.6 E | Results Presentation ceremony for the Pesticide Survey and Research |  | 4.1 | 524.8 | PC | Ex-Post | 100% | 0 | 0 | No | 2016-09-01 | 2017-06-02 | 2017-06-30 | Pending
| 2.2.6 F | PR activities for Pesticides survey: Promotional Material |  | 1 | 128 | PC | Ex-Post | 100% | 0 | 0 | No | 2016-09-01 | 2017-06-02 | 2017-06-30 | Pending
| 2.3.1 (G) | Implement workshops for implementation and strategic planning for the AH Policy |  | 2 | 256 | PC | Ex-Post | 100% | 0 | 0 | No | 2017-05-15 | 2017-06-15 | 2017-07-02 | Pending |  | N
| 2.3.2 E | Organize and execute workshop to revise and update animal diseases surveillance procedures and manuals |  | 3 | 384 | PC | Ex-Post | 100% | 0 | 0 | No | 2017-04-15 | 2017-05-15 | 2017-06-30 | Pending |  | N
| 3.2.2.0 | Advertising costs for activities related to Agro Park Infrastructural Development |  | 6 | 768 | PC | Ex-Post | 100% | 0 | 0 | No | 2016-04-01 | 2016-09-11 | 2017-05-15 | InProgress |  | W
| 3.2.2A | Value Chain Institutional Strengthening(Strengthening Institutional Capacity in Value Chain Development) |  | 55 | 7040 | PC | Ex-Post | 100% | 0 | 0 | No | 2016-04-01 | 2016-06-11 | 2017-05-01 | Pending |  | N
| 2.3.2 F1 | OIE: Freedom Application |  | 16 | 2048 | SSS | Ex-Post | 100% | 0 | 0 | No | 2015-12-01 | 2016-02-01 | 2017-08-31 | In Progress
| 2.3.2 M8 | GAP Workshop & Training- Quality Management Systems, GAP Awareness,Food Handlers certification, HACCP, Plant Protection fertilizer and IPM, Documentation process mapping and root cause analysis, Food safety, First Aid , GAP Auditor Experience, Food Safety Management Systems, Farm Assurer |  | 140 | 17920 | PC | Ex-post | 100% | 0 | 0 | No | 2016-01-16 | 2016-02-14 | 2017-08-31 | In Progress | HASSAP Training for Farmers. Lorran-Notdoing this. Incorporated contents in other training. Lorran to give Garfiled Receipte
| 4.3.3 D | PIU Training & Workshop |  | 53 | 6784 | PC | Ex-ante | 100% | 0 | 0 | No | 2015-06-15 | 2016-06-23 | 2017-06-02 | In Progress |  | N
| 4.3.3 E | General Administrative activities- Advertisement , Office Supplies etc. |  | 25 | 3200 | PC | Ex-post | 100% | 0 | 0 | No | 2010-10-01 | 2010-12-10 | 2017-06-03 | In Progress |  | N
|  | SUB-TOTAL - NON-CONSULTANCY SERVICES |  | 317.1 | 40588.8
| D | CONSULTANCY SERVICES
| 2.2.6 B | Pesticide Survey: Travelling for RADA officers conducting survey |  | 12.6 | 1612.8 | SSS | Ex-Post | 100% | 0 | 0 | No | 2016-08-01 | 2016-09-02 | 2017-02-01 | Completed
| 2.2.6 D | Pesticide Survey Data Coding Entry analysis |  | 19.3798 | 2500 | SSS | Ex-Post | 100% | 0 | 0 | No | 2016-09-01 | 2016-11-02 | 2017-06-06 | Pending
| 2.3.2 M5 | GAP application and certification |  | 70 | 8960 | SSS | Ex-ante | 100% | 0 | 0 | No | 2016-10-01 | 2017-09-14 | 2017-09-30 | Pending | this will be done at theend
| 2.3.2 M6 | GAP PR activities |  | 32.093 | 4140 | QCBS | Ex-post | 100% | 0 | 0 | No | 2016-09-01 | 2017-07-14 | 2017-07-30 | Pending
| 2.3.8 | Consultancy to Establish FS, PH and AH Laboratory Networks with QA Systems incorporated |  | 20 | 2560 | QCBS | Ex-ante | 100% | 0 | 0 | No | 2016-09-01 | 2017-02-01 | 2017-04-12 | Cancelled |  | C
| 3.2.2 C82 | Permits and Licences DHNF and Hounslou |  | 1.16 | 148.48 | SSS | Ex-ante | 100% | 0 | 0 | No | 2016-10-01 | 2017-02-02 | 2017-04-30 | In Progress
| 3.2.2 A1 | SPSS training Consultancy |  | 12 | 1536 | PC | Ex-ante | 100% | 0 | 0 | No | May 30 2017 | 2017-02-03 | 2017-06-01 | Pending
| 5.1.4 | Consultancy to finalise project |  | 40 | 5120 | QCNI | Ex-ante | 100% | 0 | 0 | No | 2016-07-01 | 2017-08-01 | 2017-09-01 | Pending |  | C
| 1.1.2/ 2.1.3/2.3.3 and 3.1 | Public Relation/ Information Events |  | 20 | 2560 | QCBS | Ex-post | 100% | 0 | 0 | No | 2016-05-14 | 2017-06-11 | 2017-10-09 | In Progress |  |  |  | To Utilize International Advertising
| 1.1.4 | Group Dynamics/Capacity Building Workshop (Farmers/Producers) 40 Worshops and 5 Prenters |  | 9 | 1152 | QCNI | Ex-ante | 100% | 0 | 0 | No | 2015-05-01 | 2015-06-23 | 2017-03-31 | In Progress | Ongoing Workshops | C
| 1.2.2B | Videographer- video/publication on post-harvest handling. |  | 13 | 1664 | SSS | Ex- ante | 100% | 0 | 0 | No | 2017-05-07 | 2017-07-28 | 2017-10-01 | In Progress |  | C
| 2.1.2 G | Hire international consultant to review the surveillance system of foodborne illnesses; update and edit FBD manuals |  | 40 | 5120 | QCII | Ex-ante | 100% | 0 | 0 | No | 2016-09-15 | 2017-05-11 | 2017-09-01 | Pending |  | C
| 2.1.4 | Hire national consultant(s) to develop, produce and disseminate manuals and protocols on GAP/ GMPs for major non-traditional products. |  | 40 | 5120 | QCNI | Ex-Ante | 100% | 0 | 0 | No | 2016-04-14 | 2016-05-18 | 2017-10-28 | In Progress |  | C
| 2.1.4 A | Hire three (3) national consultants to provide technical assistance for the implementation of food safety assurance requirements in supported value chains (Prepare procedures manuals and for integrated food safety assurance based on GAP, GMP, HACCP & SSOPs). |  | 60 | 7680 | QCNI | Ex-Ante | 100% | 0 | 0 | No | 2016-04-14 | 2016-05-18 | 2017-12-28 | In Progress |  | C
| 2.3.3 B | Bulletins on AH issues - Development of promotional material for AH |  | 10 | 1280 | QCNI | Ex-post | 100% | 0 | 0 | No | 2016-04-01 | 2017-04-30 | 2017-06-30 | In Progress |  | N |  | Date Changed
| 3.4.1A | Water Based Environmental Analysis, Water analysis within the four agro-parks |  | 237.563 | 30408.064 | QCBS | Ex-ante | 100% | 0 | 0 | No | 2014-09-01 | 2017-06-30 | 2017-10-03 | In progress |  | C
| 5.1.1 | M&E Short Term Consultancy |  | 21.2093 | 2714.796 | QCNI | Ex-post | 100% | 0 | 0 | No | 2015-05-14 | 2016-05-30 | 2017-06-30 | Awarded |  | C
| 5.1.2 | Employment of a Consultant to conduct and present a Performance Vision and Strategy (PVS) assessment |  | 80 | 10240 | QCNI | Ex-Ante | 100% | 0 | 0 | No | 2017-03-01 | 2017-03-31 | 2017-08-01 | Pending
| 5.1.3 | Employment of a consultant to conduct and present Consumer Awareness Survey |  | 120 | 15360 | QCNI | Ex-Ante | 100% | 0 | 0 | No | 2017-03-01 | 2017-04-01 | 2017-08-02 | Pending
| 5.1.4 | Final survey (base line survey) |  | 24 | 3072 | SSS | Ex-post | 100% | 0 | 0 | No | 2017-07-01 | 2017-06-01 | 2017-08-02 | Pending
| 5.1.5 | Competitiveness study to assess sales and estimate employment in value Chain |  | 40 | 5120 | QCNI | Ex-post | 100% | 0 | 0 | No | 2017-07-01 | 2017-06-01 | 2017-10-01 | Pending
|  | SUB-TOTAL - CONSULTANCY SERVICES |  | 845.4052 | 108263.34
|  | SUB-TOTAL TO BE AWARDED |  | 4281.6924 | 153368871.6453 | [11 empty] | W
AWARDED & COMPLETED
GOODS
| 1.2.2 A | Training Materials and Equipment for Farmer Field Schools |  | 15 | 1920 | PC | Ex-post | 100% | 0 | 0 | No | 2014-04-01 |  |  | Awarded |  | G
| 1.2.3 A | Leadership & Organization Skills Workshops 52 worshops |  | 38 | 4864 | PC | Ex-ante | 100% | 0 | 0 | No | 2016-04-22 | 2016-05-28 | 2017-02-22 | In Progress | 2 workshops remian. They will be executed over the Jan-Feb 2017 period
| 2.1.2 A | Computers, GPS and ICT peripherals for labs and AIT Unit |  | 52.5 | 6720 | PC | Ex-ante | 100% | 0 | 0 | No | 2013-12-01 |  |  | Awarded |  | G
| 2.1.2 C | Purchase equipment and supplies MOH- EH, VSD, FSPID/MIIC, Bodles Plant Health labs, PQ Risk Analysis Unit and RADA (Lot 1-3) |  | 261.42 | 33461.76 | ICB | Ex-ante | 100% | 0 | 0 | No | 2014-01-01 | 2015-04-01 | 2015-09-17 | Awarded |  | G
| 2.1.2 F1 | Purchase equipment and supplies MOH/EH, VSD, FSPID, MIIC, Bodles, Plant Health Labs and RADA (Contract 1) |  | 11.06 | 1415.68 | ICB | Ex-Ante | 100% | 0 | 0 | No | 2012-10-10 |  |  | Completed |  | G
| 2.1.2 F2 | Purchase equipment and supplies MOH/EH, VSD, FSPID, MIIC, Bodles, Plant Health Labs and RADA (contract 2) |  | 25.63 | 3280.64 | ICB | Ex-Ante | 100% | 0 | 0 | No | 2012-10-10 |  |  | Completed |  | G
| 2.1.3 C | Elevator Bucket for Metal Detector for Fisheries Export Division |  | 31.82 | 4072.96 | SSS | Ex-Ante | 100% | 0 | 0 | No | 2014-12-14 | 2015-04-15 | 2015-09-29 | Awarded |  | G
| 2.2.2 (B) | Purchase of equipment for Pesticide analysis, Gas Chromatograph Mass Spectrometer |  | 140 | 17920 | NCB | Ex-ante | 100% | 0 | 0 | No | 2014-12-01 | 2015-04-22 | 2015-10-07 | Awarded |  | G
Awarded | 2.1.2 F | Purchase equipment and supplies MOH/EH, VSD, FSPID, MIIC, Bodles, Plant Health Labs and RADA (Lot 4-6) |  | 321.65 | 41171.2 | ICB | Ex-Ante | 100% | 0 | 0 | No | 2015-12-01 | - | - | In Progress | DR-To be awarded in 2 weeks | G
|  | Lot 4 |  | 111.1 | 14220.8 | ICB | Ex-Ante | 100% | 0 | 0 | No | 2015-12-01 | 2017-04-17 | 2017-07-31 | In Progress
|  | Lot 5 |  | 189.171 | 24213.8867 | ICB | Ex-Ante | 100% | 0 | 0 | No | 2015-12-01 | 2017-01-13 | 2017-04-30 | In Progress
|  | Lot 6 |  | 17.3491 | 2220.681 | ICB | Ex-Ante | 100% | 0 | 0 | No | 2015-12-01 | 2017-01-13 | 2017-04-30 | In Progress
| 2.2.2 (C ) | RT-PCR Real time mini kits for Bodles |  | 5 | 640 | PC | Ex-ante | 100% | 0 | 0 | No | 2015-01-01 | 2015-04-30 | 2015-05-21 | Awarded |  | G
| 2.2.2(E ) | Refractometer for Bodles |  | 0.05 | 6.4 | PC | Ex-ante | 100% | 0 | 0 | No | 2014-11-01 | 2015-04-22 | 2015-10-07 | Awarded |  | G
| 2.2.3 | West Indian Fruit Fly Surveillance Project (The purchase of trapping equipment) |  | 20 | 2560 | PC | Ex-ante | 100% | 0 | 0 | No | 2015-04-01 | 2015-05-18 | 2016-05-16 | Awarded |  | G
| 2.2.8 | Procurement of 16000 Delta Traps, TriMed lure and inserts |  | 95 | 12160 | PC | Ex-Ante | 100% | 0 | 0 | No | 2014-10-14 |  |  | Awarded |  | G
| 2.3.2 M7 | GAP Equipment, Stationary and Material |  | 40 | 5120 | PC | Ex-post | 100% | 0 | 0 | No | 2016-01-16 | 2016-02-14 | 2017-07-12 | In Progress | All stationery items have been procured. The Planting Material for Produce to be Global GAP Certified are the material remaining to be procured
| 2.3.2. M7.2 | GAP Equipment , Material ,Logistics and Tracebility Supplies |  | 65 | 8320 | PC | Ex-post | 100% | 0 | 0 | No | 2016-11-01 | 2017-01-01 | 2017-09-09 | Pending | Pending the nearing of completion of infrastructure activities
| 3.2.2 (J) | Purchase of Irrigation Design Software. - W-CADI |  | 10 | 1280 | SSS | Ex-post | 100 | 0 | 0 | No | 2015-11-01 | 2015-04-30 | 2017-04-30 | In Progress | SA - Ditto | G
| 2.3.2 B | Microsoft Share Point 2010 |  | 7 | 896 | SSS | Ex-Ante | 100% | 0 | 0 | No | 2014-08-01 |  |  | Awarded |  | G
| 2.3.2 F4 | OIE: Materials and equipment for OIE training |  | 4.5 | 576 | PC | Ex-Post | 100% | 0 | 0 | No | 2015-11-01 | 2015-11-30 | 2015-12-15 | Awarded |  |  | Speak to Naeen
| 2.3.4 | Equipment for AIT (tagging equipment and cattle passport) |  | 43 | 5504 | ICB | Ex-ante | 100% | 0 | 0 | No | 2012-09-01 |  |  | Awarded |  | G
| 2.3.4 D | Restraint Material for NAITS |  | 1.3 | 166.4 | PC | Ex-ante | 100% | 0 | 0 | No | 2014-12-14 | 2015-04-29 | 2015-06-09 | Awarded |  | G
| 2.3.4 F | Equipment for AIT/Security Paper |  | 9 | 1152 | PC | Ex-ante | 100% | 0 | 0 | No | 2014-09-01 | 2015-04-29 | 2015-06-09 | Awarded |  | G
| 3.2.2 ( E) | New Forrest Duff House Farmer Field School – Sweet Potato and Onions |  | 5.38 | 688.64 | PC | Ex-ante | 100% | 0 | 0 | No | 2014-07-01 |  |  | Completed |  | G
| 3.2.2 (B) | New Forrest Duff House - 1 Farmer Field School |  | 2.27 | 290.56 | PC | Ex-ante | 100% | 0 | 0 | No | 2013-12-01 |  |  | Completed |  | G
| 3.2.2 (C) | New Forrest Duff House - 2 No. Demo Plots Onions (0.5 acres each) |  | 10.76 | 1377.28 | PC | Ex-Ante | 100% | 0 | 0 | No | 2013-12-01 |  |  | Completed |  | G
| 3.2.2 (F) | New Forrest Duff House Demo Plot – 1 acre Sweet Potato |  | 25.56 | 3271.68 | PC | Ex-ante | 100% | 0 | 0 | No | 2014-07-01 |  |  | Completed |  | G
| 3.2.2 (H) | Yallahs Demo Plot – 1 acre Sweet Potato |  | 30.75 | 3936 | PC | Ex-post | 100% | 0 | 0 | No | 2014-07-01 |  |  | Awarded |  | G
| 3.2.2 (K) | Yallahs Demo Plot – Sweet Potato |  | 10 | 1280 | PC | Ex-post | 100% | 0 | 0 | No | 2015-08-01 | 2015-09-17 | 2015-12-30 | Awarded |  | G
| 3.2.2 (L) | Yallahs Demo Plot – Onions |  | 8 | 1024 | PC | Ex-post | 100% | 0 | 0 | No | 2015-08-01 | 2015-09-17 | 2015-12-30 | Awarded |  | G
| 3.2.2 (M) | Yallahs & New Forrest Duff House Farmer Field School - Sweet Potato |  | 8 | 1024 | PC | Ex-post | 100% | 0 | 0 | No | 2015-08-01 | 2015-09-17 | 2016-01-30 | Awarded |  | G
| 3.2.2 (N) | New Forrest Duff House Demo Plot – Sweet Potato |  | 8 | 1024 | PC | Ex-post | 100% | 0 | 0 | No | 2015-08-16 | 2015-10-01 | 2016-01-30 | Awarded |  | G
| 3.2.2 A | New Forrest Duff House - Demonstration plot and FFS (MD2 Pineapples)1/2 acre |  | 15.31 | 1959.68 | PC | Ex-ante | 100% | 0 | 0 | No | 2013-12-01 |  |  | Completed |  | G
| 3.2.2 G | New Forrest Duff House Farmer Field School – Sweet Potato and Onions |  | 7 | 896 | PC | Ex-Ante | 100% | 0 | 0 | No | 2014-06-01 |  |  | Completed |  | G
| 3.2.2 Q3 | Sweet Potato Clean Seed Development |  | 57 | 7296 | PC | Ex-post | 100% | 0 | 0 | No | 2015-03-01 | 2015-07-22 | 2016-02-02 | Awarded |  | G
| 3.2.2 Q4 | Sweet Potato Clean Seed Procurement |  | 25 | 3200 | PC | Ex-post | 100% | 0 | 0 | No | 2015-03-01 | 2015-07-22 | 2016-02-02 | Awarded |  | G
| 4.1.1 (B) | Office: Office Equipment , Furniture and Supplies for PIU |  | 36.5 | 4672 | PC | Ex-post | 100% | 0 | 0 | No | 2010-10-01 | 2010-11-01 | 2017-02-18 | Awarded |  | G
| 4.1.1A | Office Equipment , Furniture and Supplies for PIU |  | 27 | 3456 | PC | Ex-post | 100% | 0 | 0 | No | 2013-10-01 |  |  | Awarded |  | G
| 4.2.7 | Equipment and Supplies |  | 5 | 640 | PC | Ex-ante | 100% | 0 | 0 | No | 2014-03-01 |  |  | Awarded |  | G
|  | SUB-TOTAL : AWARDED (GOODS) |  | 1791.0801 | 229258.2477
WORKS
| 2.2.1 (A) | Refurbish RD Bodles Plant Health labs |  | 101 | 12928 | NCB | Ex-ante | 100% | 0 | 0 | No | 2014-09-01 | 2015-12-19 | 2016-03-11 | Awarded |  | W
| 2.2.1 (C) | Construction of contraband room at Montego Bay export complex |  | 67 | 8576 | NCB | Ex-ante | 100% | 0 | 0 | No | 2014-12-01 | 2015-12-19 | 2016-03-11 | Awarded |  | W
| 2.3.1 | Refurbish facilities of 2 parish offices – Hanover and Portland |  | 170 | 21760 | NCB | Ex-ante | 100% | 0 | 0 | No | 2014-09-01 | 2015-11-11 | 2016-02-23 | Awarded |  | W
| 2.3.1 (F) | Refurbish Quarantine Laboratory at Plumb Point |  | 90 | 11520 | NCB | Ex-ante | 100% | 0 | 0 | No | 2014-09-01 | 2015-12-12 | 2016-03-23 | Awarded |  | W
| 3.2.2 (B 1) | Infrastructure Yallahs 11,000 M of farm access way (306.9) |  | 806.21 | 103194.88 | NCB | Ex-ante | 100% | 0 | 0 | No | 2014-01-01 | 2014-05-01 |  | Awarded |  | W
| 3.2.2 (B 2) | Infrastructure Yallahs 5,000 M on farm water channel way (57.5) |  | 980 | 125440 | NCB | Ex-ante | 100% | 0 | 0 | No | 2014-01-01 | 2014-05-01 |  | Awarded |  | W
| 3.2.2 (C 2) | Infrastructure Spring Plain/Ebony Pipes, fittings, valves motors etc. |  | 1945.5 | 249024 | NCB | Ex-ante | 100% | 0 | 0 | No | 2013-12-01 | 2014-05-28 | 2014-10-28 | Awarded |  | W
| 3.2.2 (C 3) | Infrastructure Spring Plain/Ebony Re establish 3400M access way (904.8) and 800M of on farm water channel (482) |  | 752.17 | 96277.76 | NCB | Ex-ante | 100% | 0 | 0 | No | 2013-12-01 | 2014-05-28 | 2014-10-28 | Awarded |  | W
| 3.2.2 (C4) | Infrastructure Electrical Works - Spring plain / Ebony |  | 68 | 8704 | SSS | Ex-ante | 100% | 0 | 0 | No | 2015-06-01 | 2015-07-12 | 2015-11-09 | Awarded |  | W
| 3.2.2 A1 | Infrastructure- New Forrest Duff House 8,000 M Farm access way 2,300 M Water channel way |  | 693.67 | 88789.76 | NCB | Ex-ante | 100% | 0 | 0 | No | 2014-01-01 | 2014-05-28 | 2014-10-28 | Awarded |  | W
| 3.2.2 A2 | Infrastructure New Forrest Duff House Packaging Facility |  | 600 | 76800 | NCB | Ex-ante | 100% | 0 | 0 | No | 2014-01-01 | 2014-05-28 | 2014-10-28 | Awarded |  | W
| 3.2.2(C 1) | Infrastructure Spring Plain/Ebony Irrigation: Pumps, and Pump Houses, |  | 647.72 | 82908.16 | NCB | Ex-ante | 100% | 0 | 0 | No | 2014-02-01 | 2014-05-28 | 2014-10-28 | Awarded |  | W
| 4.1.1(C) | PIU Housing |  | 50.5 | 6464 | PC | Ex-ante | 100% | 0 |  | No | 2015-12-12 | 2015-12-30 | 2016-02-02 | Awarded
| 3.2.2 (A3) | Infrastructure Electrical Works - New Forrest Duff House |  | 50 | 6050 | SSS | Ex-ante | 100% | 0 | 0 | No | 2016-01-01 | 2016-03-01 | 2016-06-09 | Awarded |  | W
| 3.2.2 (B) 2 | Electrical Infrastructure Yallahs Design, Supply & Install |  | 20 | 2560 | NCB | Ex-ante | 100% | 0 | 0 | No | 2016-04-01 | 2016-07-12 | 2016-12-23 | Awarded |  | W
|  | SUB-TOTAL: AWARDED (WORKS) |  | 4911.88 | 628720.64
NON CONSULTANCY SERVICES
| 1.1.1 | Export Market Access – Market Research Abroad |  | 48.6 | 6220.8 | QCBS | Ex-ante | 100% | 0 | 0 | No | 2013-06-01 |  |  | Cancelled |  | N
| 1.1.1 (A) | Development of Export Market Platform |  | 4.9 | 627.2 | PC | Ex-ante | 100% | 0 | 0 |  | 2014-02-01 | 2014-03-01 | 2014-03-01 | Completed
| 1.1.1 E | Value Chain Institutional Strengthening 5 workshops to include participants the MICAF, RADA, AIC, ACP , Exporters and the Agro-Park. Airfare , accommodation and per diem for two IICA Consultants |  | 14 | 1176 | PC | Ex-Ante | 100% | 0 | 0 | No | 2016-08-01 | 2016-05-01 | 2017-05-28 | Pending
| 1.1.1 K | Farmer/Exporter ( Business Mission to the US) Airfare, perdiem and ground transport for 5 MICAF/ACP Official and 10 Producers/Exporters and 6 Presenters |  | 25 | 3200 | PC | Ex-ante | 100% | 0 | 0 | No | 2016-09-01 | 2016-11-01 | 2017-05-29 | Pending |  | N
| 1.1.1 G | Export Market Access and the Development of the Export market Platform with special emphasis on two sweet potato varieties for mainstream markets |  | 45 | 5760 | PC | Ex-Ante | 100% | 0 | 0 | No | 2014-11-01 |  |  | Awarded |  | N
| 1.1.1 H | Local Supply export readiness analysis (15) |  | 15 | 1920 | SSS | Ex-ante | 100% | 0 | 0 | No | 2014-12-01 | 2015-05-08 | 2015-07-31 | Awarded |  | N
| 1.1.1 J | US Buyer Mission to Jamaica.(18) |  | 18 | 2304 | PC | Ex-ante | 100% | 0 | 0 | No | 2015-05-05 | 2015-05-29 | 2015-08-20 | Awarded |  | N
| 1.1.1 L | Export Management Capacity Building Farmers/Exporters to US |  | 12 | 1536 | PC | Ex-ante | 100% | 0 | 0 | No | 2015-05-01 | 2015-05-29 | 2015-08-20 | Awarded |  | N
| 2.1.1 B | Diploma in Veterinary Public Health (overseas) |  | 40 | 5120 | SSS | Ex-ante | 100% | 0 | 0 | No | 2013-09-01 |  |  | Awarded |  | N
| 2.1.1E | Prepare and disseminate bulletin on National Food Safety Policy |  | 10 | 1190 | PC | Ex-post | 100% | 0 | 0 | No | 2015-10-15 | 2015-11-16 | 2015-11-30 | Completed |  | N
| 2.1.2 B | Workshop on pest surveillance |  | 6 | 768 | PC | Ex-post | 100% | 0 | 0 | No | 2013-02-01 |  |  | Completed |  | N
| 2.1.3 | Organize Food Safety Week- 2013 |  | 10.89 | 1393.92 | PC | Ex-ante | 100% | 0 | 0 | No | 2013-09-01 |  |  | Completed |  | N
| 2.1.3 A | Organize Food Safety Week- 2014 |  | 10.89 | 1393.92 | PC | Ex-ante | 100% | 0 | 0 | No | 2014-10-01 | 2014-10-01 |  | Completed |  | N
| 2.1.3 B | Organize Food Safety Week- 2015 |  | 15 | 1920 | PC | Ex-Post | 100% | 0 | 0 | No | 2015-09-01 | 2015-09-30 | 2015-11-22 | Awarded |  | N
| 2.1.5 | ISO 22000 & 14001 Training internationally to support certification of agro-parks |  | 23 | 2944 | SSS | Ex-Ante | 100% | 0 | 0 | No | 2015-05-01 | 2015-06-01 | 2015-08-21 | Awarded |  | N
| 2.1.6 | Workshops to prepare and evaluate the implementation plan, budget and operational manuals to implement the National Food Safety Policy |  | 4 | 476 | PC | Ex-post | 100% | 0 | 0 | No | 2015-12-15 | 2016-01-30 | 2016-02-15 | Completed |  | N
| 2.2.5 | Integrated Pest Management Training At Bodles Research Station |  | 5 | 640 | PC | Ex-ante | 100% | 0 | 0 | No | 2015-04-14 | 2015-04-30 | 2015-07-22 | Awarded |  | N
| 2.2.7 | Pest Identification and Recognition Training |  | 2 | 256 | PC | Ex-ante | 100% | 0 | 0 | No | 2014-07-14 | 2014-08-01 |  | Awarded |  | N
| 2.3.1 (B) | Measurement of Uncertainty |  | 4 | 512 | SSS | Ex-ante | 100% | 0 | 0 | No | 2014-06-01 |  |  | Completed |  | N
| 2.3.1 (C) | Practical and applied Gas Chromatography (Overseas) |  | 4 | 512 | SSS | Ex-ante | 100% | 0 | 0 | No | 2014-02-01 |  |  | Completed |  | N
| 2.3.1 (D) | Training in Quality Assurance (Overseas) |  | 3 | 384 | SSS | Ex-ante | 100% | 0 | 0 | No | 2014-10-01 |  |  | Completed |  | N
| 2.3.1 (E) | Overseas training (epidemiology, surveillance, risk analysis) |  | 28 | 3584 | SSS | Ex-ante | 100% | 0 | 0 | No | 2014-05-01 |  |  | Awarded |  | N
| 2.3.1 (H) | Overseas training Molecular Biology Techniques (USA) |  | 4 | 512 | SSS | Ex-ante | 100% | 0 | 0 | No | 2014-10-01 |  |  | Completed |  | N
| 2.3.2 A | Practical Food Microbiology |  | 10 | 1280 | SSS | Ex- ante | 100% | 0 | 0 | No | 2014-10-01 |  |  | Awarded |  | N
| 2.3.2 C | Overseas training in Methods of Pesticide Residue Analysis and Laboratory Accreditation according to ISO17025 |  | 81 | 10368 | SSS | Ex- ante | 100% | 0 | 0 | No | 2014-04-01 |  |  | Awarded |  | N
| 2.3.2 D | Overseas conference 46th session of the Codex Committee on Food hygiene |  | 4 | 512 | SSS | Ex-Ante | 100% | 0 | 0 | No | 2014-11-01 |  |  | Awarded |  | N
| 2.3.2 D1 | Attendance to 47th Codex Conference 2015 |  | 10 | 1280 | SSS | Ex-Post | 100% | 0 |  | No | 2015-09-01 | 2015-11-20 | 2015-11-20 | Awarded
| 2.3.2 F2 | OIE: Elisa Test Kits and Disposables |  | 31 | 3968 | PC | Ex-Post | 100% | 0 | 0 | No | 2015-04-01 | 2014-10-03 | 2014-08-15 | Awarded
| 2.3.2 F3 | OIE: Stakeholders Sensitization & Training |  | 4 | 512 | PC | Ex-Post | 100% | 0 | 0 | No | 2014-09-01 | 2014-10-01 | 2014-11-15 | Awarded
| 2.3.2 F5 | OIE: Staff Training in OIE |  | 5 | 640 | SSS | Ex-Post | 100% | 0 | 0 | No | 2014-11-01 | 2016-02-01 | 2016-02-15 | Awarded
| 2.3.2 L | Workshop to train farmers in personal protective equipment and environmental management |  | 19 | 2432 | PC | Ex-Post | 100% | 0 | 0 | No | 2015-07-01 | 2015-06-01 | 2015-08-21 | Awarded |  | N
| 2.3.4 G | Hosting services for six months and service transfer for AIT database |  | 11 | 1408 | SSS | Ex-Ante | 100% | 0 | 0 | No | 2014-12-01 |  |  | Awarded |  | N
| 2.3.4 H | Overseas Training in Heavy metals including mercury analysis |  | 28 | 3584 | SSS | Ex-Ante | 100% | 0 | 0 | No | 2015-07-01 | 2015-08-01 | 2015-11-01 | Awarded |  | N
| 2.3.7 | Method of Determination of Drug Residue in Aquaculture, Meats & Poultry |  | 20 | 2560 | SSS | Ex-ante | 100% | 0 | 0 | No | 2015-06-01 | 2015-06-30 | 2015-07-22 | Awarded |  | N
| 3.2.2 (C ) 8 | Permits & Licence for Spring Plains |  | 9 | 1152 | SSS | Ex-ante | 100% | 0 | 0 | No | 2015-01-01 |  |  | Awarded |  | N
| 3.2.2 C81 | Permits & Licence for New Forrest Duff House |  | 4 | 512 | SSS | Ex-ante | 100% | 0 | 0 | No | 2015-01-01 |  |  | Awarded |  | N
| 3.2.2 C82 | Permits & Licence for Yallahs |  | 4 | 512 | SSS | Ex-ante | 100% | 0 | 0 | No | 2015-01-01 |  |  | Awarded |  | N
| 3.2.2 C83 | Permits & Licence for Hill Run |  | 8 | 1024 | SSS | Ex-ante | 100% | 0 | 0 | No | 2015-01-01 |  |  | Awarded |  | N
| 4.2.8 | PIU Administrative and Promotional Expense |  | 40.12 | 5135.36 | QCNI | Ex-ante | 100% | 0 | 0 | No | 2013-01-01 |  |  | Awarded |  | N
| 4.3.3 | ACP PIU Retreat 2014 |  | 4.5 | 576 | PC | Ex-ante | 100% | 0 | 0 | No | 2014-11-01 |  |  | Awarded |  | N
| 4.3.3 A | ACP PIU Retreat 2015 |  | 6 | 768 | PC | Ex-ante | 100% | 0 | 0 | No | 2015-10-01 | 2015-11-18 | 2015-11-20 | Awarded |  | N
| 1.1.1 | Export Market Access and the Development of the Export market Platform |  | 45 | 5445 | SSS | Ex-ante | 100% | 0 | 0 | No | 2015-01-01 | 2015-02-20 | 2016-11-30 | Completed |  | N
| 1.2.3 B | Promotional Activities for Component 1 |  | 15 | 1815 | PC | Ex-ante | 100% | 0 | 0 | No | 2015-07-01 | 2015-08-10 | 2016-09-22 | Awarded |  | N
| 1.3.1 A | Market Linkage for the UK. (Airfare, Accommodation, Per Diem for 5 MICAF/Personell with cost share for 10 agro-park procuders supported by JAMPRO |  | 40 | 4840 | PC | Ex-ante | 100% | 0 | 0 | No | 2014-12-01 | 2016-02-08 | 2016-06-28 | Completed |  | N
| 3.2.3 | International conferences and market access assessment to create and strengthen agri-business linkages |  | 15 | 1815 | PC | Ex-ante | 100% | 0 | 0 | No | 2016-04-01 | 2016-05-01 | 2016-10-30 | Completed |  | N
| 3.3.1 | Workshop: Value Chain Strategic Workshop - Export Management Capacity Building (MOAF, AIC, RADA, ACP, Exporters) |  | 6 | 726 | PC | Ex -ante | 100% | 0 | 0 | No | 2015-04-16 | 2016-06-21 | 2016-12-30 | Awarded |  | N
| 4.3.3 D1 | PIU Servers & Equipment |  | 15 | 1815 | PC | Ex-post | 100% | 0 | 0 | No | 2015-12-16 | 2016-01-18 | 2016-03-23 | Awarded
| 1.1.1 C | Farmer Enterprise Management Capacity Building (77) to the US- Airfare , accommodation and per diem for two IICA Consultants and cost for 8 workshopa |  | 30 | 3840 | PC | Ex-ante | 100% | 0 | 0 | No | 2016-06-01 | 2016-07-01 | 2016-07-30 | Completed |  | N
| 1.1.1 F | Technical Cooperation Support |  | 6 | 768 | PC | Ex-ante | 100% | 0 | 0 | No | 2014-08-01 | 2016-08-30 | 2017-01-22 | Completed |  | N
| 2.2.6 A | Pesticides Survey Training Workshops (Venue Rental, Meals ) |  | 5.5 | 704 | PC | Ex-Post | 100% | 0 | 0 | No | 2016-05-01 | 2016-06-10 | 2017-05-30 | Completed
|  | SUB-TOTAL: AWARDED (NON-CONSULTANCY SERVICES) |  | 640.4 | 81229.2
CONSULTANCY SERVICES
| 1.1.5 | Conduct further update to the Jamaica Agricultural Marketing Information System (JAMIS) system |  | 7.5 | 960 | QCBS | Ex- ante | 100 | 0 | 0 | No | 2013-02-01 |  |  | Completed |  | C
| 1.2.7 | international Agribusiness and marketing consultant- US Market Validation |  | 25 | 3200 | SSS | Ex- ante | 100 | 0 | 0 | No | 2014-02-01 |  |  | Awarded |  | C
| 1.3.1 | Soil test and analysis within the agro-parks |  | 1.5 | 192 | SSS | Ex- ante | 100 | 0 | 0 | No | 2013-11-01 |  |  | Completed |  | C
| 2.1.1 | Architectural Services |  | 50 | 6400 | QCBS | Ex-ante | 100 | 0 | 0 | No | 2012-07-01 |  |  | Awarded |  | C
| 2.1.1 A | Hire legal consultant to prepare legislation of the Food Safety Policy. |  | 20.8 | 2662.4 | QCNI | Ex-Ante | 100 | 0 | 0 | No | 2013-06-01 |  |  | Awarded |  | C
| 2.3.1 | Consultant to provide editorial services for the Animal Health and Welfare Policy |  | 1.6 | 204.8 | SSS | Ex-ante | 100 | 0 | 0 | No | July, 2013 |  |  | Awarded |  | C
| 3.2.2 A2 | Quantity Surveying Consultancy for New Forrest Duff House Packaging Facility |  | 13 | 1664 | LCS | Ex-ante | 100% | 0 | 0 | No | 2015-11-28 | 2015-12-28 | 2016-07-28 | Awarded
| 2.3.3 | Purchase external hosting for (AIT database) |  | 18 | 2304 | SSS | Ex-ante | 100 | 0 | 0 | No | 2014-01-01 |  |  | Awarded |  | C
| 2.3.4 A | Animal Identification& Traceability (AIT) (including software development) |  | 165 | 21120 | SSS | Ex-ante | 100 | 0 | 0 | No | 2012-09-01 |  |  | Awarded |  | C
| 2.3.4 B | PR Consultancy for NAIT'S Programme |  | 100 | 12800 | QCBS | Ex- Ante | 100% | 0 | 0 | No | 2014-09-01 | 2015-11-20 | 2016-03-30 | Awarded |  | C
| 3.1.1 | Monitoring & Travelling RADA Officers |  | 45 | 5760 | SSS | Ex-ante | 100 | 0 | 0 | No | 2014-01-01 |  |  | Awarded |  | C
| 3.1.3 A | Value Chain Manager (3 #) |  | 90.222 | 11548.416 | QCNI | Ex-post | 100 | 0 | 0 | No | 2012-05-01 |  |  | Awarded |  | C
| 3.2.2 D 2 | Hire national consultant to a Design Reeds Bed for the Hill Run Agro Park |  | 5 | 640 | QCNI | Ex-ante | 100% | 0 | 0 | No | 2014-11-01 | 2015-04-13 | 2015-08-10 | Awarded |  | C
| 3.2.2 E | 3 Site Managers /Project Management Consultant Engineers for Agro Park Infrastructure Work |  | 280 | 35840 | QCNI | Ex-ante | 100 | 0 | 0 | No | 2014-01-01 |  |  | Awarded |  | C
| 3.3.1C | Consultancy Services Land Surveyor |  | 22.12 | 2831.36 | QCNI | Ex-Ante | 100 | 0 | 0 | No | 2014-10-01 |  |  | Awarded |  | C
| 3.3.1D | Documentation, Digitizing and Archiving of AIC/ACP Records |  | 22.5 | 2880 | CQS | Ex-ante | 100 | 0 | 0 | No | 2013-01-01 |  |  | Awarded |  | C
| 3.3.2 | Study of the Operational Procedures of the Agro-Investment Corporation and to Design of a Cost Recovery Mechanism |  | 35 | 4480 | QCNI | Ex-Post | 100 | 0 | 0 | No | 2012-08-01 |  |  | Cancelled |  | C
| 3.3.3 (A) | Agro-Processing and Marketing Specialist |  | 48 | 6144 | SSS | EX-Ante | 100 | 0 | 0 | No | 2014-04-14 |  |  | Awarded |  | C
| 3.3.3 C | IT Officer |  | 36.32 | 4648.96 | QCNI | Ex-ante | 100% | 0 | 0 | No | 2015-02-01 | 2015-05-25 | 2016-06-20 | Awarded |  | C
| 4.2.1 | Programme Director |  | 149.46 | 19130.88 | QCNI | Ex-ante | 100 | 0 | 0 | No | 2013-01-01 | 2013-09-01 | 2015-03-01 | Awarded |  | C
| 4.2.2 | Programme Admin Assistant |  | 46.52 | 5954.56 | QCNI | Ex-ante | 100 | 0 | 0 | No | 2013-07-01 | 2013-04-01 | 2015-04-01 | Awarded |  | C
| 4.2.3 | Financial Administrative Officer |  | 112.1 | 14348.8 | QCNI | Ex-ante | 100 | 0 | 0 | No | 2013-02-01 | 2013-10-01 | 2015-11-01 | Awarded |  | C
| 4.2.4 | Component 1 Coordinator |  | 35.35 | 4524.8 | SSS | Ex -ante |  |  |  |  | 2012-07-01 | 2013-12-01 |  | Awarded |  | C
| 4.2.4 | Procurement Officer No. 1 |  | 47.63 | 6096.64 | QCNI | Ex -ante | 100 | 0 | 0 | No | 2014-01-01 | 2014-06-01 | 2015-06-01 | Awarded |  | C
| 4.2.4 A | Procurement Officer No.2 |  | 43.01 | 5505.28 | QCNI | Ex -ante | 100 | 0 | 0 | No | 2014-04-01 | 2014-09-01 | 2015-07-01 | Awarded |  | C
| 4.2.5 | Procurement Assistants No. 1 |  | 38.77 | 4962.56 | QCNI | Ex -ante | 100 | 0 | 0 | No | 2014-02-01 |  |  | Awarded |  | C
| 4.2.5 (A) | Procurement Assistants No. 2 |  | 33.6 | 4300.8 | QCNI | Ex -ante | 100 | 0 | 0 | No | 2014-09-01 |  |  | Awarded |  | C
| 5.1.1 A | M & E Short-Term Consultancy |  | 26 | 3328 | QCNI | Ex-ante | 100% | 0 | 0 | No | 2015-03-14 | 2015-05-11 | 2015-09-04 | Awarded |  | C
| 4.2.6 &3.3.3A | Component 2 Coordinator & Evironmental Evaluation Specialist |  | 150.97 | 19324.16 | QCNI
| 5.1.2 | Baseline Design & Implementation Consultant |  | 16 | 2048 | SSS | Ex-ante | 100 | 0 | 0 | No | 2012-08-01 | 2012-10-01 |  | Awarded |  | C
| 5.1.3 A | Baseline survey for agro-parks |  | 5.5 | 704 | SSS | Ex-ante | 100% | 0 | 0 | No | 2016-01-01 | 2016-03-09 | 2016-06-15 | Awarded |  | C
| 5.1.4 | Mid Term Evaluation |  | 25 | 3200 | QCII | Ex-post | 100 | 0 | 0 | No | 2013-07-01 | 2013-07-01 |  | Awarded |  | C
| 1.2.3 | 1 National Cluster Coordinator and 2 Cluster Coordintors (3 No.) |  | 101.322 | 12259.962 | QCNI | Ex-ante | 100% | 0 | 0 | No | 2014-11-14 | 2016-02-04 | 2017-02-28 | Awarded |  | C
| 3.2.2 (C4A) | Electrical Consultancy for Infrastructure Electrical Works - Spring plain / Ebony |  | 13 | 1573 | QCNI | Ex-ante | 100% | 0 | 0 | No | 2015-10-01 | 2015-12-01 | 2016-01-30 | Awardeed |  | C
| 4.2.6 | Component Coordinator 3 |  | 43 | 5203 | QCNI | Ex-post | 100% | 0 | 0 | No | 2014-11-14 | 2015-12-15 | 2017-01-01 | Awarded |  | C
| 2.3.2 M10 | GAP Consultant |  | 113.3 | 13709.3 | CQS | Ex-Ante | 100% |  |  |  | 2016-05-01 | 2016-06-01 | 2016-07-30 | Awarded
| 3.2.2 A2.1 | Land Surveying Consultancy for New Forrest Duff House Parking Facility |  | 1.6533 |  | CQS | Ex-ante | 100% | 0 | 0 | No | 2016-02-18 | 2016-04-08 | 2016-04-28 | Awarded |  | C
| 2.3.2 M4 | Employment of 3 Implementing Officers and 1 Compliance Manager for GAP certification & Four Farm Hands |  | 143 | 18304 | QCNI | Ex-post | 100% | 0 | 0 | No | 2015-10-01 | 2016-01-01 | 2017-03-31 | In Progress | Awarded |  |  | Check back with Naeen re dates. Compare with PIP
|  | TOTAL: AWARDED (CONSULTANCY) |  | 1519.002 | 194432.256
|  | TOTAL: AWARDED |  | 8862.3621 | 1133640.3437
|  | TOTAL ALL ACTIVITIES |  | 13144.0545 | 154502511.989
KEY:
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: QCNI: Selection based on comparison of qualifications of national individual consultants; QCII: Selection based on comparison of qualifications of international individual consultants.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
JUSTIFICATION FOR PROCUREMENT USING THE SOLE SOURCE METHOD
1.1.1-Export Market Access – Market Research Abroad,1.1.1(A).Market and related workshop, 1.2.1 Marketing and Negotiation skills workshop 1.1.3 Workshop for Exporters and Potential Exporters :The execution of the ACP has been constrained by difficulties in sourcing the required technical expertise to execute this activity. In the most recent bidding activity, the sole qualified bidder tendered a price which was more than three times the estimated budget of USD$48,000. Following consultation with regional development partners, IICA has agreed to provide technical assistance to the programme based on their mandate to support small and medium scale agricultural and rural producers to penetrate local, regional and international markets and their ongoing work in development of the local agricultural sector. IICA has proven capacity, specialized knowledge and experience of exceptional value in this area required to execute this activity. Based on the agreement, the ACP will pay airfare, accommodation and per diem for three IICA consultants amounting to approximately US$41,000.00. While the savings indicated is important, the main justification for selecting IICA using the sole source method is due to its experience of exceptional value in the field of market studies.
1.1.1 C Farmer Enterprise Management Capacity Building to the US, 1.1.1 H Local Supply export readiness analysis, 1.1.4 Group Dynamics/Capacity Building Workshop (Farmers/Producers): Being implemented through Technical Cooperation agreement with IICA
1.2.1 Group Dynamics Workshops, 1.2.1(B) 1.2.3 Cluster sensitization and cluster formation workshop, 1.2.3 (A) Leadership & Organization skills workshop: These activities will be undertaken by IICA and coordinated by a Cluster Coordinator who is expected to join the ACP team shortly. The ACP intends to work with IICA in critical consultancies and workshops in the above areas. IICA has a mandate to support the Member States such as Jamaica in their efforts to increase and extend innovation in agriculture, to improve productivity, food security, competitiveness and trade facilitation. This alliance with IICA expected to result in significant savings to the ACP with IICA providing high quality service based on its experience and proven track record in this area.
1.2.2 - Farmer field school workshop, 1.2.2(A) –Create and manage demonstration plots for Onion and Iris potato: Rural Agricultural Development Agency (RADA) will be engaged to conduct the farmer field school and manage three demonstration plots for onion and Irish potato. Conducting farmer field school is consistent with the operations of RADA. They have conducted several training sessions with farmers under this component and conducting the farmer field school will be a natural continuation of such training. As far as we are aware no other entity in Jamaica conducts farmer field school which would make a bidding process futile. RADA is the only entity in Jamaica that offers extension services (including training) to farmers. RADA has the technical capacity and institutional structure to respond to farmers on an ongoing basis even after the training is completed. RADA therefore has the experience of exceptional value for the service.
1.2.2 (B). Videographer- video/publication on post-harvest handling: The Jamaica Information Service (JIS) is to be engaged to produce a video publication and 8000 brochures on GAP and Post Harvest Handling. The JIS possesses the necessary technical and creative competencies with decades of experience in production of works of a similar nature and as an inter-government agency, there are significant cost savings to be achieved against that of open market tendering. Through time reserved for government broadcast on electronic media, the JIS can also significantly increase the exposure of the information being disseminated beyond the initial scope of the project. JIS therefore has the experience of exceptional value for service.
1.2.7. Residential Training Courses – International Agribusiness & Marketing 3.3 Conduct Value Chain Strategic Training and Stakeholders workshop: These are specialized Training will also be provided by IICA targeting resource persons in the MOAF along with other stakeholders in the agricultural sector. IICA assists the countries like Jamaica in developing the policies, institutional frameworks and capabilities required to create enabling environments for agribusinesses. IICA will also help Jamaica to develop public policies, strategies and institutions for the promotion and development of more transparent and efficient local markets, and to develop mechanisms and tools that will reduce risks and enable small-scale producers to establish more links with markets. Moreover, it helps to develop strategies and strengthen the institutional framework for promoting international agricultural trade as a factor in development; and assists its member countries in developing capabilities that will enable them to better administer the trade agreements they sign and take greater advantage of them.
1.3.1 Soil test and water analysis within the agro parks
Justification for 2.1.2 A & B
These tests and analysis will be conducted by agencies of the government such as Water Resource Authority (WRA) which have the capacity to carry out these analyses. The budgeted sum of US$7000 for this activity is relatively small and is another justification for the sole source method of procurement.
2.1.1B Diploma in Veterinary Public Health, 2.1.1F - MOH Training EPI action, 2.1.1
These programmes are not offered by any local university. The Diploma in Veterinary Public Health is a specialized course which is only offered regionally by the University of Trinidad and Tobago (UTT). This case UTT is the sole purveyor of this training regionally and has experience of exceptional value for the provision of training services;
For the training in International Epidemiology (B), facilitate the upgrading the national systems for Food-borne Illness (FBI) surveillance, this training represents a continuation of the strengthening of the National Surveillance Unit in surveillance, statistical analysis and reporting on FBI’s. The International Course in Applied Epidemiology is cosponsored by the Emory University and the Centres for Disease Control and Prevention and represents a natural continuation of services provide by the institution, in that the MOH has previously utilized this institution for epidemiology training of previous occasion, including two courses sponsored by ACP in 2012;
All 2.3.1 training courses are geared toward upgrading the technical capacity of the Veterinary Services laboratory services; training topics have been prioritized to facilitate laboratory accreditation. These programmes are not offered by any local universities or training institutions. Each overseas training institution is elected based on the best fit of curriculum with specific training needs.
(A) Overseas training Molecular Biology Techniques – University of Warwick
(B) Measurement of Uncertainty - Joint Research Institute
(C) Practical and applied Gas Chromatography - American Chemical Society Professional Education
(D) Overseas Training in Quality Assurance – UK Accreditation Services
(E) Overseas training (epidemiology surveillance, risk analysis) –University of Colorado, USA
Given the relatively small budget for all these training activities and the fact that each training course will be selected in line with specific training need and budget, the sole source procurement methodology will be utilized.
2.1.3 C Elevator Bucket for Metal Detector for Fisheries Export Division
Existing sections of the Metal Detector already installed, was acquired through direct Contracting for the supply and installation of a Spiral Gravity Separator and bucket Elevator to Profile Industries of Rogers, Minnesota, USA Continued association with Profile Industries in this matter allows for standardization of equipment (Clause 3.6 b) and a smooth continuation of the installation process
2.1.1D Method of Determination of Drug Residue in Aquaculture, Meats & Poultry, 2.1.2 E MOH Training EPI in action (overseas), 2.1.2 F Surveillance activity & application to OIE for disease free status – FMD &CSF
This course is to be sourced from a sole institution providing the course material within the timeframe required. | [16 empty] | This is the only entity to provide the service
2.2.6 B Pesticide Survey: Travelling for RADA officers conducting survey
Activity conducted by Rural Agricultural Development Agency (RADA)
2.3.1 (H) Overseas training Molecular Biology Techniques (USA)
This course is to be sourced from a sole institution providing the course material within the timeframe required.
2.3.2 F Surveillance activity & application to OIE for disease free status – FMD &CSF 2.3.2 F5 Staff Traiining inOIE
Based on difficulties faced by the ACP in procurement specialist consultancy services for all Components of the programme (including a non-response to bids and non-compliant bids) and subsequent intensive consultation with agricultural health and food safety stakeholders, a new approach has been proposed for the surveillance of animal disease. This activity will be now be coordinated by and executed by a Technical Committee and relevant animal health entities. This approach was agreed during the IDB Administrative Mission of August 16th - Review of Component 2.
The activity will be led by the Veterinary Service Division (VSD), which is mandated to (i)develop policies to ensure that Jamaica remains free of exotic disease and (ii) conduct surveillance and monitoring for animal diseases as part of its current work programme. Funding support of the ACP will be used to update the current surveillance programme which is in place; review the protocols with a view to increase sampling and inspection as appropriate; pay additional expenses which will be incurred for active surveillance and monitoring towards declaring disease free status for Classical Swine Flu and Foot& Mouth Disease. While these GOJ agencies lack the budget to carry out effective surveillance, these activities are actually part of their work programmes and the entities already have the technical capacity to successfully execute. The sole sourcing of services in this instance will be utilized given the fact that only VSD, in collaboration with relevant animal health agencies, can successfully execute this activity given its island-wide presence and its years of experience in surveillance for animal diseases.
2.3.2 H ISO 22000 & 14001 Training internationally to support certification of agro-parks
This is the only entity to provide the service
2.3.2 J Farm-to Table Study Programme for food protection, safety, public health and animal health and welfare
This course is being offered by the Costa Rica Government
2.3.2 M5 GAP Application &
Consultant can only be sourced from GAP
2.3.2 M10 GAP Consultant
Consultant can only be sourced from GAP
2.3.6 West Indian Fruit Fly Surveillance Project
5.1.3 Baseline survey for agro-parks
To be done by the MOAF/AMID will be engaged to do this. Only travelling being paid under this arrangement.
2.3.2 F1 OIE: Freedom Application
This is the only entity to provide the service
3.1.1 Technical Seminars – These seminars will target mainly farmers on the four agro parks and other resource persons within AIC and MOAF. The seminars will be by representatives from IICA along with resource persons in RADA. These programmes will look at production systems and management from the methodological and operational side of agricultural operations. IICA with its vast knowledge and expertise in the agribusiness can provided information and techniques to support stakeholders in their efforts to increase and extend innovation in agriculture, in order to improve productivity, competitiveness and trade. IICA undoubtedly has experience of exceptional value to provide this service
3.2.2A Demonstration plots, 3.2.2 Farmer Field Schools (Onion, Pineapple, Sweet Potato and Irish Potato)
These demonstration plots on the agro parks will be managed by RADA as part of its mandate to promote best practices in the agricultural sector. The operations of demonstration plots and farmer field schools on the agro parks will be conducted by RADA which has experience of exceptional value for the services. RADA as part of its core function provides training to farmers across the island on proper farming techniques. The entity has developed a high level competence in the administration and execution of farmer field schools. They have successfully conducted farmer field schools on other Agro Parks such as Plantain Garden River (PGR). RADA is in a position to provide post farmer school visits and consultation which are usually required. RADA undoubtedly has experience of exceptional value to provide this service.
2.3.2 (B) Microsoft has an application called SharePoint 2010, works naturally in Microsoft office, a web-based intranet that can help to improve the organization’s effectiveness by streamlining the management of data, storage of data and access to data. It makes it easier for people to work together.
3.2.2 (J)Purchase of Irrigation Design Software. - W-CADI
This is a patented software that can only be purchased from a single supplier.
3.2.2 (A3) Infrastructure Electrical Works - New Forrest Duff House 3.2.2 (B3) Infrastructure Electrical Works - Yallahs 3.2.2 (C4) Infrastructure Electrical Works - Spring plain / Ebony
The JPSCo is the only Provider of this work.

## Sheet1
Procurement Plan Activities
January 2016 to May 2017
Goods | Works | Non Consultancy Services | Consultancy Services | Status | Total | % | Activities Actioned
4 | 2 | 8 | 7 | Pending | 21 | 36.21%
4 | 4 | 7 | 12 | In Progress | 27 | 46.55%
| 1 | 8 | 1 | Awarded | 10 | 17.24% | 63.79%
8 | 7 | 23 | 20 | Total for Period | 58