## Project Structure
Agency | Sub-Agency (If applies) | Agency's Initials
NATIONAL PETROLEUM CORPORATION |  | NPC
NOTE: 1. There may only be one Organism which coordinates the Procurement Plan information and submits it to the Bank 2. Each Sub-executing Agency shall upload one sheet #2 with its activities
COMPONENTS? (YES / NO) | Component's Name (list by number or letter)
YES | COMPONENT 1. NG INFRASTRUCTURE
COMPONENT 2. SMART ENERGY SOLUTIONS
COMPONENT 3. TECHNICAL ADVISORY SERVICES
NOTE: Name the components in the loan agreement; use only main components

## Procurement Plan 34M
INFORMATION FOR PROCUREMENT PLAN INITIAL UPLOAD ONGOING AND/OR LAST PRESENTED
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: | 2016-12-01 | 2022-11-01
2. Procurement Plan Details
Version 1 (2016) : | 2016-09-15
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Works | 1090000 | 0
Goods | 3264000 | 0
Non Consulting Services | 22126000 | 0
Training | 750000 | 0
Operative Costs | 0 | 0
Consulting Services (Firms + Individuals) | 5495000 | 0
Transfers | 0 | 0
Community Participation | 0 | 0
Contingencies | 1200000 | 0
Total | 33925000 | 0
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
Component 1 - NG INFRASTRUCTURE | 25025000 | 0
Component 2 - SMART ENERGY SOLUTIONS | 3350000 | 0
Component 3 - TECHNICAL ADVISORY SERVICES | 4050000 | 0
OTHER COSTS | 1575000 | 0
Total | 34000000 | 0

## Detailed Procurement Plan 34M
PROCUREMENT PLAN INITIAL LOAD INFORMATION (ONGOING AND/OR LAST PRESENTED)
WORKS
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
National Petroleum Corporation | Blast walls | Pending |  |  |  | 100000 | 100% |  | 2 | Ex-Post
National Petroleum Corporation | Civil Works | Pending |  |  |  | 450000 | 100% |  | 2 | Ex-Post
National Petroleum Corporation | Geotech | Pending |  |  |  | 50000 | 100% |  | 2 | Ex-Post
National Petroleum Corporation | Fencing | Pending |  |  |  | 40000 | 100% |  | 2 | Ex-Post
National Petroleum Corporation | Security | Pending |  |  |  | 50000 | 100% |  | 2 | Ex-Post
National Petroleum Corporation | Electrical | Pending |  |  |  | 70000 | 100% |  | 2 | Ex-Post
National Petroleum Corporation | Lighting | Pending |  |  |  | 20000 | 100% |  | 2 | Ex-Post
National Petroleum Corporation | Housing | Pending |  |  |  | 100000 | 100% |  | 2 | Ex-Post
National Petroleum Corporation | Road repairs etc | Pending |  |  |  | 110000 | 100% |  | 2 | Ex-Post
National Petroleum Corporation | Land | Pending |  |  |  | 100000 | 100% |  | 2 | Ex-Post
SUB TOTAL WORKS : | [5 empty] | 1090000
GOODS
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
National Petroleum Corporation | Purchase of documents management software | Pending |  |  |  | 100000 | 100% |  | 3 | Ex-Post
National Petroleum Corporation | Purchase equipment to monitor, gather, document and integrate current system | Pending |  |  |  | 1000000 | 100% |  | 3 | Ex-Post
National Petroleum Corporation | Purchase appropiate on-road NG distribution vehicles | Pending |  |  |  | 1500000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Furniture/fixtures | Pending |  |  |  | 4000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Boil off gas infrastructures | Pending |  |  |  | 60000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Trucks (2) | Pending |  |  |  | 250000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Chasis | Pending |  |  |  | 350000 | 100% |  | 1 | Ex-Post
SUB TOTAL GOODS : | [5 empty] | 3264000
NON CONSULTING SERVICES
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Bidding Documents | Contract Signature
National Petroleum Corporation | Installation of SCADA |  |  |  |  | 3500000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Meter replacement/upgrade |  |  |  |  | 700000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Automatic meter infrastructure |  |  |  |  | 1800000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Infraestructural repairs - Phase 1 |  |  |  |  | 1300000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Infraestructural repairs - Phase 2 |  |  |  |  | 7000000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Surveying cost |  |  |  |  | 30000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Plant Pipework |  |  |  |  | 1021000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Plant Operations |  |  |  |  | 1975000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Storage facility |  |  |  |  | 1420000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Installation & transport of iso-containers |  |  |  |  | 30000 | 100% |  | 1 | Ex-Post
National Petroleum Corporation | Design and Installation of PV systems |  |  |  |  | 540000 | 100% |  | 2 | Ex-Post
National Petroleum Corporation | Design and Installation of NG compressors |  |  |  |  | 910000 | 100% |  | 2 | Ex-Post
National Petroleum Corporation | Design and Installation of 850 kW wind turbine |  |  |  |  | 1900000 | 100% |  | 2 | Ex-Post
SUB TOTAL NON CONSULTING SERVICES : | [5 empty] | 22126000
CONSULTING FIRMS
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
National Petroleum Corporation | Facilitating the amalgamation between NPC and BNOCL |  |  |  | 500000 | 100% |  | 3
National Petroleum Corporation | Improving corporate governance, legal, and regulatory functions |  |  |  | 250000 | 100% |  | 3
National Petroleum Corporation | Developing quality management system |  |  |  | 450000 | 100% |  | 3
National Petroleum Corporation | Operational audits |  |  |  | 500000 | 100% |  | 3
National Petroleum Corporation | Project management |  |  |  | 1500000 | 100% |  | 3
National Petroleum Corporation | Procurement process for a very small-scale LNG terminal under PPP scheme |  |  |  | 2000000 | 100% |  | 3
National Petroleum Corporation | Consultancy for the transition of current information to GIS |  |  |  | 150000 | 100% |  | 1
National Petroleum Corporation | Engineering |  |  |  | 50000 | 100% |  | 1
National Petroleum Corporation | Hazard, Risk, Fire analysis |  |  |  | 30000 | 100% |  | 1
National Petroleum Corporation | Dispersion modelling |  |  |  | 35000 | 100% |  | 1
SUB TOTAL CONSULTING FIRMS : |  |  |  |  | 5465000
INDIVIDUAL CONSULTANTS
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature
National Petroleum Corporation | Study on the appropiate type of vehicles |  |  |  | 30000 | 100% |  | 1
SUB TOTAL INDIVIDUAL CONSULTANTS : |  |  |  |  | 30000
TRAINING
Executing Agency | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Annual Training Plan (ATP) | End of Activity
National Petroleum Corporation | PLC Programming training |  |  |  | 100000 | 100% |  | 3
National Petroleum Corporation | Training on operational software |  |  |  | 150000 | 100% |  | 3
National Petroleum Corporation | SCADA Training |  |  |  | 500000 | 100% |  | 1
SUB TOTAL TRAINING : |  |  |  |  | 750000
TRANSFERS
Executing Agency | Transfer Purpose: | Additional Information: | Process Number: | Estimated Amount |  |  | Associated Component: | Estimated Number of Transfers: | Dates |  | Comments - for UCS include selection method
|  |  |  | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Contract Signature | Transfer Date
SUB TOTAL TRAINING : |  |  |  | 0
SUB-PROJECTS
Executing Agency | Transfer Purpose: | Additional Information: | Process Number: | Estimated Amount |  |  | Associated Component: | Estimated Number of Sub-projects: | Dates |  | Comments
|  |  |  | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Contract Signature | Transfer Date
SUB TOTAL SUB-PROJECTS : |  |  |  | 0
|  |  | TOTAL : | 32725000

## Global Procurement Plan 34M
PROJECT NAME: DEPLOYMENT OF CLEANER FUELS AND RENEWABLE ENERGIES IN BARBADOS
PROJECT NUMBER: BA-L1012
PERIOD: From November 2016 until October 2022
PLURIANNUAL EXECUTION PLAN (PEP)
(in US dollars)
2016-10-14
Description and type of procurement contract | Estimated contract cost (US$) | Procurement method (1) | Review (ex ante or ex post) | Source of financing and porcentage | Pre-qualification (Yes/No) | Estimated dates |  | Status (pending in process, awarded, cancelled) | Comments | Estimated cost IDB (US$) | Estimated cost JICA (US$) | Local funding (US$)
|  |  |  | IDB % |  | Publication of specific procurement notice | Completion of contract
COMPONENT 1. NG INFRASTRUCTURE |  |  |  | 100%
1.1 NG INFRASTRUCTURE UPGRADE | 17480000 | [6 empty] | Pending
1.1.1 Develop a Geographic Information System (GIS) of the curent network | 1150000 |  |  |  | No | 2017-03-01 | 2018-02-01
1.1.1.1 Consultancy for the transition of current information to GIS | 150000 | LIB | ex-post |  |  | 2017-03-01 | 2017-10-01 |  | Consultancy
1.1.1.2 Purchase equipment to monitor, gather, document and integrate current system | 1000000 | LIB | ex-post |  |  | 2017-11-01 | 2018-02-01 |  | Goods
1.1.2 Upgrade of the Supervisory Control and Data Acquisition (SCADA) of NG processing and distribution | 4000000 |  |  |  | No | 2018-08-01 | 2020-12-01
1.1.2.1. Installation of SCADA | 3500000 | ICB | ex-post |  |  | 2018-08-01 | 2020-12-01 |  | Non Consulting Services
1.1.2.2 SCADA Training | 500000 | ICB | ex-post |  |  | 2020-05-01 | 2020-12-01 |  | Training
1.1.3 Meter replacement/upgrade | 700000 | ICB | ex-post |  | No | 2018-05-01 | 2019-03-01 |  | Non Consulting Services
1.1.4 Automatic meter infrastructure | 1800000 | ICB | ex-post |  | No | 2016-12-01 | 2017-05-01 |  | Non Consulting Services
1.1.5 Modernization of On-Road NPC fleet | 1530000 |  |  |  |  | 2017-03-01 | 2017-09-01
1.1.5.1 Study on the appropiate type of vehicles | 30000 | LIB | ex-post |  |  | 2017-03-01 | 2017-06-01 |  | Individual Consultancy
1.1.5.2 Purchase appropiate on-road NPC fleet (including low emission vehicles) | 1500000 | NBC | ex-post |  |  | 2017-07-01 | 2017-09-01 |  | Goods
1.1.6 Infraestructural repairs - Phase 1 | 1300000
1.1.6.1 Procure pipelines for the installation | 800000 | NBC | ex-post |  |  | 2017-04-01 | 2018-05-01 |  | Non Consulting Services
1.1.6.2 Procure trenching, pipe busrting, etc. | 500000 | NBC | ex-post |  |  | 2017-04-01 | 2018-05-01 |  | Non Consulting Services
1.1.7 Infraestructural repairs - Phase 2 | 7000000
1.1.7.1 Procure pipelines for the installation | 4000000 | NBC | ex-post |  |  | 2018-06-01 | 2020-05-01 |  | Non Consulting Services
1.1.7.2 Procure trenching, pipe busrting, etc. | 3000000 | NBC | ex-post |  |  | 2018-06-01 | 2020-05-01 |  | Non Consulting Services
1.2 EXPANSION OF MICRO LNG REGASIFICATION FACILITY - WOODBOURNE | 7545000 |  | ex-post |  | No | 2016-12-01 | 2020-06-01 | Pending
1.2.1 Site preparation | 1124000 |  |  |  |  | 2017-02-01 | 2018-05-01
1.2.1.1 Environmental mitigation measures | 0
1.2.1.2 Blast walls | 100000 | NCB | [6 empty] | Works
1.2.1.3 Civil Works | 450000 | NCB | [6 empty] | Works
1.2.1.4 Geotech | 50000 | NCB | [6 empty] | Works
1.2.1.5 Fencing | 40000 | NCB | [6 empty] | Works
1.2.1.6 Security | 50000 | NCB | [6 empty] | Works
1.2.1.7 Surveying cost | 30000 | NCB | [6 empty] | Non Consulting Services
1.2.1.8 Electrical | 70000 | NCB | [6 empty] | Works
1.2.1.9 Lighting | 20000 | NCB | [6 empty] | Works
1.2.1.10 Housing | 100000 | NCB | [6 empty] | Works
1.2.1.11 Road repairs etc | 110000 | NCB | [6 empty] | Works
1.2.1.12 Land | 100000 | - | [6 empty] | Works
1.2.1.13 Furniture/fixtures | 4000 | NBC | [6 empty] | Goods
1.2.2 Plant Pipework | 1021000 |  | - |  |  | 2017-07-01 | 2019-06-01
1.2.2.1 Vaporizers | 500000 | ICB | [6 empty] | Non Consulting Services
1.2.2.2 Grounding equipment | 30000 | ICB | [6 empty] | Non Consulting Services
1.2.2.3 Odorizers | 0 | - | [6 empty] | Non Consulting Services
1.2.2.4 Cryogenic meter | 50000 | ICB | [6 empty] | Non Consulting Services
1.2.2.5 Plumbing | 5000 | PC | [6 empty] | Non Consulting Services
1.2.2.6 Stainless piping & valves | 80000 | ICB | [6 empty] | Non Consulting Services
1.2.2.7 Safety valves | 50000 | ICB | [6 empty] | Non Consulting Services
1.2.2.8 Painting/labelling | 7000 | PC | [6 empty] | Non Consulting Services
1.2.2.9 Insulation | 10000 | ICB | [6 empty] | Non Consulting Services
1.2.2.10 Instrumentation | 0 | - | [6 empty] | Non Consulting Services
1.2.2.11 Regulation | 7000 | ICB | [6 empty] | Non Consulting Services
1.2.2.12 Meter | 0 | - | [6 empty] | Non Consulting Services
1.2.2.13 Welding | 215000 | ICB | [6 empty] | Non Consulting Services
1.2.2.14 SS piping | 30000 | ICB | [6 empty] | Non Consulting Services
1.2.2.15 NDE testing | 30000 | ICB | [6 empty] | Non Consulting Services
1.2.2.16 Welding moving flare line | 7000 | PC | [6 empty] | Non Consulting Services
1.2.3 Plant Operations | 1975000 |  |  |  |  | 2019-02-01 | 2020-07-01
1.2.3.1 Moving equipment from LPG to LNG | 120000 | ICB | [6 empty] | Non Consulting Services
1.2.3.2 System controls | 65000 | ICB | [6 empty] | Non Consulting Services
1.2.3.3 Gas chromo | 60000 | ICB | [6 empty] | Non Consulting Services
1.2.3.4 Backup generator | 0 | - | [6 empty] | Non Consulting Services
1.2.3.5 Automation | 1000000 | ICB | [6 empty] | Non Consulting Services
1.2.3.6 Fire fighting equipment | 600000 | ICB | [6 empty] | Non Consulting Services
1.2.3.7 Ground monitor water etc | 130000 | ICB | [6 empty] | Non Consulting Services
1.2.4 Storage facility | 1420000 |  |  |  |  | 2019-11-01 | 2020-12-01
1.2.4.1 Storage tanks (2 X 50,000 gal) | 1200000 | ICB | [6 empty] | Non Consulting Services
1.2.4.2 Cryogenic pumps | 120000 | ICB | [6 empty] | Non Consulting Services
1.2.4.3 Cryogenic pipes | 100000 | ICB | [6 empty] | Non Consulting Services
1.2.5 Purchase of three (3) Iso-containers | 90000 |  |  |  |  | 2020-11-01 | 2020-05-01
1.2.5.1 Boil off gas infrastructures | 60000 | ICB | [6 empty] | Goods
1.2.5.2 Installation & transport of iso-containers | 30000 | PC | [6 empty] | Non Consultancy Services
1.2.6 Consultancy | 115000 |  |  |  |  | 2016-12-01 | 2017-11-01
1.2.6.1 Engineering | 50000 | ICB | [6 empty] | Consultancy
1.2.6.2 Hazard, Risk, Fire analysis | 30000 | ICB | [6 empty] | Consultancy
1.2.6.3 Dispersion modelling | 35000 | ICB | [6 empty] | Consultancy
1.2.6.4 Project Code Certification | 0 | -
1.2.7 Transportation | 600000 |  |  |  |  | 2017-11-01 | 2018-02-01
1.2.7.1 Trucks (2) | 250000 | ICB | [6 empty] | Goods
1.2.7.2 Chasis | 350000 | ICB | [6 empty] | Goods
1.2.8 Contingencies | 1200000
SUB-TOTAL COMPONENT 1. | 25025000
COMPONENT 2. SMART ENERGY SOLUTIONS |  |  |  | 100%
2.1 PV AND SMART SYSTEMS AND NEW FACILITY
2.1.1 Design and Installation of PV systems | 540000 | ICB | ex-post |  |  | 2020-05-01 | 2022-04-01 |  | Non Consulting Services
2.2 CONVERSION OF COMPRESSORS FROM NG TO SOLAR
2.2.1 Design and Installation of NG compressors | 910000 | ICB | ex-post |  |  | 2019-04-01 | 2021-05-01 |  | Non Consulting Services
2.3 WIND FACILITY
2.3.1 Design and Installation of 850 kW wind turbine | 1900000 | ICB | ex-post |  |  | 2019-10-01 | 2022-04-01 |  | Non Consulting Services
SUB-TOTAL COMPONENT 2. | 3350000
COMPONENT 3. TECHNICAL ADVISORY SERVICES |  |  |  | 100%
3.1 - NPC AND BNOCL AMALGAMATION | 2050000
3.1.1 Facilitating the amalgamation between NPC and BNOCL | 500000 | QCBS | ex-post |  | No | 2017-06-01 | 2018-01-01 |  | Consultancy
3.1.2 Improving corporate governance, legal, and regulatory functions | 250000 | QCBS | ex-post |  | No | 2017-06-01 | 2017-11-01 |  | Consultancy
3.1.3 Developing quality management system | 450000 | QCBS | ex-post |  | No | 2017-06-01 | 2018-05-01 |  | Consultancy
3.1.4 Improving information technology (SCADA, PLC programming, etc.) | 350000
3.1.4.1 PLC Programming training | 100000 | QCBS | ex-post |  | No | 2017-03-01 | 2017-06-01 |  | Training
3.1.4.2 Purchase of documents management software | 100000 | QCBS | ex-post |  | No | 2017-05-01 | 2017-07-01 |  | Goods
3.1.4.3 Training on operational software | 150000 | QCBS | ex-post |  | No | 2017-07-01 | 2017-10-01 |  | Training
3.1.5 Operational audits (Review NG processing, distribution and accounting systems) | 500000 | QCBS | ex-post |  |  | 2016-12-01 | 2017-11-01 |  | Consultancy
3.2 - PPP FOR VERY SMALL (VS) LNG REGASIFICATION FACILITY | 2000000
3.2.1 Procurement of consulting services (including legal services) for the preparation and awarding of the bidding process for a very small-scale LNG terminal under PPP scheme | 2000000 | QCBS | ex-post |  |  | 2018-02-01 | 2022-11-01 |  | International Firm
SUB-TOTAL COMPONENT 3. | 4050000
OTHER COSTS |  |  |  | 100%
4.1 Mid-Project evaluation | 30000 |  |  |  |  | 2016-12-01 | 2022-11-01
4.2 Final evaluation | 45000 |  |  |  |  | 2016-12-01 | 2022-11-01
4.3 Project management | 1500000 |  |  |  |  | 2016-12-01 | 2022-11-01 |  | Consultancy
4.3.1 Project Manager | 415000 |  |  |  |  | 2016-12-01 | 2022-11-01 |  | Consultancy
4.3.2 Procurement Officer | 360000 |  |  |  |  | 2016-12-01 | 2022-11-01 |  | Consultancy
4.3.3 Project Administrator | 300000 |  |  |  |  | 2016-12-01 | 2022-11-01 |  | Consultancy
4.3.4 Project Administrator | 270000 |  |  |  |  | 2016-12-01 | 2022-11-01 |  | Consultancy
4.3.5 Other monitoring, reporting and evaluation activities including data collection | 155000 |  |  |  |  | 2016-12-01 | 2022-11-01 |  | Consultancy
SUB-TOTAL OTHER COSTS. | 1575000
TOTAL | 34000000
(1) Goods and Works: ICB: international competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: procurement through specilaized agencies; PA: procrement agents; IA: inspection Agents; PLFI: procurement in loans to financial intermediaries; BOO/BOT/BOOT: build own, operate/build, operate, transfer/build, own,operate, transfer; PBP: performance-based procurement; PLGB: procurement under loans guaranteed by Bank; PCP: community participation procurement. Consulting Firms: QCBS: quality and cost-based selection; QBS: quality-based selection; FBS: selection under a fixed budget; LCS: least-cost selection; CQS: selection based on the Consultant's Qualifications; SSS: single-source selection. Individual Consultants: NICQ: national individual Consultant selection based on qualifications; IICQ: international individual Consultant selection based on Qualifications.