## Procurement Plan for 18months
PROCUREMENT PLAN FOR THE PERIOD: JUNE 2017 TO DECEMBER 2018
PROJECT NAME: DEPLOYMENT OF CLEANER FUELS AND RENEWABLE ENERGIES IN BARBADOS
PROJECT NUMBER: BA-L1012
LOAN CONTRACT NUMBER: 3843/OC-BA
Previous Ref. No. | Ref. No.¹ | Description and type of procurement contract | Estimated contract cost (US$) | Procurement Type | Procurement method² | Review (ex ante or ex post) | Source of financing and percentage |  | Pre-qualification³ (Yes/No) | Estimated dates |  | Status⁴ (pending in process, awarded, cancelled)
[7 empty] | IDB % | Local/Other % |  | Publication of specific procurement notice | Completion of contract
GOODS
Component 1
1.1.1.1 | 1.1.1.1 | Acquisition and installation of ArcGIS Desktop Software | 65000 | Goods | SSS | Ex Post | 100 | 0 | No | 2017-05-01 | 2017-08-01 | Completed
1.1.1 | 1.1.1.1 | Acquisition and installation of GIS software Module 1 | 20175 | Goods | Shopping | Post | 100 | 0 | No | 2017-05-01 | 2017-08-01 | AWARDED
1.1.1.2 | 1.1.1.2 | Acquisition and installation of GIS Enterprise and ArcPad Software | 35000 | Goods | SSS | Ex-ante | 100 | 0 | No | 2017-10-29 | 2017-12-01 | In Process
1.1.1.4 | 1.1.1.3a | Acquisition of Substructure Assessment Equipment | 70000 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2017-10-01 | 2018-01-31 | In Process
| 1.1.1.3b | Acquisition of GNSS Data Collecting and Processing Equipment | 70000 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2017-10-02 | 2018-01-31 | In Process
| 1.1.1.3c | Acquisition of GIS Post Processing Software | 5000 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2017-10-03 | 2018-12-29 | In Process
1.1.2.2 | 1.1.2.1 | Purchase & Installation of Servers for Virtualisation, related software and Networking Equipment | 300000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2017-11-01 | 2018-05-01 | In Process
1.1.2.1 | 1.1.2.2 | Acquisition and Installation of SCADA for the consolidation of BNOC/NPC field operations | 2965000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2017-12-01 | 2019-05-01 | Pending
1.1.2.3 | 1.1.2.4 | Purchase of 20 GPS systems and 1 Emergency Monitoring System for Lone Workers | 100000 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2018-06-01 | 2018-11-01 | Pending
1.1.2.4 | 1.1.2.3 | Purchase of Document Management System | 145000 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2017-11-01 | 2018-06-29 | In Process
1.1.2.5 | 1.1.2.5 | Purchase of mobile solutions for field work | 75000 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2019-02-01 | 2019-07-18 | Pending
1.1.3.2 | 1.3.1.1 | Supply of Ultrasonic (Smart) Natural Gas Meters | 149000 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2017-11-01 | 2018-04-01 | In Process
1.1.3.3 | 1.3.1.2 | Acquisition and installation of Meter Calibration Prover | 300000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2017-11-01 | 2018-05-01 | In Process
1.1.3.1 | 1.3.1.3 | Acquisition and Installation of an Automatic Metering Infrastructure for NPC's 21,000 customers | 2016000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2018-03-01 | 2020-08-01 | Pending
1.1.4.1 | 1.4.1.1 | Upgrade of NPC transportation fleet (trucks) | 500000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2018-04-01 | 2019-05-01 | Pending
1.1.4.2 | 1.4.1.2 | Upgrade of NPC transportation fleet ( 4x4) | 700000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2018-04-01 | 2019-05-01 | Pending
1.1.4.3 | 1.4.1.3 | Upgrade of NPC transportation fleet (cars) | 300000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2018-04-01 | 2019-05-01 | Pending
1.1.5.2 | 1.5.1.1 | Procure pipelines for all planned infrastructural replacements | 500000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2017-11-01 | 2018-05-01 | In Process
Component 2
2.1.1 | 2.1.1.1 | Design, Acquisition & Installation of Renewable Energy Systems (PVs) | 3000000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2017-11-01 | 2019-05-01 | In Process
2.2.1 | 2.2.1.1 | Purchase of two (2) Compressors for the Natural Gas Plant | 900000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2018-05-01 | 2019-01-01 | Pending
Component 5
5.1.1 | 5.1.1 | Laptops with docking Stations | 34518 | Goods | Shopping | Ex Post | 100 | 0 | No | 2017-03-01 | 2017-11-01 | AWARDED
5.1.2 | 5.1.2 | Printer/Scanner | 2000 | Goods | SSS | Ex Post | 100 | 0 | No | 2017-03-01 | 2017-09-01 | AWARDED
5.1.3 | 5.1.3 | Software & Licences, AutoCAD, Microsoft Projects | 13482 | Goods | Shopping | Ex Post | 100 | 0 | No | 2017-03-01 | 2017-11-01 | In Process
5.2.1 | 5.2.1 | Office Desk & workstations | 15000 | Goods | Shopping | Ex Post | 100 | 0 | No | 2017-03-01 | 2017-07-01 | AWARDED
5.2.2 | 5.2.2 | Office Chairs | 7200 | Goods | Shopping | Ex Post | 100 | 0 | No | 2017-03-02 | 2017-08-02 | AWARDED
5.3 | 5.3 | Office Supplies | 30000 | Goods | Shopping | Ex post | 100 | 0 | No | 2017-03-01 | 2019-09-01 | In Process
WORKS
Component 1
1.1.5.5 | 1.5.2.1 | Infrastructural Replacement- Natural Gas pipeline for PVC/cast iron main - (Highway 7) & Belle to Welches, St. Michael | 2250000 | Works | ICB | Ex-ante | 100 | 0 | Yes | 2018-02-01 | 2019-02-01 | Pending
- | 1.5.2.2 | Infrastructural Replacement- Natural Gas pipeline for PVC/cast iron main - Bridgetown Area | 2400000 | Works | ICB | Ex-ante | 100 | 0 | Yes | 2018-02-01 | 2019-07-01 | Pending
1.1.5.3 | 1.5.2.3 | Infrastructural Replacement - Natural Gas Pipeline Trents to Portvale, St. James (tie-in and round feed) | 500000 | Works | ICB | Ex-ante | 100 | 0 | Yes | 2018-02-01 | 2023-04-01 | Pending
| 1.5.2.4 | Installation of Mains and Live Connections | 1400000 | Works | FA | Ex-ante | 100 | 0 | No | 2018-03-05 | 2023-04-02 | Pending
1.2.2.1, 1.2.2.2, 1.2.2.3,1.2.3.1 | 1.2.1.3 | Construction of Very Small (VS) LNG Re-Gasification Facility | 6920462 | Works | ICB | Ex-ante | 100 | 0 | Yes | 2018-05-01 | 2019-08-01 | Pending
| 1.2.1.4 | Construction of Modular Bio-Methane Plant (First Phase) | 600000 | Works | ICB | Ex-ante | 100 | 0 | No | 2018-05-02 | 2019-08-02 | Pending
CONSULTANCY
Component 1
1.1.5.1 | 1.5.1.2 | Consultancy Services for Supervisor(s) - NG Infrastructural Replacement | 500000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2018-01-01 | 2019-06-01 | Pending
1.2.1.1, 1.2.1.2, 1.2.1.3 | 1.2.1.1 | Consultancy: FEED Study, Regulatory Requirements, Engineering Designs and Supervision for VS LNG Facility | 435000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2017-12-01 | 2019-09-01 | In Process
Component 2
2.3.1 | 2.3.1.1 | Consultancy to prepare a Scoping Study for a Wind Turbine facility at Woodbourne | 260000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2018-02-01 | 2018-12-01 | Pending
Component 3
3.1.1.1 | 3.1.1.1 | Training PPP contract negotiation, large infrastructure project design, execution and management | 100000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2018-06-01 | 2019-06-01 | Pending
3.1.1.2 | 3.1.1.2 | Training on operational software(SAP, KRONOS) | 50000 | Consulting Firm | SSS | Ex-ante | 100 | 0 | No | 2018-04-01 | 2019-04-01 | Pending
3.1.1.3 | 3.1.2.1 | Completing Operational audits (Review NG processing, distribution and accounting systems) for NPC/BNOCL | 400000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2018-06-01 | 2019-06-01 | Pending
3.1.2.1 | 3.1.4.1 | Developing studies for Standard Operating Procedures for entity including Governance functions | 300000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2018-09-01 | 2019-11-01 | Pending
3.1.2.2 | 3.1.5.1 | Consultancy Services for the Implementation of Employee integration programmes for newly formed company | 100000 | Consulting Firm | CQS | Ex-ante | 100 | 0 | No | 2017-10-01 | 2018-09-01 | In Process
3.1.3.1 | 3.1.3.1 | Consulting Services for the development of Quality Management System (ISO Consultation) | 180000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2017-11-01 | 2020-03-01 | In Process
Component 5
5.4 | 5.4 | External Financial Audit - PEU | 100000 | Consulting Firm | SSS | Ex-ante | 100 | 0 | No | 2017-11-01 | 2023-10-01 | In Process
5.5.1 | 5.5.1 | Project Manager | 520195.7041 | Individual Consultant | NICQ | Ex-ante | 65 | 35 | No | 2017-03-01 | 2023-09-01 | AWARDED
5.5.2 | 5.5.2 | Procurement Officer | 343846.4596 | Individual Consultant | NICQ | Ex-ante | 65 | 35 | No | 2017-03-02 | 2023-06-01 | AWARDED
5.5.3 | 5.5.3 | Project Accountant | 362890.2182 | Individual Consultant | NICQ | Ex-ante | 65 | 35 | No | 2017-03-03 | 2023-09-01 | AWARDED
5.5.4 | 5.5.4 | Project Engineer (Technical Coordinator) | 388459.3453 | Individual Consultant | NICQ | Ex-ante | 65 | 35 | No | 2017-03-04 | 2023-06-01 | AWARDED
5.5.5 | 5.5.5 | Technician-GIS | 268580.0576 | Individual Consultant | NICQ | Ex-ante | 65 | 35 | No | 2017-03-05 | 2019-04-19 | AWARDED
5.5.7 | 5.5.7 | Project Officer - Quality Assurance | 388459.3453 | Individual Consultant | NICQ | Ex-ante | 65 | 35 | No | 2017-03-04 | 2023-06-01 | AWARDED
5.5.8 | 5.5.8 | Project Administrator | 415306.9287 | Individual Consultant | NICQ | Ex-ante | 66 | 35 | No | 2017-03-04 | 2023-09-01 | AWARDED
|  | Grand Total | 31500575.0588
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education Program that includes school construction might include an item labelled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: NICQ National individual Consultant Selection based on comparison of qualifications; IICQ: International Individual Consultant Selection based on comparison of qualifications.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services. 4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.