## Sheet1
PROCUREMENT PLAN FOR THE PERIOD: JANUARY 1, 2019 - JUNE 30, 2020
PROJECT NAME: DEPLOYMENT OF CLEANER FUELS AND RENEWABLE ENERGIES IN BARBADOS
PROJECT NUMBER: BA-L1012
LOAN CONTRACT NUMBER: 3843/OC-BA
Ref. No.¹ | Description and type of procurement contract | Estimated/Actualcontract cost (US$) | Procurement Type | Procurement method² | Review (ex ante or ex post) | Source of financing and percentage |  | Pre-qualification³ (Yes/No) | Estimated/Actual dates |  |  | Status⁴ (pending, in process, in preparation, awarded, cancelled) | Comments
[6 empty] | IDB % | Local/Other % |  | Publication of specific procurement notice | Contract Signature Dates | Completion of contract
GOODS
Procurement No.
Component 1 - NG Infrastructure
1.1.2.1 | Acquisition & Installation of Servers for Virtualisation, related software and Networking Equipment | 315735.31 | Goods | ICB | Ex-ante | 100 | 0 | No | 2018-03-14 | 2018-09-12 | 2019-05-16 | AWARDED
1.1.2.2 | Acquisition and Installation of SCADA System | 2965000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2019-03-11 | 2019-10-25 | 2021-04-12 | In process
1.1.2.3 | Acquisition and Installation of Document Management System (DMS) | 144796 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2017-10-02 | 2018-04-30 | 2019-12-03 | AWARDED
1.1.2.4 | Acquisition and Installation of Emergency Monitoring System for Lone Workers | 100000 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2019-01-14 | 2019-04-07 | 2019-11-01 | In Process
1.1.2.5 | Acquisition of Mobile Solutions for Field Workers | 75000 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2019-07-01 | 2019-10-01 | 2020-02-27 | In preparation
1.1.3.1 | Acquisition of Ultrasonic NG Meters | 160083.8 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2017-10-19 | 2018-06-15 | 2019-02-05 | AWARDED
1.1.3.2 | Acquisition and Installation of Meter Calibration Provers | 200000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2019-03-15 | 2019-09-12 | 2023-07-21 | In process
1.4.1.1 | Acquisition of On Road Distribution Fleet | 1500000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2019-01-07 | 2019-09-01 | 2023-03-05 | In Process | This procurement activity will be offered in four lots as follows: (i) Electric Cars - $275,000 (ii) Mini-Truck - $125,000 (iii) Double Cab Trucks - $300,000 (iv) Double Cab Pick Ups and Single Cab Pick Ups - $800,000
1.5.1.1 | Acquisition of Pipes | 500000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2019-06-07 | 2020-01-14 | 2020-06-25 | In preparation
Component 2 - Smart Energy Solutions
2.1.1.1 | Design, Acquisition & Installation of Renewable Energy Systems (PVs) | 5174619.53 | Goods | ICB | Ex-ante | 100 | 0 | No | 2018-04-17 | 2019-02-19 | 2023-09-11 | AWARDED
2.2.1.1 | Acquisition and Installation of Compressors (2) for NG Plant | 650000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2020-06-11 | 2021-02-02 | 2023-05-07 | Pending
2.4.1.1 | Acquisition and Installation of An Energy Storage Facility | 7355462 | Goods | ICB | Ex-ante | 100 | 0 | No | 2019-06-21 | 2020-02-19 | 2021-04-20 | In preparation
2.2.2.1 | Acquisition and Installation of Energy Efficient (EE) Lights and Smart System | 200000 | Goods | ICB | Ex-ante | 100 | 0 | No | 2020-06-25 | 2021-02-16 | 2021-08-12 | Pending
Component 5 - Project Management and Monitoring
5.1.3 | Software | 53482 | Goods | Shopping | Ex-ante | 100 | 0 | No | 2020-03-15 | 2020-06-15 | 2020-09-16 | Pending
5.3 | Office Supplies | 50000 | Goods | Shopping | Ex-post | 100 | 0 | No | 2019-01-15 | 2019-03-19 | 2020-06-30 | In Preparation
WORKS
Component 1 - NG Infrastructure
1.5.2.1 | Pipeline Installation and Replacement Works - Hwy 7, Bridgetown Area, and Trents (Hwy 1) to Lancaster and Belle to Welches | 5150000 | Works | ICB | Ex-ante | 100 | 0 | No | 2019-11-15 | 2020-07-09 | 2022-09-20 | Pending
1.5.2.2 | Pipeline Replacement and Live Connections | 1400000 | Works | FA | Ex-ante | 100 | 0 | No | n/a | 2019-12-05 | 2022-09-16 | Pending | Connecting operational pipelines to replaced pipelines is specialized work that is only undertaken by the NPC. The Agreement Document between the PEU and the NPC for the llive connections will be submitted to the Bank by September 30, 2019
CONSULTANCY
Component 1 - NG Infrastructure
1.5.3 | Acquisition of Consulting Firm for Supervisory Services - NG Infrastructural Replacement | 500000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2019-09-05 | 2020-06-29 | 2022-09-20 | In Process
Component 2 - Smart Energy Solutions
2.3.1.1 | Acquisition of Consultancy Services to prepare a Technical Feasibility Study for a Wind Turbine Facility in Barbados | 260000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2018-07-09 | 2019-08-16 | 2021-04-20 | In Process
Component 3 - Technical Advisory Services
3.1.1.2 | Training on Operational Software (SAP, KRONOS) | 50000 | Consulting Firm | DC | Ex-ante | 100 | 0 | No | 2019-08-13 | 2019-10-08 | 2020-08-26 | Pending | Justification to be submitted for Bank's non-objection by June 2019
3.1.2.1 | Completing Operational Audits (Review NG Processing, Distribution and Accounting Systems) for NPC/BNOCL | 400000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2018-04-13 | 2019-05-29 | 2020-03-20 | In Process
3.1.2.2 | Acquisition of Consultancy Services for the Provision of Standard Operating Procedures (SOPs) for NPC/BNOCL including Governance Functions | 300000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2019-07-31 | 2020-06-19 | 2021-04-14 | In preparation
3.1.2.3 | Acquisition of Consultancy Services for the Implementation of Employee Integration Programmes for the Newly Formed Company | 100000 | Consulting Firm | CQS | Ex-ante | 100 | 0 | No | 2018-02-09 | 2019-06-18 | 2019-11-21 | In process
3.1.2.4.1 | Acqusition of Consultancy Services for the development of Quality Management System (QMS) - ISO Consultation | 180000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2020-09-07 | 2021-03-08 | 2023-03-20 | Pending
3.1.2.4.2 | Acqusition of Consultancy Services for ISO Certification (NPC/BNOCL Staff) | 270000 | Consulting Firm | QCBS | Ex-ante | 100 | 0 | No | 2020-09-20 | 2021-02-12 | 2023-06-21 | Pending
Component 4 - Project Evaluation and Monitoring
4.1.1.1 | Acquisition of Consultant for Midterm Evaluation | 30000 | Individual Consultant | IICQ | Ex-ante | 100 | 0 | No | 2020-03-25 | 2020-09-08 | 2021-02-28 | Pending
Component 5 - Project Management and Monitoring
5.4.1 | Acquisition of External Financial Auditor | 100000 | Consulting Firm | DC | Ex-ante | 100 | 0 | No | 2018-09-24 | 2019-04-12 | 2023-11-22 | In process
5.5.1 | Project Manager | 520195.7041 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-01 | 2017-09-01 | 2019-08-30 | Awarded
5.5.2 | Procurement Officer | 343846.4596 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-02 | 2017-08-01 | 2019-07-31 | Awarded
5.5.3 | Project Accountant | 362890.2182 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2018-02-03 | 2018-03-19 | 2019-02-14 | Awarded
5.5.4 | Project Engineer (Technical Coordinator) | 388459.3453 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-04 | 2017-06-12 | 2018-12-31 | Awarded
5.5.5 | Technician-GIS | 268580.0576 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-05 | 2017-06-12 | 2019-06-10 | Awarded
5.5.6 | Project Officer - Quality Assurance | 388459.3453 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-07 | 2017-09-01 | 2019-08-31 | Awarded
5.5.7 | Project Administrator | 415306.9287 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-03-08 | 2017-06-12 | 2019-06-10 | Awarded
5.5.8 | Electrical Engineering Technician | 40000 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No | 2017-02-08 | 2018-04-03 | 2020-04-02 | Awarded
5.5.9 | Project Engineer | 47000 | Individual Consultant | NICQ | Ex-ante | 100 | 0 | No |  |  | 2023-09-19 | Pending | Deferred until required
NON-CONSULTING SERVICES
Component 5 - Project Management and Monitoring
5.6 | Training/Certificaiton of PEU staff, affilated training cost (rental of venue, catering, rental of equipment, etc) | 25000 | Various | Shopping | Ex-ante | 100 | 0 | No | 2019-03-01 | 2019-06-01 | 2020-06-30 | Pending
| Grand Total | 30229036.8988
1 If there are a number of similar individual contracts to be executed in different places or at different times, these can be grouped together under a single heading, with an explanation in the comments column, indicating the average individual amount and the period during which the contracts would be executed. For example: an education Program that includes school construction might include an item labelled “School Construction” for an estimated cost of US$20 million and an explanation under the Comments column such as this: “This item encompasses some 200 contracts for school construction averaging US$100,000 each, to be awarded individually by the participating municipal governments over a three-year period between January 2006 and December 2008.”
2 Goods and Works: ICB: International competitive bidding; LIB: limited international bidding; NCB: national competitive bidding; PC: price comparison; DC: direct contracting; FA: force account; PSA: Procurement through specialized agencies; PAs: Procurement agents; IA: Inspection agents; PLFI: Procurement in loans to financial intermediaries; BOO/BOT/BOOT: Build, own, operate/build, operate, transfer/build, own, operate, transfer; PBP: Performance-based procurement; PLGB: Procurement under loans guaranteed by the Bank; PCP: Community participation procurement; Consulting Firms: QCBS: Quality- and cost-based selection; QBS: Quality-based selection; FBS: Selection under a fixed budget; LCS: Least-cost selection; CQS: Selection based on the consultants’ qualifications; SSS: Single-source selection; Individual Consultants: NICQ National individual Consultant Selection based on comparison of qualifications; IICQ: International Individual Consultant Selection based on comparison of qualifications.
3 Applicable only to Goods and Works in case the new Policies apply. In the case of previous Policies, it is applicable to Goods, Works and Consulting Services.
4 Column “Status” will be used for retroactive procurement and when updating the procurement plan.
Key | In Process | When the IDB has granted its ‘no objection’ to the respective Terms of Reference (TOR) and/or Bidding Documents.
| Pending | Not yet started
Awarded
| In Preparation | TOR and/or Bidding Document is being developed.