## Sheet1
Procurement Plan | [9 empty] | Reference Bidder Name
Approval Number | 4641/OC-BR | [8 empty] | Name + (A) Award
Operation Number | BR-L1429 | [8 empty] | Name + (P) Participant
Country | BRAZIL | [8 empty] | Name + (R) Rejected
Coverage Plan | 29 Oct 2021 - 29 Apr 2023
Executing Agency | SECRETARIA MUNICIPAL DE SAÚDE DE SÃO PAULO
Goods and Services Total | $ 48,229,096.42
Works Total | $ 139,885,937.11
Consulting Services Total | $ 722,461.36
Version | 2021-6
Proc Id | Procurement Process name | Description | Estimated Amount (USD) | Procurement Type | Procurement Method | Process Status | Lots | Process Start Estimated Date | Signed Contract Estimated date | Bidder/Proponent Name | Nationality | Contract Status | Start Date Contract | End Date Contract | Contract Amount USD
BR-L1429-P5340 | UBS Jd. Ladeira Rosa |  | $ 386,627.69 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 20 Jul 2007 | 04 Aug 2020
BR-L1429-P5341 | UBS Humaitá |  | $ 370,796.60 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 04 Feb 2020 | 27 Mar 2020
BR-L1429-P5342 | UBS Vila Regina |  | $ 359,153.47 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 17 Jun 2020 | 20 Jul 2020
BR-L1429-P5343 | UBS Vila Progresso - Jd. Monte Alegre |  | $ 215,389.40 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 21 Dec 2019 | 19 Mar 2020
BR-L1429-P5344 | UBS Bom Retiro |  | $ 162,964.46 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 17 Apr 2020 | 29 May 2020
BR-L1429-P5345 | UBS Wamberto Dias da Costa |  | $ 410,295.74 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 04 Feb 2020 | 17 Apr 2020
BR-L1429-P5346 | AMA/UBS Geraldo da Silva Ferreira |  | $ 431,551.87 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 09 Jun 2020 | 20 Jul 2020
BR-L1429-P5347 | UBS Pq. Arthur Alvim |  | $ 243,374.93 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 06 Jul 2020 | 25 Aug 2020
BR-L1429-P5348 | UBS/AMA Integrada Parí |  | $ 393,927.31 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 04 Feb 2020 | 09 Apr 2020
BR-L1429-P5349 | UBS Pq.Anhanguera |  | $ 371,414.21 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 20 Dec 2019 | 22 Feb 2020
BR-L1429-P5350 | UBS Jd. Aeroporto |  | $ 512,951.87 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 23 Sep 2020 | 09 Nov 2021
BR-L1429-P5351 | UBS Veleiros |  | $ 308,047.84 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 17 Apr 2020 | 29 May 2020
BR-L1429-P5352 | UBS Pq. Novo Mundo II |  | $ 239,309.42 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 15 Apr 2020 | 01 Jun 2020
BR-L1429-P5353 | AMA/UBS Integrada Massagista Mário Américo - Sítio Ma |  | $ 0.00 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 19 May 2020 | 24 Jun 2020
BR-L1429-P5354 | UBS Vl. Nossa Sra Aparecida |  | $ 415,541.65 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 31 Mar 2020 | 06 May 2020
BR-L1429-P5355 | UBS Jd. São Pedro |  | $ 358,455.75 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 23 Apr 2020 | 29 May 2020
BR-L1429-P5356 | UBS Vila Jacuí |  | $ 367,795.58 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 27 Mar 2020 | 06 May 2020
BR-L1429-P5357 | UBS Vila Romana |  | $ 361,673.22 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 26 Jun 2020 | 25 Aug 2020
BR-L1429-P5358 | AMA/UBS Vl. Santa Catarina |  | $ 198,027.60 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 23 Apr 2020 | 29 May 2020
BR-L1429-P5359 | AMA/UBS Jd. Paulistano |  | $ 285,460.66 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 22 May 2020 | 23 Jun 2020
BR-L1429-P5360 | UBS Jd. Guanabara |  | $ 408,525.36 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 16 Apr 2020 | 15 May 2020
BR-L1429-P5361 | AMA/UBS Americanópolis |  | $ 409,383.33 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 30 Sep 2020 | 09 Nov 2020
BR-L1429-P5362 | UBS Vila Nova Manchester |  | $ 280,648.24 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 30 Sep 2020 | 10 Dec 2020
BR-L1429-P5363 | UBS Casa Verde |  | $ 378,990.60 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 16 Jun 2020 | 23 Jul 2020
BR-L1429-P5364 | UBS Jd. Marcelo |  | $ 441,509.59 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 08 Jun 2020 | 20 Jul 2020
BR-L1429-P5365 | AMA/UBS Burgo Paulista |  | $ 402,439.65 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 31 Mar 2020 | 06 May 2020
BR-L1429-P5366 | AMA/UBS Jd. Santo André |  | $ 372,260.49 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 15 Oct 2020 | 28 Dec 2020
BR-L1429-P5367 | UBS Vila Zatt |  | $ 432,490.83 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 19 Dec 2019 | 23 Mar 2020
BR-L1429-P5368 | AMA/UBS Castro Alves |  | $ 347,859.12 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 12 Jun 2020 | 23 Jul 2020
BR-L1429-P5369 | UBS Cidade Kemel |  | $ 358,917.15 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 21 May 2020 | 01 Jul 2020
BR-L1429-P5370 | Complexo Jd. Peri-Peri |  | $ 401,474.14 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 18 Jun 2020 | 20 Jul 2020
BR-L1429-P5371 | AMA/UBS Jd. das Oliveiras |  | $ 407,240.11 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 22 May 2020 | 30 Jun 2020
BR-L1429-P5372 | UBS Itaquera |  | $ 460,263.56 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 19 Jun 2020 | 23 Jul 2020
BR-L1429-P5373 | UBS Caxingui |  | $ 179,825.08 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 03 Jul 2020 | 06 Aug 2020
BR-L1429-P5374 | UBS Jd. Colonial |  | $ 366,825.34 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 26 Jun 2020 | 03 Aug 2020
BR-L1429-P5375 | UBS Jd. Colorado |  | $ 327,813.63 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 03 Jul 2020 | 03 Aug 2020
BR-L1429-P5376 | UBS Vila Palmeiras |  | $ 224,699.20 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 17 Dec 2019 | 18 Mar 2020
BR-L1429-P5377 | UBS 1 de Outubro |  | $ 365,282.38 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 15 May 2020 | 30 Jun 2020
BR-L1429-P5378 | UBS Vila Paranaguá |  | $ 442,947.86 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 08 Jun 2020 | 20 Jul 2020
BR-L1429-P5379 | UBS Pq. da Lapa |  | $ 373,262.73 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 16 Oct 2020 | 27 Nov 2020
BR-L1429-P5380 | UBS Vila Borges |  | $ 354,588.61 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 07 Oct 2020 | 27 Nov 2020
BR-L1429-P5381 | UBS Panamericano |  | $ 316,613.19 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 23 Jun 2020 | 23 Jul 2020
BR-L1429-P5382 | UBS Vila Jaguara |  | $ 301,128.03 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 06 Oct 2020 | 27 Nov 2020
BR-L1429-P5383 | UBS Rio Claro |  | $ 446,034.16 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 06 Jul 2020 | 06 Aug 2020
BR-L1429-P5384 | UBS Jd. Vera Cruz |  | $ 326,237.73 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 19 Dec 2019 | 21 Feb 2020
BR-L1429-P5385 | AMA/UBS Vila Antonieta |  | $ 437,331.00 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 28 Sep 2020 | 27 Nov 2020
BR-L1429-P5386 | UBS CRHMTIPIS Bosque da Saúde |  | $ 487,518.79 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 19 Jun 2020 | 07 Aug 2020
BR-L1429-P5387 | UBS Comdor. José Gonzales |  | $ 359,699.24 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 15 Oct 2020 | 11 Dec 2020
BR-L1429-P5388 | UBS Dr. Joaquim Rossini |  | $ 294,759.54 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 03 Jul 2020 | 18 Aug 2020
BR-L1429-P5389 | UBS Jd. Iva |  | $ 397,341.78 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 28 Sep 2020 | 10 Dec 2020
BR-L1429-P5390 | UBS Vila Cupecê |  | $ 485,098.53 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 26 Jun 2020 | 03 Aug 2020
BR-L1429-P5391 | UBS Alto de Pinheiros |  | $ 484,160.25 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 28 Sep 2020 | 06 Nov 2020
BR-L1429-P5392 | UBS Ch. Santo Antonio |  | $ 379,539.99 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 15 Jun 2020 | 20 Jul 2020
BR-L1429-P5393 | AMA/UBS Anhanguera I |  | $ 443,225.23 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 22 Jun 2020 | 23 Jul 2020
BR-L1429-P5394 | UBS Adelaide Lopes |  | $ 412,842.77 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 15 Apr 2020 | 08 Jun 2020
BR-L1429-P5395 | UBS Vila Praia |  | $ 272,082.48 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 30 Mar 2020 | 06 May 2020
BR-L1429-P5396 | UBS Jd. Umuarama |  | $ 438,757.32 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 12 Jun 2020 | 27 Oct 2020
BR-L1429-P5397 | UBS Dr. Julio de Gouveia |  | $ 497,032.07 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 14 Dec 2020 | 11 Mar 2021
BR-L1429-P5398 | AMA/UBS Integrada São Jorge |  | $ 439,080.21 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 24 Nov 2020 | 02 Feb 2021
BR-L1429-P5399 | UBS Vila Dalva |  | $ 472,717.81 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 03 Dec 2020 | 11 Mar 2021
BR-L1429-P5400 | UBS Cid. Pedro José Nunes |  | $ 362,622.74 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 20 Dec 2019 | 21 Feb 2020
BR-L1429-P5401 | UBS Dr. Luiz Paulo Gnecco |  | $ 385,419.04 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 04 Nov 2020 | 08 Jan 2021
BR-L1429-P5402 | UBS Vl. Sabrina |  | $ 230,255.31 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 04 Nov 2020 | 08 Jan 2021
BR-L1429-P5403 | UBS Fazenda do Carmo |  | $ 498,164.07 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 19 Nov 2020 | 08 Jan 2021
BR-L1429-P5404 | UBS Parque Boa Esperança |  | $ 427,339.16 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 24 Nov 2020 | 19 Jan 2021
BR-L1429-P5405 | UBS Parque São Raphael - Dr. Ora Rosen |  | $ 389,626.59 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 19 Nov 2020 | 08 Jan 2021
BR-L1429-P5406 | UBS Jardim IV Centenário |  | $ 414,119.85 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 11 Nov 2020 | 19 Jan 2021
BR-L1429-P5407 | UBS Manuel Joaquim Pera |  | $ 127,679.49 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 20 Dec 2019 | 18 Mar 2020
BR-L1429-P5408 | UBS Jd.Marília |  | $ 299,944.63 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 19 Nov 2020 | 11 Jan 2021
BR-L1429-P5409 | UBS Jd. Roseli |  | $ 372,612.21 | Works | Shopping/Request for minimun 3 Quotations | Contract finished |  | 04 Feb 2020 | 09 Apr 2020
BR-L1429-P5410 | UPA Vila Maria Baixa |  | $ 1,701,147.54 | Works | National Competive Bidding | Expected |  | 09 Jul 2021 | 07 Oct 2021
BR-L1429-P5411 | UPA Butantã/ Caetano Virgilio Neto |  | $ 590,890.29 | Works | National Competive Bidding | Expected |  | 08 Dec 2021 | 25 Jan 2022
BR-L1429-P5412 | UPA Atualpa |  | $ 2,326,500.00 | Works | National Competive Bidding | Expected |  | 07 Oct 2021 | 30 Nov 2021
BR-L1429-P5413 | UPA Sacomã (US) |  | $ 590,890.29 | Works | National Competive Bidding | Expected |  | 06 May 2022 | 23 Jun 2022
BR-L1429-P5414 | UPA Augusto Gomes de Matos |  | $ 590,890.29 | Works | National Competive Bidding | Expected |  | 12 May 2022 | 28 Jun 2022
BR-L1429-P5415 | UPA Vergueiro + UPA D.Maria Antonieta F. de Barros |  | $ 1,792,601.70 | Works | National Competive Bidding | Contract under execution |  | 30 Jan 2020 | 02 Jun 2020
BR-L1429-P5416 | PS HSPM |  | $ 2,258,333.40 | Works | Procurement 100% funded by Agency | Contract under execution |  | 15 Oct 2019 | 12 Nov 2019
BR-L1429-P5417 | UPA Jardim Helena |  | $ 2,241,088.80 | Works | National Competive Bidding | Expected |  | 09 Jul 2021 | 07 Oct 2021
BR-L1429-P5418 | UPA Barra Funda |  | $ 1,788,481.27 | Works | National Competive Bidding | Expected |  | 08 Oct 2021 | 24 Nov 2021
BR-L1429-P5421 | UPA Santana |  | $ 990,890.29 | Works | National Competive Bidding | Expected |  | 08 Dec 2021 | 25 Jan 2022
BR-L1429-P5422 | UPA 21 de Junho |  | $ 1,690,890.29 | Works | National Competive Bidding | Expected |  | 08 Dec 2021 | 28 Jan 2022
BR-L1429-P5423 | CCI Leste |  | $ 1,517,071.71 | Works | National Competive Bidding | Contract under execution |  | 30 Oct 2020 | 31 Jan 2021
BR-L1429-P5427 | UPA Vila Mariana II |  | $ 1,135,581.99 | Works | Procurement 100% funded by Agency | Contract under execution |  | 12 Dec 2019 | 05 May 2020
BR-L1429-P5428 | UPA Moóca |  | $ 1,090,349.08 | Works | Procurement 100% funded by Agency | Contract under execution |  | 03 Dec 2019 | 06 May 2020
BR-L1429-P5429 | UPA Parelheiros |  | $ 1,157,276.30 | Works | Procurement 100% funded by Agency | Contract under execution |  | 03 Dec 2019 | 05 May 2020
BR-L1429-P5430 | UPA Jd. Peri |  | $ 615,000.00 | Works | Procurement 100% funded by Agency | Expected |  | 06 Oct 2021 | 21 Oct 2021
BR-L1429-P5431 | UPA Rio Pequeno |  | $ 2,599,967.33 | Works | National Competive Bidding | Expected |  | 18 Jun 2021 | 07 Oct 2021
BR-L1429-P5432 | UPA Laranjeiras |  | $ 1,247,946.07 | Works | National Competive Bidding | Expected |  | 12 Jan 2022 | 28 Feb 2022
BR-L1429-P5433 | UPA Lapa |  | $ 1,226,500.00 | Works | National Competive Bidding | Expected |  | 06 May 2022 | 23 Jun 2022
BR-L1429-P5434 | UPA Sapopemba |  | $ 1,226,500.00 | Works | National Competive Bidding | Expected |  | 06 May 2022 | 24 Jun 2022
BR-L1429-P5435 | UPA Carrão |  | $ 2,340,492.02 | Works | National Competive Bidding | Expected |  | 09 Jul 2021 | 07 Oct 2021
BR-L1429-P5436 | UPA City Jaraguá |  | $ 1,250,935.39 | Works | Procurement 100% funded by Agency | Contract under execution |  | 03 Dec 2019 | 06 May 2020
BR-L1429-P5437 | UPA Cidade Tiradentes |  | $ 1,128,592.69 | Works | Procurement 100% funded by Agency | Contract under execution |  | 12 Dec 2019 | 31 Mar 2020
BR-L1429-P5438 | UPA Jabaquara |  | $ 1,111,830.98 | Works | Procurement 100% funded by Agency | Contract under execution |  | 03 Dec 2019 | 06 May 2020
BR-L1429-P5439 | UBS Jd. Progresso |  | $ 1,226,500.00 | Works | National Competive Bidding | Expected |  | 08 Oct 2021 | 19 Nov 2021
BR-L1429-P5440 | UBS Pq. Sto. Antonio II |  | $ 1,485,000.00 | Works | National Competive Bidding | Expected |  | 06 Oct 2021 | 23 Nov 2021
BR-L1429-P5441 | UBS Reimberg |  | $ 1,485,000.00 | Works | National Competive Bidding | Expected |  | 06 Oct 2021 | 23 Nov 2021
BR-L1429-P5442 | UBS Jd. São Bernardo |  | $ 1,815,000.00 | Works | National Competive Bidding | Expected |  | 06 Oct 2021 | 17 Nov 2021
BR-L1429-P5443 | UBS Vl. Rubi |  | $ 896,274.91 | Works | National Competive Bidding | Expected |  | 03 Dec 2021 | 19 Jan 2022
BR-L1429-P5444 | UBS Conquista II |  | $ 1,682,140.17 | Works | National Competive Bidding | Expected |  | 09 Jul 2021 | 07 Oct 2021
BR-L1429-P5445 | UBS Atualpa |  | $ 1,637,236.66 | Works | National Competive Bidding | Expected |  | 09 Jul 2021 | 07 Oct 2021
BR-L1429-P5446 | UBS Primavera Colorado |  | $ 515,000.00 | Works | National Competive Bidding | Expected |  | 08 Nov 2021 | 20 Dec 2021
BR-L1429-P5447 | UBS Integrada Elisa Maria |  | $ 886,181.15 | Works | National Competive Bidding | Contract under execution |  | 30 Oct 2020 | 21 Dec 2020
BR-L1429-P5448 | UBS Cosmopolita |  | $ 1,728,737.62 | Works | National Competive Bidding | Expected |  | 09 Jul 2021 | 07 Oct 2021
BR-L1429-P5449 | UBS Keralux |  | $ 1,606,114.95 | Works | National Competive Bidding | Expected |  | 09 Jul 2021 | 07 Oct 2021
BR-L1429-P5450 | UBS Pq. Das Flores |  | $ 1,509,615.38 | Works | National Competive Bidding | Expected |  | 08 Sep 2021 | 21 Oct 2021
BR-L1429-P5451 | UBS Jd. Popular |  | $ 1,624,394.35 | Works | National Competive Bidding | Expected |  | 11 Oct 2021 | 26 Nov 2021
BR-L1429-P5452 | UBS Jd. Antártica |  | $ 548,000.00 | Works | Procurement 100% funded by Agency | Expected |  | 11 Oct 2021 | 21 Oct 2021
BR-L1429-P5453 | UBS Jd. Brasília |  | $ 715,000.00 | Works | National Competive Bidding | Expected |  | 08 Dec 2021 | 25 Jan 2022
BR-L1429-P5454 | UBS Caju |  | $ 715,000.00 | Works | National Competive Bidding | Expected |  | 12 Jan 2022 | 25 Feb 2022
BR-L1429-P5455 | UBS Malta II |  | $ 715,000.00 | Works | National Competive Bidding | Expected |  | 12 Jan 2022 | 25 Feb 2022
BR-L1429-P5456 | UBS Guarani/Vargas |  | $ 1,565,120.80 | Works | National Competive Bidding | Expected |  | 09 Jul 2021 | 07 Oct 2021
BR-L1429-P5457 | UBS Cidade Dutra |  | $ 1,815,000.00 | Works | National Competive Bidding | Expected |  | 11 Oct 2021 | 24 Nov 2121
BR-L1429-P5460 | Construção do Hospital Brasilândia |  | $ 45,098,458.33 | Works | Procurement 100% funded by Agency | Contract finished |  | 02 Jan 2019 | 02 Jan 2019
BR-L1429-P5461 | Aquisição de Selo de Qualidade ONA e Recertificação |  | $ 3,173,333.80 | Non-Consulting Services | International Competitive Bidding | Expected |  | 10 Nov 2021 | 13 Dec 2021
BR-L1429-P5462 | Gerenciamento integrado de classificação de riscos e articulação de rede |  | $ 5,420,204.66 | Goods | Direct Contracting/Selection | Contract under execution |  | 10 Jun 2020 | 11 Aug 2020
BR-L1429-P5463 | Equipamentos Hospital Parelheiros |  | $ 9,462,485.87 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Jun 2020 | 01 Jun 2020
BR-L1429-P5464 | Equipamentos Hospital Brasilândia |  | $ 2,843,386.28 | Goods | Procurement 100% funded by Agency | Contract under execution |  | 04 Aug 2020 | 31 Aug 2020
BR-L1429-P5465 | Equip.Med./Mob. - UPA Vila Mariana II |  | $ 629,704.42 | Goods | Procurement 100% funded by Agency | Expected |  | 01 Jun 2021 | 01 Jun 2021
BR-L1429-P5466 | Equip.Med./Mob. - UPA Moóca |  | $ 658,184.51 | Goods | Procurement 100% funded by Agency | Expected |  | 01 Jun 2021 | 01 Jun 2021
BR-L1429-P5467 | Equip.Med./Mob. - UPA Parelheiros |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 01 Aug 2021 | 31 Aug 2021
BR-L1429-P5468 | Equip.Med./Mob. - UPA Jd. Peri |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 17 Feb 2023 | 19 Feb 2023
BR-L1429-P5469 | Equip.Med./Mob. - UPA Rio Pequeno |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 10 Nov 2022 | 10 Nov 2022
BR-L1429-P5470 | Equip.Med./Mob. - UPA Laranjeiras |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Sep 2023 | 01 Oct 2023
BR-L1429-P5471 | Equip.Med./Mob. - UPA Lapa |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Jan 2024 | 31 Jan 2024
BR-L1429-P5472 | Equip.Med./Mob. - UPA Sapopemba |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Jan 2024 | 31 Jan 2024
BR-L1429-P5473 | Equip.Med./Mob. - UPA Carrão |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 10 Nov 2022 | 10 Nov 2022
BR-L1429-P5474 | Equip.Med./Mob. - UPA City Jaraguá |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 01 Sep 2021 | 01 Sep 2021
BR-L1429-P5475 | Equip.Med./Mob. - UPA Cidade Tiradentes |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Sep 2021 | 30 Sep 2021
BR-L1429-P5477 | Equip.Med./Mob. - UBS Jd. Progresso |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Jun 2023 | 29 Jun 2023
BR-L1429-P5478 | Equip.Med./Mob. - UBS Pq. Sto. Antonio II |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Jun 2023 | 30 Jun 2023
BR-L1429-P5479 | Equip.Med./Mob. - UBS Reimberg |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Jun 2023 | 30 Jun 2023
BR-L1429-P5480 | Equip.Med./Mob. - UBS Jd. São Bernardo |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Jun 2023 | 30 Jun 2023
BR-L1429-P5481 | Equip.Med./Mob. - UBS Vl. Rubi |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Jun 2023 | 30 Jun 2023
BR-L1429-P5482 | Equip.Med./Mob. - UBS Conquista II |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 10 Nov 2022 | 10 Nov 2022
BR-L1429-P5483 | Equip.Med./Mob. - UBS Atualpa |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 10 Nov 2022 | 10 Nov 2022
BR-L1429-P5484 | Equip.Med./Mob. - UBS Primavera Colorado |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Jul 2023 | 31 Jul 2023
BR-L1429-P5485 | Equip.Med./Mob. - UBS Cosmopolita |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 10 Nov 2022 | 10 Nov 2022
BR-L1429-P5486 | Equip.Med./Mob. - UBS Integrada Elisa Maria |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Oct 2021 | 29 Oct 2021
BR-L1429-P5487 | Equip.Med./Mob. - UBS Keralux |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 10 Nov 2022 | 10 Nov 2022
BR-L1429-P5488 | Equip.Med./Mob. - UBS Pq. Das Flores |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 17 Feb 2023 | 17 Feb 2023
BR-L1429-P5489 | Equip.Med./Mob. - UBS Jd. Popular |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 26 Jan 2024 | 26 Jan 2024
BR-L1429-P5490 | Equip.Med./Mob. - UBS Jd. Antártica |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 16 Feb 2023 | 16 Feb 2023
BR-L1429-P5491 | Equip.Med./Mob. - UBS Jd. Brasília |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 28 Aug 2023 | 28 Aug 2023
BR-L1429-P5492 | Equip.Med./Mob. - UBS Caju |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 28 Sep 2023 | 28 Sep 2023
BR-L1429-P5493 | Equip.Med./Mob. - UBS Malta II |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 28 Sep 2023 | 28 Sep 2023
BR-L1429-P5494 | Equip.Med./Mob. - UBS Guarani/Vargas |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 14 Nov 2022 | 14 Nov 2022
BR-L1429-P5495 | Equip.Med./Mob. - UBS Cidade Dutra |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Jun 2023 | 30 Jun 2023
BR-L1429-P5498 | Equip.Med./Mob. - UPA 21 de Junho |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 28 Aug 2023 | 28 Aug 2023
BR-L1429-P5499 | Equip.Med./Mob. - UPA Vila Maria Baixa |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 10 Nov 2022 | 10 Nov 2022
BR-L1429-P5500 | Equip.Med./Mob. - UPA Butantã/ Caetano Virgilio Neto |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 28 Aug 2023 | 28 Aug 2023
BR-L1429-P5501 | Equip.Med./Mob. - UPA Atualpa |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 17 Feb 2023 | 17 Feb 2023
BR-L1429-P5502 | Equip.Med./Mob. - UPA Sacomã (US) |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 26 Jan 2024 | 26 Jan 2024
BR-L1429-P5503 | Equip.Med./Mob. - UPA Augusto Gomes de Matos |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Jan 2024 | 30 Jan 2024
BR-L1429-P5504 | Equip.Med./Mob. - UPA D.Maria Antonieta F. de Barros |  | $ 207,239.56 | Goods | Procurement 100% funded by Agency | Expected |  | 03 Mar 2022 | 03 Mar 2022
BR-L1429-P5505 | Equip.Med./Mob. - UPA Vergueiro |  | $ 343,676.51 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Jan 2021 | 30 Apr 2021
BR-L1429-P5506 | Equip.Med./Mob. - PS do HSPM |  | $ 380,022.28 | Goods | Procurement 100% funded by Agency | Contract under execution |  | 01 Feb 2021 | 28 Jan 2022
BR-L1429-P5507 | Equip.Med./Mob. - UPA Jardim Helena |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 10 Nov 2022 | 10 Nov 2022
BR-L1429-P5508 | Equip.Med./Mob. - UPA Barra Funda |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 04 Jul 2023 | 04 Jul 2023
BR-L1429-P5511 | Equip.Med./Mob. - UPA Santana |  | $ 50,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Aug 2023 | 30 Aug 2023
BR-L1429-P5512 | Equip.Med./Mob. - UBS Jd. Ladeira Rosa |  | $ 6,694.06 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5513 | Equip.Med./Mob. - UBS Humaitá |  | $ 11,739.73 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Jan 2021 | 31 Jan 2021
BR-L1429-P5514 | Equip.Med./Mob. - UBS Vila Regina |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Sep 2021 | 01 Oct 2021
BR-L1429-P5515 | Equip.Med./Mob. - UBS Vila Progresso - Jd. Monte Alegre |  | $ 8,606.65 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5516 | Equip.Med./Mob. - UBS/AE Freguesia do Ó |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 28 Oct 2021 | 28 Oct 2021
BR-L1429-P5517 | Equip.Med./Mob. - UBS Bom Retiro |  | $ 18,815.49 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Jan 2021 | 31 Jan 2021
BR-L1429-P5518 | Equip.Med./Mob. - UBS Wamberto Dias da Costa |  | $ 15,693.69 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5519 | Equip.Med./Mob. - AMA/UBS Geraldo da Silva Ferreira |  | $ 15,054.59 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Jan 2021 | 31 Jan 2021
BR-L1429-P5520 | Equip.Med./Mob. - UBS Pq. Arthur Alvim |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 01 Nov 2021 | 01 Nov 2021
BR-L1429-P5521 | Equip.Med./Mob. - UBS/AMA Integrada Parí |  | $ 27,953.06 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Jan 2021 | 31 Jan 2021
BR-L1429-P5522 | Equip.Med./Mob. - UBS Pq.Anhanguera |  | $ 15,264.33 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5523 | Equip.Med./Mob. - UBS Jd. Aeroporto |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Nov 2021 | 30 Nov 2021
BR-L1429-P5524 | Equip.Med./Mob. - UBS Elisa Maria II |  | $ 146,305.96 | Goods | Procurement 100% funded by Agency | Expected |  | 28 Feb 2022 | 28 Feb 2022
BR-L1429-P5525 | Equip.Med./Mob. - UBS Veleiros |  | $ 5,046.74 | Goods | Procurement 100% funded by Agency | Expected |  | 01 Mar 2021 | 31 Mar 2021
BR-L1429-P5526 | Equip.Med./Mob. - UBS Pq. Novo Mundo II |  | $ 15,227.38 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5527 | Equip.Med./Mob. - AMA/UBS Integrada Massagista Mário Américo - Sítio Mandaqui |  | $ 15,416.37 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5528 | Equip.Med./Mob. - UBS Vl. Nossa Sra Aparecida |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 01 Oct 2021 | 01 Oct 2021
BR-L1429-P5529 | Equip.Med./Mob. - UBS Jd. São Pedro |  | $ 14,296.35 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5530 | Equip.Med./Mob. - UBS Vila Jacuí |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 01 Sep 2021 | 01 Sep 2021
BR-L1429-P5531 | Equip.Med./Mob. - UBS Vila Romana |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 01 Oct 2021 | 01 Oct 2021
BR-L1429-P5532 | Equip.Med./Mob. - AMA/UBS Vl. Santa Catarina |  | $ 11,830.42 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Jan 2021 | 31 Jan 2021
BR-L1429-P5533 | Equip.Med./Mob. - UBS Jd. Tiete II/HD São Matheus |  | $ 98,779.79 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Sep 2022 | 30 Sep 2022
BR-L1429-P5534 | Equip.Med./Mob. - AMA/UBS Jd. Paulistano |  | $ 11,495.93 | Goods | Procurement 100% funded by Agency | Contract finished |  | 02 Dec 2020 | 01 Jan 2021
BR-L1429-P5535 | Equip.Med./Mob. - UBS Jd. Guanabara |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Oct 2021 | 29 Oct 2021
BR-L1429-P5536 | Equip.Med./Mob. - AMA/UBS Americanópolis |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Oct 2021 | 31 Oct 2021
BR-L1429-P5537 | Equip.Med./Mob. - UBS Vila Nova Manchester |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Dec 2021 | 31 Dec 2021
BR-L1429-P5538 | Equip.Med./Mob. - UBS Casa Verde |  | $ 7,514.10 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5539 | Equip.Med./Mob. - UBS Jd. Marcelo |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 23 Dec 2021 | 23 Dec 2021
BR-L1429-P5540 | Equip.Med./Mob. - UBS Jd. Macedônia |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Dec 2021 | 31 Dec 2021
BR-L1429-P5541 | Equip.Med./Mob. - AMA/UBS Burgo Paulista |  | $ 11,826.18 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5542 | Equip.Med./Mob. - AMA/UBS Jd. Santo André |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Jan 2022 | 31 Jan 2022
BR-L1429-P5543 | Equip.Med./Mob. - AMA/UBS Castro Alves |  | $ 10,434.48 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5544 | Equip.Med./Mob. - UBS Vila Zatt |  | $ 18,758.30 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5545 | Equip.Med./Mob. - UBS Cidade Kemel |  | $ 9,312.00 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5546 | Equip.Med./Mob. - Complexo Jd. Peri-Peri |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 01 Dec 2021 | 01 Dec 2021
BR-L1429-P5547 | Equip.Med./Mob. - AMA/UBS Jd. das Oliveiras |  | $ 18,975.26 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5548 | Equip.Med./Mob. - AMA/UBS Vila Nova Jaguaré |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 28 Feb 2022 | 28 Feb 2022
BR-L1429-P5549 | Equip.Med./Mob. - UBS Gráficos |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 02 Mar 2022 | 02 Mar 2022
BR-L1429-P5550 | Equip.Med./Mob. - UBS Itaquera |  | $ 9,250.92 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5551 | Equip.Med./Mob. - UBS Caxingui |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 22 Oct 2021 | 22 Oct 2021
BR-L1429-P5552 | Equip.Med./Mob. - UBS Jd. Colonial |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Sep 2021 | 30 Sep 2021
BR-L1429-P5553 | Equip.Med./Mob. - UBS Jd. Colorado |  | $ 10,667.62 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5554 | Equip.Med./Mob. - UBS 1 de Outubro |  | $ 12,026.57 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5555 | Equip.Med./Mob. - UBS Vila Palmeiras |  | $ 11,665.29 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5556 | Equip.Med./Mob. - UBS Vila Paranaguá |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 21 Dec 2023 | 21 Dec 2023
BR-L1429-P5557 | Equip.Med./Mob. - Complexo Sta Cecília |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Mar 2022 | 31 Mar 2022
BR-L1429-P5558 | Equip.Med./Mob. - UBS Pq. da Lapa |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Sep 2021 | 30 Sep 2021
BR-L1429-P5559 | Equip.Med./Mob. - UBS Jd. Das Camélias |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 May 2022 | 31 May 2022
BR-L1429-P5560 | Equip.Med./Mob. - UBS Vila Borges |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Oct 2021 | 31 Oct 2021
BR-L1429-P5561 | Equip.Med./Mob. - UBS Panamericano |  | $ 9,541.19 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5562 | Equip.Med./Mob. - UBS Vila Jaguara |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Oct 2021 | 31 Oct 2021
BR-L1429-P5563 | Equip.Med./Mob. - UBS Rio Claro |  | $ 13,760.32 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5564 | Equip.Med./Mob. - AMA/UBS Vila Antonieta |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Sep 2021 | 30 Sep 2021
BR-L1429-P5565 | Equip.Med./Mob. - UBS CRHMTIPIS Bosque da Saúde |  | $ 7,751.09 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Jan 2021 | 31 Jan 2021
BR-L1429-P5566 | Equip.Med./Mob. - UBS Jd. Vera Cruz |  | $ 7,738.88 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5567 | Equip.Med./Mob. - UBS Comdor. José Gonzales |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 02 Nov 2021 | 02 Nov 2021
BR-L1429-P5568 | Equip.Med./Mob. - UBS Dr. Joaquim Rossini |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Oct 2021 | 31 Oct 2021
BR-L1429-P5569 | Equip.Med./Mob. - UBS Jd. Iva |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Sep 2021 | 30 Sep 2021
BR-L1429-P5570 | Equip.Med./Mob. - UBS Vila Cupecê |  | $ 21,120.82 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Jan 2021 | 31 Jan 2021
BR-L1429-P5571 | Equip.Med./Mob. - UBS Alto de Pinheiros |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Nov 2021 | 30 Nov 2021
BR-L1429-P5572 | Equip.Med./Mob. - UBS Ch. Santo Antonio |  | $ 5,547.69 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Mar 2021 | 31 Mar 2021
BR-L1429-P5573 | Equip.Med./Mob. - AMA/UBS Anhanguera I |  | $ 17,085.89 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5574 | Equip.Med./Mob. - UBS Adelaide Lopes |  | $ 12,539.02 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5575 | Equip.Med./Mob. - UBS Jd. Umuarama |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 23 Jun 2022 | 23 Jun 2022
BR-L1429-P5576 | Equip.Med./Mob. - AMA/UBS Vila Itapema |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 26 Aug 2022 | 26 Aug 2022
BR-L1429-P5577 | Equip.Med./Mob. - UBS Vila Praia |  | $ 13,485.25 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Mar 2021 | 31 Mar 2021
BR-L1429-P5578 | Equip.Med./Mob. - UBS Dr. Julio de Gouveia |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Dec 2021 | 31 Dec 2021
BR-L1429-P5579 | Equip.Med./Mob. - UBS Jardim São Carlos CEO II |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 28 Feb 2022 | 28 Feb 2022
BR-L1429-P5580 | Equip.Med./Mob. - UBS José Bonifácio II |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 28 Feb 2022 | 28 Feb 2022
BR-L1429-P5581 | Equip.Med./Mob. - AMA/UBS Integrada São Jorge |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Dec 2021 | 31 Dec 2021
BR-L1429-P5582 | Equip.Med./Mob. - UBS Jardim D'Abril |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 01 Jul 2022 | 01 Jul 2022
BR-L1429-P5583 | Equip.Med./Mob. - UBS Vila Dalva |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Dec 2021 | 31 Dec 2021
BR-L1429-P5584 | Equip.Med./Mob. - UBS Jd. Selma - Cidade Ademar |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 12 Jul 2022 | 12 Jul 2022
BR-L1429-P5585 | Equip.Med./Mob. - UBS Vl. Ramos - Freguesia do Ó |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Aug 2022 | 31 Aug 2022
BR-L1429-P5586 | Equip.Med./Mob. - UBS Dr. Luiz Paulo Gnecco |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Oct 2021 | 31 Oct 2021
BR-L1429-P5587 | Equip.Med./Mob. - UBS Vl. Sabrina |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Oct 2021 | 31 Oct 2021
BR-L1429-P5588 | Equip.Med./Mob. - UBS Cid. Pedro José Nunes |  | $ 11,505.42 | Goods | Procurement 100% funded by Agency | Contract finished |  | 01 Dec 2020 | 31 Dec 2020
BR-L1429-P5589 | Equip.Med./Mob. - UBS Vl. Terezinha |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Dec 2021 | 31 Dec 2021
BR-L1429-P5590 | Equip.Med./Mob. - UBS Jardim São Francisco II |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 28 Feb 2022 | 28 Feb 2022
BR-L1429-P5591 | Equip.Med./Mob. - UBS Fazenda do Carmo |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 21 Oct 2021 | 21 Oct 2021
BR-L1429-P5592 | Equip.Med./Mob. - UBS Cidade Satélite Santa Bárbara |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 May 2022 | 31 May 2022
BR-L1429-P5593 | Equip.Med./Mob. - UBS Vila Cisper |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 31 Mar 2022 | 31 Mar 2022
BR-L1429-P5594 | Equip.Med./Mob. - UBS Parque Boa Esperança |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Oct 2021 | 29 Oct 2021
BR-L1429-P5595 | Equip.Med./Mob. - UBS Parque São Raphael - Dr. Ora Rosen |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Nov 2021 | 30 Nov 2021
BR-L1429-P5596 | Equip.Med./Mob. - UBS Jardim IV Centenário |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 30 Nov 2021 | 30 Nov 2021
BR-L1429-P5597 | Equip.Med./Mob. - UBS Jd.Marília |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Oct 2021 | 29 Oct 2021
BR-L1429-P5598 | Equip.Med./Mob. - UBS Manuel Joaquim Pera |  | $ 3,333.65 | Goods | Procurement 100% funded by Agency | Contract under execution |  | 02 Dec 2020 | 01 Jan 2021
BR-L1429-P5599 | Equip.Med./Mob. - UBS Jd. Roseli |  | $ 13,163.72 | Goods | Procurement 100% funded by Agency | Contract under execution |  | 02 Dec 2020 | 01 Jan 2021
BR-L1429-P5600 | Equip.Med./Mob. - CCI Leste |  | $ 514,423.09 | Goods | Procurement 100% funded by Agency | Expected |  | 01 Dec 2021 | 20 Dec 2021
BR-L1429-P5604 | Gerenciamento de Convênios e Contratos/Núcleo Estratégico da Saúde |  | $ 2,361,211.24 | Non-Consulting Services | National Competive Bidding | Expected |  | 10 Nov 2021 | 01 Feb 2022
BR-L1429-P5605 | Sistema gerenciamento de contratos administrativos |  | $ 200,000.00 | Non-Consulting Services | National Competive Bidding | Expected |  | 10 Nov 2021 | 01 Feb 2022
BR-L1429-P5606 | Sistemas de gerenciamento de suprimentos |  | $ 4,400,000.00 | Non-Consulting Services | National Competive Bidding | Expected |  | 16 Aug 2021 | 03 Nov 2021
BR-L1429-P5607 | Solução para consolidação e compartilhamento de dados clínicos para fins assistenciais e telemedicina |  | $ 9,768,375.20 | Non-Consulting Services | Direct Contracting/Selection | Contract under execution |  | 21 Apr 2020 | 21 Jun 2020
BR-L1429-P5609 | Contratação de Auditoria |  | $ 123,561.83 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Contract under execution |  | 24 Dec 2020 | 16 Mar 2021
BR-L1429-P5610 | Análise de Impacto |  | $ 191,054.16 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Expected |  | 15 Sep 2021 | 01 Nov 2021
BR-L1429-P5611 | Avaliações Intermediárias e final |  | $ 200,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected |  | 17 Sep 2021 | 01 Nov 2021
BR-L1429-P5614 | Apoio ao Gerenciamento do Programa |  | $ 5,262,922.65 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Contract under execution |  | 28 Jun 2019 | 21 Feb 2020
BR-L1429-P5616 | Assessoria de Marketing e Comunicação para o Projeto |  | $ 0.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Cancelled |  | 02 Feb 2022 | 11 May 2022
BR-L1429-P5617 | Consultoria individual para apoio à UCP na área de Obras |  | $ 211,230.68 | Individual Consultants | Single-Source Selection of Individual Consultant (SSS) | Contract under execution |  | 11 Dec 2019 | 13 Mar 2020
BR-L1429-P5618 | Consultoria Sustentabilidade |  | $ 157,788.76 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Contract finished |  | 23 Dec 2019 | 20 Apr 2020
BR-L1429-P5620 | Consultoria individual para apoio à UCP na área de Aquisições |  | $ 100,000.00 | Individual Consultants | Single-Source Selection of Individual Consultant (SSS) | Expected |  | 15 Jun 2021 | 30 Aug 2021
BR-L1429-P5621 | Consultoria individual para apoio à UCP na área Financeira |  | $ 211,230.68 | Individual Consultants | Single-Source Selection of Individual Consultant (SSS) | Contract under execution |  | 10 Dec 2019 | 21 Feb 2020
BR-L1429-P5622 | Projetos de menor porte |  | $ 166,160.11 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Contract finished |  | 11 Nov 2019 | 23 Apr 2020
BR-L1429-P5623 | Projetos Executivos dos equipamentos de saúde a serem construídos e reformas de maior porte e fiscalização de obras |  | $ 485,293.72 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Contract under execution |  | 27 Dec 2019 | 02 Jul 2020
BR-L1429-P5624 | Projetos Executivos dos equipamentos de saúde a serem construídos e reformas de maior porte |  | $ 755,955.84 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Contract under execution |  | 27 Dec 2019 | 02 Jul 2020
BR-L1429-P5625 | AMA/UBS Integrada Massagista Mário Américo - Sítio Mandaqui |  | $ 351,861.59 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 18 May 2020 | 23 Jun 2020
BR-L1429-P8169 | UBS Vila Cisper |  | $ 414,418.73 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 15 Dec 2020 | 04 Mar 2021
BR-L1429-P8170 | UBS Cidade Satélite Santa Bárbara |  | $ 361,165.44 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 11 Dec 2020 | 28 Apr 2021
BR-L1429-P8171 | UBS Jardim São Francisco II |  | $ 472,973.44 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 19 Nov 2020 | 22 Apr 2021
BR-L1429-P8172 | UBS Vl. Terezinha |  | $ 447,749.83 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 10 Nov 2020 | 03 Mar 2021
BR-L1429-P8173 | UBS Vl. Ramos - Freguesia do Ó |  | $ 413,636.27 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 15 Dec 2020 | 28 Apr 2021
BR-L1429-P8174 | UBS Jd. Selma - Cidade Ademar |  | $ 333,195.79 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 14 Dec 2020 | 12 Mar 2021
BR-L1429-P8175 | UBS Jardim D'Abril |  | $ 316,352.08 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 23 Aug 2021 | 21 Sep 2021
BR-L1429-P8176 | UBS José Bonifácio II |  | $ 463,646.77 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 14 Dec 2020 | 22 Apr 2021
BR-L1429-P8177 | UBS Jardim São Carlos CEO II |  | $ 427,056.21 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 14 Dec 2020 | 10 May 2021
BR-L1429-P8178 | AMA/UBS Vila Itapema |  | $ 434,090.05 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 25 Jun 2021 | 30 Aug 2021
BR-L1429-P8179 | UBS Jd. Das Camélias |  | $ 335,634.16 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 03 Dec 2020 | 05 Apr 2021
BR-L1429-P8180 | Complexo Sta Cecília |  | $ 466,413.67 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 24 Nov 2020 | 30 Mar 2021
BR-L1429-P8181 | UBS Gráficos |  | $ 362,288.60 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 15 Dec 2020 | 12 Apr 2021
BR-L1429-P8182 | AMA/UBS Vila Nova Jaguaré |  | $ 443,089.45 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 11 Dec 2020 | 22 Apr 2021
BR-L1429-P8183 | UBS Jd. Macedônia |  | $ 405,150.32 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 11 Dec 2020 | 19 Mar 2021
BR-L1429-P8184 | UBS Elisa Maria II |  | $ 535,865.06 | Works | National Competive Bidding | Expected |  | 13 Nov 2020 | 19 Mar 2021
BR-L1429-P8185 | UBS/AE Freguesia do Ó |  | $ 394,098.76 | Works | Shopping/Request for minimun 3 Quotations | Expected |  | 11 Dec 2020 | 01 Apr 2021
BR-L1429-P8186 | UBS Jd. Tiete II/HD São Matheus |  | $ 1,733,839.37 | Works | National Competive Bidding | Expected |  | 13 Nov 2020 | 17 Mar 2021
BR-L1429-P8187 | Reforma Hospital Santa Catarina |  | $ 1,250,000.00 | Works | National Competive Bidding | Expected |  | 04 Oct 2021 | 26 Nov 2021
BR-L1429-P8188 | Prorrogação da Solução para consolidação e compartilhamento de dados clínicos para fins assistenciais e telemedicina. |  | $ 4,831,624.80 | Non-Consulting Services | International Competitive Bidding | Expected |  | 17 Aug 2021 | 04 Nov 2021
BR-L1429-P8189 | Consultoria para acompanhamento da implantação da ONA (Núcleo Interno de Qualidade) |  | $ 288,461.54 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Expected |  | 20 Aug 2021 | 20 Oct 2021
BR-L1429-P8190 | Formação e capacitação de lideres gestores em Saúde |  | $ 250,000.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Expected |  | 15 Oct 2021 | 15 Dec 2021
BR-L1429-P8191 | Capacitação em Protocolo de Risco Manchester |  | $ 250,000.00 | Non-Consulting Services | Direct Contracting/Selection | Expected |  | 14 Mar 2022 | 13 Apr 2022
BR-L1429-P8192 | Formação e capacitação de profissionais da rede |  | $ 250,000.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Expected |  | 07 Jul 2022 | 07 Sep 2022
BR-L1429-P8200 | Apoio Técnico à Fiscalização das Obras |  | $ 2,981,306.50 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Expected |  | 27 Dec 2019 | 02 Jul 2020
BR-L1429-P15173 | UBS Eng. Trindade |  | $ 715,000.00 | Works | National Competive Bidding | Expected |  | 12 Jan 2022 | 28 Feb 2022
BR-L1429-P15174 | Equip.Med./Mob. - UBS Eng. Trindade |  | $ 17,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 28 Sep 2023 | 28 Sep 2023
BR-L1429-P15179 | Capacitação lideres para certificação |  | $ 250,000.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Expected |  | 15 Oct 2021 | 15 Dec 2021