## Summary
Project Completion Report
Project to Support Job Placement (PR-L1066)
Development Effectiveness
Summary
I. Development Effectiveness - Core Criteria
Recommended overall rating: |  | Highly successful
Recommended overall rating: | 6 | Highly successful
Weighted score | 4
Initial Score | 6
After adjustment (rule 1) | 6
After adjustment (rule 2) | 6
After adjustment (rule 3) | 6
6
Weight
1. Relevance | 4 | 20%
2. Effectiveness | 4 | 40%
% of outcomes that were achieved | 100%
% of outputs that were achieved | 100%
3. Efficiency | 4 | 20%
4. Sustainability | 4 | 20%
II. Development Effectiveness - Non core Criteria
Bank's Performance | Excellent
Borrower's Performance | Satisfactory
Reference table:
PCR overall rating
> 3.5 Numeric scale: 6 Ordinary Scale: Highly Successful
> 3.0 Numeric scale: 5 Ordinary Scale: Successful
> 2.5 Numeric scale: 4 Ordinary Scale: Partly Successful
> 2.0 Numeric scale: 3 Ordinary Scale: Partly Unsuccessful
> 1.5 Numeric scale: 2 Ordinary Scale: Unsuccessful
< 1.5 Numeric scale: 1 Ordinary Scale: Highly Unsuccessful

## General
Core Criteria | Rating | Description | Additional comments if necessary
Relevance | 4 | Excellent
Effectiveness | 4 | Excellent
Specific Development Objective 1 | 4 | Excellent
Specific Development Objective 2 | 4 | Excellent
Specific Development Objective 3
Specific Development Objective 4
Specific Development Objective 5
Specific Development Objective 6
Specific Development Objective 7
Specific Development Objective 8
Specific Development Objective 9
Specific Development Objective 10
% ratio of outcomes that were achieved | 100%
Efficiency | 4 | Excellent
Cost Benefit Analysis |  | Yes
Cost Effectiveness Analysis |  | No
CTOA Analysis (PMR Indicators) |  | No
Sustainability | 4 | Excellent
Non Core Criteria |  |  | Additional comments if necessary
Bank's Performance | Excellent
Borrower's Performance | Satisfactory

## Guidelines
General Instructions: To sector specialists: Please fill in all blank spaces (white cells) of the worksheets "Summary", "Effectiveness" and "General" according to the evaluation criteria explained in the guidelines.
PCR overall rating
>= 3.5 | Numeric scale: 6 Ordinary Scale: Highly Successful
>= 3.0 | Numeric scale: 5 Ordinary Scale: Successful
>= 2.5 | Numeric scale: 4 Ordinary Scale: Partly Successful
>= 2.0 | Numeric scale: 3 Ordinary Scale: Partly Unsuccessful
>= 1.5 | Numeric scale: 2 Ordinary Scale: Unsuccessful
< 1.5 | Numeric scale: 1 Ordinary Scale: Highly Unsuccessful
Note: • With an Unsatisfactory rating for relevance, effectiveness, or sustainability, the highest achievable rating is Partly Unsuccessful. • For a Highly Successful rating, no rating on any core criteria can be less than Satisfactory. • With a Partly Unsatisfactory rating for relevance, effectiveness, or sustainability, the highest achievable overall rating is Partly Successful.
Core Criteria |  | Rating
Relevance Rating (weight 20%)
Excellent (E) | Project development objectives and original vertical logic are aligned with country development needs and priorities (IDB Country Strategy) at the time of approval. Project development objectives and vertical logic are completely aligned with country development needs and priorities (IDB Country Strategy) at the time of closure; OR if the project objectives and vertical logic are not aligned with the IDB Country Strategy at the time of closure, the analysis provides justification of the relevance of the project to country development challenges at the time of closure. The vertical logic of the intervention is properly described and demonstrates the relevance of the operation. It shows a clear link between the causal chain of the intervention, the development objectives of the operation, and the country development needs and context. The analysis clearly discusses how the outputs and outcomes achieved are aligned to the IDB Country Strategy at approval, and at closure (if applicable at closure). | 4
Satisfactory (S) | Project development objectives and original vertical logic are not aligned with country development needs and priorities (IDB Country Strategy), at the time of approval and/or at the time of closure. However, the analysis provides justification of the relevance of the project to country development challenges at the time of approval and at the time of closure. However, the analysis provides justification of the relevance of the project to country development challenges at the time of approval and at the time of closure. The vertical logic of the intervention is properly described and demonstrates the relevance of the operation. It shows a clear link between the causal chain of the intervention, the development objectives of the operation, and the country development needs and context. | 3
Partly Unsatisfactory (PU) | Project development objectives and original vertical logic are aligned with country development needs and priorities (IDB Country Strategy) at the time of approval. Project development objectives and vertical logic are completely aligned with country development needs and priorities (IDB Country Strategy) at the time of closure; OR if the project objectives and vertical logic are not aligned with the IDB Country Strategy at the time of closure, the analysis provides justification of the relevance of the project to country development challenges at the time of closure. The vertical logic of the intervention is not described and cannot demonstrate the relevance of the operation. It does not show a link between the causal chain of the intervention, the development objectives of the operation, and the country development needs and context. | 2
Unsatisfactory (U) | Project development objectives and vertical logic are not aligned with country development needs and priorities (IDB Country Strategy) at the time of approval and at the time of closure. The vertical logic of the intervention is not described and cannot demonstrate the relevance of the operation. It does not show a link between the causal chain of the intervention, the development objectives of the operation, and the country development needs and context. | 1
Note: Two aspects are considered here: 1. Alignment of project development objectives with country development needs and Bank Country Strategy/corporate goals at time of approval, during execution, and at time of evaluation (project closure). 2. Alignment of project design with country realities, needs, and project objectives.
Effectiveness Rating (weight 40% for Investment loans, 60% for PBLs)
OVERALL EFFECTIVENESS RATING
Excellent (E) | The project’s specific objectives were fully achieved or exceeded and are attributable to the project. | 4
Satisfactory (S) | More than 50% of the project’s specific objectives were largely or fully achieved (no specific objectives are rated Unsatisfactory) and results are attributable to the project. | 3
Partly Unsatisfactory (PU) | More than 50% of project’s specific objectives were largely or fully achieved (and results are attributable to the project) and at least one specific objective is rated Unsatisfactory; OR when 50% or more of the project’s specific objectives were partly achieved (or above), AND the specific objectives rated Unsatisfactory do not exceed the specific objectives rated Satisfactory or Excellent | 2
Unsatisfactory (U) | The project’s specific objectives were not achieved, OR if the project’s specific objectives have only a combination of Partly Satisfactory and Unsatisfactory ratings. | 1
SPECIFIC DEVELOPMENT OBJECTIVE RATING
The achievement of each specific objective will be rated separately under the effectiveness section and the overall effectiveness rating will be an average of these individual objective ratings. Results Achieved: The project can demonstrate specific development objectives and their expected development results were reached as summarized in the Results Matrix, taking into consideration the consistency with the vertical logic.
Excellent (E) | The project results were fully achieved or exceeded. The results indicators targets were fully achieved or surpassed and are attributable to the project. | 4
Satisfactory (S) | The project results were largely achieved. At least 80% of the targets of the results indicators were met, on average, and are attributable to the project. | 3
Partly Unsatisfactory (PU) | The project results were partly achieved. Between 51% and 79% of the results indicators were met, on average, and are attributable to the project. | 2
Unsatisfactory (U) | Project results were not achieved. Only 50% or less of the results indicators were met equal and are attributable to the project. | 1
Results attribution: The results achieved are attributable to the project through a counterfactual analysis: impact evaluation, theory based or evidence-based approach, or other type of counterfactual analysis.
Attribution | The result was achieved, and attribution is supported by a counterfactual analysis. | Select Method: •Impact Evaluation •Other evidence-based •Other
No Attribution (NA) | The result was achieved but attribution analysis indicates that achievement is not attributed to inputs and outputs of the project or there is no attribution analysis to support the result. | None
For evaluation purposes, absence of data for assessing the achievement of result indicators will be considered as if outcome indicators targets had not been achieved. However, impacts tied strictly to the general development objective need not be measured and do not count against achievement. Targets: The achievement is based on the result indicators (baselines and targets) established at approval and corresponding to specific development objectives, adjusted in the Start-up Plan, or added during project execution (if applicable), measured at the end of the project and reported in the Results Matrix in Convergence. If there is no evidence of achievements the indicators should nevertheless be listed and rated with zero achievement.
Attribution:Can the results achieved be attributed to the operation? When the desired result is achieved but there is evidence that the results chain is weak and/or that the results are primarily due to other factors, the rating should be adjusted to 0 (zero). If there is not enough evidence to indicate that the results are attributable to the project, the overall effectiveness rating should be rated Unsatisfactory, regardless of the level of achievement.
Results Indicators Achievement Ratio: Formulas to calculate the achievement ratio follow. P refers to the baseline value and EOP refers to the end of the project
To calculate the achievement ratio for results indicators that are expected to reach a value lower than the baseline:
To calculate the achievement ratio for results indicators that are expected to reach a value higher than the baseline
To calculate the achievement ratio in rare cases where a result indicator is expected to maintain the baseline value:
However, if the end of project value of the indicator shows improvement against its baseline, the achievement ratio is automatically 1 (one).
If the achievement ratio is greater than 1 (one) the maximum value permitted is 1. If the achievement ratio is less than 0 (zero) the minimum value permitted is 0.
Efficiency Rating (weight 20%) -not applicable for PBLs-
Excellent (E) | If a cost-benefit analysis (CBA) was conducted, the economic rate of return (ERR) exceeds the discount rate (%) used in the ex post evaluation.a If a cost-effectiveness analysis (CEA) was conducted, the project results were achieved at a cost below the cost of the alternative ways to achieve the same or similar results or of the comparator. There were no other factors that reduced efficiency. | 4
Satisfactory (S) | If a CBA was conducted, the ERR is between 85% and 100% of the discount rate used in the ex post evaluation If a CEA was conducted, the project results were achieved at a cost equal to or no more than 110% of the cost of alternative ways to achieve the result or of the comparator. If only a Cost and Time Overrun Analysis (CTOA) was feasible (that is, there is an acceptable exception consistent with these Guidelines): the efficiency rating should be classified as “Satisfactory” if the project is classified as "Satisfactory" in the Progress Monitoring Report (PMR) and there were no other factors that reduced efficiency. There were no other factors that reduced efficiency. | 3
Partly Unsatisfactory (PU) | If a CBA was conducted, the ERR is between 51% and 84% of the discount rate used in the ex post evaluation and/or there were significant inefficiencies caused by other factors. If a CEA was conducted, the project results were achieved at a cost between 111% and 125% of the cost of the alternative ways to achieve the same or similar results or of the comparator, and/or there were significant inefficiencies caused by other factors. If a CBA or CEA were feasible but only a CTOA was conducted (that is, there is no acceptable exception consistent with these Guidelines): the efficiency rating should be classified as “Partly Unsatisfactory” if the project is classified as "Satisfactory" in the PMR. | 2
Unsatisfactory (U) | If a CBA was conducted, the ERR is less or equal to 50% of the discount rate used in the ex post evaluation and/or major inefficiencies caused by other factors. If a CEA was conducted, project results achieved at a cost of more than 125% above the cost of the alternative ways to achieve the same or similar results, or sector/industry standards (comparator), and/or major inefficiencies caused by other factors. If a CBA or CEA were feasible but only a CTOA was conducted (that is, there is no acceptable exception consistent with these Guidelines): the efficiency rating should be classified as “Unsatisfactory” if the project is classified as “Alert” or "Problem" in the PMR. | 1
Notes:
For those cases lacking a CEA or CBA, a maximum score of 2 (Partial Unsatisfactory) can be assigned if a CTOA has been conducted (unless the projects qualify under a list of admissible exceptions that make an ex post CEA or CBA unfeasible). a: The most commonly used discount rate is 12%. In cases where a different rate is used, a clear justification should be provided.
Sustainability Rating (weight = 20% for Investment Loans and PBLs)
Note: For Environmental and Social (E&S) Safeguards, the sustainability rating should take into consideration the E&S Supervision Report’s Safeguards Performance Rating (SPR) for operations rated with High or Substantial risk at any point during project execution, and the summary of the key safeguards implementation issues for operations with consistently low or moderate risks.
Excellent (E) | No unmitigated risks (technical, political, financial, economic, environmental, social) to continuation of results and safeguards performance was satisfactory. | 4
Satisfactory (S) | Minor unmitigated risks to continuation of results, and the impact of realized risks is likely to be small and safeguards performance was satisfactory. | 3
Partly Unsatisfactory (PU) | Significant unmitigated risks to continuation of results and/or the impact or realized risks are likely to be significant and/or safeguards performance was unsatisfactory. | 2
Unsatisfactory (U) | Major unmitigated risks to continuation of results and/or impact of realized risks is likely to be high and/or safeguards performance was unsatisfactory. | 1
Non-Core Criteria
Bank's Performance
The rating of overall Bank’s performance is based on the ratings for each of the two dimensions: (1) Bank performance in ensuring quality at entry; and (2) the quality of supervision. The quality at entry and quality of supervision ratings should be combined into a rating of overall Bank’s performance. Overall Bank’s Performance
Excellent (E) | Bank performance was rated Excellent on both dimensions.
Satisfactory (S) | Bank performance was rated Satisfactory on both dimensions, OR was rated Satisfactory on one dimension and Excellent on the other dimension
Partly Unsatisfactory (PU) | Bank performance was rated Partly Unsatisfactory on one or both dimensions
Unsatisfactory (U) | Bank performance was rated Unsatisfactory on both dimensions OR was rated Partly Unsatisfactory on one dimension and Unsatisfactory on the other dimension.
Quality at Entry
Excellent (E) | There were no shortcomings in identification, preparation, or approval.
Satisfactory (S) | There were moderate shortcomings in identification, preparation, or approval.
Partly Unsatisfactory (PU) | There were significant shortcomings in identification, preparation, or approval.
Unsatisfactory (U) | There were severe shortcomings in identification, preparation, or approval.
Quality of Supervision
Excellent (E) | There were no shortcomings in the proactive identification of opportunities and resolution of threats.
Satisfactory (S) | There were moderate shortcomings in the proactive identification of opportunities and resolution of threats.
Partly Unsatisfactory (PU) | There were significant shortcomings in the proactive identification of opportunities and resolution of threats.
Unsatisfactory (U) | There were severe shortcomings in the proactive identification of opportunities and resolution of threats.
Borrower's Performance
Excellent (E) | There were no shortcomings in the borrower's performance.
Satisfactory (S) | There were moderate shortcomings in the borrower's performance.
Partly Unsatisfactory (PU) | There were significant shortcomings in the borrower's performance.
Unsatisfactory (U) | There were severe shortcomings in the borrower's performance.

## Dictionary Support
Dictionary Support to fill the Effectiveness Section
Variable Name | Variable Type | Variable Range | Comments
Outcome Indicator Name | String - No limit of characters |  | Use same names as in Table 2 of PCR
Results Matrix [Approval, Start-Up Plan, Added] | String Variable | {Approval, Start-Up Plan, Added after Start-up Plan} | Select form dropdown menu
Unbounded Achievement Ratio | Numeric Variable (Continuous) | Include all integer numbers. Examples: {-25%, 87%, 125%} | The achievement % is unbounded. Values can be neagtive or greater than 100%
Achievement Ratio (0-1) | Numeric Variable (Continuous) | The proportion of achievement takes value between 0 and 1 | Negative unbounded achievements ratio map to 0, those greater than 100% map to 1, any other number XX% map to 0.XX (example: 85% map to 0.85)
Type of counterfactual analysis | String Variable | {Impact Evaluation, Other Evidence-Based, Other, None} | Select form dropdown menu
Attributable achievement | Numeric Variable (Continuous) | The proportion of achievement takes value between 0 and 1 | This is automatically calculated.
Effectiveness Issues | String Variable | {No issues, Design: specific objective had no metric, Design: weak Results Matrix (causal chain/ no SMART indicators), Design: targets too ambitious, Design: other issues, Execution: cancelled /not enough outputs, Execution: did not report on original indicators, Execution: other issues, Other issues not listed above} | Select form dropdown menu. A reason needs to be reported for all indicators with an Achievement Ratio (0-1) equal to 0.8 or lower. When OTHER is selected, please describe what was the issue under the Comments to Self-Assessment Column.

## dropdown_lists (hidden)
| Y |  | types | type_zero |  |  | ratio-type
| N |  | Impact Evaluation | None |  |  | 0
Eficiencia | 4 |  | Other Evidence-based |  |  |  | 1
| 3 |  | Other
| 2 |  | None
1
Relevancia | 4
3
| 2 | General rule: |  | Weighted score | Numerical scale | Ordinal scale |  | Converting categorical into numerical ratings: |  | output achievement
| 1 |  | >= | 3.5 | 6 | Highly successful |  | Performance areas: |  | 100% | Output targets are fully met or exceeded
|  |  | >= | 3 | 5 | Successful |  | Unsatisfactory | 1 | >75% | Output targets were largely met or exceeded.
Sostenibilidad | 4 |  | >= | 2.5 | 4 | Partly successful |  | Partly unsatisfactory | 2 | >50% | Outputs were at least partly achieved
| 3 |  | >= | 2 | 3 | Partly unsuccessful |  | Satisfactory | 3
| 2 |  | >= | 1.5 | 2 | Unsuccessful |  | Excellent | 4
| 1 |  | < | 1.5 | 1 | Highly unsuccessful
Bank's and Borrower's Performance
| Unsatisfactory | Additional rules: | [5 empty] | Results Matrix:
| Partly unsatisfactory | Rule 1: | [5 empty] | Approval
| Satisfactory | With unsatisfactory rating for relevance, effectiveness, sustainability: highest achievable rating is partly unsuccessful | [5 empty] | Start-Up Plan
| Excellent | Rule 2: | [5 empty] | Added after Start-Up Plan
For a highly successful rating, no indicator rating can be less than satisfactory.
Rule 3:
With a partly unsatisfactory rating for relevance, effectiveness or sustainability, highest achievable overall rating is partly successful
outputs | 4
3
2
| 1 | Effectiveness Issues Management: |  |  |  |  | Effectiveness Issues OVE (TENTATIVE):
|  | No issues |  |  |  |  | Objective was added/changed/etc by OVE
|  | Design: specific objective had no metric |  |  |  |  | Not accepting additional indicators
| Yes | Design: weak Results Matrix (causal chain/ no SMART indicators) |  |  |  |  | Not accepting attribution analysis
| No | Design: targets too ambitious |  |  |  |  | Changed RM (added/deleted indicators)
|  | Design: other issues |  |  |  |  | Other issues not listed above
Execution: cancelled /not enough outputs
Execution: did not report on original indicators
Execution: other issues
Other issues not listed above