## Original Procurement Plan TC
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: The Bahamas |  |  |  |  | Executing agency: IDB |  |  |  |  | Public or private sector: Public Sector
Project number: BH-T1078 |  |  |  |  | Project Title: Capacity Strengthening for a More Resilient Bahamas
Period covered by the plan: 24 months
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$): 100,000 |  |  |  | Consulting services(in US$):500,000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other % |  |  |  | Direct Contracting
1 |  | Component 1 | 200000 | [7 empty] | International Competitive Bidding
National Competitive Bidding
Consulting services
|  | Diagnostic, recommendations and proposals for an efficient and effective reconstruction and resilience governance, developed | 50000 | QCS | N/A | 100% | 0% | 2020A |  |  | Quality and Cost Based Selection
|  | National standard for hazard and risk assessment: | 100000 | QCS | N/A | 100% | 0% | 2020B |  | Incldudes: - development of Comprehensive hazard and risk assessment - development of National Hazard and Hurricane Risk data Catalog - Development of Action Plan for improving Hazard and Risk Assessment as National standard - Technical seminar to disseminate The National standard for hazard and risk analysis
|  | Services other than consulting | [8 empty] | Quality and Cost Based Selection
|  | International workshop in Nassau | 50000 |  | N/A | 100% | 0% | 2020A |  | objective: to share lessons learned from past international reconstruction programs in other countries
2 |  | Component 2 | 300000 | [7 empty] | Selection Based on the Consultants' Qualifications
Consulting services
|  | Urban Planning Tool for resilient infrastructure and local society | 300000 | QCS | N/A | 100% | 0% | 2020B |  | Includes: - Development of the Urban Planning tool - Training of how to use the Tool - Application of the Tool to develop pilot Urban/Sub-urban Sustainable and Resilient Plan
Individual Consultant
2 |  | Component 3 | 100000 | [7 empty] | Selection Based on the Consultants' Qualifications
Consulting services
|  | Development of communication materials to share lessons learned, best practices, procedures and protocols from Hurricane Dorian | 50000 | QCS | N/A | 100% | 0% | 2020B |  | including pamphlets, brochures, infographics, and short videos
|  | Services other than consulting | [8 empty] | Individual Consultant
|  | Community sensitization workshops in priority areas | 50000 |  | N/A | 100% | 0% | 2021A
Ex Post
National System
Total |  |  | 600000 | Prepared by: CBH |  |  | Date: 9/Apr/2020
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.

## Updated Procurement Plan
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: The Bahamas |  |  |  |  | Executing agency: IDB |  |  |  |  | Public or private sector: Public Sector
Project number: BH-T1078 |  |  |  |  | Project Title: Capacity Strengthening for a More Resilient Bahamas
Period covered by the plan: 24 months
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$): 100,000 |  |  |  | Consulting services(in US$):500,000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other % |  |  |  | Direct Contracting
1 |  | Component 1 | 248500 | [7 empty] | International Competitive Bidding
National Competitive Bidding
1.1 |  | Consulting services
1.1.1 |  | Consultancy Baseline for Critical Sectors (Education) | 20000 | IICQ | Approval and candidate selection Pending | 100% | 0% | 2021B |  | This consultancy is still pending approval from the GOBH authorities to be carried out. | Quality and Cost Based Selection
|  | Consultancy Baseline for Critical Sectors (Tourism) | 20000 | IICQ | Complete | 100% | 0% | 2020B
|  | Consultancy Baseline for Critical Sectors (Housing) | 20000 | IICQ | Complete | 100% | 0% | 2020B
|  | DRA Consultancy for Strategy & Recovery Plan Peer Review | 16500 | IICQ | Candidate Selection and approval pending | 100% | 0% | 2021A
|  | Consultancy for Project Management Technical Assistance for DRA | 20000 | IICQ | Contracting for Jan 2021 | 100% | 0% | 2021A
|  | DRA Consultancy for Evaluation of Project Reconstruction Execution Prioritization Impact on the economy of the Country (Cancelled) To be executed by MoF | 0 | IICQ | Pending preparation of TOR's / Proposed Scope | 100% | 0% | 2021A
|  | National standard for hazard and risk assessment: | 100000 | QCS | TOR's submitted pending approval to start contracting process | 100% | 0% | 2021A |  | Incldudes: - development of Comprehensive hazard and risk assessment - development of National Hazard and Hurricane Risk data Catalog - Development of Action Plan for improving Hazard and Risk Assessment as National standard - Technical seminar to disseminate The National standard for hazard and risk analysis
|  | Update the iGOPP Report for The Bahamas | 32000 | IICQ | Individual Consultants contracted | 100% | 0% | 2021A
|  | Updating the iGOPP Report - local consulting Firm | 20000 | SSS
|  | Concepts note Business Development Risk |  | IICQ | Pending Discussions with DRA and approval of concept | 100% | 0% | 2021A
|  | Services other than consulting | [8 empty] | Quality and Cost Based Selection
|  | International workshop in Nassau |  |  | Completed | 100% | 0% | 2020B |  | objective: to share lessons learned from past international reconstruction programs in other countries
2 |  | Component 2 | 250000 | [7 empty] | Selection Based on the Consultants' Qualifications
Consulting services
|  | Development and Piloting of a Pre- and Post-Disaster Land Use Planning Toolkit for the Family Islands) | 250000 | QCS | TOR's submitted pending approval to start contracting process | 100% | 0% | 2021A |  | Includes: - Development of the Urban Planning tool - Training of how to use the Tool - Application of the Tool to develop pilot Urban/Sub-urban Sustainable and Resilient Plan
Individual Consultant
2 |  | Component 3 | 75240 | [7 empty] | Selection Based on the Consultants' Qualifications
Consulting services
|  | Support to NEMA / DRA Communication Department technical Assistance Social Media | 15120 | IICQ | Complete | 1 | 0 | 2020B
|  | Support to NEMA / DRA Communication Department technical Assistance Digital marketing | 15120 | IICQ | Complete | 1 | 0 | 2020B
|  | Support to NEMA/ DRA Communication Department “Sharping Disaster Risk and Crisis Communication by applying behavioral Insights” | 15000 | IICQ | TOR's submitted pending approval to start contracting process | 1 | 0 | 2021A
|  | Disaster Reconstruction Communications Campaign and Public Awareness/Community Sensitizations Consultant | 30000 | IICQ | TOR's Approved, pending resumes of potential candidates to start contracting process | 1 | 0 | 2021A |  | including pamphlets, brochures, infographics, and short videos
|  | Services other than consulting | [8 empty] | Individual Consultant
Ex Post
National System
Total |  |  | 573740 | Prepared by: CBH |  |  | Date: Jan 8, 2021
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be modified Reply: Amount budgeted is correct. TORs are changing.
Note on D19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actualizar a 20.000 Reply: Done
Note on D20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amount eliminated
Note on D22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please verify budget against list presented to PS Smith Reply: Amount here is correct. Updated in the other file