## Sheet1
Procurement Plan | [9 empty] | Reference Bidder Name
Approval Number | 4359/GR-HA | [8 empty] | Name + (A) Award
Operation Number | HA-L1107 | [8 empty] | Name + (P) Participant
Country | HAITI | [8 empty] | Name + (R) Rejected
Coverage Plan | 27 Aug 2021 - 27 Feb 2023
Executing Agency | MINISTERE DE L'AGRICULTURE DES RESOURCES NATURELLES ET DU DEVELOPPEMENT RURAL
Goods and Services Total | $ 2,400,000.00
Works Total | $ 0.00
Consulting Services Total | $ 586,437.67
Version | 2021-6
Proc Id | Procurement Process name | Description | Estimated Amount (USD) | Procurement Type | Procurement Method | Process Status | Lots | Process Start Estimated Date | Signed Contract Estimated date | Bidder/Proponent Name | Nationality | Contract Status | Start Date Contract | End Date Contract | Contract Amount USD
HA-L1107-P11942 | Acquisition de pompes à energie solaire (Lot 2 : 14) | MARNDR/PITAG/B/AOI-05/20 | $ 1,680,000.00 | Goods | International Competitive Bidding | Contract under execution |  | 01 Mar 2020 | 29 Jan 2021
HA-L1107-P11943 | Acquisition de 4 véhicules Pick-Up double cabine | Marché co-financé par la HA-G1041 MARNDR/PITAG/B/AOI-06/21 | $ 130,000.00 | Goods | International Competitive Bidding | Process ongoing |  | 01 Apr 2021 | 01 Jun 2021
HA-L1107-P11944 | Acquisition d'équipements (matériels de bureau) pour la composante 1 | MARNDR/PITAG/B/AON-03/20 | $ 79,500.00 | Goods | National Competitive Bidding | Contract finished |  | 01 Jun 2020 | 02 Jan 2021
HA-L1107-P11945 | Acquisition de 16 motocyclettes tout terrain | MARNDR/PITAG/B/AON-06/21 | $ 70,000.00 | Goods | National Competitive Bidding | Process ongoing |  | 01 Apr 2021 | 30 Jun 2021
HA-L1107-P11946 | Generatrice/DI | MARNDR/PITAG/B/CP-02/21 | $ 39,500.00 | Goods | Shopping/Request for Quotations by Open Invitation | Process ongoing |  | 01 May 2021 | 01 Jul 2021
HA-L1107-P11947 | Achat d'Equipement et materiel de bureau et d'informatique pour la DI | MARNDR/PITAG/B/CP-___/21 | $ 21,000.00 | Goods | Shopping/Request for Quotations by Open Invitation | Expected |  | 31 May 2021 | 30 Jul 2021
HA-L1107-P11948 | Entité financière | MARNDR/PITAG/SNC/SED-01/21 | $ 380,000.00 | Non-Consulting Services | Direct Contracting/Selection | Process ongoing |  | 01 Feb 2021 | 01 Jul 2021
HA-L1107-P11949 | Sous programme Maraichage - Relance mai 2021 | MARNDR/PITAG/SFQ-22/21 | $ 997,291.97 | Consulting Firms | Quality-Based Selection (QBS) | Process ongoing |  | 30 Apr 2021 | 29 Dec 2021
HA-L1107-P11950 | Recrutement d'un opérateur pour les Champs Ecoles Paysans | Financé par le HA-G1041 MARNDR/PITAG/SFQ-21/20 | $ 900,000.00 | Consulting Firms | Quality-Based Selection (QBS) | Process ongoing |  | 28 Feb 2020 | 30 Nov 2020
HA-L1107-P11951 | Amélioration de fertilité des sols en conditions de faibles intrants (Relance) |  | $ 500,000.00 | Consulting Firms | Quality-Based Selection (QBS) | Contract under execution |  | 28 Feb 2019 | 08 Jan 2021
HA-L1107-P11952 | Stockage et conservation des denrees agricoles (PS3) - Relance III | MARNDR/PITAG/SFQ-23/21 | $ 500,000.00 | Consulting Firms | Quality-Based Selection (QBS) | Process ongoing |  | 26 Feb 2021 | 30 Jul 2021
HA-L1107-P11953 | Identification et gestion de maladies et ravageurs (PS4-Relance) | MARNDR/PITAG/SFQ-18/20 | $ 500,000.00 | Consulting Firms | Quality-Based Selection (QBS) | Contract under execution |  | 28 Feb 2019 | 30 Sep 2019
HA-L1107-P11954 | Sous programme transformation produits agricoles | MARNDR/PITAG/SFQ-25/21 | $ 500,000.00 | Consulting Firms | Quality-Based Selection (QBS) | Expected |  | 30 Apr 2021 | 30 Dec 2021
HA-L1107-P11955 | Opérateur mise en place système information scientifique et technique | MARNDR/PITAG/SFQ-24/21 | $ 127,000.00 | Consulting Firms | Quality-Based Selection (QBS) | Expected |  | 01 Apr 2021 | 02 Dec 2021
HA-L1107-P11956 | Consultant pour l'audit technique des incitations-Relance |  | $ 200,000.00 | Individual Consultants | Individual Consultant Selection (Open Invitation) | Process ongoing |  | 30 Jun 2021 | 08 Sep 2021
HA-L1107-P11957 | Consultant pour étude des espèces invasives-Relance | MARNDR/PITAG/QCIN-___/21 | $ 0.00 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Cancelled |  | 01 Feb 2021 | 02 May 2021
HA-L1107-P11958 | Spécialiste senior en ciblage, inclusion, genre et jeunesse - Temps partiel |  | $ 28,800.00 | Individual Consultants | Single-Source Selection of Individual Consultant (SSS) | Expected |  | 26 Feb 2021 | 31 May 2021
HA-L1107-P11959 | Assistant administratif 2 | MARNDR/PITAG/CI/QCIN-21/21 | $ 30,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing |  | 19 Feb 2021 | 31 May 2021
HA-L1107-P11960 | Protocole de coopération technique | MARNDR/PITAG/PA/SED-01/19 | $ 200,000.00 | Consulting Firms | Single-Source Selection of Firms (SSS) | Contract under execution |  | 01 Mar 2021 | 01 Apr 2021
HA-L1107-P11961 | Spécialiste Senior en ciblage, inclusion, genre et jeunesse - Temps partiel | Financé par le HA-G1041 MARNDR/PITAG/CI/SED-13/21 | $ 28,800.00 | Individual Consultants | Single-Source Selection of Individual Consultant (SSS) | Process ongoing |  | 01 Feb 2021 | 01 May 2021
HA-L1107-P11962 | Consultant en appui à la structuration des planteurs et à la commercialisation des produits agricoles | MARNDR/PITAG/CI/SED-12/21 | $ 22,357.67 | Individual Consultants | Single-Source Selection of Individual Consultant (SSS) | Contract under execution |  | 02 Feb 2021 | 31 Mar 2021
HA-L1107-P11963 | Consultant pour l'audit technique des incitations-Relance | MARNDR/PITAG/CI/QCIN-20/20 | $ 200,000.00 | Individual Consultants | Individual Consultant Selection (Open Invitation) | Process ongoing |  | 01 May 2021 | 01 Jul 2021
HA-L1107-P11964 | Consultant pour étude des espèces invasives-Relance | MARNDR/PITAG/CI/QCIN-24/21 | $ 0.00 | Individual Consultants | Individual Consultant Selection (Open Invitation) | Cancelled |  | 01 May 2021 | 01 Jul 2021
HA-L1107-P11965 | Assistant administratif 2 | MARNDR/PITAG/CI/QCIN-21/21 | $ 30,000.00 | Individual Consultants | Individual Consultant Selection (Open Invitation) | Contract under execution |  | 01 Feb 2021 | 01 May 2021
HA-L1107-P11966 | Spécialiste junior en ciblage, inclusion, genre et jeunesse | Financé par le HA-G1041 MARNDR/PITAG/CI/QCIN-22/21 | $ 8,000.00 | Individual Consultants | Individual Consultant Selection (Open Invitation) | Process ongoing |  | 31 May 2021 | 30 Sep 2021
HA-L1107-P11967 | Personnel d'appui à la DI (assistante administrative) | MARNDR/PITAG/CI/QCIN-23/21 | $ 6,480.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected |  | 30 Apr 2021 | 30 Aug 2021
HA-L1107-P17427 | Évaluation a mi-parcours du PITAG |  | $ 32,000.00 | Individual Consultants | Individual Consultant Selection (Open Invitation) | Expected |  | 31 Aug 2021 | 19 Nov 2021