## Sheet1
Procurement Plan | [9 empty] | Reference Bidder Name
Approval Number | 4437/OC-JA | [8 empty] | Name + (A) Award
Operation Number | JA-L1072 | [8 empty] | Name + (P) Participant
Country | JAMAICA | [8 empty] | Name + (R) Rejected
Coverage Plan | 25 Mar 2022 - 25 Sep 2023
Executing Agency | OFFICE OF THE PRIME MINISTER
Goods and Services Total | $ 38,089,275.68
Works Total | $ 4,111,835.49
Consulting Services Total | $ 8,445,076.49
Version | 2022-13
Proc Id | Procurement Process name | Description | Estimated Amount (USD) | Procurement Type | Procurement Method | Process Status | Lots | Process Start Estimated Date | Signed Contract Estimated date | Bidder/Proponent Name | Nationality | Contract Status | Start Date Contract | End Date Contract | Contract Amount USD
JA-L1072-P10843 | Firm - Acquire and Implement a Civil Registration and Vital Statistics Solution | Two stage process is to be used. | $ 1,000,000.00 | Goods | International Competitive Bidding | Process ongoing | 1 | 04 Oct 2021 | 09 Dec 2022
JA-L1072-P10844 | LTM Load Balancer Cluster Solution and Global load balancer service from ISP (eGovMDA14/15) |  | $ 366,259.17 | Goods | Direct Contracting/Selection | Contract finished | 1 | 07 Mar 2019 | 06 Nov 2019
JA-L1072-P10845 | Data Centre monitoring tool - support renewal & expansion (eGovSOF3) |  | $ 99,576.00 | Goods | Direct Contracting/Selection | Contract finished | 1 | 25 Nov 2019 | 21 Feb 2020
JA-L1072-P10846 | Firewall - Additinoal VPN (user) licenses (unlimited) - merged with CPU cores (eGovSOF5) | Fujitsu Caribbean (Jamaica) Limited is the only authorized vendor for checkpoint in Jamaica | $ 21,000.00 | Goods | Direct Contracting/Selection | Contract finished | 1 | 09 Mar 2019 | 01 Apr 2019
JA-L1072-P10847 | Use of Goods & Services - Microsoft Licenses | Ministry of Science and Technology is the authorized dealer on behalf of the Government of Jamaica | $ 6,400.00 | Goods | Direct Contracting/Selection | Contract finished | 1 | 25 Feb 2019 | 15 Mar 2019
JA-L1072-P10848 | Hyper Convergence Infrastructure for eGovJa's DR (Phase II) | There is only one supplier meeting eGov's requirements. | $ 280,000.00 | Goods | Direct Contracting/Selection | Cancelled | 1 | 21 Sep 2020 | 12 Feb 2021
JA-L1072-P10849 | Microsoft Licenses - RGD | Ministry of Science and Technology is the authorized dealer on behalf of the Government of Jamaica | $ 4,400.00 | Goods | Direct Contracting/Selection | Contract finished | 1 | 06 May 2020 | 15 Jun 2020
JA-L1072-P10850 | Cable Management Tray |  | $ 833.75 | Goods | Direct Contracting/Selection | Cancelled | 1 | 23 Oct 2020 | 09 Dec 2020
JA-L1072-P10851 | Microsoft Licenses | Ministry of Science and Technology is the authorized dealer on behalf of the Government of Jamaica | $ 4,150.00 | Goods | Direct Contracting/Selection | Contract finished | 1 | 18 Jan 2021 | 28 Jan 2021
JA-L1072-P10852 | Production & Placement - Outdoor (billboards, video boards, supermarket screens, bus sheds, bus sides etc. | 7 Companies are to be engaged. The selected companies have proprietary rights to the Digital Boards. | $ 7,000.00 | Non-Consulting Services | Direct Contracting/Selection | Contract terminated | 1 | 01 Jan 2019 | 11 Jan 2019
JA-L1072-P10853 | Production - Digital Media (including Google Ads) |  | $ 9,468.00 | Non-Consulting Services | Direct Contracting/Selection | Contract under execution | 1 | 16 Apr 2020 | 03 Dec 2020
JA-L1072-P10854 | Additional Placements -Television including Outside Broadcast (up to March 2019) | There are only two free to air television stations. Both are to be engaged for placements. | $ 432,643.00 | Non-Consulting Services | Direct Contracting/Selection | Contract finished | 2 | 23 Nov 2018 | 11 Dec 2018
JA-L1072-P10855 | Placement - Radio including Outside Broadcast | The 6 top- ranked radio stations will each be engaged for placements. The selection will be based on results of the market research survey. | $ 33,428.57 | Non-Consulting Services | Direct Contracting/Selection | Contract finished | 1 | 24 Dec 2020 | 24 Dec 2020
JA-L1072-P10856 | Additional Placements - Print (up to March 2019) | There are only two service providers in Jamaica: Gleaner and Observer. Both will be engaged. | $ 28,150.00 | Non-Consulting Services | Direct Contracting/Selection | Contract finished | 2 | 24 Nov 2018 | 12 Dec 2018
JA-L1072-P10857 | Television Placements | There are only two free to air television stations. Both are to be engaged for placements. | $ 52,000.00 | Non-Consulting Services | Direct Contracting/Selection | Contract finished | 3 | 24 Dec 2020 | 24 Dec 2020
JA-L1072-P10858 | Print Placements | There are only two print placement firms. Both are to be engaged. | $ 25,000.00 | Non-Consulting Services | Direct Contracting/Selection | Contract under execution | 2 | 24 Dec 2020 | 24 Dec 2020
JA-L1072-P10859 | 10 mb DIA from Central to RGD | Service is only obtainable from one source. The Government of Jamaica through the National Works Agency (NWA) and in collaboration with eGov Jamaica Limited has been building out a secure, wide-area network linking ministries, departments and agencies to minimize cost and increase the speed of data transmission. The NWA owns GovNet and utilizes the network to manage its city traffic lights nationally. | $ 37,063.21 | Non-Consulting Services | Direct Contracting/Selection | Cancelled | 1 | 22 Jan 2020 | 30 Nov 2020
JA-L1072-P10860 | Fibre Links from Central to Lots 2-4 | Service is only obtainable from one source. The Government of Jamaica through the National Works Agency (NWA) and in collaboration with eGov Jamaica Limited has been building out a secure, wide-area network linking ministries, departments and agencies to minimize cost and increase the speed of data transmission. The NWA owns GovNet and utilizes the network to manage its city traffic lights nationally. | $ 480,000.00 | Non-Consulting Services | Direct Contracting/Selection | Expected | 1 | 13 Dec 2021 | 21 Apr 2022
JA-L1072-P10861 | Outdoor Rentals/Postering & Transport | 7 Companies are to be engaged. The selected companies have proprietary rights to the Digital Boards. | $ 10,000.00 | Non-Consulting Services | Direct Contracting/Selection | Cancelled | 1 | 28 Aug 2020 | 08 Oct 2020
JA-L1072-P10862 | 1GB Fibre link from Central to Lot 1 Sites |  | $ 55,688.76 | Goods | Shopping/Request for minimun 3 Quotations | Expected | 1 | 15 Jun 2022 | 22 Jun 2022
JA-L1072-P10863 | Placement - Radio including Outside Broadcast | The justification for direct contracting is that the service is obtainable from only one source. The media houses have different program offerings and reach and so we are seeking to engage the various media entities to share messages with Jamaican citizens, residents and the Diaspora. | $ 33,278.79 | Non-Consulting Services | Direct Contracting/Selection | Cancelled | 6 | 14 Dec 2020 | 24 Dec 2020
JA-L1072-P10864 | Placement - Television including Outside Broadcast | The justification for direct contracting is that the service is obtainable from only one source. The media houses have different program offerings and reach and so we are seeking to engage the various media entities to share messages with Jamaican citizens, residents and the Diaspora. | $ 55,507.72 | Non-Consulting Services | Direct Contracting/Selection | Cancelled | 3 | 14 Dec 2020 | 24 Dec 2020
JA-L1072-P10865 | Placement - Print | The justification for direct contracting is that the service is obtainable from only one source. The media houses have different program offerings and reach and so we are seeking to engage the various media entities to share messages with Jamaican citizens, residents and the Diaspora. | $ 23,502.99 | Non-Consulting Services | Direct Contracting/Selection | Cancelled | 2 | 14 Dec 2020 | 24 Dec 2020
JA-L1072-P10866 | Placement - Television including Outside Broadcast-2021 | The justification for direct contracting is that the service is obtainable from only one source. The media houses have different program offerings and reach and so we are seeking to engage the various media entities to share messages with Jamaican citizens, residents and the Diaspora. | $ 40,000.00 | Non-Consulting Services | Direct Contracting/Selection | Expected | 3 | 17 Aug 2021 | 30 Sep 2021
JA-L1072-P10867 | Placement - Radio including Outside Broadcast 2021 | The justification for direct contracting is that the service is obtainable from only one source. The media houses have different program offerings and reach and so we are seeking to engage the various media entities to share messages with Jamaican citizens, residents and the Diaspora. | $ 30,000.00 | Non-Consulting Services | Direct Contracting/Selection | Expected | 7 | 17 Aug 2021 | 30 Sep 2021
JA-L1072-P10868 | Placements - Print (2021 - 2022) | The justification for direct contracting is that the service is obtainable from only one source. The media houses have different program offerings and reach and so we are seeking to engage the various media entities to share messages with Jamaican citizens, residents and the Diaspora. | $ 25,000.00 | Non-Consulting Services | Direct Contracting/Selection | Expected | 2 | 14 Feb 2022 | 28 Mar 2022
JA-L1072-P10869 | Virtual/Community Meetings | The justification for direct contracting is the exceptional case of JIS being an agency of the Office of the Prime Minister and is also the arm of government that is mandated to disseminate information that will enhance public awareness and increase knowledge of the policies and programmes of the Government of Jamaica. | $ 15,000.00 | Non-Consulting Services | Direct Contracting/Selection | Contract finished | 1 | 11 Jan 2021 | 12 Jan 2021
JA-L1072-P10870 | Digital Media Placement 2022 | The justification for direct contracting is the exceptional case of JIS being an agency of the Office of the Prime Minister and is also the arm of government that is mandated to disseminate information that will enhance public awareness and increase knowledge of the policies and programmes of the Government of Jamaica. Additionally, for digital placement, the company will be required to have administrative privileges to manage social media platforms on behalf of the NIDS Project. | $ 20,000.00 | Non-Consulting Services | Direct Contracting/Selection | Process ongoing | 1 | 11 Oct 2021 | 14 Jan 2022 | Jamaica Information Service (A) | JAMAICA
JA-L1072-P10871 | Developer 2 |  | $ 47,500.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 25 Apr 2019 | 16 May 2019
JA-L1072-P10872 | Consultant to Manage Installation of 10 LANs (eGovTECH6) |  | $ 40,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 28 Jun 2021 | 05 Jul 2021
JA-L1072-P10873 | Coordinator-Financial Sector Activities |  | $ 44,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 15 Jul 2022 | 10 Aug 2022
JA-L1072-P10874 | Project Coordinator - MOEYI NIDS Adoption |  | $ 40,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 11 Jul 2022 | 04 Aug 2022
JA-L1072-P10875 | Project Coordinator TOR - Coordinate all MLSS NIDS Adoption Activities |  | $ 40,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 15 Jul 2022 | 10 Aug 2022
JA-L1072-P10876 | Project Coordinator TOR - Coordinate all MNS NIDS Adoption Activities |  | $ 40,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 15 Jul 2022 | 10 Aug 2022
JA-L1072-P10877 | Project Coordinator TOR - Coordinate all HEART Trust NTA for NIDS Adoption Activities |  | $ 40,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 15 Jul 2022 | 10 Aug 2022
JA-L1072-P10878 | Consultant - Develop Action Plan for NIDS Adoption and Integration |  | $ 100,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 15 Jul 2022 | 10 Aug 2022
JA-L1072-P10879 | Project Coordinator - Implement Modified System & Processes in the Tax Services |  | $ 110,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 24 Nov 2020 | 01 Dec 2020
JA-L1072-P10880 | Architect |  | $ 69,717.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 26 Jun 2019 | 19 Aug 2019
JA-L1072-P10881 | Project Coordinator, RGD Activities |  | $ 48,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 17 Dec 2018 | 12 Dec 2019
JA-L1072-P10882 | Senior Media Officer |  | $ 56,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 16 Sep 2020 | 01 Oct 2020
JA-L1072-P10883 | Technical Communications Specialist |  | $ 10,750.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 24 Mar 2020 | 16 Apr 2020
JA-L1072-P10884 | Monitoring and Evaluation Officer |  | $ 85,714.29 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 20 Jan 2021 | 25 Jan 2021
JA-L1072-P10885 | Structural/Civil Engineer |  | $ 8,711.24 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 13 Mar 2020 | 30 Mar 2020
JA-L1072-P10886 | Legal Specialist - RGD |  | $ 90,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 13 Aug 2021 | 09 Sep 2021
JA-L1072-P10887 | RGD Record Retrievers |  | $ 107,836.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 12 | 01 Jul 2020 | 28 Oct 2020 | Collin Clarke (R) | JAMAICA
JA-L1072-P10887 | RGD Record Retrievers |  | $ 107,836.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 12 | 01 Jul 2020 | 28 Oct 2020 | Oshane Dixon (R) | JAMAICA
JA-L1072-P10887 | RGD Record Retrievers |  | $ 107,836.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 12 | 01 Jul 2020 | 28 Oct 2020 | Russheda Fraser-Dacres (A) | JAMAICA | Execution | 15 Nov 2021 | 14 Nov 2022 | 8,166.35
JA-L1072-P10887 | RGD Record Retrievers |  | $ 107,836.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 12 | 01 Jul 2020 | 28 Oct 2020 | Aaliyah Morlese (R) | JAMAICA
JA-L1072-P10887 | RGD Record Retrievers |  | $ 107,836.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 12 | 01 Jul 2020 | 28 Oct 2020 | Norton Larmond (R) | JAMAICA
JA-L1072-P10887 | RGD Record Retrievers |  | $ 107,836.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 12 | 01 Jul 2020 | 28 Oct 2020 | Michael Tulloch (R) | JAMAICA
JA-L1072-P10887 | RGD Record Retrievers |  | $ 107,836.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 12 | 01 Jul 2020 | 28 Oct 2020 | Kemar Thelwell (R) | JAMAICA
JA-L1072-P10887 | RGD Record Retrievers |  | $ 107,836.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 12 | 01 Jul 2020 | 28 Oct 2020 | Nicola Gow (R) | JAMAICA
JA-L1072-P10888 | Border Control- Develop requirements and designs details for use of the Automated Border Control e-Gate Solution |  | $ 65,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 21 May 2020 | 04 Jun 2020
JA-L1072-P10889 | National Digital Society Ambassador |  | $ 16,514.29 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 02 Nov 2020 | 16 Nov 2020
JA-L1072-P10890 | Digital Society Parish Ambassadors | 3 Individuals | $ 29,076.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 3 | 16 Apr 2020 | 07 May 2020
JA-L1072-P10891 | Digital Society Community Ambassadors | 30 Individuals | $ 12,320.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 02 Jan 2020 | 06 Jul 2020
JA-L1072-P10892 | Audio Visual Production Specialist |  | $ 17,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 17 Jun 2020 | 15 Jul 2020
JA-L1072-P10893 | Creative Writer |  | $ 7,301.54 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 10 Aug 2020 | 16 Sep 2020
JA-L1072-P10894 | Project Coordinator - MOEYI NIDS Adoption |  | $ 80,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 11 Jul 2022 | 04 Aug 2022
JA-L1072-P10895 | Legal Specialist | Replacement hire | $ 107,142.86 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 31 Aug 2020 | 06 Nov 2020
JA-L1072-P10896 | Modification of Spaces Manager |  | $ 65,714.29 | Individual Consultants | Individual Consultant Selection (3CV) | Contract terminated | 1 | 04 Nov 2020 | 08 Jan 2021
JA-L1072-P10897 | Structural/Civil Engineer (Lots 2-7) |  | $ 22,857.14 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 04 Nov 2020 | 13 Nov 2020
JA-L1072-P10898 | Mechanical/Electrical Engineer (Lots 2-7) |  | $ 26,571.43 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 04 Nov 2020 | 13 Nov 2020
JA-L1072-P10899 | Developer 1 - replacement hire |  | $ 85,714.29 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 26 Mar 2021 | 15 Apr 2021
JA-L1072-P10900 | Enrolment Officers - Lot 1 (19) | 19 vacancies | $ 176,428.57 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 19 | 27 Sep 2021 | 13 Dec 2021
JA-L1072-P10901 | Corporate Compliance Consultant |  | $ 60,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 18 Jan 2021 | 07 Apr 2021
JA-L1072-P10902 | Project Officers - RGD (2) |  | $ 142,857.14 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 2 | 02 Nov 2020 | 01 Dec 2020
JA-L1072-P10903 | Organizational Development Consultant - Information Commissioner Office |  | $ 40,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 04 Jul 2022 | 28 Jul 2022
JA-L1072-P10904 | Procurement Officer 1 - replacement hire |  | $ 89,285.71 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 02 Nov 2020 | 09 Mar 2021 | Corran Bell (A) | JAMAICA
JA-L1072-P10904 | Procurement Officer 1 - replacement hire |  | $ 89,285.71 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 02 Nov 2020 | 09 Mar 2021 | Andrew Richards (P) | JAMAICA
JA-L1072-P10904 | Procurement Officer 1 - replacement hire |  | $ 89,285.71 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 02 Nov 2020 | 09 Mar 2021 | Donna-Kay Nelson (R) | JAMAICA
JA-L1072-P10904 | Procurement Officer 1 - replacement hire |  | $ 89,285.71 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 02 Nov 2020 | 09 Mar 2021 | Kimala Tulloch (R) | JAMAICA
JA-L1072-P10904 | Procurement Officer 1 - replacement hire |  | $ 89,285.71 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 02 Nov 2020 | 09 Mar 2021 | Zoe Jones (R) | JAMAICA
JA-L1072-P10904 | Procurement Officer 1 - replacement hire |  | $ 89,285.71 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 02 Nov 2020 | 09 Mar 2021 | Mahatma McLean (R) | JAMAICA
JA-L1072-P10904 | Procurement Officer 1 - replacement hire |  | $ 89,285.71 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 02 Nov 2020 | 09 Mar 2021 | Fitz-Robert Dillon (R) | JAMAICA
JA-L1072-P10904 | Procurement Officer 1 - replacement hire |  | $ 89,285.71 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 02 Nov 2020 | 09 Mar 2021 | Sangenia Pinnock (R) | JAMAICA
JA-L1072-P10905 | PKI Auditor |  | $ 50,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 29 Jan 2021 | 10 Feb 2021
JA-L1072-P10906 | Development of RGD's Information Security Policies & Procedures |  | $ 65,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 15 Oct 2020 | 29 Oct 2020
JA-L1072-P10907 | Project Coordinator, RGD Activities - replacement hire |  | $ 85,714.29 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 02 Nov 2020 | 16 Nov 2020
JA-L1072-P10908 | Enrolment Outreach Officer |  | $ 70,967.74 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 15 Dec 2021 | 09 Mar 2022
JA-L1072-P10909 | System Administrator - PKI |  | $ 100,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 10 Jan 2022 | 03 Feb 2022 | Charis Cayetano (A) | JAMAICA
JA-L1072-P10909 | System Administrator - PKI |  | $ 100,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 10 Jan 2022 | 03 Feb 2022 | Lennox Tate (P) | JAMAICA
JA-L1072-P10909 | System Administrator - PKI |  | $ 100,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 10 Jan 2022 | 03 Feb 2022 | Jon-Marc James (R) | JAMAICA
JA-L1072-P10909 | System Administrator - PKI |  | $ 100,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 10 Jan 2022 | 03 Feb 2022 | Neil Powell (R) | JAMAICA
JA-L1072-P10909 | System Administrator - PKI |  | $ 100,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 10 Jan 2022 | 03 Feb 2022 | Dushane Forbes (R) | JAMAICA
JA-L1072-P10909 | System Administrator - PKI |  | $ 100,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 10 Jan 2022 | 03 Feb 2022 | Trevaughn Chambers (R) | JAMAICA
JA-L1072-P10910 | Developer 3 - Part time |  | $ 25,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 22 Sep 2021 | 02 Oct 2021
JA-L1072-P10911 | PKI Manager |  | $ 114,285.71 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 15 Nov 2021 | 25 Nov 2021
JA-L1072-P10912 | PKI Specialist (2) |  | $ 200,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 03 Feb 2022 | 15 Feb 2022
JA-L1072-P10913 | Enrolment Supervisors Lot 1 (5) |  | $ 64,285.71 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 5 | 15 Nov 2021 | 24 Jan 2022
JA-L1072-P10914 | Enrolment Site Supervisors -Lot 2 | 6 consultancies | $ 150,967.74 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 6 | 19 May 2022 | 29 Jul 2022
JA-L1072-P10915 | Enrolment Officers -Lot 2 (19) | 19 vacancies | $ 355,483.87 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 19 | 19 May 2022 | 29 Jul 2022
JA-L1072-P10916 | Enrolment Officers -Lot 4 (18) | 18 vacancies | $ 336,774.19 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 19 | 20 Sep 2021 | 14 Dec 2021
JA-L1072-P10917 | Customer Support Officers -Lot 1 (5) |  | $ 46,428.57 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 29 Mar 2021 | 08 Jun 2021
JA-L1072-P10918 | Customer Support Officers -Lot 3 (6) |  | $ 55,714.29 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 06 Oct 2021 | 13 Jan 2022
JA-L1072-P10919 | Customer Support Officers -Lot 4 (7) |  | $ 65,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 20 Sep 2021 | 14 Dec 2021
JA-L1072-P10920 | Comprehensive review of the MLSS systems |  | $ 70,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 11 Jul 2022 | 04 Aug 2022
JA-L1072-P10921 | Quality Control Officers |  | $ 184,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 27 Jan 2022 | 08 Apr 2022
JA-L1072-P10922 | Digital Society Parish Ambassadors - Additional Hire | 3 Individuals | $ 14,538.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 27 Jan 2021 | 20 Apr 2021
JA-L1072-P10923 | Digital Society Community Ambassadors - Additional Hire | 23 Individuals | $ 40,480.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 27 Jan 2021 | 20 Apr 2021
JA-L1072-P10924 | Project Coordinator - MOH Activities |  | $ 40,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 15 Jul 2022 | 04 Aug 2022
JA-L1072-P10925 | Enrolment Site Supervisor -Lot 4 |  | $ 176,129.03 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 7 | 20 Sep 2021 | 14 Dec 2021
JA-L1072-P10926 | Business Analyst - Tax Administration |  | $ 70,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 14 Dec 2021 | 07 Jan 2022
JA-L1072-P10927 | Application Manager |  | $ 100,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 04 Aug 2022 | 16 Aug 2022
JA-L1072-P10928 | eID & Biometric Expert |  | $ 44,472.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 12 Mar 2021 | 24 Mar 2021
JA-L1072-P10929 | Project Coordinator |  | $ 70,800.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 16 Oct 2019 | 22 Oct 2019
JA-L1072-P10930 | Modification of Spaces Officer |  | $ 56,578.95 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 3 | 08 Nov 2021 | 23 Dec 2021 | Marvin McDonald (R) | JAMAICA
JA-L1072-P10930 | Modification of Spaces Officer |  | $ 56,578.95 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 3 | 08 Nov 2021 | 23 Dec 2021 | Janet Thompson (R) | JAMAICA
JA-L1072-P10930 | Modification of Spaces Officer |  | $ 56,578.95 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 3 | 08 Nov 2021 | 23 Dec 2021 | Nicola Thompson (P) | JAMAICA
JA-L1072-P10930 | Modification of Spaces Officer |  | $ 56,578.95 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 3 | 08 Nov 2021 | 23 Dec 2021 | Michael Blidgen (R) | JAMAICA
JA-L1072-P10930 | Modification of Spaces Officer |  | $ 56,578.95 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 3 | 08 Nov 2021 | 23 Dec 2021 | Shawn Brooks (A) | JAMAICA | Pending Signature
JA-L1072-P10931 | Public Relations Coordinator |  | $ 65,789.47 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 22 Nov 2021 | 16 Dec 2021 | Amoy Smith (R) | JAMAICA
JA-L1072-P10931 | Public Relations Coordinator |  | $ 65,789.47 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 22 Nov 2021 | 16 Dec 2021 | Felicia Bailey (P) | JAMAICA
JA-L1072-P10931 | Public Relations Coordinator |  | $ 65,789.47 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 22 Nov 2021 | 16 Dec 2021 | Richard Delapenha (A) | JAMAICA | Execution | 01 Feb 2022 | 31 Jan 2024 | 63,963.98
JA-L1072-P10931 | Public Relations Coordinator |  | $ 65,789.47 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 22 Nov 2021 | 16 Dec 2021 | Merna Hinds (R) | JAMAICA
JA-L1072-P10931 | Public Relations Coordinator |  | $ 65,789.47 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 22 Nov 2021 | 16 Dec 2021 | Dania Bogle (R) | JAMAICA
JA-L1072-P10931 | Public Relations Coordinator |  | $ 65,789.47 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 22 Nov 2021 | 16 Dec 2021 | Tanya Wright (R) | JAMAICA
JA-L1072-P10931 | Public Relations Coordinator |  | $ 65,789.47 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 22 Nov 2021 | 16 Dec 2021 | Angela Johnson Dawkins (R) | JAMAICA
JA-L1072-P10932 | Procurement Manager |  | $ 60,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 12 Sep 2018 | 11 Jul 2019
JA-L1072-P10933 | Project Assistant |  | $ 64,516.13 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 15 Nov 2021 | 25 Nov 2021
JA-L1072-P10934 | Project Accountant |  | $ 40,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 06 Apr 2019 | 16 Apr 2019
JA-L1072-P10935 | Legal Specialist |  | $ 45,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 02 Apr 2019 | 26 Apr 2019
JA-L1072-P10936 | Chief Security Officer |  | $ 53,571.43 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 16 Oct 2018 | 05 Jan 2021
JA-L1072-P10937 | Business Processes and Documentation Officer |  | $ 85,714.29 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 04 Jul 2018 | 10 Feb 2021
JA-L1072-P10938 | Procurement Officer 2 |  | $ 50,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 23 Nov 2018 | 11 Dec 2018
JA-L1072-P10939 | Administrative Assistant 1 - Project Coordinator |  | $ 28,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 19 Apr 2019 | 08 May 2019
JA-L1072-P10940 | Administrative Assistant 2 - Financial Management |  | $ 28,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Cancelled | 1 | 25 May 2018 | 06 Mar 2020
JA-L1072-P10941 | Legal Support and Capacity Building Consultant |  | $ 9,235.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 06 Nov 2018 | 08 Nov 2018
JA-L1072-P10942 | Phase 1 Enrolment Sites - QS |  | $ 37,179.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 16 Aug 2018 | 02 Aug 2019
JA-L1072-P10943 | Consultant 1 - New and Optimized Civil Registration Processes and Work Flows |  | $ 60,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 08 Jun 2018 | 07 Dec 2018
JA-L1072-P10944 | Consultant 1 - Media Officer |  | $ 16,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 09 May 2018 | 18 Feb 2019
JA-L1072-P10945 | Consultant 1 - Social Media Services |  | $ 61,536.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 21 May 2018 | 18 Feb 2019
JA-L1072-P10946 | Developer 1 |  | $ 47,500.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 26 Apr 2019 | 31 May 2019
JA-L1072-P10947 | Project Director |  | $ 184,800.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 05 Jan 2020 | 05 Jan 2020
JA-L1072-P10948 | Financial Manager |  | $ 160,714.29 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 05 Oct 2017 | 02 Feb 2018
JA-L1072-P10949 | Research & Development Officer |  | $ 33,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 05 Jan 2020 | 05 Jan 2020
JA-L1072-P10950 | Marketing, PR & Communication |  | $ 160,714.29 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 25 Jan 2018 | 05 Mar 2018
JA-L1072-P10951 | Procurement Officer 1 |  | $ 50,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 18 Jan 2018 | 02 Feb 2018
JA-L1072-P10952 | Monitoring and Evaluation Officer |  | $ 60,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 13 Mar 2018 | 23 Jun 2018
JA-L1072-P10953 | Consultant 1 - Develop Regulations for NIRA Act 2017 |  | $ 40,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract terminated | 1 | 28 May 2018 | 26 Jul 2018
JA-L1072-P10954 | RGD Project Coordinator - RGD Activities |  | $ 48,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 05 Jan 2020 | 15 Jan 2020
JA-L1072-P10955 | National Ambassador |  | $ 11,417.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract terminated | 1 | 25 May 2018 | 30 Jul 2018
JA-L1072-P10956 | Consultant to prepare BQ and LAN Designs |  | $ 64,500.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 15 Feb 2018 | 08 Jun 2018
JA-L1072-P10957 | Jamaica Post Project Coordinator |  | $ 40,800.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 20 Mar 2018 | 11 Oct 2018
JA-L1072-P10958 | ICT Coordinator |  | $ 85,526.32 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 08 Dec 2021 | 16 Feb 2022 | Andrew Russell (A) | JAMAICA | Pending Signature | 01 Apr 2022 | 26 Feb 2024 | 83,609.78
JA-L1072-P10958 | ICT Coordinator |  | $ 85,526.32 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 08 Dec 2021 | 16 Feb 2022 | Peter Morris (R) | JAMAICA
JA-L1072-P10958 | ICT Coordinator |  | $ 85,526.32 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 08 Dec 2021 | 16 Feb 2022 | Shakeem O'Gilvie (R) | JAMAICA
JA-L1072-P10959 | ICT - Deployment and Support Personnel | 4 vacancies | $ 264,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 4 | 01 Jun 2021 | 01 Sep 2021 | Jomo Wynter (P) | JAMAICA
JA-L1072-P10959 | ICT - Deployment and Support Personnel | 4 vacancies | $ 264,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 4 | 01 Jun 2021 | 01 Sep 2021 | Richard Bernard (A) | JAMAICA | Execution | 01 Apr 2022 | 26 Feb 2024 | 58,413.59
JA-L1072-P10959 | ICT - Deployment and Support Personnel | 4 vacancies | $ 264,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 4 | 01 Jun 2021 | 01 Sep 2021 | Giovann Gusaran (R) | JAMAICA
JA-L1072-P10959 | ICT - Deployment and Support Personnel | 4 vacancies | $ 264,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 4 | 01 Jun 2021 | 01 Sep 2021 | Lanois Carroll (R) | JAMAICA
JA-L1072-P10960 | Senior Manager, Card & NIN Services |  | $ 120,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 05 Nov 2021 | 25 Jan 2022 | Collin Daley (A) | JAMAICA
JA-L1072-P10960 | Senior Manager, Card & NIN Services |  | $ 120,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 05 Nov 2021 | 25 Jan 2022 | Garfield Lynch (R) | JAMAICA
JA-L1072-P10960 | Senior Manager, Card & NIN Services |  | $ 120,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 05 Nov 2021 | 25 Jan 2022 | Lateisha Ellis-Marks (R) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Celia Blair (A) | JAMAICA | Execution | 01 Apr 2022 | 26 Feb 2024 | 78,016.33
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Marva Rose Chambers (P) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Toni-Ann Mitchell (P) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Beverley Ferril (R) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Oshane Morgan (R) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Romaro Black (R) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Godfrey Grant (R) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Keisha McCarthy (R) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Rusheda Brown (R) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Dwayne Brown (R) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Rayon Gowie (R) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Lateisha Ellis-Marks (R) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Shannon Thomas (R) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Monique Johnson (R) | JAMAICA
JA-L1072-P10961 | Manager- Card Production Services |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 1 | 25 Oct 2021 | 03 Jan 2022 | Trae Dussard (R) | JAMAICA
JA-L1072-P10962 | Vetting Manager |  | $ 88,944.00 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 07 Jul 2021 | 29 Sep 2021
JA-L1072-P10963 | Machine Operators-Printers |  | $ 88,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution | 2 | 31 Mar 2021 | 23 Jul 2021
JA-L1072-P10964 | Vetting Officers |  | $ 184,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 4 | 20 Jul 2021 | 30 Jul 2021 | Garfield Lynch (A) | JAMAICA
JA-L1072-P10964 | Vetting Officers |  | $ 184,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 4 | 20 Jul 2021 | 30 Jul 2021 | O'Dean Bailey (P) | JAMAICA
JA-L1072-P10964 | Vetting Officers |  | $ 184,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 4 | 20 Jul 2021 | 30 Jul 2021 | Raymond Stewart (R) | JAMAICA
JA-L1072-P10965 | Investigation Officers - Printing Room |  | $ 92,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 2 | 08 Dec 2021 | 18 Feb 2022 | Sean Grey (A) | JAMAICA
JA-L1072-P10965 | Investigation Officers - Printing Room |  | $ 92,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 2 | 08 Dec 2021 | 18 Feb 2022 | O'Dean Bailey (P) | JAMAICA
JA-L1072-P10965 | Investigation Officers - Printing Room |  | $ 92,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 2 | 08 Dec 2021 | 18 Feb 2022 | Sandeen Downie (R) | JAMAICA
JA-L1072-P10965 | Investigation Officers - Printing Room |  | $ 92,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 2 | 08 Dec 2021 | 18 Feb 2022 | Toni-Ann Dacres (R) | JAMAICA
JA-L1072-P10965 | Investigation Officers - Printing Room |  | $ 92,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 2 | 08 Dec 2021 | 18 Feb 2022 | Malaika Onywere (R) | JAMAICA
JA-L1072-P10965 | Investigation Officers - Printing Room |  | $ 92,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 2 | 08 Dec 2021 | 18 Feb 2022 | Raymond Stewart (R) | JAMAICA
JA-L1072-P10965 | Investigation Officers - Printing Room |  | $ 92,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 2 | 08 Dec 2021 | 18 Feb 2022 | Raymond Henry (R) | JAMAICA
JA-L1072-P10966 | Store Room and Distribution Officer |  | $ 18,709.68 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 08 Mar 2022 | 16 May 2022 | Christopher Collman (A) | JAMAICA
JA-L1072-P10966 | Store Room and Distribution Officer |  | $ 18,709.68 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 08 Mar 2022 | 16 May 2022 | Lovita Anderson (P) | JAMAICA
JA-L1072-P10966 | Store Room and Distribution Officer |  | $ 18,709.68 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 08 Mar 2022 | 16 May 2022 | Rashaun Johnson (R) | JAMAICA
JA-L1072-P10966 | Store Room and Distribution Officer |  | $ 18,709.68 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 08 Mar 2022 | 16 May 2022 | Keither-Gay Roache (R) | JAMAICA
JA-L1072-P10966 | Store Room and Distribution Officer |  | $ 18,709.68 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 08 Mar 2022 | 16 May 2022 | Leon Moore (R) | JAMAICA
JA-L1072-P10966 | Store Room and Distribution Officer |  | $ 18,709.68 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 08 Mar 2022 | 16 May 2022 | Elicia Price (R) | JAMAICA
JA-L1072-P10967 | Consultant 2 - Develop Acceptable Use Policy Manual - NIRA Civil Registry and Identity Services Users |  | $ 65,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 06 Feb 2019 | 05 Jul 2019
JA-L1072-P10968 | Consultant 3- Review Acceptable Use Policy Manual - NIRA Civil Registry and Identity Services Users |  | $ 3,555.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished | 1 | 25 Jun 2020 | 13 Jul 2020
JA-L1072-P10969 | Consultant - Change Management Strategies and Plan for NIDS Adoption and Integration |  | $ 100,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 04 Apr 2022 | 14 Apr 2022
JA-L1072-P10970 | Records Management Expert |  | $ 64,516.13 | Individual Consultants | Individual Consultant Selection (3CV) | Process ongoing | 1 | 11 Oct 2021 | 22 Oct 2021
JA-L1072-P10971 | Redundant emergency power for NIDS hosting site (Replacement of both generators & ATS) (eGovMDA4) |  | $ 679,860.03 | Goods | International Competitive Bidding | Contract under execution | 1 | 29 May 2019 | 15 Mar 2021
JA-L1072-P10972 | Replacement of redundant UPS system to improve power uptime for NIDS and supporting ICT systems hosted at eGovJa (eGovMDA6) |  | $ 502,906.00 | Goods | International Competitive Bidding | Contract finished | 1 | 20 Jul 2019 | 25 Feb 2021
JA-L1072-P10973 | Web Filtering Security Solution Application (eGovSOF8) |  | $ 148,985.00 | Goods | International Competitive Bidding | Contract finished | 1 | 16 Nov 2020 | 18 Aug 2021
JA-L1072-P10974 | Supply and installation of the NIDS |  | $ 29,618,291.00 | Goods | International Competitive Bidding | Contract under execution | 1 | 25 Apr 2017 | 22 Mar 2019
JA-L1072-P10975 | Hyper Convergence Infrastructure for eGovJa's DR (Phase I) | There is only one supplier meeting eGov's requirements. | $ 160,571.00 | Goods | International Competitive Bidding | Contract finished | 1 | 11 Jan 2020 | 26 Jan 2021
JA-L1072-P10976 | Network Devices for eGov |  | $ 198,400.00 | Goods | International Competitive Bidding | Contract finished | 3 | 30 Sep 2019 | 18 May 2020
JA-L1072-P10977 | Border Control Solution |  | $ 960,000.00 | Goods | International Competitive Bidding | Process ongoing | 1 | 28 Aug 2021 | 18 May 2022
JA-L1072-P10978 | Provision of centralized Windows Management platform to streamline integration of supporting applications with NIDS [Windows System Centre (Hyper-V), Windows Server - Data Centre Edition] (eGovSOF6) |  | $ 114,000.00 | Goods | Direct Contracting/Selection | Process ongoing | 1 | 04 Jan 2022 | 16 May 2022
JA-L1072-P10979 | Network Infrastructure Installation - Tier 1 and Tier 2 Enrolment Sites |  | $ 69,793.22 | Goods | National Competive Bidding | Contract under execution | 1 | 13 Feb 2021 | 27 Aug 2021
JA-L1072-P10980 | Man Trap Door |  | $ 86,000.00 | Goods | National Competive Bidding | Contract under execution | 1 | 26 Mar 2021 | 04 Aug 2021
JA-L1072-P10981 | Fire Detection System |  | $ 42,857.14 | Goods | National Competive Bidding | Cancelled | 1 | 08 Mar 2021 | 08 Jun 2021
JA-L1072-P10982 | Replacement of second CRAC unit to support onsite redundancy (eGovMDA12) |  | $ 700,000.00 | Goods | International Competitive Bidding | Process ongoing | 1 | 18 Sep 2021 | 12 May 2022
JA-L1072-P10983 | Public Key Infrastructure (PKI) Safes |  | $ 138,000.00 | Goods | National Competive Bidding | Contract under execution | 1 | 20 Apr 2021 | 18 Oct 2021
JA-L1072-P10984 | UPS, Server and NAS Drives for RGD |  | $ 114,000.00 | Goods | National Competive Bidding | Contract finished | 1 | 20 Jul 2019 | 24 Oct 2019
JA-L1072-P10985 | Modification of Spaces - Tier 1 Enrolment Sites |  | $ 725,174.85 | Works | National Competive Bidding | Procurement Complete | 1 | 31 Oct 2020 | 25 Oct 2021
JA-L1072-P10986 | Modification of Spaces - Lots 2-4 Enrolment Sites |  | $ 2,417,636.08 | Works | National Competive Bidding | Expected | 3 | 03 Nov 2021 | 02 Aug 2022
JA-L1072-P10987 | Modification of Spaces - Production Centre |  | $ 804,772.43 | Works | National Competive Bidding | Contract under execution | 1 | 18 Jul 2020 | 15 Apr 2021
JA-L1072-P10988 | Use of Goods & Services - Office Printer |  | $ 2,600.00 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 02 Nov 2018 | 12 Dec 2018
JA-L1072-P10989 | Additional LTO tape drives to facilitate backup regime of the NIDS solution (eGovMDA11) |  | $ 14,000.00 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 23 Jan 2019 | 29 Apr 2019
JA-L1072-P10990 | MDA Connectivity - Rack Server for Network Management Tool |  | $ 10,612.26 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 19 Jun 2018 | 13 Nov 2018
JA-L1072-P10991 | MDA Connectivity - 22 Network Switches |  | $ 22,089.00 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 10 Jul 2018 | 15 Nov 2018
JA-L1072-P10992 | Vulnerability Management Tool |  | $ 11,310.24 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 03 Nov 2017 | 13 Nov 2018
JA-L1072-P10993 | Office Tools |  | $ 800.00 | Goods | Procurement 100% funded by Agency | Cancelled | 1 | 02 Dec 2021 | 10 Dec 2021
JA-L1072-P10994 | Central UPS (10 KVA) |  | $ 20,161.29 | Goods | Procurement 100% funded by Agency | Contract under execution | 1 | 09 Apr 2021 | 29 Jun 2021
JA-L1072-P10995 | Use of Goods & Services - Computers, Laptops and Related Equipment |  | $ 6,315.00 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 15 Oct 2019 | 02 Dec 2019
JA-L1072-P10996 | Switches - Data Centre |  | $ 22,000.00 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 06 Apr 2018 | 20 Nov 2018
JA-L1072-P10997 | Production of Printing Materials |  | $ 10,000.00 | Goods | Procurement 100% funded by Agency | Expected | 1 | 19 Jul 2022 | 11 Aug 2022
JA-L1072-P10998 | Administrative Expenses - Stationery - Legal Consultation, Training, etc. | Activity to be carried out throughout the year | $ 4,000.00 | Goods | Procurement 100% funded by Agency | Cancelled | 1 | 16 Apr 2021 | 13 May 2021
JA-L1072-P10999 | Office Tools - High Definition Video Camera and PA/Karaoke System |  | $ 4,715.00 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 06 Jan 2020 | 23 Feb 2020
JA-L1072-P11000 | Central UPS - 10 KVA |  | $ 20,161.00 | Goods | Procurement 100% funded by Agency | Cancelled | 1 | 02 Sep 2020 | 29 Oct 2020
JA-L1072-P11001 | Use of Goods & Services - Projector and Projector Screens |  | $ 1,994.76 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 13 Dec 2019 | 08 Jan 2020
JA-L1072-P11002 | Computers for Customer Service Representatives/Change Management |  | $ 17,400.00 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 29 Jul 2020 | 12 Oct 2020
JA-L1072-P11003 | CUG for PEU Staff |  | $ 1,750.00 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 13 Jan 2021 | 18 Jan 2021
JA-L1072-P11004 | Multifunctional Printer- Production Centre |  | $ 15,714.29 | Goods | Procurement 100% funded by Agency | Expected | 1 | 27 Oct 2021 | 15 Dec 2021
JA-L1072-P11005 | Stationery and Office supplies- Production Centre |  | $ 5,155.71 | Goods | Procurement 100% funded by Agency | Expected | 1 | 27 Oct 2021 | 02 Dec 2021
JA-L1072-P11006 | Printer |  | $ 2,500.00 | Goods | Procurement 100% funded by Agency | Cancelled | 1 | 06 Apr 2022 | 06 Apr 2022
JA-L1072-P11007 | Customer Service furniture |  | $ 2,069.00 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 07 Oct 2020 | 17 Nov 2020
JA-L1072-P11008 | Chairs - Customer Service and other support |  | $ 235.00 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 02 Feb 2021 | 18 Feb 2021
JA-L1072-P11009 | Materials - Temporary Relocation of Staff - Production Centre |  | $ 4,299.17 | Goods | Procurement 100% funded by Agency | Contract finished | 1 | 29 Mar 2021 | 09 Apr 2021
JA-L1072-P11010 | SQL Server Licences |  | $ 18,000.00 | Goods | Direct Contracting/Selection | Process ongoing | 1 | 27 Sep 2021 | 14 Dec 2021
JA-L1072-P11011 | Use of Goods & Services - Stationery and Office supplies, etc. |  | $ 7,142.86 | Goods | Procurement 100% funded by Agency | Process ongoing | 1 | 25 Jan 2021 | 10 Feb 2021
JA-L1072-P11012 | Virtual Town Hall/ Community Meetings |  | $ 28,000.00 | Non-Consulting Services | Direct Contracting/Selection | Expected | 1 | 16 May 2022 | 25 Jul 2022
JA-L1072-P11013 | Surveyors ID Report |  | $ 4,285.71 | Non-Consulting Services | Procurement 100% funded by Agency | Contract finished | 1 | 05 Jan 2021 | 25 Jan 2021
JA-L1072-P11014 | Administrative Expenses - Venue and Refreshments - Training, Legal Consultation, etc | Activity to be carried out throughout the year | $ 4,000.00 | Non-Consulting Services | Procurement 100% funded by Agency | Cancelled | 1 | 15 Apr 2021 | 13 May 2021
JA-L1072-P11015 | Survey ID Report - CSO |  | $ 1,786.00 | Non-Consulting Services | Procurement 100% funded by Agency | Contract finished | 1 | 29 Jun 2020 | 10 Jul 2020
JA-L1072-P11016 | Relocation of Generator Room |  | $ 20,000.00 | Works | Procurement 100% funded by Agency | Contract finished | 1 | 03 Jul 2018 | 31 Oct 2018
JA-L1072-P11017 | Removal and Installation of Agency Stand-by Generator |  | $ 60,000.00 | Works | Procurement 100% funded by Agency | Contract finished | 1 | 03 Jul 2018 | 26 Oct 2018
JA-L1072-P11018 | Financial Audit (3 years) |  | $ 60,000.00 | External Audit | Quality-and-Cost Based Selection (QCBS) | Evaluation of Bids/Proposals | 1 | 12 Feb 2019 | 03 Jul 2019
JA-L1072-P11019 | FIRM/Consultancy 1 - RGD/NIRA Transformation Plan ( Business/Revenue Model, Organization Structure, Job Descriptions, Competency Framework, Transition Strategy for RGD Staff to NIRA) NIRAEST |  | $ 359,089.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Contract under execution | 1 | 06 Oct 2018 | 17 Nov 2020
JA-L1072-P11020 | Digitization of RGD Records |  | $ 2,400,000.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Contract under execution | 1 | 06 Jun 2020 | 06 Jan 2022 | Abergower Limited (R) | UNITED KINGDOM
JA-L1072-P11020 | Digitization of RGD Records |  | $ 2,400,000.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Contract under execution | 1 | 06 Jun 2020 | 06 Jan 2022 | Fujitsu Caribbean (Jamaica) Limited (A) | JAMAICA | Pending Signature | 28 Feb 2022 | 18 Aug 2024 | 4,149,891.31
JA-L1072-P11020 | Digitization of RGD Records |  | $ 2,400,000.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Contract under execution | 1 | 06 Jun 2020 | 06 Jan 2022 | Xsomo International Limited (P) | JAMAICA
JA-L1072-P11021 | External Auditing Services (3 years) |  | $ 60,000.00 | External Audit | Quality-and-Cost Based Selection (QCBS) | Contract under execution | 1 | 21 Sep 2021 | 21 Jan 2022 | KPMG Jamaica (A) | JAMAICA | Execution | 01 Apr 2022 | 26 Feb 2024 | 64,510.63
JA-L1072-P11022 | Public Relations Consultancy |  | $ 263,158.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Process ongoing | 1 | 16 Aug 2021 | 14 Jul 2022
JA-L1072-P11023 | UPS manufacturer training (eGovCONSULT3) |  | $ 18,000.00 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Cancelled | 1 | 16 Oct 2020 | 10 Feb 2021
JA-L1072-P11024 | Red Hat Enterprise Linux (RHCE) Training (eGovCONSULT12) |  | $ 22,400.00 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Cancelled | 1 | 03 Jul 2020 | 04 Feb 2021
JA-L1072-P11025 | Development of Web Application |  | $ 25,000.00 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Cancelled | 1 | 05 Mar 2021 | 23 Jun 2021
JA-L1072-P11026 | Midterm Evaluation |  | $ 110,700.00 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Contract under execution | 1 | 10 May 2021 | 01 Dec 2021 | Ernst & Young Services Limited (A) | JAMAICA | Execution | 02 Apr 2022 | 01 Aug 2022 | 188,632.02
JA-L1072-P11027 | Windows Server training (eGovCONSULT11) |  | $ 30,000.00 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Contract finished | 1 | 20 Jul 2019 | 11 Jun 2020
JA-L1072-P11028 | Network Switches for NIDs |  | $ 25,733.75 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished | 1 | 08 May 2018 | 08 Jun 2018
JA-L1072-P11029 | Electrical Cables to Upgrade RGD Power |  | $ 45,480.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished | 1 | 08 Apr 2019 | 26 Apr 2019
JA-L1072-P11030 | Additional Vmware Licences for DR Site |  | $ 83,094.35 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished | 1 | 13 Dec 2019 | 19 Dec 2019
JA-L1072-P11031 | Surveillance Camera and Access Control System- Production Site |  | $ 60,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Process ongoing | 1 | 09 Nov 2021 | 14 Dec 2021
JA-L1072-P11032 | Branding of NIRA (Lot 1) |  | $ 6,000.00 | Goods | Procurement 100% funded by Agency | Expected | 1 | 14 Dec 2021 | 24 Jan 2022
JA-L1072-P11033 | Laptops for NIDS PEU Staff |  | $ 26,142.86 | Goods | Shopping/Request for minimun 3 Quotations | Expected | 2 | 23 Feb 2021 | 09 Mar 2021
JA-L1072-P11034 | Checkpoint Firewall for eGov | The are only three authorized checkpoint partners in Jamaica | $ 71,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Process ongoing | 1 | 23 Sep 2021 | 07 Oct 2021 | Fujitsu Caribbean (Jamaica) Limited (A) | JAMAICA
JA-L1072-P11035 | Safes for ID Cards Storage |  | $ 46,052.63 | Goods | Shopping/Request for minimun 3 Quotations | Cancelled | 1 | 27 Aug 2021 | 08 Nov 2021
JA-L1072-P11036 | Placement - Promotional Material e.g. t-shirts, cups, pens, flyers etc. |  | $ 76,994.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished | 4 | 19 Jan 2019 | 13 Feb 2019
JA-L1072-P11037 | Audio Visual Graphics Production Services |  | $ 1,500.00 | Non-Consulting Services | Shopping/Request for minimun 3 Quotations | Cancelled | 1 | 29 Dec 2020 | 11 Jan 2021
JA-L1072-P11038 | NIDS Project - Bidders due Diligence Report |  | $ 33,000.00 | Non-Consulting Services | Shopping/Request for minimun 3 Quotations | Contract finished | 1 | 06 Mar 2019 | 19 Mar 2019
JA-L1072-P11039 | Quantity Surveyor - Design of NIDS Stations, Enrolment Sites |  | $ 8,000.00 | Consulting Firms | Single-Source Selection of Firms (SSS) | Contract finished | 1 | 23 Oct 2018 | 18 Dec 2018
JA-L1072-P11040 | Modification of ESMS, MOEYI |  | $ 180,000.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Process ongoing | 1 | 12 Jul 2021 | 19 May 2022
JA-L1072-P11041 | Preparation of Cabinet Submission for NIDS Solution |  | $ 1,000.00 | Individual Consultants | Single-Source Selection of Individual Consultant (SSS) | Contract finished | 1 | 15 Jan 2019 | 18 Jan 2019
JA-L1072-P19509 | Modified Container for Jamaica Post |  | $ 23,350.00 | Goods | Direct Contracting/Selection | Process ongoing |  | 24 Sep 2021 | 07 Dec 2021
JA-L1072-P19510 | F5 SFP Module for eGov |  | $ 12,420.00 | Goods | Direct Contracting/Selection | Process ongoing |  | 26 Oct 2021 | 21 Jan 2022
JA-L1072-P19513 | Developer 2 - Replacement hire |  | $ 85,714.29 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 1 | 14 Mar 2022 | 24 Mar 2022
JA-L1072-P20119 | Additional Equipment for UPS Upgrade |  | $ 25,000.00 | Goods | Direct Contracting/Selection | Process ongoing | 1 | 26 Oct 2021 | 07 Jan 2022 | Accupower Jamaica Limited (A) | JAMAICA | Pending Signature | 10 Dec 2021 | 09 Mar 2022 | 25,062.15
JA-L1072-P20120 | Equipment for Production Centre Showroom |  | $ 25,000.00 | Goods | Procurement 100% funded by Agency | Process ongoing | 1 | 28 Oct 2021 | 14 Jan 2022
JA-L1072-P23216 | Penetration Testing and Vulnerability Scanning Services | The scope of work cannot be advertised due to security reasons. Only select firms will be invited to bid. | $ 21,250.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Evaluation of Bids/Proposals |  | 05 Nov 2021 | 16 Mar 2022
JA-L1072-P26119 | Mobile Phones and Laptops for eGov Jamaica Limited |  | $ 3,290.00 | Goods | Procurement 100% funded by Agency | Contract under execution | 2 | 10 Nov 2021 | 21 Dec 2021 | PBS Technologies (A) | JAMAICA | Finished | 10 Dec 2021 | 09 Mar 2022 | 4,055.15
JA-L1072-P26119 | Mobile Phones and Laptops for eGov Jamaica Limited |  | $ 3,290.00 | Goods | Procurement 100% funded by Agency | Contract under execution | 2 | 10 Nov 2021 | 21 Dec 2021 | Smart Mobile Solutions (P) | JAMAICA
JA-L1072-P26119 | Mobile Phones and Laptops for eGov Jamaica Limited |  | $ 3,290.00 | Goods | Procurement 100% funded by Agency | Contract under execution | 2 | 10 Nov 2021 | 21 Dec 2021 | Innovative Superstore (P) | JAMAICA
JA-L1072-P26119 | Mobile Phones and Laptops for eGov Jamaica Limited |  | $ 3,290.00 | Goods | Procurement 100% funded by Agency | Contract under execution | 2 | 10 Nov 2021 | 21 Dec 2021 | Smart Mobile Solutions (A) | JAMAICA | Pending Signature | 10 Dec 2021 | 09 Mar 2022 | 1,038.36
JA-L1072-P28242 | Power Distribution Units for the Card Production Server Room |  | $ 775.00 | Goods | Procurement 100% funded by Agency | Expected |  | 11 Nov 2021 | 08 Dec 2021
JA-L1072-P30265 | Modification of Spaces - Jamaica Post Banking Hall - CSO |  | $ 64,516.13 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 31 Jan 2022 | 10 Feb 2022 | Skymar Building Construction and Maintenance Limited (A) | JAMAICA | Execution | 09 Mar 2022 | 30 Mar 2022 | 60,899.99
JA-L1072-P30265 | Modification of Spaces - Jamaica Post Banking Hall - CSO |  | $ 64,516.13 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 31 Jan 2022 | 10 Feb 2022 | Cambridge Trading Limited (P) | JAMAICA
JA-L1072-P30265 | Modification of Spaces - Jamaica Post Banking Hall - CSO |  | $ 64,516.13 | Works | Shopping/Request for minimun 3 Quotations | Contract under execution |  | 31 Jan 2022 | 10 Feb 2022 | J & L Equipment and Construction Services Limited (R) | JAMAICA
JA-L1072-P30343 | Stationery - Legal Consultation |  | $ 1,935.48 | Goods | Procurement 100% funded by Agency | Expected |  | 02 May 2022 | 30 May 2022
JA-L1072-P30344 | Venue Rental - Legal Consultation |  | $ 3,870.97 | Non-Consulting Services | Procurement 100% funded by Agency | Expected |  | 02 May 2022 | 30 May 2022
JA-L1072-P30345 | TV Placements 2022 |  | $ 45,000.00 | Non-Consulting Services | Direct Contracting/Selection | Expected |  | 14 Jul 2022 | 26 Aug 2022
JA-L1072-P30346 | Radio Placements 2022 |  | $ 35,000.00 | Non-Consulting Services | Direct Contracting/Selection | Expected |  | 14 Jul 2022 | 26 Aug 2022
JA-L1072-P30347 | Outdoor Advertising |  | $ 30,000.00 | Non-Consulting Services | Direct Contracting/Selection | Expected |  | 14 Jul 2022 | 26 Aug 2022
JA-L1072-P30348 | Print Placement 2022 |  | $ 35,000.00 | Non-Consulting Services | Direct Contracting/Selection | Expected |  | 14 Jul 2022 | 26 Aug 2022
JA-L1072-P30349 | Promotional Material |  | $ 30,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Expected |  | 15 Sep 2022 | 22 Sep 2022
JA-L1072-P30350 | Branding of NIRA (Lots 2-4) |  | $ 24,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 07 Jul 2022 | 31 Aug 2022
JA-L1072-P30351 | Firewall Hardware |  | $ 315,000.00 | Goods | International Competitive Bidding | Expected |  | 07 Mar 2022 | 18 Oct 2022
JA-L1072-P30352 | Enrolment Site Supervisor -Lot 3 | 6 vacancies | $ 150,967.74 | Individual Consultants | Individual Consultant Selection (3CV) | Expected | 6 | 30 Aug 2022 | 13 Sep 2022
JA-L1072-P30353 | Enrolment Officers - Lot 3 | 18 vacancies | $ 336,774.19 | Individual Consultants | Individual Consultant Selection (3CV) | Expected |  | 16 Aug 2022 | 02 Sep 2022
JA-L1072-P37429 | Chief Digital Strategist, Tax Administration |  | $ 100,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected |  | 22 Mar 2022 | 19 Apr 2022
JA-L1072-P37430 | Printer - Renovation of Spaces Manager |  | $ 1,000.00 | Goods | Procurement 100% funded by Agency | Expected |  | 03 Feb 2022 | 11 Mar 2022
JA-L1072-P37431 | Administrative Assistant - Renovation of Spaces Manager |  | $ 39,709.68 | Individual Consultants | Individual Consultant Selection (3CV) | Expected |  | 14 Apr 2022 | 12 May 2022
JA-L1072-P37432 | Standard Operating Procedures Consultant |  | $ 100,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected |  | 22 Mar 2022 | 19 Apr 2022
JA-L1072-P39575 | Modification of Spaces Manager - replacement hire |  | $ 38,709.68 | Individual Consultants | Individual Consultant Selection (3CV) | Expected |  | 02 May 2022 | 27 May 2022
JA-L1072-P40914 | Development of Website for NIRA | JIS is mandated to disseminate information on behalf of the Government of Jamaica. Additionally, the assignment is very small and the firm has experience of exceptional worth for the assignment. | $ 5,200.00 | Consulting Firms | Single-Source Selection of Firms (SSS) | Expected |  | 07 Mar 2022 | 02 Jun 2022
JA-L1072-P40915 | Enrolment Site Manager |  | $ 48,387.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected |  | 24 Jun 2022 | 09 Aug 2022
JA-L1072-P45600 | Project Management Support - Fibre Link Connections Installation |  | $ 3,850.00 | Non-Consulting Services | Direct Contracting/Selection | Expected |  | 11 Mar 2022 | 18 May 2022
JA-L1072-P45666 | Computer Monitor for Procurement Officer |  | $ 200.00 | Goods | Procurement 100% funded by Agency | Expected |  | 29 Mar 2022 | 18 Apr 2022
JA-L1072-P45667 | Office Furniture - Modification of Spaces Staff |  | $ 5,217.00 | Goods | Procurement 100% funded by Agency | Expected |  | 11 Apr 2022 | 06 Jun 2022
JA-L1072-P45668 | Modification of Office Spaces - PEU Staff |  | $ 19,736.00 | Works | Procurement 100% funded by Agency | Expected |  | 11 Apr 2022 | 20 Jun 2022
JA-L1072-P47944 | Pest Control Services |  | $ 2,260.00 | Non-Consulting Services | Procurement 100% funded by Agency | Expected |  | 29 Mar 2022 | 29 Apr 2022