## Sheet1
Procurement Plan | [9 empty] | Reference Bidder Name
Approval Number | 5049/OC-TT | [8 empty] | Name + (A) Award
Operation Number | TT-L1057 | [8 empty] | Name + (P) Participant
Country | TRINIDAD AND TOBAGO | [8 empty] | Name + (R) Rejected
Coverage Plan | 14 Apr 2022 - 14 Oct 2023
Executing Agency | MINISTRY OF HOUSING AND URBAN DEVELOPMENT
Goods and Services Total | $ 985,478.00
Works Total | $ 0.00
Consulting Services Total | $ 243,528.95
Version | 2022-19
Proc Id | Procurement Process name | Description | Estimated Amount (USD) | Procurement Type | Procurement Method | Process Status | Lots | Process Start Estimated Date | Signed Contract Estimated date | Bidder/Proponent Name | Nationality | Contract Status | Start Date Contract | End Date Contract | Contract Amount USD
TT-L1057-P2308 | Procurement of ArcGIS Software for Housing Development Corporation of T&T |  | $ 110,000.00 | Goods | Direct Contracting/Selection | Expected |  | 08 Feb 2021 | 15 Mar 2021
TT-L1057-P2309 | Procurement of Yardi Software for Housing Development Corporation of T&T | At the time of preparation for the loan in 2019, provision was made for the update of the Yardi operation system. It should be noted that this system is now outdated and therefore no longer supported. YARDI Voyager 7s is the updated software and License to the former version and provides the full suite of functions required by the Housing Development Corporation of Trinidad and Tobago. Consequently, the escalation in cost has to do with the fact that an updated version and new license are required. | $ 544,378.00 | Goods | Direct Contracting/Selection | Contract under execution |  | 05 Jul 2021 | 09 Aug 2021 | Yardi Systems (A) | CANADA | Execution | 12 Aug 2021 | 11 Aug 2022 | 544,378.00
TT-L1057-P2310 | Completion of National Squatter Survey |  | $ 150,000.00 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Expected |  | 01 Apr 2021 | 02 Jun 2021
TT-L1057-P2311 | Study on appropriate development standards for hillside development, MHUD/MPD Urban Revitalization Policy Development of Standards for Urban Areas |  | $ 50,000.00 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Expected |  | 01 Dec 2020 | 01 Feb 2021
TT-L1057-P2312 | Infrastructure Investment Plan for Tobago |  | $ 250,000.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Expected |  | 14 Apr 2021 | 02 Jun 2021
TT-L1057-P2313 | Wastewater Management Plan and Drainage Plan for Diego Martin area |  | $ 300,000.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Expected |  | 16 Jun 2021 | 25 Aug 2021
TT-L1057-P2314 | National Housing Market Study, MHUD |  | $ 250,000.00 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Expected |  | 14 Apr 2021 | 02 Jun 2021
TT-L1057-P2315 | Information Systems (Real State Management and Housing Market) updates |  | $ 130,000.00 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Expected |  | 28 May 2021 | 21 Jul 2021
TT-L1057-P2316 | Impact evaluation of squatter regularization |  | $ 100,000.00 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Expected |  | 28 May 2021 | 02 Jul 2021
TT-L1057-P2317 | Cleaning and analysis of the database and digitization of records of the Housing Development Corporation of T&T |  | $ 75,000.00 | Individual Consultants | Individual Consultant Selection (3CV) | Expected |  | 25 Oct 2021 | 25 Nov 2021
TT-L1057-P2318 | Certification training - Business and Conversational Spanish |  | $ 75,000.00 | Non-Consulting Services | National Competive Bidding | Expected |  | 01 Apr 2021 | 01 Jun 2021
TT-L1057-P2319 | Real State Management and analysis |  | $ 75,000.00 | Non-Consulting Services | National Competive Bidding | Expected |  | 01 Apr 2021 | 01 Jun 2021
TT-L1057-P2329 | Customer Service Representative | Client Relations Assistant 1 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 04 Jan 2021 | 15 Feb 2021 | Ateasha Castillo (A) | TRINIDAD AND TOBAGO | Finished | 18 Nov 2020 | 17 Nov 2021 | 12,402.92
TT-L1057-P2329 | Customer Service Representative | Client Relations Assistant 1 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 04 Jan 2021 | 15 Feb 2021 | Ateasha Castillo (A) | TRINIDAD AND TOBAGO | Execution | 18 Nov 2021 | 17 Nov 2022 | 12,398.25
TT-L1057-P2329 | Customer Service Representative | Client Relations Assistant 1 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 04 Jan 2021 | 15 Feb 2021 | Ateasha Castillo (A) | TRINIDAD AND TOBAGO
TT-L1057-P2329 | Customer Service Representative | Client Relations Assistant 1 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 04 Jan 2021 | 15 Feb 2021 | Maria Hosten (P) | TRINIDAD AND TOBAGO
TT-L1057-P2329 | Customer Service Representative | Client Relations Assistant 1 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 04 Jan 2021 | 15 Feb 2021 | Anishka Howell (P) | TRINIDAD AND TOBAGO
TT-L1057-P2330 | Procurement of equipment- I.T.; Office Furniture; Conference Equipment |  | $ 93,000.00 | Goods | Shopping/Request for Quotations by Open Invitation | Expected |  | 30 Nov 2020 | 15 Jan 2021
TT-L1057-P2419 | Customer Service Representative | Client Relations Assistant 2 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished |  | 30 Oct 2020 | 12 Nov 2020 | Simaya Crosby (A) | TRINIDAD AND TOBAGO | Finished | 18 Nov 2020 | 17 Nov 2021 | 12,402.92
TT-L1057-P2419 | Customer Service Representative | Client Relations Assistant 2 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished |  | 30 Oct 2020 | 12 Nov 2020 | Keston Roberts (P) | TRINIDAD AND TOBAGO
TT-L1057-P2419 | Customer Service Representative | Client Relations Assistant 2 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract finished |  | 30 Oct 2020 | 12 Nov 2020 | Olufemi Bansell (P) | TRINIDAD AND TOBAGO
TT-L1057-P2420 | Customer Service Representative | Client Relations Assistant 3 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 30 Oct 2020 | 12 Nov 2020 | Nadine Wheeler (A) | TRINIDAD AND TOBAGO | Finished | 18 Nov 2020 | 17 Nov 2021 | 12,402.92
TT-L1057-P2420 | Customer Service Representative | Client Relations Assistant 3 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 30 Oct 2020 | 12 Nov 2020 | Nadine Wheeler (A) | TRINIDAD AND TOBAGO | Execution | 18 Nov 2021 | 17 Nov 2022 | 12,398.25
TT-L1057-P2420 | Customer Service Representative | Client Relations Assistant 3 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 30 Oct 2020 | 12 Nov 2020 | Nadine Wheeler (A) | TRINIDAD AND TOBAGO
TT-L1057-P2420 | Customer Service Representative | Client Relations Assistant 3 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 30 Oct 2020 | 12 Nov 2020 | Nicolette Richards (P) | TRINIDAD AND TOBAGO
TT-L1057-P2420 | Customer Service Representative | Client Relations Assistant 3 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 30 Oct 2020 | 12 Nov 2020 | Kadisha Murray (P) | TRINIDAD AND TOBAGO
TT-L1057-P2420 | Customer Service Representative | Client Relations Assistant 3 | $ 48,529.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 30 Oct 2020 | 12 Nov 2020 | Danielle Charles (R) | TRINIDAD AND TOBAGO
TT-L1057-P2437 | SAGE 500 Software | Sage 50 Software | $ 1,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 30 Oct 2020 | 06 Nov 2020 | Personalized Quality System Limited (A) | TRINIDAD AND TOBAGO | Finished | 12 Nov 2020 | 11 Dec 2020 | 1,261.75
TT-L1057-P2437 | SAGE 500 Software | Sage 50 Software | $ 1,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 30 Oct 2020 | 06 Nov 2020 | Professional Computing Limitedprofess (P) | TRINIDAD AND TOBAGO
TT-L1057-P2437 | SAGE 500 Software | Sage 50 Software | $ 1,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 30 Oct 2020 | 06 Nov 2020 | Support 911 Limitedsupport (P) | TRINIDAD AND TOBAGO
TT-L1057-P2438 | Procurement of IT equipment -Laptops and Ipads | Procurement of IT equipment | $ 16,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 04 Nov 2020 | 18 Dec 2020 | Diamond System and Supplies Limited (R) | TRINIDAD AND TOBAGO
TT-L1057-P2438 | Procurement of IT equipment -Laptops and Ipads | Procurement of IT equipment | $ 16,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 04 Nov 2020 | 18 Dec 2020 | Memory Bank Computers Ltd (A) | TRINIDAD AND TOBAGO | Finished | 27 Jan 2021 | 03 Mar 2021 | 10,969.79
TT-L1057-P2438 | Procurement of IT equipment -Laptops and Ipads | Procurement of IT equipment | $ 16,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 04 Nov 2020 | 18 Dec 2020 | The Wizz Computers Ltd (P) | TRINIDAD AND TOBAGO
TT-L1057-P3428 | Procurement of Office Furniture- Chairs, Tables, Credenza |  | $ 14,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished | 4 | 25 Jan 2021 | 25 Feb 2021 | Amaranth Business Solutions Limited (A) | TRINIDAD AND TOBAGO | Finished | 29 Mar 2021 | 31 May 2021 | 11,258.73
TT-L1057-P3428 | Procurement of Office Furniture- Chairs, Tables, Credenza |  | $ 14,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished | 4 | 25 Jan 2021 | 25 Feb 2021 | Cubicle Limited (R) | TRINIDAD AND TOBAGO
TT-L1057-P3428 | Procurement of Office Furniture- Chairs, Tables, Credenza |  | $ 14,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished | 4 | 25 Jan 2021 | 25 Feb 2021 | Galt and Littlepage Limited (R) | TRINIDAD AND TOBAGO
TT-L1057-P3428 | Procurement of Office Furniture- Chairs, Tables, Credenza |  | $ 14,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished | 4 | 25 Jan 2021 | 25 Feb 2021 | Total Office (P) | TRINIDAD AND TOBAGO
TT-L1057-P3429 | Procurement of PPE Equipment |  | $ 2,700.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 25 Jan 2021 | 08 Feb 2021 | National Shoe and Occupational Solutions (R) | TRINIDAD AND TOBAGO
TT-L1057-P3429 | Procurement of PPE Equipment |  | $ 2,700.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 25 Jan 2021 | 08 Feb 2021 | Safety Plus Limited (R) | TRINIDAD AND TOBAGO
TT-L1057-P3429 | Procurement of PPE Equipment |  | $ 2,700.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 25 Jan 2021 | 08 Feb 2021 | A. Moses and Sons Limited (A) | TRINIDAD AND TOBAGO | Finished | 18 Feb 2021 | 19 Apr 2021 | 2,979.70
TT-L1057-P3430 | Procurement of Safety Equipment for Covid-19 Protocols- Sneeze Guards and Sanitizing Station |  | $ 2,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 25 Jan 2021 | 08 Feb 2021 | Amaranth Business Solutions Limited (R) | TRINIDAD AND TOBAGO
TT-L1057-P3430 | Procurement of Safety Equipment for Covid-19 Protocols- Sneeze Guards and Sanitizing Station |  | $ 2,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 25 Jan 2021 | 08 Feb 2021 | PSI Services Limited (A) | TRINIDAD AND TOBAGO | Finished | 18 Feb 2021 | 19 Apr 2021 | 4,475.10
TT-L1057-P3430 | Procurement of Safety Equipment for Covid-19 Protocols- Sneeze Guards and Sanitizing Station |  | $ 2,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 25 Jan 2021 | 08 Feb 2021 | N. Gopie Marketing Limited (P) | TRINIDAD AND TOBAGO
TT-L1057-P3552 | Procurement of Decor for Office-Carpets and Blinds |  | $ 5,600.00 | Goods | Shopping/Request for minimun 3 Quotations | Expected |  | 22 Feb 2021 | 01 Mar 2021
TT-L1057-P3553 | Procurement of Office Electronic Equipment-Printers, Photocopiers/Scanners |  | $ 21,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 22 Feb 2021 | 08 Mar 2021 | Busy Business Systems and Equipment (Rental) Ltd (A) | TRINIDAD AND TOBAGO | Finished | 12 Aug 2021 | 10 Sep 2021 | 11,379.23
TT-L1057-P3553 | Procurement of Office Electronic Equipment-Printers, Photocopiers/Scanners |  | $ 21,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 22 Feb 2021 | 08 Mar 2021 | PBS Technologies Trinidad Limited (P) | TRINIDAD AND TOBAGO
TT-L1057-P3553 | Procurement of Office Electronic Equipment-Printers, Photocopiers/Scanners |  | $ 21,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 22 Feb 2021 | 08 Mar 2021 | Amaranth Business Solutions Limited (P) | TRINIDAD AND TOBAGO
TT-L1057-P3554 | Procurement of Office Communication Equipment-Bluetooth, Digital Cams |  | $ 1,200.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 15 Feb 2021 | 01 Mar 2021 | The Wizz Computers Ltd (A) | TRINIDAD AND TOBAGO | Finished | 03 Aug 2021 | 07 Sep 2021 | 1,767.40
TT-L1057-P3554 | Procurement of Office Communication Equipment-Bluetooth, Digital Cams |  | $ 1,200.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 15 Feb 2021 | 01 Mar 2021 | iPRO Caribbean Ltd (P) | TRINIDAD AND TOBAGO
TT-L1057-P3554 | Procurement of Office Communication Equipment-Bluetooth, Digital Cams |  | $ 1,200.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 15 Feb 2021 | 01 Mar 2021 | Circuit Zone Ltd (R) | TRINIDAD AND TOBAGO
TT-L1057-P3753 | Procurement of Multi Media-Projector |  | $ 1,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 08 Feb 2021 | 22 Feb 2021 | Memory Bank Computers Ltd (P) | TRINIDAD AND TOBAGO
TT-L1057-P3753 | Procurement of Multi Media-Projector |  | $ 1,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 08 Feb 2021 | 22 Feb 2021 | Busy Business Systems and Equipment (Rental) Ltd (A) | TRINIDAD AND TOBAGO | Finished | 18 Feb 2021 | 19 Apr 2021 | 1,691.32
TT-L1057-P3753 | Procurement of Multi Media-Projector |  | $ 1,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 08 Feb 2021 | 22 Feb 2021 | Massy Technologies Infocom (Trinidad) Ltd (P) | TRINIDAD AND TOBAGO
TT-L1057-P3754 | Procurement of Communication Equipment -Cellular Telephones | Procurement of Cellular Phones | $ 2,800.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 22 Feb 2021 | 01 Mar 2021 | Five 9'S Solutions Limited (A) | TRINIDAD AND TOBAGO | Finished | 17 May 2021 | 30 Jun 2021 | 5,270.70
TT-L1057-P3754 | Procurement of Communication Equipment -Cellular Telephones | Procurement of Cellular Phones | $ 2,800.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 22 Feb 2021 | 01 Mar 2021 | Southern Supplies Limited (P) | TRINIDAD AND TOBAGO
TT-L1057-P3754 | Procurement of Communication Equipment -Cellular Telephones | Procurement of Cellular Phones | $ 2,800.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 22 Feb 2021 | 01 Mar 2021 | SNG Tech (P) | TRINIDAD AND TOBAGO
TT-L1057-P3755 | Procurement of Security Equipment- Security Cameras |  | $ 500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 15 Feb 2021 | 22 Feb 2021 | The Wizz Computers Ltd (A) | TRINIDAD AND TOBAGO | Finished | 17 May 2021 | 19 Jul 2021 | 620.17
TT-L1057-P3755 | Procurement of Security Equipment- Security Cameras |  | $ 500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 15 Feb 2021 | 22 Feb 2021 | iPRO Caribbean Ltd (P) | TRINIDAD AND TOBAGO
TT-L1057-P4012 | Procurement of two executive chairs |  | $ 2,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 08 Mar 2021 | 15 Mar 2021 | Amaranth Business Solutions Limited (P) | TRINIDAD AND TOBAGO
TT-L1057-P4012 | Procurement of two executive chairs |  | $ 2,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 08 Mar 2021 | 15 Mar 2021 | Total Office (P) | TRINIDAD AND TOBAGO
TT-L1057-P4012 | Procurement of two executive chairs |  | $ 2,500.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 08 Mar 2021 | 15 Mar 2021 | Galt and Littlepage Limited (A) | TRINIDAD AND TOBAGO | Finished | 12 May 2021 | 12 Jun 2021 | 945.20
TT-L1057-P20116 | Procurement of additional protective shields |  | $ 2,300.00 | Goods | Direct Contracting/Selection | Contract finished | 1 | 27 Sep 2021 | 11 Oct 2021 | PSI Services Limited (A) | TRINIDAD AND TOBAGO | Finished | 12 Oct 2021 | 24 Dec 2021 | 2,214.18
TT-L1057-P26509 | Procurement of Uninterrupted Power Supplies (UPS) |  | $ 4,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 03 Nov 2021 | 12 Nov 2021 | Busy Business Systems and Equipment (Rental) Ltd (A) | TRINIDAD AND TOBAGO | Finished | 18 Nov 2021 | 17 Jan 2022 | 1,533.83
TT-L1057-P26509 | Procurement of Uninterrupted Power Supplies (UPS) |  | $ 4,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 03 Nov 2021 | 12 Nov 2021 | Super Technologies Limited (R) | TRINIDAD AND TOBAGO
TT-L1057-P26509 | Procurement of Uninterrupted Power Supplies (UPS) |  | $ 4,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 03 Nov 2021 | 12 Nov 2021 | Informatics Engineering (R) | TRINIDAD AND TOBAGO
TT-L1057-P26509 | Procurement of Uninterrupted Power Supplies (UPS) |  | $ 4,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Contract finished |  | 03 Nov 2021 | 12 Nov 2021 | Circuit Zone Ltd (P) | TRINIDAD AND TOBAGO
TT-L1057-P26517 | Customer Service Representative | Replacement of Previously Hired Customer Service Representative | $ 10,589.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 08 Oct 2021 | 01 Nov 2021 | Antonio Beckles (A) | TRINIDAD AND TOBAGO | Execution | 08 Nov 2021 | 07 Nov 2022 | 10,607.50
TT-L1057-P26517 | Customer Service Representative | Replacement of Previously Hired Customer Service Representative | $ 10,589.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 08 Oct 2021 | 01 Nov 2021 | Akeem Wilson (P) | TRINIDAD AND TOBAGO
TT-L1057-P26517 | Customer Service Representative | Replacement of Previously Hired Customer Service Representative | $ 10,589.00 | Individual Consultants | Individual Consultant Selection (3CV) | Contract under execution |  | 08 Oct 2021 | 01 Nov 2021 | Nahassce Noel (P) | TRINIDAD AND TOBAGO
TT-L1057-P42731 | Procurement of Conference Equipment | Conference Equipment for Meeting Room | $ 10,000.00 | Goods | Shopping/Request for minimun 3 Quotations | Expected |  | 07 Mar 2022 | 31 Mar 2022
TT-L1057-P50821 | Customer Service Representative -Shadiyah Williams | Comparison of the qualifications of three (3) Individuals | $ 12,352.95 | Individual Consultants | Individual Consultant Selection (3CV) | Expected |  | 29 Mar 2022 | 22 Apr 2022