## Sheet1
Procurement Plan
Approval Number | 5049/OC-TT
Operation Number | TT-L1057
Country | TRINIDAD AND TOBAGO
Coverage Plan | 04 Feb 2021 - 04 Aug 2022
Executing Agency | MINISTRY OF HOUSING AND URBAN DEVELOPMENT
Goods and Services Total | $ 474,800.00
Works Total | $ 0.00
Consulting Services Total | $ 220,587.00
Version | 2021-9
Procurement Name | Procurement Type | Procurement Method | Process ID | Total Estimated Cost | % IDBCost | % Counterpart | % Cofinancier | Component | Supervision Method | Specific Procurement Notice | Bidding Opening Documents | Evaluation Report | Contract Signed | Status | Description | Comments
Procurement of ArcGIS Software for Housing Development Corporation of T&T | Goods | Direct Contracting/Selection | TT-L1057-P2308 | $ 110,000.00 | 100.00 % | 0.00 % | 0.00 % | Component 4: Strengthening of Housing and Urban Development Sector Stakeholders | Ex-ante |  |  |  |  | Expected
Procurement of Yardi Software | Goods | Direct Contracting/Selection | TT-L1057-P2309 | $ 50,000.00 | 100.00 % | 0.00 % | 0.00 % | Component 4: Strengthening of Housing and Urban Development Sector Stakeholders | Ex-ante |  |  |  |  | Expected
Completion of National Squatter Survey | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | TT-L1057-P2310 | $ 150,000.00 | 100.00 % | 0.00 % | 0.00 % | Component 4: Strengthening of Housing and Urban Development Sector Stakeholders | Ex-ante |  |  |  |  | Expected
Study on appropriate development standards for hillside development, MHUD/MPD Urban Revitalization Policy Development of Standards for Urban Areas | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | TT-L1057-P2311 | $ 50,000.00 | 100.00 % | 0.00 % | 0.00 % | Component 4: Strengthening of Housing and Urban Development Sector Stakeholders | Ex-ante |  |  |  |  | Expected
Infrastructure Investment Plan for Tobago | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | TT-L1057-P2312 | $ 250,000.00 | 100.00 % | 0.00 % | 0.00 % | Component 4: Strengthening of Housing and Urban Development Sector Stakeholders | Ex-ante |  |  |  |  | Expected
Wastewater Management Plan and Drainage Plan for Diego Martin area | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | TT-L1057-P2313 | $ 300,000.00 | 100.00 % | 0.00 % | 0.00 % | Component 4: Strengthening of Housing and Urban Development Sector Stakeholders | Ex-ante |  |  |  |  | Expected
National Housing Market Study, MHUD | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | TT-L1057-P2314 | $ 250,000.00 | 100.00 % | 0.00 % | 0.00 % | Component 4: Strengthening of Housing and Urban Development Sector Stakeholders | Ex-ante |  |  |  |  | Expected
Information Systems (Real State Management and Housing Market) updates | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | TT-L1057-P2315 | $ 130,000.00 | 100.00 % | 0.00 % | 0.00 % | Component 4: Strengthening of Housing and Urban Development Sector Stakeholders | Ex-ante |  |  |  |  | Expected
Impact evaluation of squatter regularization | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | TT-L1057-P2316 | $ 100,000.00 | 100.00 % | 0.00 % | 0.00 % | Component 4: Strengthening of Housing and Urban Development Sector Stakeholders | Ex-ante |  |  |  |  | Expected
Cleaning and analysis of Housing Development Corporation of T&T database | Individual Consultants | Individual Consultant Selection (3CV) | TT-L1057-P2317 | $ 75,000.00 | 100.00 % | 0.00 % | 0.00 % | Component 4: Strengthening of Housing and Urban Development Sector Stakeholders | Ex-ante |  |  |  |  | Expected
Certification training - Business and Conversational Spanish | Non-Consulting Services | National Competive Bidding | TT-L1057-P2318 | $ 75,000.00 | 100.00 % | 0.00 % | 0.00 % | Component 4: Strengthening of Housing and Urban Development Sector Stakeholders | Ex-ante |  |  |  |  | Expected
Real State Management and analysis | Non-Consulting Services | National Competive Bidding | TT-L1057-P2319 | $ 75,000.00 | 100.00 % | 0.00 % | 0.00 % | Component 4: Strengthening of Housing and Urban Development Sector Stakeholders | Ex-ante |  |  |  |  | Expected
Customer Service Representative | Individual Consultants | Individual Consultant Selection (3CV) | TT-L1057-P2329 | $ 48,529.00 | 100.00 % | 0.00 % | 0.00 % | OtherCost Component | Ex-ante |  |  | 11 Jan 2021 | 18 Jan 2021 | Contract under execution | Client Relations Assistant 1
Procurement of equipment- I.T.; Office Furniture; Conference Equipment | Goods | Shopping/Request for Quotations by Open Invitation | TT-L1057-P2330 | $ 93,000.00 | 100.00 % | 0.00 % | 0.00 % | OtherCost Component | Ex-ante |  |  |  |  | Expected
Customer Service Representative | Individual Consultants | Individual Consultant Selection (3CV) | TT-L1057-P2419 | $ 48,529.00 | 100.00 % | 0.00 % | 0.00 % | OtherCost Component | Ex-ante |  |  | 06 Nov 2020 | 11 Nov 2020 | Contract under execution | Client Relations Assistant 2
Customer Service Representative | Individual Consultants | Individual Consultant Selection (3CV) | TT-L1057-P2420 | $ 48,529.00 | 100.00 % | 0.00 % | 0.00 % | OtherCost Component | Ex-ante |  |  | 06 Nov 2020 | 11 Nov 2020 | Contract under execution | Client Relations Assistant 3
SAGE 500 Software | Goods | Shopping/Request for minimum 3 Quotations | TT-L1057-P2437 | $ 1,000.00 | 100.00 % | 0.00 % | 0.00 % | OtherCost Component | Ex-ante |  |  |  | 05 Nov 2020 | Contract finished | Sage 50 Software
Procurement of IT equipment -Laptops and Ipads | Goods | Shopping/Request for minimum 3 Quotations | TT-L1057-P2438 | $ 16,000.00 | 100.00 % | 0.00 % | 0.00 % | OtherCost Component | Ex-ante |  |  |  | 17 Dec 2020 | Contract under execution | Procurement of IT equipment
Procurement of Office Furniture- Chairs, Tables, Credenza | Goods | Shopping/Request for minimum 3 Quotations | TT-L1057-P3428 | $ 17,000.00 | 100.00 % | 0.00 % | 0.00 % | OtherCost Component | Ex-ante |  |  |  | 25 Feb 2021 | Expected
Procurement of PPE Equipment | Goods | Shopping/Request for minimum 3 Quotations | TT-L1057-P3429 | $ 2,700.00 | 100.00 % | 0.00 % | 0.00 % | OtherCost Component | Ex-ante |  |  |  | 08 Feb 2021 | Expected
Procurement of Safety Equipment for Covid-19 Protocols- Sneeze Guards and Sanitizing Station | Goods | Shopping/Request for minimum 3 Quotations | TT-L1057-P3430 | $ 2,500.00 | 100.00 % | 0.00 % | 0.00 % | OtherCost Component | Ex-ante |  |  |  | 08 Feb 2021 | Expected
Procurement of Decor for Office-Carpets and Blinds | Goods | Shopping/Request for minimum 3 Quotations | TT-L1057-P3552 | $ 5,600.00 | 100.00 % | 0.00 % | 0.00 % | OtherCost Component | Ex-ante |  |  |  | 01 Mar 2021 | Expected
Procurement of Office Electronic Equipment-Printers, Projectors, Photocopiers, Security Camera | Goods | Shopping/Request for minimum 3 Quotations | TT-L1057-P3553 | $ 23,000.00 | 100.00 % | 0.00 % | 0.00 % | OtherCost Component | Ex-ante |  |  |  | 08 Mar 2021 | Expected
Procurement of Office Communication Equipment-Bluetooth, Digital Cams, Cellular Telephone | Goods | Shopping/Request for minimum 3 Quotations | TT-L1057-P3554 | $ 4,000.00 | 100.00 % | 0.00 % | 0.00 % | OtherCost Component | Ex-ante |  |  |  | 01 Mar 2021 | Expected