## TCM Period 2018
|  | Operation Number: |  |  |  | PE-T1376
|  | TCM Cycle: |  |  |  | TCM Period 2018
|  | Last Update: |  |  |  | 2018-08-20 10:23
Results Matrix
Outcomes
Outcome: | 1 Tax reform proposal updated, which contributes to collection and the equity of the system
Indicators |  |  | Flags* |  | Unit of Measure |  |  | Baseline |  | Baseline Year |  | Means of verification |  |  | 2018 |  | 2019 |  | 2020 |  | EOP
1.1 Tax reform proposal disclosed and presented to the authorities of MEF and SUNAT |  |  |  |  | Number |  |  | 0 |  | 2018 |  | Report of MEF and SUNAT with the approval of the proposal |  | P | 0 |  | 1 |  | 0
[14 empty] | P(a) | 0 |  | 1 |  | 0
A
Outcome: | 2 Control of compliance with VAT is done in an integrated manner between internal taxes and customs in SUNAT
Indicators |  |  | Flags* |  | Unit of Measure |  |  | Baseline |  | Baseline Year |  | Means of verification |  |  | 2018 |  | 2019 |  | 2020 |  | EOP
2.1 Comprehensive VAT control strategy for internal taxes and customs, implemented |  |  |  |  | Number |  |  | 0 |  | 2018 |  | Report of the National Intendency of Process Management - SUNAT |  | P | 0 |  | 0 |  | 1
[14 empty] | P(a) | 0 |  | 0 |  | 1
A
Outcome: | 3 Proposed dimensioning of the staff in SUNAT is incorporated in its organizational strengthening plan
Indicators |  |  | Flags* |  | Unit of Measure |  |  | Baseline |  | Baseline Year |  | Means of verification |  |  | 2018 |  | 2019 |  | 2020 |  | EOP
3.1 Proposal for SUNAT staff sizing, is incorporated in its organizational strengthening plan |  |  |  |  | Number |  |  | 0 |  | 2018 |  | Report of the National Intendency of Human Resources - SUNAT |  | P | 0 |  | 0 |  | 1
[14 empty] | P(a) | 0 |  | 0 |  | 1
A
Outcome: | 4 SUNAT has integrated tax databases and information of quality
Indicators |  |  | Flags* |  | Unit of Measure |  |  | Baseline |  | Baseline Year |  | Means of verification |  |  | 2018 |  | 2019 |  | 2020 |  | EOP
4.1 SUNAT officials use the integrated databases for their fiscal intelligence and enforcement efforts |  |  |  |  | Number |  |  | 0 |  | 2018 |  | Report of the National Intendency of Strategies and Risks - SUNAT |  | P | 0 |  | 0 |  | 1
[14 empty] | P(a) | 0 |  | 0 |  | 1
A
Outputs: Annual Physical and Financial Progress
1 1. Tax policy reform design | [15 empty] | Physical Progress | [7 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2018 |  | 2019 |  | 2020 | EOP |  | 2018 | 2019 |  |  | 2020 |  |  | EOP |  |  | Theme | Fund | Flags
1.1 Policies designed |  |  |  | Study with a tax policy reform design proposal |  |  | Policies (#) |  | 0 |  | 2018 |  | Report of MEF and SUNAT with approval to the study |  |  | P |  | 0 |  | 1 |  | 0 | 1 | P | 0 | 75000 |  |  | 0 |  |  | 75000 |  |  | Institutional Development | INS
[16 empty] | P(a) |  | 0 |  | 1 |  | 0 | 1 | P(a) | 0 | 75000 |  |  | 0 |  |  | 75000
[16 empty] | A | [7 empty] | A
2 2. Strengthening organizational capacity for tax control | [15 empty] | Physical Progress | [7 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2018 |  | 2019 |  | 2020 | EOP |  | 2018 | 2019 |  |  | 2020 |  |  | EOP |  |  | Theme | Fund | Flags
2.1 Strategies designed |  |  |  | Study with the proposal for the integral control strategy of VAT, for internal taxes and customs |  |  | Strategies (#) |  | 0 |  | 2018 |  | Report of the National Intendency of Process Management - SUNAT |  |  | P |  | 0 |  | 1 |  | 0 | 1 | P | 0 | 45000 |  |  | 0 |  |  | 45000 |  |  | Institutional Development | INS
[16 empty] | P(a) |  | 0 |  | 1 |  | 0 | 1 | P(a) | 0 | 45000 |  |  | 0 |  |  | 45000
[16 empty] | A | [7 empty] | A
2.2 Institutional development plan designed |  |  |  | Study with the proposed sizing for the staff in SUNAT |  |  | Plans (#) |  | 0 |  | 2018 |  | Report of the National Intendency of Human Resources - SUNAT |  |  | P |  | 0 |  | 1 |  | 0 | 1 | P | 0 | 15000 |  |  | 0 |  |  | 15000 |  |  | Institutional Development | INS
[16 empty] | P(a) |  | 0 |  | 1 |  | 0 | 1 | P(a) | 0 | 15000 |  |  | 0 |  |  | 15000
[16 empty] | A | [7 empty] | A
3 3. Use of tax information for better digital control | [15 empty] | Physical Progress | [7 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2018 |  | 2019 |  | 2020 | EOP |  | 2018 | 2019 |  |  | 2020 |  |  | EOP |  |  | Theme | Fund | Flags
3.1 Institutional capacity analysis conducted |  |  |  | Document with the diagnosis of the quality and dispersion of the data that SUNAT has, including a proposal for its debugging and articulation |  |  | Assessments (#) |  | 0 |  | 2018 |  | Report of the National Intendency of Strategies and Risks - SUNAT |  |  | P |  | 0 |  | 1 |  | 0 | 1 | P | 0 | 25000 |  |  | 0 |  |  | 25000 |  |  | Institutional Development | INS
[16 empty] | P(a) |  | 0 |  | 1 |  | 0 | 1 | P(a) | 0 | 25000 |  |  | 0 |  |  | 25000
[16 empty] | A | [7 empty] | A
4 4. Dissemination of results | [15 empty] | Physical Progress | [7 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2018 |  | 2019 |  | 2020 | EOP |  | 2018 | 2019 |  |  | 2020 |  |  | EOP |  |  | Theme | Fund | Flags
4.1 Seminars organized |  |  |  | Seminars for the dissemination, discussion and validation of the products developed |  |  | Seminars (#) |  | 0 |  | 2018 |  | IDB Report on Seminars |  |  | P |  | 0 |  | 0 |  | 1 | 1 | P | 0 | 0 |  |  | 30000 |  |  | 30000 |  |  | Institutional Development | INS
[16 empty] | P(a) |  | 0 |  | 0 |  | 1 | 1 | P(a) | 0 | 0 |  |  | 30000 |  |  | 30000
[16 empty] | A | [7 empty] | A
Other Cost | [24 empty] | 2018 |  |  | 2019 |  |  | 2020 |  |  | Cost
[24 empty] | P | 0 |  |  | 5000 |  |  | 5000 |  |  | 10000
Monitoring and Evaluation Activities
[24 empty] | P(a) | 0 |  |  | 5000 |  |  | 5000 |  |  | 10000
A
Total Cost | [24 empty] | 2018 |  | 2019 |  |  | 2020 |  |  | Total Cost
[24 empty] | P |  |  | 165000 |  |  | 35000 |  |  | 200000
[24 empty] | P(a) |  |  | 165000 |  |  | 35000 |  |  | 200000
A