## Second period Jan-Dec 2014
|  | Operation Number: | HA-L1056 | [6 empty] | Inter-American Development Bank - IDB
|  | Year- PMR Cycle: | Second period Jan-Dec 2014 |  |  | Chief of Operations validation date: |  |  | 4/17/2015 | Office of Strategic Planning and Development Effectiveness
|  | Last Update: | 2015-04-14 11:28 |  |  | Division Chief validation date: |  |  | 4/28/2015 |  | Current Validated Classification ( validated as of 5/6/2015 ) | SATISFACTORY
|  | PMR Validation Stage: | Validated by Representative |  |  | Country Representative validation date: |  |  | 5/6/2015
Changes to the Matrix
Section | Name |  |  | Type of Change | Subtype |  | Modified by | Reasons |  |  |  |  | Entered in the System | Agreed with Executing Agency
Output | Surveyors trained with new equipment and software |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | cbidault | Output 2.12 was overestimated whereas output 2.5 was largely underestimated. Additional budget to cover output 2.5 was reallocated from output 2.8 and 2.12,without reducing the physical outputs. |  |  |  |  | 06-Apr-15
Output | GOH Land Agency staff, judges and private sector professionals trained in land tenure, property rights and land administration |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | cbidault | Output 2.5 was underestimated whereas output 2.8 and 2.12 were largely overestimated. Additional budget to cover output 2.5 was reallocated from output 2.8 and 2.12,without reducing the physical outputs. |  |  |  |  | 06-Apr-15
Output | Public and private sector surveyors trained in the use of the Geographic Positioning Network |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | cbidault | Output 2.12 was overestimated whereas output 2.5 was largely overestimated. Additional budget to cover output 2.5 was reallocated from output 2.8 and 2.12,without reducing the physical outputs. |  |  |  |  | 02-Apr-15
Output | Persons trained with a masters degree in land administration |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | cbidault | The first student started his master degree in September 2014. |  |  |  |  | 02-Apr-15
Output | GNSS (Global Navigation Satellite System) Continually Operating Receiving Stations upgraded and/or installed |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | cbidault | The contract was signed but the first payment was made during first quarter 2015 only, instead of late 2014. |  |  |  |  | 02-Apr-15
Output | Public and private sector surveyors trained in the use of the Geographic Positioning Network |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | cbidault | The budget regarding the training in Geographic Positioning Network was underestimated. |  |  |  |  | 26-Mar-15

## Second period Jan-Dec 2015
|  | Operation Number: | HA-L1056 | [6 empty] | Inter-American Development Bank - IDB
|  | Year- PMR Cycle: | Second period Jan-Dec 2015 |  |  | Chief of Operations validation date: |  |  | 3/30/2016 | Office of Strategic Planning and Development Effectiveness
|  | Last Update: | 2016-03-30 13:39 |  |  | Division Chief validation date: |  |  | 4/14/2016 |  | Current Validated Classification ( validated as of 4/14/2016 ) | PROBLEM
|  | PMR Validation Stage: | Validated by Representative |  |  | Country Representative validation date: |  |  | 4/14/2016
Changes to the Matrix
Section | Name |  |  | Type of Change | Subtype |  | Modified by | Reasons |  |  |  |  | Entered in the System | Agreed with Executing Agency
Output | Parcels surveyed, with tenure clarified and recorded into the database |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | anastasiat | Due to the overall underestimation of the total number of parcels for each commune, the number of communes for which the pre-cadaster will be done had to be revised, and so the cost for each commune, which had to be increased. |  |  |  |  | 09-Mar-16
Output | Analyses of the local land ownership situations |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | anastasiat | As the Parcel demarcation and land tenure clarification process was just being completed for one municipality, the studies for the local land ownerships situations should start once the same process is sufficiently advanced for the other municipalites. |  |  |  |  | 08-Mar-16
Output | Local land administrative offices refurbished (Office National du Cadastre/Direction Générale des Impôts - ONACA/DGI) |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | anastasiat | It was decided to postpone this activity to 2017 due to the lack of human resources available to monitor it (Executing Agency human resources largely mobilized for the implementation of the Parcel demarcation and land tenure clarification process). A mission of administration will take place in April with the Executing Agency to work on the end of project planning. |  |  |  |  | 08-Mar-16
Output | GOH Land Agency staff, judges and private sector professionals trained in land tenure, property rights and land administration |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | anastasiat | For 2015, the number of private sectors professionals (surveyors, technical staff for the surveys and legal analysis) to be trained at the local level was much more important thant expected, due to the underestimation in the number of parcels, but also to the deployment on a new commune while the first one has not been completed yet. However, as the training partly directly provided by the executing agency, the costs are planned to be less important. |  |  |  |  | 07-Mar-16 | 3/4/2016
Output | Surveyors trained with new equipment and software |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | anastasiat | Due to delays in hiring the firm for the execution of pre-cadaster in the north, the surveyors that will work in the North will have finished their training in 2017, and the payments will continue until this date. |  |  |  |  | 07-Mar-16 | 3/4/2016
Output | Study on credit mechanisms |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | anastasiat | It was decided to postpone this study to 2017 due to the lack of avalaible human resources to monitor it (human resources largely mobilized for the implementation of the Parcel demarcation and land tenure clarification process). A mission of administration will take place in April with the Executing Agency to work on the end of project planning. |  |  |  |  | 07-Mar-16 | 3/4/2016
Output | Notaries equiped with new equipment and software in the pilot areas |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | anastasiat | Due to delays in the execution of parcel demarcation and land tenure clarification in Camp Perrin, and the process being currently deployed in the other municipalites, notaries should be fully equipped in 2017. |  |  |  |  | 07-Mar-16 | 3/4/2016
Output | Study on judicial role in land tenure and administration finalized |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | anastasiat | It was decided to postpone this study to 2016 due to the lack of avalaible human resources to monitor it (human resources largely mobilized for the implementation of the Parcel demarcation and land tenure clarification process). A mission of administration will take place in April with the Executing Agency to work on the end of project planning. |  |  |  |  | 07-Mar-16 | 3/4/2016
Output | GNSS (Global Navigation Satellite System) Continually Operating Receiving Stations upgraded and/or installed |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | anastasiat | There were delays due to the negotisation on the technical offer of the firm to build proper fences for the equipment that will be installed. Construction works have now started and are expected to be completed in 2016. |  |  |  |  | 07-Mar-16 | 3/4/2016
Output | Parcels surveyed, with tenure clarified and recorded into the database |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | anastasiat | Due to the overall underestimation of the total number of parcels for each commune, the executing unit had to review the number of communes for which the cadaster will be done, but also the cost for each commune, which has increased. |  |  |  |  | 07-Mar-16 | 3/4/2016
Output | Persons trained with a masters degree in land administration |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | anastasiat | One of the third students has conmpleted his degree, before originally planned. The two other students will have completed their degree by 2017. |  |  |  |  | 07-Mar-16 | 3/4/2016
Output | GOH Land Agency staff, judges and private sector professionals trained in land tenure, property rights and land administration |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | anastasiat | Due to direct implementation of the Parcel demarcation and land tenure clarification process by the executing agency, and underestimation of the number of parcels, the poriginal planned number of private sectors professionals to be trained was too low. More staff needed to be trained. |  |  |  |  | 07-Mar-16 | 3/4/2016

## First period Jan-Jun 2016
|  | Operation Number: | HA-L1056 | [6 empty] | Inter-American Development Bank - IDB
|  | Year- PMR Cycle: | First period Jan-Jun 2016 |  |  | Chief of Operations validation date: |  |  | 10/17/2016 | Office of Strategic Planning and Development Effectiveness
|  | Last Update: | 2016-10-03 13:40 |  |  | Division Chief validation date: |  |  |  |  | Current Validated Classification ( validated as of 4/14/2016 ) | PROBLEM
|  | PMR Validation Stage: | Validated by Chief of Operations |  |  | Country Representative validation date:
Changes to the Matrix
Section | Name |  |  | Type of Change | Subtype |  | Modified by | Reasons |  |  |  |  | Entered in the System | Agreed with Executing Agency
Output | Parcels surveyed, with tenure clarified and recorded into the database |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | anastasiat | Initial financial planning was not good for the all project for years 2016 and 2017 so we had to adjust it for this output. |  |  |  |  | 03-Oct-16 | 9/30/2016
Output | Private parcels formalized (with notary act) |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | anastasiat | Provided that the 'Proces verbal d'Arpentage" is sufficient in rural areas in order to prove ownership of a plot and due to budgetary reasons, it was decided after the administration mission to decrease the number of notary acts that the project would finance in order to have full titles. |  |  |  |  | 30-Sep-16 | 6/20/2016
Output | Parcels surveyed, with tenure clarified and recorded into the database |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | anastasiat | The implementation of the PFB being an exercise highly depending on the local characteristics of the land, the overall estimation of the number of plots to be surveyed is constantly changing : the number has to be adjusted as the implementation progresses. This is due to the local characteristics of certains areas that can't be anticipated before the field work, but also to the particularity of juridcal analysis that may imply to merge plots. |  |  |  |  | 30-Sep-16 | 6/20/2016
Output | Local land administrative offices (ONACA/DGI) equipped |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | anastasiat | This activity was reviewed after the administration mission, as part of the new strategy to reallocate the remaining budget to the priority activities. |  |  |  |  | 26-Sep-16 | 6/20/2016
Output | Persons trained with a masters degree in land administration |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | anastasiat | The cost of the training in Land administrration being lower than budgeted, and the quality of the training being very good and giving high results on the ground, it was decided to finance the training for another member of the national Land institution. |  |  |  |  | 26-Sep-16 | 6/20/2016
Output | GOH Land Agency staff, judges and private sector professionals trained in land tenure, property rights and land administration |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | anastasiat | The majority of staff was trained during the first years of the project. As the implementaiton of the PFB progresses, most of this staff is being sent in other areas of the country to help with the implementation, which involves a reduction in the number of people that need to be trained. |  |  |  |  | 26-Sep-16 | 6/20/2016
Output | GNSS (Global Navigation Satellite System) Continually Operating Receiving Stations upgraded and/or installed |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | anastasiat | This activity was delayed mainly due to land issues ; it was necessary to have land tenure clarified on the plots where the satellite stations are supposed to be installed. In 2016, an effort was made to accelerate the process and all identified difficulties are in the process of being resolved. |  |  |  |  | 26-Sep-16 | 6/20/2016
Output | Study on credit mechanisms |  |  | Inactivate Output | Modify Output |  | anastasiat | The overall underestimation of the number of parcels to be surveyed had a huge impact on the financial and physical planning of the project. More precisely, the first output resulted in being more expensive than budgeted. In order to face this constraint, an administration mission was conducted in May 2016 in order to review the financial and physical planning of the project, for the last two years. As part of this administration mission, it was decided to cancel non-priority activities such as this study and rather include it in the second phase. |  |  |  |  | 12-Sep-16 | 6/20/2016
Output | Study on judicial role in land tenure and administration finalized |  |  | Inactivate Output | Modify Output |  | anastasiat | The overall underestimation of the number of parcels to be surveyed had a huge impact on the financial and physical planning of the project. More precisely, the first output resulted in being more expensive than budgeted. In order to face this constraint, an administration mission was conducted in May 2016 in order to review the financial and physical planning of the project, for the last two years. As part of this administration mission, it was decided to cancel non-priority activities such as this study and rather include it in the second phase. |  |  |  |  | 12-Sep-16 | 6/20/2016
Output | Local land administrative offices refurbished (Office National du Cadastre/Direction Générale des Impôts - ONACA/DGI) |  |  | Inactivate Output | Modify Output |  | anastasiat | The overall underestimation of the number of parcels to be surveyed had a huge impact on the financial and physical planning of the project. More precisely, the first output resulted in being more expensive than budgeted. In order to face this constraint, an administration mission was conducted in May 2016 in order to review the financial and physical planning of the project, for the last two years. As part of this administration mission, it was decided to cancel this activity provided that the 4 laws that have to be passed as part of the land reform will have an impact on the local organization of local land administrative offices, it is then better to wait for the reform to be passed to adapt rehabilitation needs to the new framework. |  |  |  |  | 12-Sep-16 | 6/20/2016
Output | Judges and clerks trained in the resolution of land tenure conflicts |  |  | Inactivate Output | Modify Output |  | anastasiat | The overall underestimation of the number of parcels to be surveyed had a huge impact on the financial and physical planning of the project. More precisely, the first output resulted in being more expensive than budgeted. In order to face this constraint, an administration mission was conducted in May 2016 in order to review the financial and physical planning of the project, for the last two years. As part of this administration mission, it was decided to cancel this activity provided that the 4 laws that have to be passed as part of the land reform will have an impact on the role of clerks ans judges in the resolution of land tenure conflicts. It is then better to wait for the reform to be passed to adapt training to the new framework needs. |  |  |  |  | 12-Sep-16 | 6/20/2016

## Second period Jan-Dec 2016
|  | Operation Number: | HA-L1056 | [6 empty] | Inter-American Development Bank - IDB
|  | Year- PMR Cycle: | Second period Jan-Dec 2016 |  |  | Chief of Operations validation date: |  |  | 4/19/2017 | Office of Strategic Planning and Development Effectiveness
|  | Last Update: | 2017-04-19 16:22 |  |  | Division Chief validation date: |  |  | 4/25/2017 |  | Current Validated Classification ( validated as of 4/27/2017 ) | SATISFACTORY
|  | PMR Validation Stage: | Validated by Representative |  |  | Country Representative validation date: |  |  | 4/27/2017
Changes to the Matrix
Section | Name |  |  | Type of Change | Subtype |  | Modified by | Reasons |  |  |  |  | Entered in the System | Agreed with Executing Agency
Outcome | Farmers benefitting from improved access to land tenure administration services in the pilot areas |  |  | Create Outcome Indicator |  |  | brunoj | New indicator created to contribute to CRF indicator aux 13. |  |  |  |  | 19-Apr-17
Output | Parcels surveyed, with tenure clarified and recorded into the database |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | brunoj | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. It has been decided not to deliver notary act for several technical and legal reasons, and rather focus on the delivery of survey minutes. |  |  |  |  | 04-Apr-17
Output | Analyses of the local land ownership situations |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | apaz | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. |  |  |  |  | 03-Apr-17
Output | Local land administrative offices (ONACA/DGI) equipped |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | apaz | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. |  |  |  |  | 03-Apr-17
Output | Notaries equiped with new equipment and software in the pilot areas |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | apaz | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. |  |  |  |  | 03-Apr-17
Output | Persons trained with a masters degree in land administration |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | apaz | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. 1 person remain to finish the Master. |  |  |  |  | 03-Apr-17
Output | GOH Land Agency staff, judges and private sector professionals trained in land tenure, property rights and land administration |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | apaz | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. |  |  |  |  | 03-Apr-17
Output | GNSS (Global Navigation Satellite System) Continually Operating Receiving Stations upgraded and/or installed |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | apaz | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. |  |  |  |  | 03-Apr-17
Output | Surveyors trained with new equipment and software |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | apaz | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. |  |  |  |  | 21-Mar-17
Output | Surveyors trained with new equipment and software |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | brunoj | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. |  |  |  |  | 17-Mar-17
Output | Analyses of the local land ownership situations |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | brunoj | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. This product has been suspended. |  |  |  |  | 17-Mar-17
Output | Local land administrative offices (ONACA/DGI) equipped |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | brunoj | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. One office will be rehabilitated in 2017. |  |  |  |  | 17-Mar-17
Output | Notaries equiped with new equipment and software in the pilot areas |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | brunoj | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. |  |  |  |  | 17-Mar-17
Output | Private parcels formalized (with notary act) |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | brunoj | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. It has been decided not to deliver notary act for several technical and legal reasons, and rather focus on the delivery of survey minutes. |  |  |  |  | 17-Mar-17
Output | Private parcels formalized (with notary act) |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | brunoj | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. It has been decided not to deliver notary act for several technical and legal reasons, and rather focus on the delivery of survey minutes. |  |  |  |  | 15-Mar-17
Output | Parcels surveyed, with tenure clarified and recorded into the database |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | brunoj | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. It has been decided not to deliver notary act for several technical and legal reasons, and rather focus on the delivery of survey minutes. |  |  |  |  | 15-Mar-17
Output | Persons trained with a masters degree in land administration |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | brunoj | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. 1 person remain to finish the Master. |  |  |  |  | 15-Mar-17
Output | GNSS (Global Navigation Satellite System) Continually Operating Receiving Stations upgraded and/or installed |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | brunoj | For project end, the physical and financial planning has been reviewed according to the results achieved to date. It has been decided to focus more on the land demarcation and clarification in order to finalize the pre-cadaster in the communes. 8 GNSS remain to be installed. this will be finalized by 2017. |  |  |  |  | 15-Mar-17

## Second period Jan-Dec 2017
|  | Operation Number: | HA-L1056 | [6 empty] | Inter-American Development Bank - IDB
|  | Year- PMR Cycle: | Second period Jan-Dec 2017 |  |  | Chief of Operations validation date: |  |  | 3/28/2018 | Office of Strategic Planning and Development Effectiveness
|  | Last Update: | 2018-03-28 14:49 |  |  | Division Chief validation date: |  |  | 4/18/2018 |  | Current Validated Classification ( validated as of 4/19/2018 ) | SATISFACTORY
|  | PMR Validation Stage: | Validated by Representative |  |  | Country Representative validation date: |  |  | 4/19/2018
Changes to the Matrix
Section | Name |  |  | Type of Change | Subtype |  | Modified by | Reasons |  |  |  |  | Entered in the System | Agreed with Executing Agency
Output | Parcels surveyed, with tenure clarified and recorded into the database |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | brunoj | The physical and financial planning was reviewed according to 2017 execution, |  |  |  |  | 28-Mar-18
Output | Analyses of the local land ownership situations |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | brunoj | The Executing unit decided to develop land tenure statistical data in order to improving the WB Doing Business scoring. The physical and financial planning was then reviewed, |  |  |  |  | 27-Mar-18
Output | Analyses of the local land ownership situations |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | brunoj | The Executing unit decided to develop land tenure statistical data in order to improving the WB Doing Business scoring. The physical and financial planning was then reviewed, |  |  |  |  | 27-Mar-18
Output | GNSS (Global Navigation Satellite System) Continually Operating Receiving Stations upgraded and/or installed |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | brunoj | The physical and financial planning was reviewed according to 2017 execution, |  |  |  |  | 27-Mar-18
Output | Parcels surveyed, with tenure clarified and recorded into the database |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | brunoj | The physical and financial planning was reviewed according to 2017 execution, |  |  |  |  | 27-Mar-18
Output | Local land administrative offices (ONACA/DGI) equipped |  |  | Modify Physical EOP P(a) value - caused by a change in the Physical P(a). | Modify Output |  | brunoj | The physical and financial planning was reviewed according to 2017 execution, |  |  |  |  | 27-Mar-18
Output | Local land administrative offices (ONACA/DGI) equipped |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | cedrickj | The physical and financial planning was reviewed according to 2017 execution, |  |  |  |  | 14-Mar-18
Output | Notaries equiped with new equipment and software in the pilot areas |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | cedrickj | The physical and financial planning was reviewed according to 2017 execution, |  |  |  |  | 14-Mar-18
Output | Persons trained with a masters degree in land administration |  |  | Modify Financial EOP P(a) value - caused by a change in the Financial P(a). | Modify Output |  | cedrickj | The physical and financial planning was reviewed according to 2017 execution, |  |  |  |  | 14-Mar-18

## Second period Jan-Dec 2020
|  | Operation Number: | HA-L1056 |  |  |  |  | Inter-American Development Bank - IDB
|  | Year- PMR Cycle: | First period Jan-Dec 2020
|  | Last Update: | 2020-10-27
PMR Validation Stage:
Changes to the Matrix
Section | Name |  |  | Type of Change | Subtype | Modified by | Reasons |  | Entered in the System | Agreed with Executing Agency
Outcome | Number of parcels demarcated, clarified and included in a PFB. |  |  | Creation of the outcome indicator. | Modify Outcome | brunoj | The measure the result and effectiveness of this SO, the PCR considers that the achievements related to parcel demarcation and clarification in the framework of the creation of PFBs should be considered as a valid outcome that is clearly related to the SO1 -- increase land tenure security of rural households. The project’s methodology, which combined a set of different techniques, including the mobilization of field teams capable of working with local communities and GPS technology to demarcate parcels; genealogical analysis of parcel ownership going back into the nineteenth century; archival research in notary records; and the scanning of documents for insertion into a PFBs, produced highly trustworthy data. With this verified information, land tenure security is substantially enhanced since land cannot be stolen, boundaries cannot be shifted, and fake ownership papers cannot be produced as a means of stealing land. The very existence of a PFB database therefore contributes to increased land tenure security in the pilot targeted areas, it constitutes an asset and a reference for any further land transactions or land management activity in the future. It provides a high level of certainty on the identification of property, people and rights on the land that have been surveyed. Local and national actors recognized the PFB’s social function. The very fact of demarcating parcels for inclusion in a PFB, a locally held plan, reduced informality and conflicts. Even though most participating farmers did not receive the official Survey Minutes (Procès Verbaux d’Arpentage, PVA) because of lack of time and resources of the project, nevertheless, the social and juridical clarification process brought certainty over what is owned by whom and delivered an element of tranquility in a national and local context defined by perceived and real land theft and conflicts. The modicum of official certainty around land tenure that was introduced by the project into an otherwise uncertain rural context contributed an important degree of confidence around a critical asset. In addition, thanks to the PFB implementation, CIAT and other land tenure stakeholders such as notaries, surveyors and DGI, were able to assess the technical feasibility and relevance in the new way to conduct land surveys and tenure clarification. This field experience substantially fed the design of the draft bills of the land tenure reform on multiple aspects, such as the best suited GPS system and Real Time Kinematic to be used for land surveys, the community participation modalities and the roles of the different stakeholders along the land registration process, among other issues. In this sense the PCR proposes considering the indicator “Number of parcels demarcated, clarified and included in a PFB” as a valid outcome to demonstrate the achievement of SO1. -- increase land tenure security of rural households. The initial target was to reach 66,000 parcels in eight communes of the country. This objective was reduced to 65,031 parcels at project start-up, and the PSFMR finally achieved 64,510 parcels surveyed and clarified, included in the PFB database, in five communes. , |  | 27-Oct-20