## Project Structure
Agency | Sub-Agency (If applies) | Agency's Initials
National Environment & Planning Agency |  | NEPA
NOTE: 1. There may only be one Organism which coordinates the Procurement Plan information and submits it to the Bank 2. Each Sub-executing Agency shall upload one sheet #2 with its activities
COMPONENTS? (YES / NO) | Component's Name (list by number or letter)
YES | Component 1
Component 2
Component 3
Component 4
Component 5
NOTE: Name the components in the loan agreement; use only main components

## Procurement Plan
INFORMATION FOR PROCUREMENT PLAN INITIAL UPLOAD ONGOING AND/OR LAST PRESENTED
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage:
2. Procurement Plan Details
Version ( 1-xxxx (Year) ) :
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Works | 0 | 0
Goods | 1082378.5007 | 0
Non Consulting Services | 1205382.4029 | 0
Training | 47424.33 | 0
Operative Costs | 0 | 0
Consulting Services (Firms + Individuals) | 1589255.77 | 0
Transfers | 0 | 0
Community Participation | 0 | 0
Unassigned | 0 | 0
Total | 3924441.0036 | 0
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
Component 1 - Institutional Strengthening and Capacity Building for Integrating biodiversity into Watershed Management | 942686.88 | 0
Component 2 - Creating Economic Incentives to support sustainable Biodiversity and Watershed Management | 699343 | 0
Component 3 - Implementing Sustainable Livelihoods, Agriculture and Forestry in Watershed Management Communities | 2223370.4336 | 0
Component 4 - Program Evaluations | 50000 | 0
Component 5 - Program Administration | 9040.69 | 0
Component 6 - Description | 0 | 0
Total | 3924441.0036 | 0

## Detailed Procurement Plan
PROCUREMENT PLAN INITIAL LOAD INFORMATION (ONGOING AND/OR LAST PRESENTED)
WORKS | [13 empty] | National System
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Ex-Post
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  | Ex-Ante
Cancelled
Contract Concluded
Contract in Execution
Contract Terminated
Null and Void
Ongoing
GOODS | [13 empty] | Planned
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Rejection of all Bids
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  | Re-Tendering
National Environment & Planning Agency | Procurement of equipment (net, bottles, etc. ) for organization of training workshops on Bio-Monitoring (multiple procurements). | Pending | Shopping |  | 1.2.4.2-1-1 | 2500 | 100% | 0% | 1 | Ex-Post | 2018-06-01 | 2018-07-01 |  | International Competitive Bidding
National Environment & Planning Agency | Production of training material for organization of training workshops on Bio-Monitoring. | Pending | Shopping |  | 1.2.4.4-1-1 | 500 | 100% | 0% | 1 | Ex-Post | 2018-06-01 | 2018-07-01 |  | National Competitive Bidding
National Environment & Planning Agency | MONITORING EQUIPMENT: Purchase and installation of sediment and rain gauges, stream flow monitors and other. (multiple procurements) | Pending | Direct Contracting |  | 1.2.5-1-1 | 78800 | 100% | 0% | 1 | Ex-Ante | 2019-01-01 | 2019-03-01
National Environment & Planning Agency | Production of material to accommodate training of practioners on inventory and mapping for carbon sequestration. | Pending | Shopping |  | 1.2.6.5-1-1 | 1000 | 100% | 0% | 1 | Ex-Post | 2018-05-01 | 2018-09-01
National Environment & Planning Agency | HARDWARE AND SOFTWARE: Purchase of computer equipment and applications for Integrated Watershed Management Decision Support System (IWM-DSS). | Pending | Shopping |  | 1.3.2-1-1 | 20000 | 100% | 0% | 1 | Ex-Ante | 2017-11-01 | 2018-02-01
National Environment & Planning Agency | Production of training material to conduct training sessions and seminars on the applications of Geographic Information Systems (GIS) to land management and physical and rural planning, and related biodiversity and ecosystem services. | Pending | Shopping |  | 1.3.3.1-1-1 | 5000 | 100% | 0% | 1 | Ex-Post | 2018-01-01 | 2018-05-01
National Environment & Planning Agency | Promotion and Public Communication for the printing, & production of communication material (development & dissemination of material). | In-progress | Shopping |  | 1.5.3-1-1 | 16000 | 100% | 0% | 1 | Ex-Ante | 2016-07-01 | 2019-08-01
National Environment & Planning Agency | Promotion and Public Communication for the printing, & production of communication material (development & dissemination of material). (Multiple procurement activities) | Pending | Direct Contracting |  | 1.5.4-1-1 | 8000 | 100% | 0% | 1 | Ex-Post | 2017-09-01 | 2019-08-01
National Environment & Planning Agency | PES Training: Production of training material to conduct training sessions and seminars - June 2018 | Pending | Shopping |  | 2.3.1.7-1-1 | 625 | 100% | 0% | 2 | Ex-Post | 2018-04-01 | 2018-06-01
National Environment & Planning Agency | PES Training: Production of training material to conduct training sessions and seminars - September 2018 | Pending | Shopping |  | 2.3.1.8-1-2 | 625 | 100% | 0% | 2 | Ex-Post | 2018-07-01 | 2018-09-01
National Environment & Planning Agency | PES Training: Production of training material to conduct training sessions and seminars - March 2019 | Pending | Shopping |  | 2.3.1.9-1-3 | 625 | 100% | 0% | 2 | Ex-Post | 2019-01-01 | 2019-03-01
National Environment & Planning Agency | PES Training: Production of training material to conduct training sessions and seminars - May 2019 | Pending | Shopping |  | 2.3.1.10-1-4 | 625 | 100% | 0% | 2 | Ex-Post | 2019-03-01 | 2019-05-01
National Environment & Planning Agency | TRAINING: Training sessions on "Land Husbandry" aspects for Government of Jamaica (GOJ) officers and community members. Includes the coverage of tools & supplies, preparation and production of training material, tool: A frames, Siv, and agricultural supplies eg. Pineapple suckers, fruit trees etc. (Multiple procurement activities) | In-progress | Shopping |  | 3.2.1.1-1-1 | 187313 | 100% | 0% | 3 | Ex-Post | 2015-11-01 | 2018-03-01 | Multiple procurement activities.
National Environment & Planning Agency | TRAINING: Training sessions on "Land Husbandry" aspects for Government of Jamaica (GOJ) officers and community members. Includes the coverage of tools & Supplies, preparation and production of training material, agricultural supplies eg. Pineapple suckers, fruit trees, stones, and other supplies (Multiple procurement activities) | In-progress | Direct Contracting |  | 3.2.1.2-1-1 | 45000 | 100% | 0% | 3 | Ex-Post | 2015-11-01 | 2018-03-01
National Environment & Planning Agency | PILOT PROJECTS: Land Husbandry & AF plots: Equipment (Projectors, laptop computer etc.) and other supplies for training workshops eg Farmer Field School & Land Husbandry Workshops. (Multiple procurement activities) | In-progress | Shopping |  | 3.2.1.3-1-1 | 40000 | 100% | 0% | 3 | Ex-Ante | 2016-01-01 | 2019-08-01
National Environment & Planning Agency | LOCAL TRAINING: Dissemination of material on good agricultural practices, land management and agroforestry practices.Includes the production of short videos, text messages to farmers and other communications activities. ( Multiple procurement activities) | In-progress | Shopping |  | 3.2.3-3-1 | 89711 | 100% | 0% | 3 | Ex-Ante | 2017-06-01 | 2019-06-01
National Environment & Planning Agency | LOCAL TRAINING: Dissemination and training activities aimed at local farming communities on fire management. Included in the procurement are tools, Equipment & other supplies | In-progress | Shopping |  | 3.2.4.1-1-1 | 7312 | 100% | 0% | 3 | Ex-Post | 2016-08-01 | 2018-06-01
National Environment & Planning Agency | LOCAL TRAINING: Dissemination and training activities aimed at local farming communities on fire management. Included in the procurement are tools, Equipment & other supplies | In-progress | Direct Contracting |  | 3.2.4.2-1-1 | 10000 | 100% | 0% | 3 | Ex-Ante | 2016-11-01 | 2018-06-01
National Environment & Planning Agency | LOCAL TRAINING: Refreshments for Team Jamaica Training Program aimed at local communities on non-agricultural aspects including commercialization, marketing, market studies and other. (Multiple procurement activities) | Pending | Shopping |  | 3.2.5.3-1-1 | 1059 | 100% | 0% | 3 | Ex-Post | 2018-01-01 | 2018-09-01
National Environment & Planning Agency | LOCAL TRAINING:Refreshments for CPR Trainer aimed at local communities on non-agricultural aspects including commercialization, marketing, market studies and other. (Multiple procurement activities) | Pending | Shopping |  | 3.2.5.4-1-1 | 1059 | 100% | 0% | 3 | Ex-Post | 2018-01-01 | 2019-06-01
National Environment & Planning Agency | LOCAL TRAINING: 6 computers to assist with ICT Training and set up ICT Centres aimed at local communities on non-agricultural aspects. | Pending | Shopping |  | 3.2.5.5-1-1 | 7800 | 100% | 0% | 3 | Ex-Post | 2018-01-01 | 2018-06-01
National Environment & Planning Agency | MONITORING EQUIPMENT: Purchase and installation of sediment and rain gauges, stream flow monitors and other. | Pending | Direct Contracting |  | 3.2.5.5-1-2 | 7941 | 100% | 0% | 3 | Ex-Ante | 2018-02-01 | 2018-04-01
National Environment & Planning Agency | PILOT PROJECTS: (Multiple payments) Fuel for Vehicle | In-progress | Direct Contracting |  | 3.3.1.3-1-1 | 86111 | 100% | 0% | 3 | Ex-Post | 2015-09-01 | 2019-10-01
National Environment & Planning Agency | PILOT PROJECTS: Land Husbandry & AF plots (incl. fertilizer, pesticide, planting material & A-Frames. Check dams/drop structures: stones, used tyres, sand, gabion basket, wire, cement, steel rods, storage container & Transportation (Multiple procurement activities) | Pending | Shopping |  | 3.3.1.5-1-1 | 70000 | 100% | 0% | 3 | Ex-Ante | 2017-09-01 | 2018-06-01
National Environment & Planning Agency | PILOT PROJECTS: Land Husbandry & AF plots (incl. fertilizer, pesticide, planting material & A-Frames. Check dams/drop structures: stones, used tyres, sand, gabion basket, wire, cement, steel rods, storage container & Transportation (Multiple procurement activities) | Pending | Shopping |  | 3.3.1.5-1-2 | 151949.61 | 100% | 0% | 3 | Ex-Post | 2018-07-01 | 2018-12-01
National Environment & Planning Agency | PILOT PROJECTS: Land Husbandry & AF plots (incl. fertilizer, pesticide, planting material & A-Frames. Check dams/drop structures: stones, used tyres, sand, gabion basket, wire, cement, steel rods, storage container & Transportation (Multiple procurement activities) | Pending | Shopping |  | 3.3.1.5-1-3 | 89914.96 | 100% | 0% | 3 | Ex-Ante | 2018-11-01 | 2019-06-01
National Environment & Planning Agency | PILOT PROJECTS: Land Husbandry & AF plots (incl. fertilizer, pesticide, planting material & A-Frames. Check dams/drop structures: stones, used tyres, sand, gabion basket, wire, cement, steel rods, storage container & Transportation (Multiple procurement activities) | Pending | Direct Contracting |  | 3.3.1.5-1.4 | 10000 | 100% | 0% | 3 | Ex-Post | 2017-09-01 | 2018-08-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: Reforestation and restoration of degraded lands. Included in the investment packages are Soil/potting mix/other production material. (Multiple procurement activities) | Pending | Shopping |  | 3.3.2.2-1-1 | 18391 | 100% | 0% | 3 | Ex-Ante | 2017-09-01 | 2017-12-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: Reforestation and restoration of degraded lands - Community engagement. Included in the investment packages are refreshments. (Multiple procurement activities) | Pending | Direct Contracting |  | 3.3.2.4-1-1 | 770 | 100% | 0% | 3 | Ex-Post | 2017-09-01 | 2017-12-01
National Environment & Planning Agency | Program Administration: Procurement of material & equipment for setting up partition for renovation of office space to accommodate the PEU | Pending | Shopping |  | 4.1.3.1-1-1 | 2490 | 100% | 0% | 4 | Ex-Post | 2018-01-01 | 2018-12-01
National Environment & Planning Agency | VEHICLE: Purchase of 4X4 Pick Up Truck for the use by the National Environment and Planning Agency (NEPA) as Program Implementing Agency (PIA), and by the Program Executing Unit (PEU). | Completed | Shopping |  | 3.1.3-1-1 | 41315 | 100% | 0% | 3 | Ex-Ante | 2015-05-01 | 2015-09-01
National Environment & Planning Agency | Program Administration: Procurement of Printer/Copier/Scanner for PEU | Completed | Shopping |  | 1-4-3-1-1 | 9000 | 100% | 0% | 4 | Ex-Ante | 2015-11-01 | 2017-08-01
National Environment & Planning Agency | Program Administration: Procurement of Printer/Copier/Scanner for PEU (Taken from Component 1 Development Orders $5,000.00 & $4,040.69 from 3.3.1.5) | Completed | Shopping |  | 1-4-3-0 | 9040.69 | 100% | 0% | 5 | Ex-Ante | 2015-11-01 | 2017-08-01
National Environment & Planning Agency | Program Administration: Material, computer(s)/other for Information Technology Infrastructural work (including office fixtures & Stationeries) for the renovation of office space to accommodate the PEU | Completed | Shopping |  | 1-4-10-1-8 | 2000 | 100% | 0% | 4 | Ex-Post | 2015-12-01 | 2016-12-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: Reforestation and restoration of degraded lands. Included in the investment packages are Soil/potting mix/other production material. | Completed | Shopping |  | 3.3.2.2-1-1 | 14643 | 100% | 0% | 3 | Ex-Ante | 2015-04-01 | 2015-12-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: Reforestation and restoration of degraded lands. Included in the investment packages are equipment/material (groung truthing from Satelite Imagery and other cost | Completed | Shopping |  | 3.3.2.2-1-2 | 3017.2414 | 100% | 0% | 3 | Ex-Post | 2015-05-01 | 2016-12-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: Reforestation and restoration of degraded lands. Included in the investment packages are GPS Equipment units, software and annual licensing fee and other cost for ground truthing from satelity imagery. | Completed | Direct Contracting |  | 3.3.2.3-1-1 | 42240.9993 | 100% | 0% | 3 | Ex-Ante | 2015-11-01 | 2016-11-01
Direct Contracting
[6 empty] | 1082378.5007 | [7 empty] | National System
NON CONSULTING SERVICES | [13 empty] | Limited Competitive Bidding
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Lots Quantity: | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Prequalification
[6 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Bidding Documents | Contract Signature |  | Two-envelope International Competitive Bidding
International Competitive Bidding by Lots
National Environment & Planning Agency | Policy Consultant: Hosting of workshop - Rental of venue, provision of meals, transportation and others to host workshop. | Pending | Shopping |  | 1.1.2-3.1 | 1000 | 100% | 0% | 1 | Ex-Post | 2017-10-01 | 2017-10-01
National Environment & Planning Agency | Advertising cost related to the contracting of consulting firm (National): Ecological Assessment and Bio-Monitoring training | In-progress | Direct Contracting |  | 1.2.4.5-3-2 | 1800 | 100% | 0% | 1+J59:N62 | Ex-Ante | 2017-08-01 | 2017-08-01
National Environment & Planning Agency | Consulting Firm: National - Rental of venue, transportation, training material, refreshment etc for organization of training workshops on Bio-Monitoring (Multiple procurement activities) | Pending | Shopping |  | 1.2.4.3-3-1 | 2500 | 100% | 0% | 1 | Ex-Post | 2018-02-01 | 2018-06-01
National Environment & Planning Agency | MONITORING EQUIPMENT: Purchase and installation of sediment and rain gauges, stream flow monitors and other - Brokerage fees. | Pending | Direct Contracting |  | 1.2.5-3-1 | 1200 | 100% | 0% | 1 | Ex-Ante | 2019-02-01 | 2019-03-01
National Environment & Planning Agency | Venue, transportation, meals, production of material etc. to accommodate training of practitioners on inventory and mapping for carbon sequestration. (Multiple procurement activities) | Pending | Shopping |  | 1.2.6.2-3-1 | 8200 | 100% | 0% | 1 | Ex-Post | 2017-11-01 | 2017-12-01
National Environment & Planning Agency | Lab Analysis for soil and tissues samples on inventory and mapping for carbon sequestration. (Multiple procurement activities) | Pending | Shopping |  | 1.2.6.3-3-2 | 9200 | 100% | 0% | 1 | Ex-Post | 2018-02-01 | 2018-04-01
National Environment & Planning Agency | Advertising Cost related to the contracting of: - An CONSULTING FIRM: International - Geographic Information Systems (GIS & DSS Watershed Management Specialist) and Land Management Specialist 1.3.1.2-3-1. - An individual consultant: National - Economist to conduct the socioeconomic surveys for the Program 1.2.3.2-3-1. | In-progress | Direct Contracting |  | 1.3.3.3-3-1 | 1900 | 100% | 0% | 1 | Ex-Ante | 2017-09-01 | 2017-12-01
National Environment & Planning Agency | Advertising Cost related to the contracting of: - Socio-economic Firm to undertake socio-economic assessment of the watershed management unitsion of on-farm demonstration projects in agroforestry, Sustainable land Management (SLM), irrigation and other. Investment packages to be defined: 3.3.1.1-3-1. | Pending | Direct Contracting |  | 1.2.3.1-3-1 | 1200 | 100% | 0% | 3 | Ex-Ante | 2017-11-01 | 2017-12-01
National Environment & Planning Agency | Program Administration: Procurement of labour to erect partition and electrical and other for the renovation of office space to accommodate the PEU | Pending | Direct Contracting |  | 4.1.3.1-3-1 | 1000 | 100% | 0% | 4 | Ex-Post | 2018-01-01 | 2018-12-01
National Environment & Planning Agency | Program Administration: Meeting and workshop expenses as needed through the period | Pending | Shopping |  | 4.1.3.1-3-2 | 510 | 100% | 0% | 4 | Ex-Post | 2018-01-01 | 2019-06-01
National Environment & Planning Agency | CONSULTING FIRM: Rental of venue, transportation, refreshmnet, mileage and other reimbursables to conduct training sessions and seminars on the applications of Geographic Information Systems (GIS) to land management and physical and rural planning, and related biodiversity and ecosystem services. (Multiple procurement activities) | Pending | Shopping |  | 1.3.3.1-3-1 | 5000 | 100% | 0% | 1 | Ex-Post | 2018-06-01 | 2018-07-01
National Environment & Planning Agency | Promotion and Public Communication: Production of Graphic Artwork(s) and printing & productioin of communicaiton material (development & dissemination of material) for the public awareness material. | In-progress | Shopping |  | 1.5.2-3-1 | 5100 | 100% | 0% | 1 | Ex-Post | 2016-07-01 | 2019-08-01
National Environment & Planning Agency | Promotion and Public Communication: Production of Graphic Artwork(s) and printing & productioin of communicaiton material (development & dissemination of material) for the public awareness material: Partnership between the Jamaica Cultural Develoment Commission (JCDC) and the NEPA for Jamaica 55 Grand Gala celebrations. | In-progress | Direct Contracting |  | 1.5.2-3-2 | 3900 | 100% | 0% | 1 | Ex-Ante | 2017-07-01 | 2017-08-01
National Environment & Planning Agency | Public Awareness: Graphic Artwork and production of comunicaion material (development & dissemination of material): for the development and continuation of service. (Multiple procurement activities) | Pending | Direct Contracting |  | 1.5.4-3-1 | 4000 | 100% | 0% | 1 | Ex-Post | 2017-10-01 | 2019-08-01
National Environment & Planning Agency | PES Training: Rental of venue, transportation, refreshmnet, mileage and other reimbursables to conduct training sessions and seminars - June 2018 | Pending | Shopping |  | 2.3.1.3-3-3 | 4375 | 100% | 0% | 2 | Ex-Post | 2018-04-01 | 2018-06-01
National Environment & Planning Agency | PES Training: Rental of venue, transportation, refreshmnet, mileage and other reimbursables to conduct training sessions and seminars - September 2018 | Pending | Shopping |  | 2.3.1.4-3-4 | 4375 | 100% | 0% | 2 | Ex-Post | 2018-07-01 | 2018-09-01
National Environment & Planning Agency | PES Training: Rental of venue, transportation, refreshmnet, mileage and other reimbursables to conduct training sessions and seminars - March 2019 | Pending | Shopping |  | 2.3.1.5-3-5 | 4375 | 100% | 0% | 2 | Ex-Post | 2019-01-01 | 2019-03-01
National Environment & Planning Agency | PES Training: Rental of venue, transportation, refreshmnet, mileage and other reimbursables to conduct training sessions and seminars - May 2019 | Pending | Shopping |  | 2.3.1.6-3-6 | 4284.57 | 100% | 0% | 2 | Ex-Post | 2019-03-01 | 2019-05-01
National Environment & Planning Agency | INDIVIDUAL CONSULTANT: International/national - Hydrological Modeling Specialist for the Hydro-Meterological Assessment Study for the Program. Pier diem and overseas travel | Pending | Direct Contracting |  | 1.2.1.2-3-1 | 7500 | 100% | 0% | 2 | Ex-Ante | 2017-09-01 | 2017-11-01
National Environment & Planning Agency | OTHER SERVICES: (Multiple procurement activities) Monitoring of overall extension and training activities undertaken by Government of Jamaica (GOJ) agencies. | Pending | Direct Contracting |  | 3.1.2-3-1 | 40421 | 100% | 0% | 3 | Ex-Post | 2018-01-01 | 2019-06-01
National Environment & Planning Agency | TRAINING: Training sessions on "Land Husbandry" aspects for Government of Jamaica (GOJ) officers and community members. Includes the coverage of venue, accommodation, meals/refreshment. (Multiple procurement activities) | In-progress | Shopping |  | 3.2.1.2-3-1 | 54512 | 100% | 0% | 3 | Ex-Ante | 2015-11-01 | 2018-03-01
National Environment & Planning Agency | TRAINING: (Multiple payments under Project Agreement) Training sessions on "Land Husbandry" aspects for Government of Jamaica (GOJ) officers and community members. Includes the coverage of venue, accommodation, meals/refreshment and promotional supplies. | In-progress | Direct Contracting |  | 3.2.1.2-3-2 | 25000 | 100% | 0% | 3 | Ex-Post | 2017-04-01 | 2019-08-01
National Environment & Planning Agency | TRAINING: (Multiple payments under Project Agreement) Training sessions on "Land Husbandry" aspects for Government of Jamaica (GOJ) officers (NGO groups). Includes the coverage of staff mileage and others | In-progress | Direct Contracting |  | 3.2.1.3-3-1 | 104500 | 100% | 0% | 3 | Ex-Post | 2016-01-01 | 2018-03-01
National Environment & Planning Agency | TRAINING: Training sessions on "Land Husbandry" aspects for Government of Jamaica (GOJ) officers (NGO groups). Includes the coverage of bus rental. | In-progress | Shopping |  | 3.2.1.3-3-2 | 20000 | 100% | 0% | 3 | Ex-Ante | 2015-11-01 | 2018-03-01
National Environment & Planning Agency | COMMUITY-BASED ACTIVITIES AND OUTREACH: Sensitization, training, and strengthening of local farmers and community on social aspects and other related to watershed management: venue, refreshment, travel/mileage and other costs. | Pending | Shopping |  | 3.2.2.1-3-1 | 94260 | 100% | 0% | 3 | Ex-Ante | 2018-01-01 | 2019-06-01
National Environment & Planning Agency | LOCAL TRAINING: (Mulitple payments) Dissemination and training activities aimed at local farming communities on fire management. Donation to Jamaica Fire Bridgage. | In-progress | Direct Contracting |  | 3.2.4-1-3-1 | 1838 | 100% | 0% | 3 | Ex-Post | 2016-10-01 | 2018-06-01
National Environment & Planning Agency | LOCAL TRAINING: (Multiple payments under Project Agreement) Coordination and monitoring of alternative livelihood training program. Reimbursement of JCDT for cordination and monitoring. | Pending | Direct Contracting |  | 3.2.5.3-3-2 | 7350 | 100% | 0% | 3 | Ex-Post | 2018-01-01 | 2018-01-01
National Environment & Planning Agency | Advertisement cost related to the employment of Marketing Specialist - Four (4) market studies to be conducted aimed at local communities on non-agricultural aspects. | Pending | Direct Contracting |  | 3.2.5.1-3-1 | 1200 | 100% | 0% | 3 | Ex-Ante | 2018-02-01 | 2018-04-01
National Environment & Planning Agency | PILOT PROJECTS: (Multiple payments) Licensing, fitness and insurance of project vehicle | In-progress | Direct Contracting |  | 3.3.1.2-3-1 | 10882 | 100% | 0% | 3 | Ex-Post | 2015-10-01 | 2019-10-01
National Environment & Planning Agency | PILOT PROJECTS: (Multiple procurement activities) Maintenance of Vehicle; cost also includes tyres. | In-progress | Direct Contracting |  | 3.3.1.4-3-1 | 28423.39 | 100% | 0% | 3 | Ex-Post | 2016-01-01 | 2019-10-01
National Environment & Planning Agency | PILOT PROJECTS: (Multiple payments under Project Agreement) Implementation of agroforestry and on-farm demonstration projects, Sustainable land Management (SLM), irrigation and other. Investment packages to be defined: Travelling (mileage & subsistence) RADA Officers. | Pending | Direct Contracting |  | 3.3.1.5-3-1 | 169222 | 100% | 0% | 3 | Ex-Post | 2018-01-01 | 2019-06-01 | Multiple payments.
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages are mileage and subsistence for Silviculture Plan for Reforestation/Planting | Pending | Direct Contracting |  | 3.3.2.1-3-1 | 1015 | 100% | 0% | 3 | Ex-Post | 2018-02-01 | 2018-04-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages are casual labour for silviculture plan reforestation/Planting | pending | Direct Contracting |  | 3.3.2.1-3-2 | 280 | 100% | 0% | 3 | Ex-Post | 2018-02-01 | 2018-04-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages are Subsistence and mileage and Bush Allowance for field officers to support Ground -truthing activities. | In-progress | Direct Contracting |  | 3.3.2.3-3-1 | 4092.3948 | 100% | 0% | 3 | Ex-Post | 2015-05-01 | 2016-12-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages are Casual labour for Ground -truthing (Survey assistance). | In-progress | Direct Contracting |  | 3.3.2.3-3-2 | 12922.7605 | 100% | 0% | 3 | Ex-Post | 2015-05-01 | 2017-12-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages are Accommodation for Bush/Survey Lines (Ground truthing). | In-progress | Direct Contracting |  | 3.3.2.3-3-3 | 67090.1468 | 100% | 0% | 3 | Ex-Post | 2016-07-01 | 2017-12-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands - Community Engagement. Included in the investment packages are mileage and subsistence for Technicians. | Pending | Direct Contracting |  | 3.3.2.4-3-1 | 1785 | 100% | 0% | 3 | Ex-Post | 2018-03-01 | 2018-05-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages are one hundred (100) hectares planted (by casual labour) for Reforestation/Planting | In-progress | Direct Contracting |  | 3.3.2.6-3-1 | 74376.7535 | 100% | 0% | 3 | Ex-Post | 2016-05-01 | 2017-12-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages: Fireslines created for Reforestation/Planting. | In-progress | Direct Contracting |  | 3.3.2.5-3-2 | 22677.3547 | 100% | 0% | 3 | Ex-Post | 2016-12-01 | 2017-12-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages are Casual labour for Seedling Production/nursery Operations | In-progress | Direct Contracting |  | 3.3.2.2-3-1 | 4598.0561 | 100% | 0% | 3 | Ex-Post | 2015-07-01 | 2019-06-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages no. of hectares maintained (by casual labour) for maintenance/weeding. | In-progress | Direct Contracting |  | 3.3.2.7-3-1 | 40468.0126 | 100% | 0% | 3 | Ex-Post | 2016-09-01 | 2019-06-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages are Beating up/Seedling replacement for maintenance/weeding. | In-progress | Direct Contracting |  | 3.3.2.6-3-2 | 149526.3586 | 100% | 0% | 3 | Ex-Post | 2018-01-01 | 2019-08-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages are Fire lines maintenance (Reopening of Existing Lines) for maintenance/weeding - Casual Labour. | Pending | Direct Contracting |  | 3.3.2.7-3-4 | 181418.8377 | 100% | 0% | 3 | Ex-Post | 2017-01-01 | 2019-08-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION:(Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages are Mileage and subsistence for land prep/planting/maintenance in support of reforestation for maintenance/weeding. | In-progress | Direct Contracting |  | 3.3.2.7-3-1 | 7182.3647 | 100% | 0% | 3 | Ex-Post | 2016-09-01 | 2017-09-01
National Environment & Planning Agency | PROJECTS IMPLEMENTATION: (Multiple payments under Project Agreement) Reforestation and restoration of degraded lands. Included in the investment packages are Accommodation/Subsistence for land prep/planting/maintenance for maintenance/weeding. | In-progress | Direct Contracting |  | 3.3.2.7-3-2 | 6006.863 | 100% | 0% | 3 | Ex-Post | 2017-01-01 | 2019-06-01
National Environment & Planning Agency | Advertising cost related to the employment of consultant firm (International) to undertake the PES activities | Completed | Direct Contracting |  | 2.2.2.2-3-1 | 624.11 | 100% | 0% | 2 | Ex-Ante | 2016-05-01 | 2016-05-01
National Environment & Planning Agency | Payment for Ecosystems Services (PES) Scheme designed. Printing of 19 reports for internal and external approval committees. | Completed | Shopping |  | 2.3.1.7-3-7 | 1090.43 | 100% | 0% | 2 | Ex-Post | 2017-07-01 | 2017-08-01
National Environment & Planning Agency | Advertising cost related to the employment of consultant re: SURVEYS: Contracting one (1) of two (2) surveys targeted at local stakeholders (to be conducted in year 1) of the Program on Knowledge, Attitude, Practices and Behaviour (KAPB) and consolidation and analysis of results. | Completed | Direct Contracting |  | 3.1.1-3-2 | 1200 | 100% | 0% | 3 | Ex-Ante | 2016-10-01 | 2016-11-01
Quality Based Selection
[6 empty] | 1205382.4029 | [7 empty] | Selection Based on the Consultants' Qualifications
CONSULTING FIRMS | [13 empty] | Single Source Selection
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method |  | National System
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature |  |  | Least cost Selection
Selection under a Fixed Budget
National Environment & Planning Agency | Consulting Firm: National - Economist to conduct the socioeconomic surveys for the Program. | Pending | Selection Based on the Consultants' Qualifications | 1.2.3.1-4-1 | 25300 | 100% | 0% | 1 | Ex-Ante | 2017-10-01 | 2018-01-01
National Environment & Planning Agency | Consulting Firm: National - Consulting firm to conduct the ecological survery which includes the preparation of technical materials and organization of training workshops on ecological, biodiversity, and Bio Monitoring (Merged with ecology and biodiversity surveys). | In-Progress | Selection Based on the Consultants' Qualifications | 1.2.4.1-4-1 | 68200 | 100% | 0% | 1 | Ex-Ante | 2017-08-01 | 2017-11-17
National Environment & Planning Agency | CONSULTING FIRM: International - Geographic Information Systems (GIS & DSS Watershed Mangement Specialist) and Land Management Specialist for the development of (and execution of training workshopfor Government of Jamaica (GOJ) officials on the deployment of the Watershed Management Decision Support System (IWM-DSS ) Integrated Wateshed Management Decision Support System (IWM-DSS). to conduct training sessions and seminars on the applications of Geographic Information Systems (GIS) to land management and physical and rural planning, and related biodiversity and ecosystem services. | Pending | Selection Based on the Consultants' Qualifications | 1.3.1.1-4-1 | 88800 | 100% | 0% | 1 | Ex-Ante | 2017-09-01 | 2017-12-01
National Environment & Planning Agency | Payment for Ecosystems Services (PES) Scheme designed. | In-Progress | Quality Based Selection | 2.1.2-4-1 | 595218.89 | 100% | 0% | 2 | Ex-Ante | 2016-04-01 | 2017-10-01
National Environment & Planning Agency | SURVEYS: Contracting one (1) of two (2) surveys targeted at local stakeholders (to be conducted in year 1) of the Program on Knowledge, Attitude, Practices and Behaviour (KAPB) and consolidation and analysis of results. | In-Progress | Selection Based on the Consultants' Qualifications | 3.1.1-3-1 | 37370 | 100% | 0% | 3 | Ex-Ante | 2016-10-01 | 2017-09-01
National Environment & Planning Agency | SURVEYS: Contracting two (2) of two (2) surveys targeted at local stakeholders (to be conducted in years 3 & 5) of the Program on Knowledge, Attitude and Practices (KAPB) and consolidation and analysis of results. | Pending | Selection Based on the Consultants' Qualifications | 3.1.1-3-2 | 39080 | 100% | 0% | 3 | Ex-Ante | 2019-01-01 | 2019-04-01
National Environment & Planning Agency | COMMUITY-BASED ACTIVITIES AND OUTREACH: Consulting Firm (Social Development Commission) to undertake sensitization, training, and strengthening of local farmers and community on social aspects and other related to watershed management. Includes travel costs. | Pending | Single Source Selection | 3.2.2.2-4-1 | 40500 | 100% | 0% | 3 | Ex-Ante | 2018-01-01 | 2018-02-01
National Environment & Planning Agency | CONSULTING FIRM: Independent accounting firm to conduct and prepare the annual external audits of the Program (April 2017- March 2018, April 2018 - March 2019 and April - October 2019). | Pending | Single Source Selection | III.B-4-3 | 25000 | 100% | 0% | 4 | Ex-Ante | 2018-01-01 | 2019-06-01
National Environment & Planning Agency | CONSULTING FIRM: Independent accounting firm to conduct and prepare the annual external audits of the Program (April 2015-March 2016). | Completed | Single Source Selection | III.B-4-1 | 5000 | 100% | 0% | 4 | Ex-Ante | 2015-11-01 | 2016-03-01
National Environment & Planning Agency | CONSULTING FIRM: Independent accounting firm to conduct and prepare the annual external audits of the Program (April 2016-March 2017). | Completed | Single Source Selection | III.B-4-2 | 5000 | 100% | 0% | 4 | Ex-Ante | 2017-01-01 | 2017-05-01
[5 empty] | 919468.89 | [8 empty] | Unit Prices | Goods
INDIVIDUAL CONSULTANTS | [13 empty] | Lump-Sum | Goods
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount |  |  | Estimated Number of Consultants: | Associated Component: | Review Method (Select one of the options): | Dates |  | Comments - for UCS include selection method | Turnkey | Works
[5 empty] | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  |  | No Objection to TOR's | Contract Signature |  | Unit Prices | Works
National Environment & Planning Agency | Program Review Specialist: To review and update the watershed management mechanism (watershed model). | In-progress | 3CV | 1.1.3-4-1 | 14000 | 100% | 0% | 1 | 1 | Ex-Ante | 2017-02-01 | 2017-10-01
National Environment & Planning Agency | Policy Consultants: To review and update Jamaica's watershed policy to move the country closer towards monitoring of watershed management. | In-progress | Single Source Selection | 1.1.2-4-1 | 7500 | 100% | 0% | 1 | 1 | Ex-Ante | 2017-04-01 | 2017-09-01
National Environment & Planning Agency | INDIVIDUAL CONSULTANT: International/national - Hydrological Modeling Specialist for the Hydro-Meterological Assessment Study for the Program. | In-progress | 3CV | 1.2.1.2-4-1 | 75000 | 100% | 0% | 2 | 1 | Ex-Ante | 2016-07-01 | 2017-09-01 | Includes $15,000.00 for reimbursable expense for WRA and Met Service to be governed under the Project Agreement.
National Environment & Planning Agency | INDIVIDUAL CONSULTANT: International - Environmental Expert to provide training activities on inventory and mapping for carbon sequestration, establishment of baseline, and collection of project monitoring data. (3 separate contracts) (Carbon Stock Monitoring). Includes travel and per diem. | Pending | Single Source Selection | 1.2.6.1-4-1 | 42000 | 100% | 0% | 1 | 1 | Ex-Ante | 2017-09-01 | 2017-11-01
National Environment & Planning Agency | INDIVIDUAL CONSULTANT: National - Promotion and Public Communication Specialist to design and implement the overall Program communication plan and public awareness campaign | Ongoing | Comparison of Qualifications - National Individual Consultant | 1.5.1-4-1 | 113000 | 100% | 0% | 1 | 1 | Ex-Ante | 2015-09-01 | 2016-07-01
National Environment & Planning Agency | LOCAL TRAINING: Marketing Specialist - Four (4) market studies to be conducted aimed at local communities on non-agricultural aspects. | Pending | Comparison of Qualifications - National Individual Consultant | 3.2.5.1-4-1 | 27966.67 | 100% | 0% | 1 | 3 | Ex-Ante | 2018-02-01 | 2018-05-01
National Environment & Planning Agency | INDIVIDUAL CONSULTANT: National - Program Coordinator for the Program Executing Unit | Ongoing | Comparison of Qualifications - National Individual Consultant | I-4-1 | 210070.21 | 100% | 0% | 1 | 5 | Ex-Ante | 2015-02-01 | 2017-01-01
National Environment & Planning Agency | INDIVIDUAL CONSULTANT: National - Administrative and Finance/Accounting Officer for the Program Executing Unit | Ongoing | Comparison of Qualifications - National Individual Consultant | I-4-2 | 115250 | 100% | 0% | 1 | 5 | Ex-Ante | 2015-04-01 | 2016-07-01
National Environment & Planning Agency | INDIVIDUAL CONSULTANT: - Specialist to prepare the mid-term and final evaluation of the Program (separate contracts). | Pending | 3CV | III.A-4-1 | 50000 | 100% | 0% | 1 | 4 | Ex-Ante | 2017-09-01 | 2019-06-01 |  |  | Non-Consulting Services
National Environment & Planning Agency | INDIVIDUAL CONSULTANT: National - Institutional Specialist to prepare the Memoranda of Understanding (MOU) between the National Environment and Planning Agency (NEPA) and participating Government of Jamaica (GOJ) Agencies and Non-Government Agencies (NGOs). | Completed | Single Source Selection | 1.1.1-4-1 | 5000 | 100% | 0% | 1 | 1 | Ex-Ante | 2015-06-01 | 2015-07-01
Non-Consulting Services
654786.88
TRAINING
Executing Agency: | Activity: | Additional Information: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount, in US$: | Estimated Amount |  |  | Review Method (Select one of the options): | Dates |  |  |  | Lump-Sum + Reimbursable Expenses | Consulting Firms
[6 empty] | Estimated Amount IDB %: | Estimated Amount | Associated Component: |  | Annual Training Plan (ATP) | End of Activity | Comments - for UCS include selection method |  | Time-Based | Consulting Firms
Individual Consultants
National Environment & Planning Agency | LOCAL TRAINING: Marketing Specialist - Four (4) market studies to be conducted aimed at local communities on non-agricultural aspects. Training for local communities in the commerical aspects of farming, packaging and other. | Pending | Selection Based on the Consultants' Qualifications | 3.2.5.2-3-1 | 3433.33 | 100% | 0% | 3 | Ex-Ante | 2018-06-01 | 2019-06-01 |  |  |  | Individual Consultants
National Environment & Planning Agency | LOCAL TRAINING: National Consultant - Team Jamaica Training Program aimed at local communities on non-agricultural aspects. | Pending | Single Source Selection | 3.2.5.3-3-1 | 3450 | 100% | 0% | 3 | Ex-Ante | 2018-01-01 | 2019-06-01
National Environment & Planning Agency | LOCAL TRAINING: CPR Renewal Training Program aimed at local communities on non-agricultural aspects. | Pending | Shopping | 3.2.5.4-3-2 | 600 | 100% | 0% | 3 | Ex-Post | 2018-01-01 | 2019-07-01
National Environment & Planning Agency | LOCAL TRAINING: Information, communication and technology (ICT) Trainers for Training Program aimed at local communities on non-agricultural aspects. | Pending | Single Source Selection | 3.2.5.5-3-2 | 5000 | 100% | 0% | 3 | Ex-Ante | 2018-01-01 | 2019-07-01 | # of renewable small contracts. HEART Trust/NTA to be contracted to conduct training
National Environment & Planning Agency | LOCAL TRAINING: Internet Access for ICT Training aimed at local communities on non-agricultural aspects. | Pending | Shopping | 3.2.5.6-3-2 | 4941 | 100% | 0% | 3 | Ex-Post | 2018-02-01 | 2019-06-01
National Environment & Planning Agency | PILOT PROJECTS: Rural Sociologist (Formerly Watershed Officer) - Implementation of on-farm demonstration projects in agroforestry, Sustainable land Management (SLM), irrigation and other. Conducting training sessions. | pending | Shopping | 3.3.1.2-3-1 | 30000 | 100% | 0% | 3 | Ex-Ante | 2018-01-01 | 2018-12-01
47424.33
TRANSFERS | [13 empty] | Time-Based
Executing Agency | Transfer Purpose: | Additional Information: | Process Number: | Estimated Amount |  |  | Associated Component: | Estimated Number of Transfers: | Dates |  | Comments - for UCS include selection method
|  |  |  | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Contract Signature | Transfer Date |  |  |  | Single Source Selection
Comparison of Qualifications - National Individual Consultant
Comparison of Qualifications - International Individual Consultant
3CV
Adjusted for this submission
Additions
Edits made for Sheries
3909441.0036
-0.0036089

## Sheet 1
Component | Goods | Non-consulting | Consulting Firm | Consulting Individual | Training | Total
1 | 131800 | 43800 | 182300 | 584786.88 |  | 942686.88
2 | 2500 | 26624.11 | 595218.89 | 75000 |  | 699343
3 | 925547.8107 | 1133448.2929 | 116950 |  | 47424.33 | 2223370.4336
4 | 13490 | 1510 | 35000 |  |  | 50000
5 | 9040.69 |  |  |  |  | 9040.69
| 1082378.5007 | 1205382.4029 | 929468.89 | 659786.88 | 47424.33 | 3924441.0036

## Sheet2
| Goods | Non-consul | Consult Firm | Individual | Training
3.3.2 | 79062.2407 | 573439.9029 | 0 | 0 | 0 | 652502.1436 | -748002.58 | -95500.4364
3.3.1 | 407975.57 | 209727.39 | 0 | 0 | 30000 | 647702.96 | -905190.5 | -257487.54
3.2.1 | 272313 | 204012 | 0 | 0 | 0 | 476325 | -179792 | 296533
3.1.1 |  | 41621 | 76450
3.2.2 |  | 94260 | 40500
3.1.3 | 41315
3.2.4 | 17312 | 1838
3.2.3 | 89711
3.2.5 | 17859 | 8550 |  | 27966.67 | 17424.33
Others | 156830.69 | 59443.68 | 807518.89 | #REF!
| 1082378.5007 | 1192891.9729 | 924468.89 | #REF! | 47424.33 | #REF!