## Sheet1
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Paraguay |  |  |  |  | Executing agency: Bank |  |  |  |  | Public or private sector: (indicate which applies)
Project number: PR-T1180 and PR-T1195 |  |  |  |  | Title of Project: Support for the implementation of extended school days in Paraguay
Period covered by the plan: 1 July 2015-31 December 2017
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$): 80,000 |  |  |  | Consulting services(in US$):720,000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (ex-ante or ex-post) (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other %
Services different from consulting
1 |  | Didactic materials | 30000 | pc | ex-post | 100% |  | 2016-01-01
2 |  | Scholas-Ciudadanía events (logistics for the events) | 50000 | pc | ex-post | 100% |  | 2016-03-01
Consulting services
3 |  | Scholas | 500000 | sss | ex-post | 100% |  | 2015-07-01
4 |  | Diagnostic of schools | 100000 | qcbs | ex-post | 100% |  | 2015-08-01
5 |  | Baseline data | 120000 | qcbs | ex-post | 100% |  | 2016-03-01
Individual consultants
6 |  | Instructors (30) | 70000 | iicq | ex-post | 100% |  | 2016-03-01
7 |  | Evaluation expert | 40000 | iicq | ex-post | 100% |  | 2015-09-01
8 |  | Research Assistant | 80000 | iicq | ex-post | 100% |  | 2015-09-01
9 |  | Editing | 10000 | iicq | ex-post | 100% |  | 2017-07-01
Total |  |  | 1000000 | Prepared by: Mercedes Mateo |  |  | Date: 05/22/2015
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.