## RFNO_SU-L1039PP_11AUG17
Project Name: | Support for the Implementation of the EBS Investment Plan
Program Number: SU-L1039
Executing Unit: N.V. Energy Bedrijven Suriname
PROCUREMENT PLAN PERIOD: 1st June 2017 - 1st Dec 2018
Dates (If it does not apply, use N/A)
WORKS | [10 empty] | Submission of the Finalized Bidding Document to the Bank |  | Date for non- objection offered by the bank |  | Publication (advertisement) |  | Bid Opening |  | Submission of Bid Evaluation & Draft Contract |  | No Objection to the Evaluation & draft contract |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date) |  | Bidder | Proposal Price (Currency ) | Comments
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Lots Quantity: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Review Method (Select one of the options): | Bid / Contract Number | Process Status (Select one of the options): | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
2A | SU-L1039-059_Civil Upgrade Substation Building Jacobusrust (J) | National Competitive Bidding | - | Procurement for Smaller Works | Lump-Sum | 500000 | 2A | Ex-Ante | SU-L1039-059 | In Process | 2017-07-05 | 2017-07-10 | 2017-07-26 | 2017-07-19 | 2017-07-30 |  | 2017-09-24 |  | 2017-10-15 |  | 2017-11-05 |  | 2017-11-26 |  | 2018-11-26
2A | SU-L1039-060_Cable Laying and Install Cable & Cable Accessories SS/J | Shopping | - | Request for Quotation | Lump-Sum | 253400 | 2A | Ex-Ante | SU-L1039-060 | Planned | 2018-03-15 |  | 2018-04-05 |  | 2018-04-08 |  | 2018-05-06 |  | 2018-05-27 |  | 2018-06-17 |  | 2018-07-01 |  | 2018-12-28 |  |  |  | Shopping based on simple works regularly carried out by small group of local contractors
2B | SU-L1039-061_Civil Upgrade Substation Building F | National Competitive Bidding | - | Procurement for Smaller Works | Lump Sum | 770000 | 2B | Ex-Ante | SU-L1039-061 | Planned | 2017-08-31 |  | 2017-09-21 |  | 2017-09-24 |  | 2017-11-05 |  | 2017-11-26 |  | 2017-12-17 |  | 2018-01-14 |  | 2018-11-10
2B | SU-L1039-062_Cable Laying SS/F | Shopping | - | Request for Quotation | Lump Sum | 100000 | 2B | Ex-Ante | SU-L1039-062 | Planned | 2018-03-26 |  | 2018-04-16 |  | 2018-04-19 |  | 2018-05-17 |  | 2018-06-07 |  | 2018-06-28 |  | 2018-07-12 |  | 2018-08-11
2C | SU-L1039-063_New Substation Building Boma | National Competitive Bidding | - | Procurement for Smaller Works | Lump Sum | 980000 | 2C | Ex-Ante | SU-L1039-063 | Planned | 2017-09-01 |  | 2017-09-15 |  | 2017-09-22 |  | 2017-11-03 |  | 2017-11-24 |  | 2017-12-15 |  | 2017-12-29 |  | 2019-06-20 |  |  |  | Shopping based on simple works regularly carried out by local contractors
2C | SU-L1039-066_Civil Upgrade Substation E | National Competitive Bidding | - | Procurement for Smaller Works | Lump Sum | 800000 | 2C | Ex-Ante | SU-L1039-066 | Planned | 2017-09-01 |  | 2017-09-22 |  | 2017-09-26 |  | 2017-11-07 |  | 2017-11-28 |  | 2017-12-19 |  | 2018-01-02 |  | 2018-10-29
2C | SU-L1039-093_Install transmission Cable SS/HL - SS/Boma- SS/E | International Competitive Bidding (ICB) | - | Procurement for Works | Lump Sum | 2350000 | 2C | Ex-Ante | SU-L1039-093 | Planned | 2018-06-01 |  | 2018-06-22 |  | 2018-06-29 |  | 2018-08-24 |  | 2018-09-21 |  | 2018-10-12 |  | 2018-10-26 |  | 2019-01-24
2C | SU-L1039-094_Install Distribution Cable SS/Boma- SS/E | International Competitive Bidding (ICB) | - | Procurement for Works | Lump Sum | 2300000 | 2C | Ex-Ante | SU-L1039-094 | Planned | 2018-06-01 |  | 2018-06-22 |  | 2018-06-29 |  | 2018-08-24 |  | 2018-09-21 |  | 2018-10-12 |  | 2018-10-26 |  | 2019-01-24
2C | SU-L1039-068_ Riser poles Foundation OS Boma | Shopping | - | Request for Quotation | Lump Sum | 25000 | 2C | Ex-Ante | SU-L1039-068 | In Process | 2017-05-23 | 2017-07-06 | 2017-06-06 | 2017-07-14 | 2017-06-13 | 2017-07-25 | 2017-07-11 |  | 2017-08-01 |  | 2017-08-22 |  | 2017-09-05 |  | 2017-11-05 |  |  |  | Riser Pole foundations
2B | SU-L1039-092_ Fencing for Substation F | Shopping | - | Request for Quotation | Lump Sum | 210000 | 2B | Ex-Ante | SU-L1039-092 | Planned | 2017-08-16 |  | 2017-08-30 |  | 2017-09-02 |  | 2017-09-30 |  | 2017-10-14 |  | 2017-10-28 |  | 2017-11-11 |  | 2018-01-11
Dates (If it does not apply, use N/A)
GOODS | [10 empty] | Submission of the Finalized Bidding Document to the Bank |  | Date for non- objection offered by the bank |  | Publication (advertisement) |  | Bid Opening |  | Submission of Bid Evaluation & Draft Contract |  | No Objection to the Evaluation |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date) |  | Bidder | Proposal Price (Currency) | Comments
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Lots Quantity: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Bid / Contract Number | Process Status (Select one of the options): | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1B | SU-L1039-002_Procurement of Server Hardware | International Competitive Bidding | 1 | Procurement Of Goods | Lump sum | 375000 | 1B | Ex-Ante | SU-L1039-002 | In Process | 2017-05-04 | 2017-07-10 | 2017-05-18 | 2017-07-24 | 2017-05-22 | 2017-07-27 | 2017-06-05 |  | 2017-06-26 |  | 2017-07-10 |  | 2017-07-17 |  | 2017-09-13
1A | SU-L1039-012_Purchase of OMS, Hardware and related services | International Competitive Bidding | 1 | Procurement of Goods | Lump Sum | 1273000 | 1A | Ex-Ante | SU-L1039-012 | Planned | 2017-08-23 |  | 2017-09-13 |  | 2017-09-18 |  | 2017-11-13 |  | 2017-12-11 |  | 2018-01-08 |  | 2018-01-29 |  | 2018-09-26 |  |  |  | Hardware now included in Tender and DMS scope removed.
1D | SU-L1039-020_Procurement of Energy Management System | International Competitive Bidding | 1 | Procurement of Goods | Lump Sum | 270000 | 1D | Ex-Ante | SU-L1039-020 | Planned | 2017-10-06 |  | 2017-10-27 |  | 2017-10-30 |  | 2017-12-11 |  | 2018-01-01 |  | 2018-01-22 |  | 2018-02-05 |  | 2018-11-18
1D | SU-L1039-019_Procurement for the LED Project | International Competitive Bidding | 2 | Procurement of Goods | Lump Sum | 558000 | 1D | Ex-Ante | SU-L1039-019 | In Process | 2017-06-21 | 2017-06-19 | 2017-07-05 | 2017-07-13 | 2017-07-08 | 2017-07-14 | 2017-08-05 |  | 2017-08-26 |  | 2017-09-09 |  | 2017-09-23 |  | 2017-12-22
2A - 2B - 2C | SU-L1039-069_Switchgear, SCADA, Protection Panels, Cap. Bank, Ext. Diff relays | Limited International Bidding | 1 | Procurement for Goods | Lump-Sum | 5300000 | 2A - 2B - 2C | Ex-Ante | SU-L1039-069 | Planned | 2017-08-22 |  | 2017-09-12 |  | 2017-09-16 |  | 2017-11-10 |  | 2017-12-01 |  | 2017-12-22 |  | 2018-01-05 |  | 2018-05-14 |  |  |  | LIB: Due to compatibility with existing equipment from specific suppliers
2A - 2B - 2C | SU-L1039-070_Electrical Materials (Aux. trafo, Sec. Mat., Sub. Grounding, DC Chargers, LV panel, Cable Ladders & Acc., 33 kV Lighting Arres. & Omicron tester) | International Competitive Bidding | 5 | Procurement for Goods | Lump-Sum | 1900000 | 2A - 2B - 2C | Ex-Ante | SU-L1039-070 | In Process | 2017-05-02 | 2017-07-12 | 2017-05-23 | 2017-08-03 | 2017-05-26 | 2017-08-10 | 2017-07-21 |  | 2017-08-11 |  | 2017-09-01 |  | 2017-09-15 |  | 2019-01-22
2A - 2B - 2C | SU-L1039-071_Cable & Cable Accessories | International Competitive Bidding | 1 | Procurement for Goods | Lump-Sum | 1255000 | 2A - 2B - 2C | Ex-Ante | SU-L1039-071 | Planned | 2017-10-06 |  | 2017-10-27 |  | 2017-10-30 |  | 2017-12-25 |  | 2018-01-15 |  | 2018-02-05 |  | 2018-02-19 |  | 2019-06-28
2B - 2C | SU-L1039-072_Riserpoles SS F & SS Boma(EL) | Shopping | 1 | Request for Quotation | Lump-Sum | 95000 | 2B - 2C | Ex-Ante | SU-L1039-072 | In Process | 2017-04-15 | 2017-04-11 | 2017-05-06 | 2017-04-24 | 2017-05-09 | 2017-04-25 | 2017-06-06 | 2017-05-26 | 2017-06-27 | 2017-06-30 | 2017-07-18 | 2017-07-05 | 2017-08-01 |  | 2018-12-08 |  |  |  | Shopping:Common Goods, not produced locally
2B - 2C | SU-L1039-074_Power Transformers 25MVA | International Competitive Bidding | 1 | Procurement of Goods | Lump-Sum | 1800000 | 2B - 2C | Ex-Ante | SU-L1039-074 | Planned | 2017-08-14 |  | 2017-09-04 |  | 2017-09-07 |  | 2017-11-02 |  | 2017-11-23 |  | 2017-12-14 |  | 2017-12-28 |  | 2019-05-06
1B | SU-L1039-008_Procurement of Goods & Services to facilitate Network Upgrades ( Communication) | Shopping | - | Procurement of Non-Consulting Services | Lump Sum | 100000 | 1B | Ex-Ante | SU-L1039-008 | In Process | 2017-04-28 | 2017-04-28 | 2017-05-19 | 2017-05-23 | 2017-05-22 | 2017-06-02 | 2017-06-26 | 2017-06-23 | 2017-07-10 |  | 2017-07-31 |  | 2017-08-07 |  | 2017-11-05
1C | SU-L1039-091B_Goods for Training in Leading Transformation | Shopping | 2 | Request for Quotation | Lump-Sum | 7500 | 1C | Ex-Post | SU-L1039-091B | Planned | n/a |  | n/a |  | 2017-08-30 |  | 2017-09-09 |  | n/a |  | n/a |  | 2017-09-23 |  | 2017-10-24
Dates (If it does not apply, use N/A)
NON CONSULTING SERVICES | [10 empty] | Submission of the Finalized Bidding Document to the Bank |  | Date for non- objection offered by the bank |  | Publication (advertisement) |  | Bid Opening |  | Submission of Bid Evaluation & Draft Contract |  | No Objection to the Evaluation & draft contract |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date) |  | Bidder | Proposal Price (Currency ) | Comments
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Lots Quantity: | Baseline Document (Select one of the options): | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Review Method (Select one of the options): | Bid / Contract Number | Process Status (Select one of the options): | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1D | SU-L1039-082_Event Planning Services for the Renewable Energy and Energy Efficiency Workshops and Seminars | Shopping | 2 | Procurement of Non-Consulting Services | Lump Sum | 50000 | 1D | Ex-Ante | SU-L1039-082 | Planned | 2017-08-28 |  | 2017-09-18 |  | 2017-09-21 |  | 2017-10-26 |  | 2017-11-16 |  | 2017-12-07 |  | 2017-12-21 |  | 2018-04-20
2A - 2B - 2C | SU-L1039-073_Transportation & Insurance of electrical equipment for SS/J | Shopping | - | Request for Quotation | Lump Sum | 75000 | 2A - 2B - 2C | Ex-Ante | SU-L1039-073 | Planned | 2018-04-26 |  | 2018-05-17 |  | 2018-05-20 |  | 2018-06-10 |  | 2018-06-24 |  | 2018-07-15 |  | 2018-07-29 |  | 2019-07-29
1D | SU-L1039-029_Event Planning Services for Energy Efficiency & Renewable Energy Education Program | Direct Contracting | - | Request for Quotation | Lump Sum | 52000 | 1D | Ex-Ante | SU-L1039-029 | Planned | 2017-10-02 |  | 2017-10-16 |  | 2017-10-17 |  | 2017-10-31 |  | 2017-11-14 |  | 2017-11-28 |  | 2017-12-05 |  | 2018-12-05 |  |  |  | Justification: Exceptional Case; Only one NGO has experience of exceptional worth for the assignment.
1D | SU-L1039-021_Event Planning Services for the Renewable Energy and Energy Efficiency Fair | Shopping | - | Request for Quotation | Lump Sum | 20000 | 1D | Ex-Ante | SU-L1039-021 | Planned | 2017-10-02 |  | 2017-10-23 |  | 2017-10-26 |  | 2017-11-16 |  | 2017-12-07 |  | 2017-12-28 |  | 2018-01-04 |  | 2018-04-04
Dates (If it does not apply, use N/A)
CONSULTING FIRMS | [9 empty] | Expression of Interest Notice |  | Submission of RFP and Short List |  | No Objection to RFP and Short List |  | RFP Submission |  | Bid Opening |  | Submission of Technical Evaluation |  | No Objection to the Technical Evaluation |  | Final Evaluation and Negotiation |  | No Objection to the Contract |  | Contract Signing (Date of contract signiture) |  | End of Contract (Final date) |  | Short List Members | Technical Score Assigned | Evaluated Price Proposal (Currency ####) | Combined Score | Comments
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Process Number: | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Bid / Contract Number | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real | Estimated | Real
1D | SU-L1039-030_Consulting services for for Building Energy Efficiency Program | Quality & Cost Based Selection | - | Lump Sum | 400000 | 1D | Ex-Ante | Planned | SU-L1039-030 | 2017-10-06 |  | 2017-10-27 |  | 2017-11-17 |  | 2017-11-20 |  | 2017-12-18 |  | 2018-01-08 |  | 2018-01-29 |  | 2018-02-19 |  | 2018-03-05 |  | 2018-03-12 |  | 2018-04-20
1C | SU-L1039-015_Consulting Services for the Implementation of the Energy Law phase 2 | Quality & Cost Based Selection | - | Lump Sum | 83000 | 1C | Ex-Ante | Planned | SU-L1039-015 | 2018-06-15 |  | 2018-06-29 |  | 2018-07-20 |  | 2018-07-27 |  | 2018-08-24 |  | 2018-09-14 |  | 2018-10-05 |  | 2018-10-19 |  | 2018-11-02 |  | 2018-11-09 |  | 2019-05-13
1C | SU-L1039-017_Consulting Services for the Design & Implementation of EBS Management Development Policy | Quality & Cost Based Selection | - | Lump Sum | 180000 | 1C | Ex-Ante | Planned | SU-L1039-017 | 2018-05-01 |  | 2018-05-15 |  | 2018-06-05 |  | 2018-06-12 |  | 2018-07-10 |  | 2018-07-31 |  | 2018-08-21 |  | 2018-09-04 |  | 2018-09-18 |  | 2018-09-25 |  | 2019-09-25
1C | SU-L1039-088_HR Consultancy Services to support EBS restructuring | Quality & Cost Based Selection | - | Lump Sum | 240000 | 1C | Ex-Ante | In Process | SU-L1039-088 | N/A | N/A | 2017-04-28 | 2017-07-10 | 2017-05-12 | 2017-07-24 | 2017-05-19 | 2017-07-26 | 2017-06-09 |  | 2017-06-23 |  | 2017-07-07 |  | 2017-07-14 |  | 2017-07-28 |  | 2017-08-04 |  | 2018-08-04
1C | SU-L1039-089_HR Consultancy to support Leadership development | Quality & Cost Based Selection | - | Lump Sum | 60000 | 1C | Ex-Ante | Planned | SU-L1039-089 | 2017-08-18 |  | 2017-09-01 |  | 2017-09-22 |  | 2017-09-29 |  | 2017-10-20 |  | 2017-11-03 |  | 2017-11-24 |  | 2017-12-01 |  | 2017-12-15 |  | 2017-12-22 |  | 2018-12-22
INDIVIDUAL CONSULTANTS
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Process Number: | Estimated Amount, in u$s : | Estimated Number of Consultants: | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Bid / Contract Number | Dates (If it does not apply, use N/A) | [5 empty] | Consultant's Name | Period |  | Title | Comments | Amount (Currency ###)
[10 empty] | No Objection to the TORs |  | Hiring Deadline |  | End of Activity |  |  | From | Until
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real
1C | SU-L1039-016_Consulting services for the Design of Corporate Planning function within EBS | CQ NI | - | 50000 | 1 | 1C | Ex-Ante | Planned | SU-L1039-016 | 2018-04-16 |  | 2018-05-21 |  | 2018-11-17 | [5 empty] | Est. dates still depending on strategy of execution
1C | SU-L1039-087_Consulting Services for the Design & Implementation of the EBS Governance Risk & Compliance Framework | CQ NI | - | 100000 | 1 | 1C | Ex-Ante | In Process | SU-L1039-087 | 2017-05-05 | 2017-06-21 | 2017-07-17 |  | 2018-04-06 | [5 empty] | Re-do of Terminated Process (SU-L1039-018). NO to baseline docs new process received 14-jul-17. Evaluation Criteria to be shared with the Bank before evaluation process.
TRAINING
Component (if applies) | Description/Contract Name: | Procurement Method (Select one of the options): | Process Number: | Contract Type (Select one of the options): | Estimated Amount, in u$s : | Associated Component: | Expost Review (Select one of the options): | Process Status (Select one of the options): | Bid / Contract Number | Dates (If it does not apply, use N/A) | [5 empty] | Detail | Amount (Currency ###) | Comments
[10 empty] | Annual Training Plan (ATP) |  | No Objection to the ATP |  | End of Activity
[10 empty] | Estimated | Real | Estimated | Real | Estimated | Real
1C | SU-L1039-091A_Facility incl. Transportation for Training Leading in Transformation | Direct Contracting | - | Lump Sum | 12500 | 1C | Ex-Post | Planned | SU-L1039-091A | 2017-08-30 |  | 2017-09-13 |  | 2017-10-24
TBD | To Be Determined
N/A | Not Applicable
Formulas:
Estimated = [Estimated]+21
Estimated = [Real]+7
Real = [Expression of Interest Notice]+21
Real = [Real]+21
End of Contract (Final date) = [Estimated]+185
Expression of Interest Notice = [Real]-14