## Update Aug 22
Procurement Plan
RG-T3298
IDB-Israel Collaboration: Improving Capacities in Water Resource Technologies
PROCUREMENT PLAN FOR IDB-EXECUTED OPERATIONS
Country: Latina America and the Caribbean co-execution of the GEF will include 5 more countries: Cuba, Grenada, Saint Kitts and Nevis, Saint Lucia, and St Vincent and the Grenadines) | [5 empty] | Executing Agency: IDB | [7 empty] | UDR: INE/INE
Project number: RG-T3298 |  |  |  |  | Project name: IDB-Israel Collaboration: Improving Capacities in Water Resource Technologies
Period covered by the Plan: 26 months |  |  |  |  | Total Project Amount: |  | 1102000
Component | Procurement Type (1) (2) | Service type (1) (2) | Description | Estimated contract cost (US$) | Selection Method (2) | Type of Contract | Source of Financing and Percentage |  |  |  | Estimated date of the procurement notice | Estimated contract start date | Estimated contract length | Comments
[7 empty] | IDB |  | PSG Funding (Israel)
[7 empty] | Amount | % | Amount | %
Select comp | Select Proc. Type | Goods Included in Firm Cons. RFP | Consultant 1: brief description |  | select method | Select Cont. Type |  |  |  |  | 2016-03-01
Component 1 | A. Consulting services | Consulting Firm (GN-2765) | Pilot Projects Design. An estimated 12 pilots will be supported. These could include, among others, site-specific solutions (i.e. desalination systems, wastewater treatment and reuse solutions, leak detection, etc,), integrated data management systems to address key challenges in water planning and design (i.e. software applications, monitoring systems, etc.), policy instrument (i.e. regulatory framework for water reuse, NRW reduction strategies, etc.), and the design of a management tool to assist in the application of a technology throughout the region (i.e. an evaluation tool for project feasibility studies, etc.). To access resources for pilot projects, a regional call for proposals will be launched, and proponents will be evaluated through a competitive process using evaluation criteria that best fit the objective of this program. | 792000 | SSS | Lump Sum | 330000 | 42% | 462000 | 58% | 2019-02-01 | 2020-04-01 | 19 months | Small contracts on average of US$100.000
Component 2 | A. Consulting services |  | Elaboration of analytical and best practice documents. Review of state of the art of Israeli and other countries’ technological and management solutions for each of the selected technologies. They include technical, socio-economic, environmental/climate, policy and financial dimensions of technology design and implementation. | 60000 | SSS | Lump Sum | 60000 | 100% | 0 | 0% | 2019-02-01 | 2019-04-01 | 7 months
Component 2 | C. Non consulting services | Corporate Procurement (GN-2303) | Exchange for selected countries | 50000 | SSS | Lump Sum | 0 | 0% | 50000 | 100% | 2019-04-01 | 2019-06-01 | 6 months
Component 3 | C. Non consulting services | Corporate Procurement (GN-2303) | Workshops in LAC. Two LAC workshop will be organized during the second year of execution. The workshops will last 5 days each, and will be organized in conjunction with regional or national entities. | 140000 | SSS | Lump Sum | 60000 | 43% | 80000 | 57% | 2019-11-01 | 2020-01-01 | 8 months
Component 3 | C. Non consulting services | Corporate Procurement (GN-2303) | Technical/Policy advisory services. Short-term visits from Israeli officials/consultants | 60000 | SSS | Lump Sum | 0 |  | 60000 | 100% | 2019-02-01 | 2020-04-01 | 19 months
Prepared by: |  |  | TOTALS | 1102000 |  |  | 450000 | 33% | 652000 | 67%
(1) Grouping together of similar procurement is recommended, such as publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) (i) Individual consultants: ICQ: Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection. Selection process to be done in accordance with AM-650.
(2) (ii) Consulting firms: Per GN-2765-1, Consulting Firm selection methods for Bank-executed Operations are: Single Source Selection (SSS); Simplified Competitive Selection (<=250K) (SCS); Fully Competitive (>250K) (FCS); and Framework Agreement Task Order (TO). All Consulting Firm selection processes under this policy must use the electronic module in Convergence.
(2) (iii) Goods: Per GN-2765-1, par. A.2.2.c: "The procurement of goods and related services, except when such goods and related services are necessary to achieve the objectives of the Bank-executed Operational Work and are included in the consulting services contract and represent less than ten percent (10%) of the consulting services contract value."